## Sheet1
Scheme Name : Overall » Agencies : All »Corporation / Municipality Name : Tambaram Status : Overall | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35 | Unnamed: 36 | Unnamed: 37 | Unnamed: 38 | Unnamed: 39
Sno | ULB Name | Scheme Name | District Name | Project Id |  |  | Name of Work | Work Type | Sub Type | AS No. /AS Date | AS Year | AS Amount | Estimate Amount | Fund Tie Up |  |  | Amount Recievedso far | Work Order Date | Agreement Value(in Cr) | Physical Progress |  |  |  | Third PartyVerification Report |  | Completion Report |  |  | UtilizationCertificate |  |  | Savings Amount | Payment Madeso far (in Cr) | % of Expenditure w.r.tEstimate Amount | Target DateAs PerAgreement | Review Remarks | AS Amount | FinalBill Status | Is Photo Uploaded
[20 empty] | Previous Stage as on |  | Current Stage as on
[5 empty] | Zones | Wards | [7 empty] | Scheme Fund | ULB Share | Other Share |  |  |  | Stage ofwork | Percent % | Stage ofwork | Percent % | Date | Certificate | Date | Copy of CR | Workdone Value | Date | Attachement | BalanceFund
1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24(5-20) | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
1 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00066 | Zone I | 2 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00066-Road Restoration of damaged portion over at PP Amman Kovil Street (007002R033) in Ward No.02 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 650000 |  |  |  | 0.07 | 2022-05-01 | 0.06 |  | 0 | Work Cancelled | 0 |  |  |  |  | 0 |  |  |  | 650000 | 0 | 0 | 2022-05-02 |  | 41050000 | No | Yes
2 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00053 | Zone II | 21 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00053-Road Restoration of damaged portion over at Karumariamman Cross Street (007021R816) in Ward No.21 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 330000 |  |  | 0 | 0.03 | 2022-03-01 | 0.03 |  | 0 | Work Cancelled | 0 |  |  |  |  | 0 |  |  |  | 330000 | 0 | 0 | 2022-03-02 |  | 41050000 | No | Yes
3 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00043 | Zone II | 26 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00043-Road Restoration of damaged portion over at Rajaji Cross Street (007026R994) in Ward No.26 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 850000 |  |  |  | 0.09 | 2022-03-01 | 0.08 |  | 0 | Work Calcelled | 0 |  |  |  |  | 0 |  |  |  | 850000 | 0 | 0 | 2022-03-02 |  | 41050000 | No | Yes
4 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/ROAD/00303 | Zone V |  | Namakku Naame Thittam NNT/2025-26/009/ROAD/00303-Relaying of Road-Bituminous Road009063R4794-SUDANANDA BHARATHI ST , Zone V in Tambaram Corporation | Roads | Bituminous Road | 14558/2025/T2Dated:27/01/26Road DetailsRoad Length :900 Mts | 2025-26 | 17345000 | 4455000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 4455000 | 0 | 0 | - |  | 17345000 | No | No
5 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/ROAD/00302 | Zone II |  | Namakku Naame Thittam NNT/2025-26/009/ROAD/00302-Relaying of Road-Bituminous Road009021R5881-English Electric Nagar 12th Street , Zone II in Tambaram Corporation | Roads | Bituminous Road | 14558/2025/T2Dated:27/01/26Road DetailsRoad Length :137 Mts | 2025-26 | 17345000 | 3000000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 3000000 | 0 | 0 | - |  | 17345000 | No | No
6 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/ROAD/00304 | Zone I |  | Namakku Naame Thittam NNT/2025-26/009/ROAD/00304-Relaying of Road-Cement Concrete Road009011R0844-ANNA SALAI , Zone I in Tambaram Corporation | Roads | Cement Concrete Road | 14558/2025/T2Dated:27/01/26Road DetailsRoad Length :1730 Mts | 2025-26 | 17345000 | 6000000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0 | 0 | - |  | 17345000 | No | No
7 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00422 | Zone V |  | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00422-Construction of SWD at Arun Nagar 3rd Main road 009062R4774,Murugesan Street 009062R4692,Thilagavathy Nagar Senthil Murugan Street 009062R4703, ROSE GARDEN IIND ST 009062R4727, North Street 009063R4792, BALARAMAN STREET 009063R4807,Arignar Anna Street 009064R4825, VOC Street 009064R4827,Mariamman koil Street 009064R4865 Tambaram City Municipal Corporation Zone V (Package No.26) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 17356000 |  |  |  | 0 | - | 0 |  | 0 | Retender To Be Called | 0 |  |  |  |  | 0 |  |  |  | 17356000 | 0 | 0 | - |  | 200000000 | No | No
8 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/ROAD/00311 | Zone III |  | Namakku Naame Thittam NNT/2025-26/009/ROAD/00311-Relaying of Road-Bituminous Road009022R1479-GANGAI AMMAN KOIL STREET , 009022R1480-GANGAI AMMAN KOIL STREET , Zone III in Tambaram Corporation | Roads | Bituminous Road | 14558/2025/T2-2Dated:20/02/26Road DetailsRoad Length :249 Mts | 2025-26 | 6700000 | 3200000 |  |  |  | 0 | - | 0 |  | 0 | Work Order To Be Issued | 0 |  |  |  |  | 0 |  |  | 0 | 3200000 | 0 | 0 | - |  | 6700000 | No | No
9 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2024-25/009/BUILDING/00094 | Zone I |  | 15thCFC-Health 15thCFCUPC/2024-25/009/BUILDING/00094-Construction of Urban Primary Health Centre at Anakaputhur,Zone 1 | Buildings | Buildings | 26154/2024/EA-2Dated:03/10/24 | 2024-25 | 42000000 | 15000000 |  |  |  | 0 | 17/12/25 | 0 |  | 0 | Work To Be Commenced | 0 |  |  |  |  | 0 |  |  |  | 15000000 | 0 | 0 | 27/12/25 |  | 42000000 | No | No
10 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/UGSS/00305 | Zone II | 21 | Namakku Naame Thittam NNT/2025-26/009/UGSS/00305-Providing Sewer line and Machine hole at Tiruthani Nagar, ward No.21 Zone II in Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 14558/2025/T2Dated:27/01/26 | 2025-26 | 17345000 | 1300000 |  |  |  | 0 | 20/02/26 | 0.13 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 1300000 | 0 | 0 | 20/05/26 |  | 17345000 | No | No
11 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00231 | Zone IV | 60 | MLA Fund MLA/2024-25/009/BUILDING/00231-Construction of VAO office building at Irumbuliyur Tamil poonga street in ward No.60 Zone IV in Tambaram Corporation | Buildings | Buildings | 1694/2024/A1Dated:19/12/24 | 2024-25 | 47450000 | 1060000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 1060000 | 0 | 0 | - |  | 47450000 | No | No
12 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00115 | Zone IV | 56 | General Fund GENERAL/2024-25/009/BUILDING/00115-Construction of Sump Room to Kamarajar Nedunchalai Sump in Ward No.56 in Zone 4 TCMC | Buildings | Buildings | 413Dated:30/12/24 | 2024-25 | 990000 | 990000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | - |  | 990000 | No | No
13 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00424 | Zone II | 13 | MLA Fund MLA Fund/2021-22/009/WS/00424-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.13 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0 | 25/05/22 | 0.09 |  | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 970000 | 0 | 0 | 25/07/22 |  | 14858000 | No | Yes
14 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2019-20/009/UGSS/00260 | Zone II |  | UGD-Internal Plumbing UGSS-IP/2019-20/009/UGSS/00260-Providing and laying under ground sewerage pipe line at gangai amman nagar 8 th main road thirutani nagar north 1 st main road, ambal nagar cross street at zone-2 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 1002/2025-26Dated:29/12/25 | 2019-20 | 2500000 | 2500000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | - |  | 2500000 | No | No
15 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00432 |  |  | MLA Fund MLA Fund/2021-22/009/BUILDING/00432-Construction of Bus Shelter's at Hastinapuram Dr Rajendra Prasad Road in Tambaram City Municipal Corporation | Buildings | Bus Shelter | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 1000000 |  |  |  | 0 | 25/05/22 | 0.09 |  | 0 | Work Cancelled | 0 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 25/06/22 |  | 14858000 | No | Yes
16 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/BUILDING/00172 | Zone III |  | MLA Fund MLA/2025-26/009/BUILDING/00172-Construction of Bus shelter work in Kumarankunram kovil near main road zone III in Tambaram Corporation | Buildings | Bus Shelter | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 1500000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 7100000 | No | No
17 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00394 | Zone III |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00394-Construction of 6.00 LL capacity of Water Storage Ground level reservoir pump arrangement at GGN park near Radha Nagar and Providing pumping main from sump to Radha Nagar OHT Zone No. III | Water Supply Improvement Scheme | Const OHT & Sump | 28485/2022/EA2-iiiDated:24/02/25 | 2024-25 | 74000000 | 21500000 |  |  |  | 0 | 29/04/25 | 2.15 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  |  | 21500000 | 0 | 0 | 26/10/25 |  | 74000000 | No | No
18 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2025-26/009/WSIS/00285 | Zone V | 45 | 15TH CFC-MPC-SWM MPC/2025-26/009/WSIS/00285-Construction of Overhead Tank (OHT) 5.00LL capacity 16m staging height at Tirupurkumaran park and Providing distribution main line Venkatesan street, Raja Iyer street, School street, Kannan street Eswaran kovil street, Muthalamman street at ward NO.45 in Zone V in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Const OHT & Sump | 327/2025/EA-2Dated:01/12/25 | 2025-26 | 164400000 | 25000000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 25000000 | 0 | 0 | - |  | 164400000 | No | No
19 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/WS/00168 | Zone II | 16 | MLA Fund MLA/2025-26/009/WS/00168-Providing to borewell,mini power pump and tank work in zone 2 ward No.16, Tambaram Corporation | Water Supply | Water Supply Improvement Works | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 280000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 280000 | 0 | 0 | - |  | 7100000 | No | No
20 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/WS/00169 | Zone II | 24 | MLA Fund MLA/2025-26/009/WS/00169-Providing to 2 place borewell, mini power pump and tank work in zone ii ward no.24 at Tambaram Corporation | Water Supply | Water Supply Improvement Works | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 560000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 560000 | 0 | 0 | - |  | 7100000 | No | No
21 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/WS/00170 | Zone II | 17 | MLA Fund MLA/2025-26/009/WS/00170-Deeping of borewell and mini power pump in 2 place, zone II ward no.17 in Tambaram Corporation | Water Supply | Water Supply Improvement Works | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 560000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 560000 | 0 | 0 | - |  | 7100000 | No | No
22 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/OTHERS/00307 | Zone I | 8 | Namakku Naame Thittam NNT/2025-26/009/OTHERS/00307-Supply and fixing of CCTV camera at ward No.08 in zone I Tambaram City Municipal Corporation | Others | CCTV Installation | 14558/2025/T2Dated:27/01/26 | 2025-26 | 17345000 | 900000 |  |  |  | 0 | 2026-05-03 | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 900000 | 0 | 0 | - |  | 17345000 | No | No
23 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/OTHERS/00308 | Zone I | 8 | Namakku Naame Thittam NNT/2025-26/009/OTHERS/00308-Supply and fixing of CCTV camera at ward No.08 in zone I Tambaram City Municipal Corporation | Others | CCTV Installation | 14558/2025/T2Dated:27/01/26 | 2025-26 | 17345000 | 690000 |  |  |  | 0 | - | 0 |  | 0 | Retender | 0 |  |  |  |  | 0 |  |  | 0 | 690000 | 0 | 0 | - |  | 17345000 | No | No
24 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00173 | Zone II | 21 | MLA Fund MLA/2025-26/009/OTHERS/00173-Supply of CC TV (camera) to Zone II ward No.21 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 300000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 300000 | 0 | 0 | - |  | 7100000 | No | No
25 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00177 | Zone II | 9 | MLA Fund MLA/2025-26/009/OTHERS/00177-Supply of CC TV (camera) to Zone II ward No.09 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 500000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 500000 | 0 | 0 | - |  | 7100000 | No | No
26 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2025-26/009/WSIS/00286 | Zone IV | 55, 59 | 15TH CFC-MPC-SWM MPC/2025-26/009/WSIS/00286-Providing Distribution line in ward NO.55 and 59 in Zone IV in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Laying of Feeder Main and Distribution Main | 327/2025/EA-2Dated:01/12/25 | 2025-26 | 164400000 | 17800000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 17800000 | 0 | 0 | - |  | 164400000 | No | No
27 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/OTHERS/00297 | Zone II |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/OTHERS/00297-Uniform signages for Tambaram City Municipal Corporation on Welcome arch gantry, street name boards, fascia replacement in Corporation building like school, Hospitals in zone II | Others | Road Sign | DMA/1161/2025-EA2Dated:30/12/25 | 2025-26 | 90370000 | 10940000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 10940000 | 0 | 0 | - |  | 90370000 | No | No
28 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/OTHERS/00298 | Zone III |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/OTHERS/00298-Uniform signages for Tambaram City Municipal Corporation on Welcome arch gantry, street name boards, fascia replacement in Corporation building like school, Hospitals in zone III | Others | Road Sign | DMA/1161/2025-EA2Dated:30/12/25 | 2025-26 | 90370000 | 25830000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 25830000 | 0 | 0 | - |  | 90370000 | No | No
29 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/OTHERS/00299 | Zone IV |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/OTHERS/00299-Uniform signages for Tambaram City Municipal Corporation on Welcome arch gantry, street name boards, fascia replacement in Corporation building like school, Hospitals in zone IV | Others | Road Sign | DMA/1161/2025-EA2Dated:30/12/25 | 2025-26 | 90370000 | 21150000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 21150000 | 0 | 0 | - |  | 90370000 | No | No
30 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/OTHERS/00300 | Zone V |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/OTHERS/00300-Uniform signages for Tambaram City Municipal Corporation on Welcome arch gantry, street name boards, fascia replacement in Corporation building like school, Hospitals in zone V | Others | Road Sign | DMA/1161/2025-EA2Dated:30/12/25 | 2025-26 | 90370000 | 21800000 |  |  |  | 0 | - | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 21800000 | 0 | 0 | - |  | 90370000 | No | No
31 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/OTHERS/00296 | Zone I |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/OTHERS/00296-Uniform signages for Tambaram City Municipal Corporation on Welcome arch gantry, street name boards, fascia replacement in Corporation building like school, Hospitals in zone I | Others | Road Sign | DMA/1161/2025-EA2Dated:30/12/25 | 2025-26 | 90370000 | 10650000 |  |  |  | 0 | - | 0 |  | 0 | Retender | 0 |  |  |  |  | 0 |  |  | 0 | 10650000 | 0 | 0 | - |  | 90370000 | No | No
32 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/ROAD/00310 | Zone III |  | Namakku Naame Thittam NNT/2025-26/009/ROAD/00310-Construction of Yoga centre, Toilet facility & Storm water drain and Relaying of Road-BT and CC Road009038R2414-THIRU VI KA 2ND STREET , 009037R2340-SIVAGAMI NAGAR FIRST MAIN ROAD , at zone III in Tambaram Corporation | Roads | BT and CC Road | 14558/2025/T2-2Dated:20/02/26Road DetailsRoad Length :418 Mts | 2025-26 | 6700000 | 3500000 |  |  |  | 0 | - | 0 |  | 0 | Work Order To Issued | 0 |  |  |  |  | 0 |  |  | 0 | 3500000 | 0 | 0 | - |  | 6700000 | No | No
33 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00061 |  |  | General Fund GENERAL/2025-26/009/WS/00061-Providing PVC Pipe Main line at Mariamamn koil street open well to Hasthinapuram link Road and punithavathy colony main road | Water Supply | Repair Works - Water Supply | 673-1Dated:25/08/25 | 2025-26 | 1020000 | 1020000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 1020000 | 0 | 0 | - |  | 1020000 | No | No
34 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2025-26/009/BUILDING/00306 | Zone I | 8 | Namakku Naame Thittam NNT/2025-26/009/BUILDING/00306-Construction of Toilet at CSIJMA middle school in ward No.08 zone I in TCMC | Buildings | Construction of Toilet | 14558/2025/T2Dated:27/01/26 | 2025-26 | 17345000 | 1000000 |  |  |  | 0 | 2026-05-03 | 0 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  | 0 | 1000000 | 0 | 0 | - |  | 17345000 | No | No
35 | Tambaram | Disaster Management - Michanung Cyclone 2023 | CHENGALPATTU | MICHA/2025-26/009/ROAD/00315 | Zone I | 10 | Disaster Management - Michanung Cyclone 2023 MICHA/2025-26/009/ROAD/00315-Providing BT Surface at Muthukariyamman koil street in ward no.10 zone-1 TCMC | Roads | Earthern to BT Road | 1037/1-2025-26Dated:29/12/25Road DetailsRoad Length :Mts | 2025-26 | 2350000 | 2350000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 2350000 | 0 | 0 | - |  | 2350000 | No | No
36 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/UGSS/00203 | Zone V | 45, 47, 62 | General Fund GENERAL/2025-26/009/UGSS/00203-Providing Sewerage line Facilities to Elumalai Street,Eswaran Kovil Street,Vidyalaksmi Street at ward 45 ,Thirumizhisai Street ward no 47 Ward 62 Ponnan Nagar and Gayathri Nagar, Repair and Maintenance of Arul Nagar Pump House Motor at Zone 5 East Tambaram Area in Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 420Dated:04/04/25 | 2025-26 | 980000 | 980000 |  |  |  | 0 | - | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 | 980000 | 0 | 0 | - |  | 980000 | No | No
37 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00395 | Zone III |  | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00395-Realignment of 450mm CI pipeline from Medavakkam main road to Keelkattalai UGS pumping main zone III in Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 28485/2022/EA2-iiiDated:24/02/25 | 2024-25 | 74000000 | 13000000 |  |  |  | 0 | 28/04/25 | 1.3 |  | 0 | Loa Issued | 0 |  |  |  |  | 0 |  |  |  | 13000000 | 0 | 0 | 25/10/25 |  | 74000000 | No | No
38 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00184 | Zone III | 42 | MLA Fund MLA/2024-25/009/BUILDING/00184-Construction of Public Distribution shop at Ponniyamman kovil street in ward No. 42 , Zone NO. III in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1250000 |  |  |  | 0 | - | 0 | Tender To Be Called On 03.01.2025 | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 1250000 | 0 | 0 | - |  | 9650000 | No | No
39 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00192 | Zone I | 2 | MLA Fund MLA/2024-25/009/BUILDING/00192-Construction of Public Distribution at Ward No. 2 zone I in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 26/10/24 | 0.11 | Site Disbute | 0 | Site Disbute | 0 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
40 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00194 | Zone II | 14 | MLA Fund MLA/2024-25/009/BUILDING/00194-Construction of PDS shop Toilet at ward No. 14 zone II in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 23/10/24 | 0 | Work Order Issued, Work To Be Started | 0 | Site Disbute | 0 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
41 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2021-22/009/OTHERS/00132 |  |  | Chennai River Restoration Trust Chennia Ri/2021-22/009/OTHERS/00132-Providing Tree Plantation work and fencing Arrangements at Adayar River Bund in Anakaputhur Municipality | Others | Planting of Trees | 846Dated:30/09/21 | 2021-22 | 2000000 | 2000000 |  |  |  | 0 | 2021-03-12 | 0.19 | Work Dropped As Per Crrt Instructions | 0 | Work Dropped As Per Instruction Of Acs, Maws Department On 11.01.2023. Mom Awaited From Crrt. | 0 |  |  |  |  | 0 |  |  |  | 2000000 | 0 | 0 | 2022-01-03 |  | 2000000 | No | Yes
42 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2021-22/009/OTHERS/00201 | Zone I | 31 | Chennai River Restoration Trust Chennia Ri/2021-22/009/OTHERS/00201-Tree Plantation (Ward No.31), Zone-1, Thiruneermalai | Others | Planting of Trees | 1Dated:09/08/21 | 2021-22 | 1000000 | 1000000 |  |  |  | 0 | 2021-03-09 | 0.09 | Work Dropped As Per Crrt Instructions | 0 | Work Dropped As Per Instruction Of Acs, Maws Department On 11.01.2023. Mom Awaited From Crrt. | 0 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 2021-02-12 |  | 1000000 | No | Yes
43 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2015-16/009/OTHERS/00154 | Zone IV | 55 | Chennai River Restoration Trust Chennia Ri/2015-16/009/OTHERS/00154-Providing Tree Plantation and removal of juli Flora jungle @ Adyar River ward-55, Perungulathur | Others | Planting of Trees | 72Dated:12/01/17 | 2015-16 | 1000000 | 1000000 |  |  |  | 0 | 2021-06-09 | 0.1 | Work Dropped As Per Instruction Of Acs, Maws Department On 11.01.2023. Mom Awaited From Crrt. | 0 | Work Dropped As Per Instruction Of Acs, Maws Department On 11.01.2023. Mom Awaited From Crrt. | 0 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 2021-05-12 | ... | 1000000 | No | Yes
44 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/SWM/00006 |  |  | 15th CFC 15th CFC/2021-22/009/SWM/00006-Purchase of 2 nos Skid Street Loader (Bobcot) to Tambaram City Municipal Corporation for Under Ground Sewerage Scheme | Solid Waste Management | Procurement of Vehicles /Machineries | 21191/2021/AMRUT-2-Tambaram-Tied-6Dated:17/12/21 | 2021-22 | 5000000 | 5000000 |  |  |  | 0.42 | 22/04/22 | 0.5 | Work Order Is Cancelled. Proposal To Be Sent Requesting Permission To Utilise The Sanctioned Amount To Remit Ulb Share For 2 Mcc Sanctioned Under Sbm(u) 2.0 - 2022-23 | 0 | Work Order Cancelled. Proposal Sent Requesting Permission To Utilise The Sanctioned Amount To Remit Ulb Share For 2 Mcc Sanctioned Under Sbm(u) 2.0-2022-23. (Letter Roc. No: 1607/2021/E1 Dt: 5.1.23), Council Resolution No: 897 Dt: 30.12.22 And Permission Obtained From Dma Vide Letter No.21191/2021/cfc-1, Dated. 06.03.2023. | 0 |  |  |  |  | 0 |  |  |  | 5000000 | 0 | 0 | 25/07/22 |  | 5000000 | No | Yes
45 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00149 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00149-Supply and delivery of 35nos printer for MCC | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 312000 | 0 |  |  | 0 | - | 0 | Revised As Sent To Dma Office On 09.12.2024 | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 312000 | 0 | 0 | - |  | 19031000 | No | No
46 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00136 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00136-Supply and delivery of 10nos, of 1 ton mini Tipper for C&D waste | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 6500000 |  |  |  | 0 | - | 0 | Tender Evaluation On 20.08.2024 | 0 | Revised As Sent To Dma Office On 09.12.2024 | 0 |  |  |  |  | 0 |  |  |  | 6500000 | 0 | 0 | - |  | 118900000 | No | No
47 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00049 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00049-Supply and delivery of 1 nos Heavy motor vehicle mounted super sucker machine 10000 ltr suction dump tank capacity | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 22500000 |  |  |  | 0 | 16/09/25 | 2.25 | Work Order Issued | 0 | Notice Issued To Contractor-retender To Be Called | 0 |  |  |  |  | 0 |  |  |  | 22500000 | 0 | 0 | 2027-05-01 |  | 77422000 | No | Yes
48 | Tambaram | SBM | CHENGALPATTU | Swach Bhar/2020-21/009/SWM/00019 |  |  | SBM Swach Bhar/2020-21/009/SWM/00019-Installation of (2nos of 50TPD) 100 TPD Incineration Plant at Venkadamangalam on Design, Build, Operate, Maintain for 3 years and Transfer (DBOT) basis by Tambaram Municipality | Solid Waste Management | Incineration Plant | G.O.(MS) No.104Dated:22/09/20 | 2020-21 | 95300000 | 95300000 |  |  |  | 8.58 | 2021-01-02 | 9.53 | Work Dropped | 0 | Dropped | 0 |  |  |  |  | 0 |  |  |  | 95300000 | 0 | 0 | 2021-01-08 |  | 95300000 | No | No
49 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SWM/00129 |  |  | SBM 2.0 SBM 2.0/2023-24/009/SWM/00129-Selection of a Concessionaire for establishment of 150TPD Municipal solid Waste based Bio-CNG Plant at Tambaram uncer PPP mode on Design,build,Finance,Operate and Transfer Basis for a period of 20 years | Solid Waste Management | Bio Methanation Plant/Compressed Natural Gas Plant | G.No.145Dated:11/03/24 | 2023-24 | 446900000 | 446900000 |  |  |  | 44.69 | - | 0 | Retender To Be Received On 26.06.2024 | 0 | Work Order Issued To M/s. Mahasakthi Bio-encon Pvt.ltd On 05.05.2025 | 0 |  |  |  |  | 0 |  |  |  | 446900000 | 0 | 0 | - |  | 446900000 | No | No
50 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/WS/00232 | Zone III | 23 | Namakku Naame Thittam NNT/2022-23/009/WS/00232-Providing Deep Borewell to Chinna street B ward No.23 Zone III | Water Supply | Borewell | 23182/2023/P2-2Dated:17/08/23 | 2022-23 | 10112000 | 210000 |  |  |  | 0.02 | 2023-03-10 | 0.02 | Geological Survey Is Completed Drilling Work To Be Started | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 210000 | 0 | 0 | - |  | 10112000 | No | Yes
51 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2023-24/009/UGSS/00071 | Zone II | 27 | Namakku Naame Thittam NNT/2023-24/009/UGSS/00071-Providing UGSS pumping main line at CLC 11th street, 2nd main road, 8th street and Rangasamy street in ward No.27, Zone II in Tambaram Corporation | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 853/2024/T2Dated:05/03/24 | 2023-24 | 9500000 | 5000000 |  |  |  | 0 | 14/05/25 | 0.5 | Site Dispute | 0 | Site Dispute | 0 |  |  |  |  | 0 |  |  | 0 | 5000000 | 0 | 0 | - |  | 9500000 | No | No
52 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00200 | Zone I | 11 | MLA Fund MLA/2024-25/009/BUILDING/00200-Construction of PDS Toilet at ward No. 11 zone-I in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 26/10/24 | 0.11 | Site Disbute | 0 | Site Disbute | 0 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
53 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00417 | Zone II | 19 | MLA Fund MLA Fund/2021-22/009/WS/00417-Concstuction of Jim building at Ward No.19 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 500000 |  |  |  | 0 | 25/05/22 | 0.04 | Work Dropped | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 500000 | 0 | 0 | 25/07/22 |  | 14858000 | No | Yes
54 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2025-26/009/BUILDING/00361 | Zone II | 20 | Kalaignar Nagarpura Mempatu Thittam KNMT/2025-26/009/BUILDING/00361-Construction of LPG, Gasifier Crematorium at Subramani Nagar Burial Ground ward No.20, Block no. 58, Survey No. 11/5, Zone II in Tambaram City Municipal Corporation | Buildings | Crematorium | CPSMC-20th meeting-2Dated:23/04/25 | 2025-26 | 23100000 | 16400000 |  |  |  | 0 | 24/07/25 | 1.64 | Site Disbute | 0 | Site Disbute | 0 |  |  |  |  | 0 |  |  |  | 16400000 | 0 | 0 | 20/04/26 |  | 23100000 | No | No
55 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00017 | Zone II | 13 | MLA Fund MLA/2023-24/009/BUILDING/00017-Construction of Kariyamandapam building at ward No.13, Zone II | Buildings | Crematorium | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 1000000 |  |  |  | 0 | 29/12/23 | 0.1 | Work Oder Issued, Work To Be Started | 0 | Work Dropped | 0 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 29/03/24 |  | 8230000 | No | Yes
56 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/021/ROAD/00004 | Zone I | 1, 3, 5 | SRP SRP/2020-21/021/ROAD/00004-Improvement to BT Surface @ Ward no.1 Shankar Nagar 12,15, 20 , 38, 43 Street and Ward no.3 Sooriyamman Koil Street Ward No.5 Padmanaban Street, Madhavan Naiyar Street and Krishna Nagar 4h cross street | Roads | Bituminous Road | 298Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 35000000 | 5800000 |  |  | 0 | 0 | 22/01/21 | 0.58 | Dropped | 0 | As Per Dma Letter Roc No. 20557/2020/E1, Dated. 04.03.2022 , Work Fully Dropped | 0 |  |  |  |  | 0 |  |  |  | 5800000 | 0 | 0 | 22/04/21 |  | 35000000 | No | Yes
57 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00042 | Zone III | 22 | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00042-Supply and fiixing of DI pipeline carrying bridge work at Nanmangalam main pumping line (near Keelkattalai) in ward NO.22 Zone III | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 5400000 |  |  |  | 0 | 2024-05-12 | 0.54 | Work To Be Staretd | 0 | Dropped | 0 |  |  |  |  | 0 |  |  |  | 5400000 | 0 | 0 | 2025-08-09 |  | 48950000 | No | No
58 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2025-26/009/WSIS/00284 | Zone I | 1 | 15TH CFC-MPC-SWM MPC/2025-26/009/WSIS/00284-Construction of 3MLD Water Treatment Plant Capacity at Tiruneermalai Quarry ward No.01 in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 327/2025/EA-2Dated:01/12/25 | 2025-26 | 164400000 | 82600000 |  |  |  | 0 | 26/02/26 | 0 |  | 0 | Level Work In Progress | 2 |  |  |  |  | 0 |  |  | 0 | 82600000 | 0 | 0 | - |  | 164400000 | No | No
59 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2024-25/009/BUILDING/00095 | Zone V |  | 15thCFC-Health 15thCFCUPC/2024-25/009/BUILDING/00095-Construction of Urban Primary Health Centre at Poondi Bazar, East Tambaram, Zone 5. | Buildings | Buildings | 26154/2024/EA-2Dated:03/10/24 | 2024-25 | 42000000 | 15000000 |  |  |  | 0 | 2025-02-12 | 0 | To Be Commenced | 0 | Column Work Is In Progress | 5 |  |  |  |  | 0 |  |  | 0 | 15000000 | 0 | 0 | 2026-09-06 |  | 42000000 | No | Yes
60 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2024-25/009/PARK/00210 | Zone IV | 57 | 15TH CFC-MPC-AAQ MPC/2024-25/009/PARK/00210-Green Space development at Ponniamman kovil kulam ward No.57 Zone IV in Tambaram Corporation | Parks | Parks | 11919/2022/EA2-2Dated:07/10/25 | 2024-25 | 52400000 | 13900000 |  |  |  | 0 | 2026-12-02 | 1.39 | Site Cleaning Work | 0 | Jungle Clearing Work Is In Progress | 5 |  |  |  |  | 0 |  |  | 0 | 13900000 | 0 | 0 | 20/05/26 |  | 52400000 | No | Yes
61 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/WS/00171 | Zone III |  | MLA Fund MLA/2025-26/009/WS/00171-Construction of Kariyamandapam and deepening of borewell, Toilet entrens shelter work in Asthinapuram Burial ground zone III at Tambaram Corporation | Water Supply | Water Supply Improvement Works | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 1400000 |  |  |  | 0 | 2025-10-09 | 0.14 |  | 0 | Earth Work | 5 |  |  |  |  | 0 |  |  | 0 | 1400000 | 0 | 0 | 17/12/25 |  | 7100000 | No | No
62 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2025-26/009/ROAD/00134 | Zone IV |  | 15TH CFC-MPC-AAQ MPC/2025-26/009/ROAD/00134-Relaying of Road BT road at -009056R4187-KAMARAJAR NEDUNSALAI in Zone IV | Roads | Bituminous Road | 11919/2022/EA-2-4Dated:14/10/25Road DetailsRoad Length :800 Mts | 2025-26 | 7850000 | 7850000 |  |  |  | 0 | 2026-12-02 | 0.65 | Picking/earthwork/milling | 0 | Milling Completed Cleaning Work Is In Progress | 5 |  |  |  |  | 0 |  |  | 0 | 7850000 | 0 | 0 | - |  | 7850000 | No | Yes
63 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2024-25/009/BUILDING/00097 | Zone III | 41 | 15thCFC-Health 15thCFCUPC/2024-25/009/BUILDING/00097-Construction of Additional UPHC at Sembakkam, ward 41 Zone III | Buildings | Buildings | 26154/2024/EA-2Dated:03/10/24 | 2024-25 | 42000000 | 6000000 |  |  |  | 0 | 2025-02-12 | 0.6 | Basement Level | 5 | Basement Level | 5 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 2026-09-06 |  | 42000000 | No | Yes
64 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SWM/00281 | Zone II |  | SBM 2.0 SBM 2.0/2023-24/009/SWM/00281-Removal of Legacy waste 48235 MT at Pallavapuram Periya Eri, Zone II in Tambaram City Municipal Corporation | Solid Waste Management | Bio Mining Work | 19009/2022/SBM1Dated:02/11/23 | 2023-24 | 36300000 | 36300000 |  |  |  | 0 | 2024-02-07 | 3.5 | Processed Quantity | 9 | Work In Progress | 9 |  |  |  |  | 0 |  |  |  | 36300000 | 0 | 0 | 24/12/25 |  | 36300000 | No | Yes
65 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00391 | Zone I | 30, 31 | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00391-Construction of 2.00 LL Capacity OHT 16m staging height with pump and pipeline distributions at Thiruneermalai ward No 30 and 31 in Zone I | Water Supply Improvement Scheme | Const OHT & Sump | 16479/2023/EA-2-iiDated:17/02/25 | 2024-25 | 42100000 | 17100000 |  |  |  | 0 | 28/08/25 | 1.71 | Excavation Work In Progress | 5 | -Footing Work Completed | 10 |  |  |  |  | 0 |  |  | 0 | 17100000 | 0 | 0 | 26/12/25 |  | 42100000 | No | Yes
66 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00177 | Zone IV | 57 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00177-Construction of 2 nos of School building class room (2 nos) at Perungalathur Krishna road in ward No.57 in zone IV in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 3500000 |  |  |  | 0 | 2025-10-07 | 0.29 | Work Order Issued | 0 | Site Levelling Work Is In Progress | 10 |  |  |  |  | 0 |  |  | 0 | 3500000 | 0 | 0 | 2026-10-04 |  | 40950000 | No | Yes
67 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2024-25/009/WB/00211 | Zone V |  | 15TH CFC-MPC-AAQ MPC/2024-25/009/WB/00211-Providing Footpath and Greenaries at Noothencheri Kulam, Madambakkam Zone V in Tambaram Corporation | WaterBodies | Improvement of Water Bodies | 11919/2022/EA2-2Dated:07/10/25 | 2024-25 | 52400000 | 17000000 |  |  |  | 0 | 2026-11-02 | 1.7 |  | 0 | Kerb Wall Work Is In Progress | 15 |  |  |  |  | 0 |  |  | 0 | 17000000 | 0 | 0 | 20/05/26 |  | 52400000 | No | Yes
68 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00046 | Zone IV | 50 | MLA Fund MLA/2023-24/009/BUILDING/00046-Construction of Public Distribution shop at Samiyar thottam 2nd street in ward No50 zone IV | Buildings | Public Distriibution Shop | 3041/2023/A3-8Dated:08/01/24 | 2023-24 | 4570000 | 1100000 |  |  |  | 0.11 | 29/01/24 | 0.09 | Alternate Site To Be Identify | 15 | Work Dropped | 15 |  |  |  |  | 0 |  |  |  | 1100000 | 0 | 0 | 2024-01-02 |  | 4570000 | No | Yes
69 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2025-26/009/WSIS/00287 | Zone V |  | 15TH CFC-MPC-SWM MPC/2025-26/009/WSIS/00287-Providing 300mm dia, 100mm dia HTPE Pipes with Anchoring, Laying of 50 square mm Aluminium cables and Motor at Melachery Headworks , Zone V in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Replacement of Old Motors and other items | 327/2025/EA-2Dated:01/12/25 | 2025-26 | 164400000 | 39000000 |  |  |  | 0 | 2026-11-02 | 3.9 |  | 0 | Work Is In Progress | 20 |  |  |  |  | 0 |  |  | 0 | 39000000 | 0 | 0 | 18/08/26 |  | 164400000 | No | No
70 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00254 | Zone III | 34 | General Fund GENERAL/2025-26/009/OTHERS/00254-Formation Of Namma Tambaram Scheme In Chitlapakkam in Ward No.34 in Zone III | Others | Miscellaneous Works | 949Dated:31/10/25 | 2025-26 | 1050000 | 1050000 |  |  |  | 0 | 29/12/25 | 0.1 |  | 0 | Works | 20 |  |  |  |  | 0 |  |  | 0 | 1050000 | 0 | 0 | 2026-05-04 |  | 1050000 | No | Yes
71 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00247 | Zone II | 9 | General Fund GENERAL/2024-25/009/SWD/00247-Construction of culvert and SWD at periyapalayathaman kovil street in ward-09 at zone-2 , TCMC | Storm Water Drain | Construction of Drain | 20-2 / 2024-25Dated:19/03/25 | 2024-25 | 880000 | 880000 |  |  |  | 0 | 25/04/25 | 0.09 | Earth Work | 20 | Completed | 20 |  |  | 29/12/25 |  | 868757 |  |  | 0 | 11243 | 0 | 0 | 25/07/25 |  | 880000 | No | Yes
72 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00413 |  |  | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00413-Construction of SWD with RCC cover slab at Nemilichery main road, Balasubramani road, Nanmangalam main road (Packag NO.17) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 22008000 |  |  |  | 0 | 19/09/25 | 2.2 | Pcc !:4:8 | 10 | Pcc !:4:8 | 20 |  |  |  |  | 0 |  |  | 0 | 22008000 | 0 | 0 | 18/12/25 |  | 200000000 | No | Yes
73 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SWM/00058 |  |  | SBM 2.0 SBM 2.0/2023-24/009/SWM/00058- Removal of Legacy waste Dumped 492834 MT (616042 cum) at Appur Dumping yard through Bio-mining Process in Tambaram City Municipal Corporation | Solid Waste Management | Bio Mining Work | G.O.(D).No.88,MAWS(MC7)Dated:21/02/24 | 2023-24 | 359900000 | 359900000 |  |  |  | 0 | 31/07/24 | 0 | Processed Quantity | 20 | 105268 Cum Legacy Waste Proceed. | 21 |  |  |  |  | 0 |  |  |  | 359900000 | 1.68 | 4.67 | 31/07/26 |  | 359900000 | No | No
74 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00390 | Zone IV |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00390-Construction of 5.00 LL capacity OHT of 16m stage height with pump room and providing pumping and delivery pipeline at Alwain garden zone IV in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Const OHT & Sump | 16479/2023/EA-2-iiDated:17/02/25 | 2024-25 | 42100000 | 25000000 |  |  |  | 0 | 18/08/25 | 2.5 | Foundation Work | 20 | Pile Work Completed, Column Steel Fabrication Work Is In Progress. | 21 |  |  |  |  | 0 |  |  | 0 | 25000000 | 0 | 0 | 15/04/26 |  | 42100000 | No | Yes
75 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WS/00392 | Zone I |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WS/00392-Providing Internal Plumbing for water supply HSC 4963 nos in Anakaputhur Zone I in Tambaram City Municipal Corporation | Water Supply | Water supply - Internal Plumbing | 28485/2022/EA-2-WSIPDated:17/02/25 | 2024-25 | 16900000 | 16900000 |  |  |  | 0 | 2025-10-07 | 1.69 | Water Supply Internal Pumbing Line Progress 200 Line Completed | 20 | Water Supply Internal Pumbing Line Progress 280 Line Completed | 22 |  |  |  |  | 0 |  |  | 0 | 16900000 | 0 | 0 | 2026-06-01 |  | 16900000 | No | Yes
76 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2025-26/009/SWM/00364 | Zone V |  | SBM 2.0 SBM 2.0/2025-26/009/SWM/00364-Construction of Transfer station for Tambaram Corporation at the location near Madambakam with a capacity of 150 TPD zone V | Solid Waste Management | SWM | 6450/2024/SBM-1 IIDated:24/03/25 | 2025-26 | 310370000 | 97720000 |  |  |  | 0 | 21/07/25 | 9.77 | Pcc 1:4:8 | 20 | Column Up To Base Plate Level Rised. | 25 |  |  |  |  | 0 |  |  |  | 97720000 | 0 | 0 | 17/04/26 |  | 310370000 | No | Yes
77 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00421 | Zone V |  | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00421-Construction of SWD at Ganapathy Colony 009045R3329,Burial ground road 009046R3467,Manimegalai Street Extn 009046R3434,iyappan Street 009047R3484,Porur Street 009048R3532,Manickavasagar Street 009048S0448 Tambaram City Municipal Corporation Zone V (Package No.25) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 12000000 |  |  |  | 0 | 2025-12-09 | 1.2 | Vent Flooring Plastering Work | 20 | Shuttering Work Completed | 25 |  |  |  |  | 0 |  |  |  | 12000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
78 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00423 | Zone V |  | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00423-Construction of SWD at Ganapathy Colony 009045R3329,Burial ground road 009046R3467,Manimegalai Street Extn 009046R3434,Ganapathy Colony - 009047R3498 ,Gnanapathy Colony 1st Cross Street - 009047R3499,Kannagi Street 009047R3502,iyappan Street 009047R3484,Porur Street 009048R3532,Manickavasagar Street 009048S0448 Tambaram City Municipal Corporation Zone V (Package No.27) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 2500000 |  |  |  | 0 | 2025-12-09 | 0.25 | Vent Flooring Plastering Work | 20 | Shuttering Work Completed | 25 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
79 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00150 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00150-Supply and delivery of 5nos of 50tons Bailing machine wit Lift in RRC | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 935000 | 0 |  |  | 0 | 2024-08-10 | 0.09 | Procurement Of Vehicles/machineries | 30 | Work Dropped | 30 |  |  |  |  | 0 |  |  |  | 935000 | 0 | 0 | 2025-06-07 |  | 19031000 | No | No
80 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2025-26/009/BRIDGE/00132 | Zone II |  | 15TH CFC-MPC-AAQ MPC/2025-26/009/BRIDGE/00132-Providing Landscaping, Greeneries and Foot path at Pallavaram Fly over in zone II in Tambaram Corporation | Bridges and Flyovers | Bridges/Flyovers | 11919/2022/EA-2-3Dated:13/10/25 | 2025-26 | 33200000 | 11700000 |  |  |  | 0 | 2025-01-12 | 0 | Work In Progress | 5 | Foot Path Work In Progress | 30 |  |  |  |  | 0 |  |  | 0 | 11700000 | 0 | 0 | - |  | 33200000 | No | Yes
81 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2025-26/009/BRIDGE/00133 | Zone II |  | 15TH CFC-MPC-AAQ MPC/2025-26/009/BRIDGE/00133-Providing Landscaping, Greeneries and Foot path at Ponds Fly over in zone II in Tambaram Corporation | Bridges and Flyovers | Bridges/Flyovers | 11919/2022/EA-2-3Dated:13/10/25 | 2025-26 | 33200000 | 21500000 |  |  |  | 0 | 2025-01-12 | 0 | Sump Marking | 5 | Leisure Seating, Turf Footing Work Completed And Civil Work In Progress | 30 |  |  |  |  | 0 |  |  | 0 | 21500000 | 0 | 0 | - |  | 33200000 | No | Yes
82 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00057 | Zone II | 9, 20, 21 | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00057-Replacing the damaged UGSS gravity main line at 200 ft radial road, Ramasamy kuttai pumping line at ward No.09,20 and 21 in Zone II | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 28485/2022/EA-2Dated:15/10/24 | 2024-25 | 31400000 | 17800000 |  |  |  | 0 | 2025-12-12 | 1.78 | Damaged Pipe Replacement Work Progress | 30 | Damaged Pipe Replacement Work Progress | 30 |  |  |  |  | 0 |  |  |  | 17800000 | 0 | 0 | - |  | 31400000 | No | Yes
83 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2025-26/009/BUILDING/00362 | Zone I | 4 | Kalaignar Nagarpura Mempatu Thittam KNMT/2025-26/009/BUILDING/00362-Construction of ABC centre building at Kalmaduvu Anakaputhur ward No.4 survey No. 308 and 309 zone I in Tambaram City Municipal Corporation | Buildings | Buildings | CPSMC-20th meeting-2Dated:23/04/25 | 2025-26 | 23100000 | 6700000 |  |  |  | 0 | 21/07/25 | 0.67 | Lintel Level Brick Work In Progress | 30 | Lintel Level Brick Work In Progress | 35 |  |  |  |  | 0 |  |  | 0 | 6700000 | 0 | 0 | 19/10/25 |  | 23100000 | No | Yes
84 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00400 | Zone II | 9 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00400-Construction of SWD at Mariamman Koil Street - 009009R0675and Culvert at Mariamman Koil Street - 009009R0675 in Ward No.09 Tambaram City Municipal Corporation Zone II (Packag NO.4) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 4400000 |  |  |  | 0 | 2025-12-09 | 0.44 | 40 % Work Completed,blance Partion Earth Work Progress | 40 | Earth Work And Wall Concrete Work Progress | 40 |  |  |  |  | 0 |  |  |  | 4400000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
85 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2024-25/009/SWD/00071 | Zone IV | 32, 33 | Namakku Naame Thittam NNT/2024-25/009/SWD/00071-Construction of RCC Storm Water Drain with Cover slab and Foot path arrangements around MEPZ, from Kadaperi outlet to Thiurneermalai Eri in Ward No .32 and 33 in Zone IV in Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 19731/2024/P2Dated:04/03/25 | 2024-25 | 172000000 | 172000000 |  |  |  | 9 | 26/06/25 | 16.61 | 550M Drain Completed | 25 | 650M Completed | 40 |  |  |  |  | 0 |  |  |  | 172000000 | 0 | 0 | 2025-03-11 |  | 172000000 | No | Yes
86 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2025-26/009/BUILDING/00263 | Zone I | 31 | Elementary Education Fund EE/2025-26/009/BUILDING/00263-Construction of Knowledge centre Building in ward 31 Thiruneermalai Zone 1 at TCMC | Buildings | Knowledge Centre | 325/2025-26Dated:24/06/25 | 2025-26 | 20000000 | 20000000 |  |  |  | 0 | 18/08/25 | 0 |  | 0 | Roof Laid | 40 |  |  |  |  | 0 |  |  | 0 | 20000000 | 0 | 0 | - |  | 20000000 | No | No
87 | Tambaram | WS Internal Plumbing | CHENGALPATTU | UIDSSMT Re/2019-20/009/WS/00118 |  |  | WS Internal Plumbing UIDSSMT Re/2019-20/009/WS/00118-Providing of Internal Plumping for Water Supply HSC at Sembakkam Municipality | Water Supply | Water supply - Internal Plumbing | 13277/2018/WS1Dated:19/06/18 | 2019-20 | 29000000 | 29000000 |  |  |  | 1.37 | 29/05/19 | 2.62 | Under Uidssmt Scheme Water Supply Connections Approved For 8200 Nos . Out Of 8200 Nos 3450 Connections Are Already Given Balance 4750 Connections Are To Be Ttransferred To Amrut .Requisiting Letter Sent To Dma , (Vide Letter Roc No : 381/2018/E1 Dt: 9.1.23 ) | 42 | Dropped | 42 |  |  |  |  | 0 |  |  |  | 29000000 | 0.98 | 33.96 | 29/02/20 | ... | 29000000 | No | Yes
88 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00199 | Zone II | 17 | General Fund GENERAL/2025-26/009/BUILDING/00199-Construction of Toilet, Kitchen and Parking Sheed at Tambaram Corporation Higher Seconadary School in Ward No.17 Tambaram City Municipal Corporation Zone II | Buildings | Construction of Schools | 358-4/2025 - 26Dated:30/08/24 | 2025-26 | 6000000 | 6000000 |  |  |  | 0 | 30/09/24 | 0.6 |  | 0 | Roof Laid | 45 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0 | 0 | 30/03/25 |  | 6000000 | No | Yes
89 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00417 | Zone IV | 58 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00417-Construction of Storm Waret Drain to MKB Nagar (Velu street, abraham street, Kurunji street, Murugaesan street, anbu street, arivu street, Muthuirulandi 1st cross street, Kannan street Ward no.58 in Zone-4 (Package No.21) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 5700000 |  |  |  | 0 | 2025-12-09 | 0.57 | Pcc 1:2:4 | 20 | Out Of 1092M Drain 521M Completed Balance Work Is In Progress | 49 |  |  |  |  | 0 |  |  | 0 | 5700000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
90 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00137 | Zone II | 17 | General Fund GENERAL/2024-25/009/PARK/00137-Improvements of Subam Nagar Park (PHASE-II) ward-17 , Zone-II, TCMC | Parks | Parks | 359-1 / 2024-25Dated:30/08/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 23/12/24 | 0.6 |  | 0 | Laying Of Paver Block | 50 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 23/06/25 |  | 6000000 | No | Yes
91 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00110 | Zone III | 37 | General Fund GENERAL/2024-25/009/SWD/00110-Construction of storm water drain and culvert to Sembakkam chitlapakkam Main road and Kakkan Street in Ward No.37 | Storm Water Drain | Construction of Drain | 94-3Dated:06/03/25 | 2024-25 | 3950000 | 3950000 |  |  |  | 0 | 2025-03-04 | 0.39 |  | 0 | Vent Flooring Plastering Work | 50 |  |  |  |  | 0 |  |  |  | 3950000 | 0 | 0 | 2025-10-07 |  | 3950000 | No | Yes
92 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00187 | Zone II |  | General Fund GENERAL/2024-25/009/WS/00187-Repair and maintance of UGSS , water supply motor, staters and generators in Zone II, TCMC | Water Supply | Repair Works - Water Supply | 20-25/2024-25Dated:13/03/25 | 2024-25 | 500000 | 500000 |  |  |  | 0 | 25/04/25 | 0.05 |  | 0 | Repair Work Started | 50 |  |  |  |  | 0 |  |  |  | 500000 | 0 | 0 | 25/10/25 |  | 500000 | No | Yes
93 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00189 | Zone V | 70 | MLA Fund MLA/2024-25/009/BUILDING/00189-Providing bus shelters at near Kozhipannai bus stop in ward No.70 zone V in Tambaram City Municipal Corporation | Buildings | Bus Shelter | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 900000 |  |  |  | 0 | 29/10/24 | 0.07 | Site Dispute Due To Highway Drain Work In Progress. | 50 | Site Dispute Due To Highway Drain Work In Progress. | 50 |  |  |  |  | 0 |  |  |  | 900000 | 0 | 0 | 26/07/25 |  | 9650000 | No | Yes
94 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00192 | Zone I |  | General Fund GENERAL/2025-26/009/PARK/00192-Labour Engaged for Sweeping and Maintenance purpose on contract Basis in Exisitng gardern park and play field at kalmaduvu park, Thendal nagar park, Thangaiya park,sivasankaran nagar , sigamani park and chandran nagar park zone 1 TCMC | Parks | Parks | 324Dated:24/06/25 | 2025-26 | 3000000 | 3000000 |  |  |  | 0 | 30/06/25 | 0.3 |  | 0 | Work Under Progress | 50 |  |  |  |  | 0 |  |  |  | 3000000 | 0 | 0 | - |  | 3000000 | No | Yes
95 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00418 | Zone IV | 55 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00418-Construction of Storm Waret Drain to Vishnu nagar main road and 4th, 3rd and 2nd street Ward no.55 in Zone-4 (Package No.22) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3300000 |  |  |  | 0 | 2025-12-09 | 0.33 | In Progress | 20 | Out Of 510M, 382M Completed | 60 |  |  |  |  | 0 |  |  | 0 | 3300000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
96 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2024-25/009/ROAD/00209 |  |  | 15TH CFC-MPC-AAQ MPC/2024-25/009/ROAD/00209-Relaying of Road-Bituminous Road009048R3536-BHARATHA MADHA STREET , | Roads | Bituminous Road | 11919/2022/EA2-2Dated:07/10/25Road DetailsRoad Length :753 Mts | 2024-25 | 52400000 | 21500000 |  |  |  | 0 | 2026-12-02 | 2.15 |  | 0 | Bm Laid | 60 |  |  |  |  | 0 |  |  | 0 | 21500000 | 0 | 0 | 20/05/26 |  | 52400000 | No | Yes
97 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00188 |  |  | General Fund GENERAL/2025-26/009/ROAD/00188-Repair /Maintenance-BT and CC Road- , | Roads | BT and CC Road | 627-2/2025-26Dated:25/08/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 18/08/25 | 0.03 |  | 0 | Bituminuous Concrete | 60 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 18/11/25 |  | 2500000 | No | Yes
98 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SN0012/00441 | Zone II |  | General Fund GENERAL/2024-25/009/SN0012/00441-Providing Annual Service Maintenance to Reverse Osmosis Plant at Zone - II | Annual Maintenance | Maintenance of RO Plant | GF 104Dated:06/03/25 | 2024-25 | 2700000 | 2700000 |  |  |  | 0 | 28/03/25 | 0.23 | Work Started | 60 | Work Under Progress | 60 |  |  |  |  | 0 |  |  |  | 2700000 | 0 | 0 | 28/03/26 |  | 2700000 | No | Yes
99 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00058 | Zone V |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00058-Construction of Infiltration well with 10HP motor pump at Melachery head works (River palar) in zone V | Water Supply Improvement Scheme | Source Augmentation | 28485/2022/EA-2Dated:15/10/24 | 2024-25 | 31400000 | 13600000 |  |  |  | 0 | 2025-02-06 | 1.14 | Supplying Of Electromagnetic Flow Meter | 60 | Supplying Of Electromagnetic Flow Meter | 60 |  |  |  |  | 0 |  |  |  | 13600000 | 0 | 0 | - |  | 31400000 | No | Yes
100 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00139 | Zone II | 17 | General Fund GENERAL/2024-25/009/WS/00139-Laying Distibution Pipeline at Amman Koil Street ,Kalainger Street ,Ambedkar Street,Anna Street, Sakrapani Stree, Duraikkannu Slai and HDPE Pipeline at Gandhi nagar 2nd Street in Ward No.17.18 & 20 TCMC at Zone-II | Water Supply | Water supply - Internal Plumbing | 97-2/2024-25Dated:06/03/25 | 2024-25 | 2820000 | 2820000 |  |  |  | 0 | 28/03/25 | 0.28 | Earth Work | 30 | Pipe Laid | 60 |  |  |  |  | 0 |  |  |  | 2820000 | 0 | 0 | 28/09/25 |  | 2820000 | No | Yes
101 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2024-25/009/BUILDING/00096 | Zone III | 23 | 15thCFC-Health 15thCFCUPC/2024-25/009/BUILDING/00096-Construction of Additional UPHC at Kullakarai Street ward 23, Zone III | Buildings | Buildings | 26154/2024/EA-2Dated:03/10/24 | 2024-25 | 42000000 | 6000000 |  |  |  | 0 | 20/11/25 | 0.6 | Roof Level | 40 | Roof Level | 60 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0 | 0 | 27/05/26 |  | 42000000 | No | Yes
102 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00048 | Zone III |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00048-Construction of Water Treatment Plant of 1.5 MLD capacity at ASK Nagar 4th street in Madambakkam lake in Zone III | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 18274/2022-2Dated:06/01/25 | 2024-25 | 40600000 | 40600000 |  |  |  | 0 | 26/06/25 | 4.06 | Plumbing Work And Installation | 60 | Plumbing Work And Installation | 65 |  |  |  |  | 0 |  |  | 0 | 40600000 | 1.11 | 27.41 | 18/12/26 |  | 40600000 | Yes | Yes
103 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00213 | Zone IV |  | General Fund GENERAL/2024-25/009/BUILDING/00213-Construction of 1st Floor Office Building at Zone 4 Office and Peerkankaranai Office in TCMC | Buildings | Office Building | 115/2024-25Dated:06/03/25 | 2024-25 | 5400000 | 5400000 |  |  |  | 0 | 23/02/26 | 0.45 |  | 0 | Partition Work Completed Balance Work Is In Progress | 65 |  |  |  |  | 0 |  |  | 0 | 5400000 | 0 | 0 | 24/05/26 |  | 5400000 | No | Yes
104 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00407 | Zone II | 19 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00407-Construction of SWD at Kumaran Street - 009019R1188, Kamaraj Street - 009019R1219,Srvs Colony Emerald St - 009019R1195 and Culvert at Srvs Colony Emerald St - 009019R1195 in Ward No.19 Tambaram City Municipal Corporation Zone II (Packag NO.11) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 6000000 |  |  |  | 0 | 2025-12-09 | 0.6 | Roof Slab Centering And Fabrication Work Progress | 65 | Roof Slab Centering And Fabrication Work Progress | 65 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
105 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2023-24/009/PARK/00072 | Zone IV | 49 | Namakku Naame Thittam NNT/2023-24/009/PARK/00072-Improvement of Park at Muthurangam park in ward No.49, Zone No. IV in Tambaram Corporation | Parks | Parks | 853/2024/T2Dated:05/03/24 | 2023-24 | 9500000 | 4500000 |  |  |  | 0 | 2024-12-06 | 0.45 | Badminton Court Work Is Progress | 60 | Cctv Camera And Light Fixing Work In Progress | 65 |  |  |  |  | 0 |  |  |  | 4500000 | 0 | 0 | 2025-09-03 |  | 9500000 | No | Yes
106 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WS/00257 |  |  | AMRUT 2.O AMRUT 2.0/2023-24/009/WS/00257-Providing 24X7 water supply to the pilot water zones in Pallavaram (Tambaram Corporation) | Water Supply | Water Supply Improvement Works | 9TH SLTC MINUTESDated:05/09/23 | 2023-24 | 188000000 | 188000000 |  |  |  | 1.68 | 2024-01-08 | 20.16 | Radha Nagar 13.50Ll Oht Tank Column Shuttering Work In Progress. | 69 | Shanthinagar 7.00Ll Oht Tank Column Reinforcement Work In Progress | 69 |  |  |  |  | 0 |  |  |  | 188000000 | 3.6 | 19.17 | 25/01/27 |  | 188000000 | No | Yes
107 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WSIS/00440 |  |  | AMRUT 2.O AMRUT 2.0/2023-24/009/WSIS/00440-Project Management Consultancy” for implementing the 24 x7 water supply work taken under AMRUT 2.0 scheme | Water Supply Scheme | Water Supply Scheme | 425/2024/WBDated:01/03/24 | 2023-24 | 4700000 | 4700000 |  |  |  | 0 | 22/08/24 | 0 | Radha Nagar 13.50Ll Oht Tank Column Shuttering Work In Progress. | 69 | Shanthinagar 7.00Ll Oht Tank Column Shuttering Work In Progress | 69 |  |  |  |  | 0 |  |  |  | 4700000 | 0 | 0 | - |  | 4700000 | No | Yes
108 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/UGSS/00102 | Zone II | 20 | General Fund GENERAL/2025-26/009/UGSS/00102-Replacing the damaged UGSS main line at industries area in ward-20 TCMC ,Zone II | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 30-2/2025-26Dated:29/08/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 20/06/25 | 0.1 |  | 0 | Erection Of Pumps | 70 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 20/03/26 |  | 1000000 | No | No
109 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00013 | Zone I | 12 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00013-Construction of New Community toilet at Veerasamy Nagar in ward no.12 zone I | Sanitation Work | Constn of Community Toilet | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 600000 |  |  |  | 0 | 18/12/24 | 0.05 | Completed | 50 | Plastering Work Completed | 70 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | - |  | 12070000 | No | Yes
110 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2021-22/009/SANITATION/00032 |  |  | SBM 2.0 SBM 2.0/2021-22/009/SANITATION/00032-Construction of 152 of Individual House holds Latrine (IHHL) at Tambaram City Municipal Corporation | Sanitation Work | IHHL Sanitation | 5990/2022/SBM1Dated:11/04/22 | 2021-22 | 4560000 | 4560000 | 0 |  |  | 0.1 | 2023-07-02 | 0 | Completed | 71 | Completed | 71 |  |  |  |  | 0 |  |  |  | 4560000 | 0.1 | 22.92 | - |  | 4560000 | Yes | Yes
111 | Tambaram | New Office Building | CHENGALPATTU | New Off. Bldg/2023-24/009/BUILDING/00083 |  |  | New Office Building New Off. Bldg/2023-24/009/BUILDING/00083-Construction of New Corporation Office building at SF No. 218/2,226/1,226/2,227 Tambaram City Municipal Corporation, Tambaram Chengalpattu District | Buildings | Office Building | 546/MC7/2024-1Dated:15/03/24 | 2023-24 | 434000000 | 434000000 |  |  |  | 6 | 22/10/24 | 0 | Third Floor Roof Centering Work Is In Progress | 70 | Third Floor Roof Laid Elevation Work Is In Progress | 71 |  |  |  |  | 0 |  |  | 0 | 434000000 | 25.89 | 59.65 | - |  | 434000000 | No | Yes
112 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00345 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00345-Relaying of Road-Cement Concrete Road009010R0729-FATHIMA MANSIL STREET , 009010R0767-KRISHNAN STREET KALYANI PURAM , 009010R0747-MUTHUSA CROSS STREET , 009010R0760-KRISHANA STREET , 009010R0770-SIVA SANKARAN STREET THIRU NAGAR , 009010R0732-THANGAVEL STREET , 009010R0715-CHARCH STREET PONNI NAHAR , 009010R0743-4TH STREET NEHRU NAGAR , 009010L0038-THRIUVALLUVAR 2ND CROSS STREET PONNI NAGAR , 009010R0716-5TH STREET AYYAPPA NAGAR , 009010R0746-11TH STREET MUNGIL ERI , 009010R0741-10TH STR | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1000 Mts | 2025-26 | 237450000 | 5600000 |  |  |  | 0 | 2025-06-06 | 0.56 | Out Of 12 Roads 9 Roads Completed ,3 Roads To Be Started | 75 | Out Of 12 Roads 9 Roads Completed ,1 Road In Progress ,2 Roads To Be Started | 75 |  |  |  |  | 0 |  |  |  | 5600000 | 0.38 | 67.74 | 2025-05-08 |  | 237450000 | No | Yes
113 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00154 |  |  | General Fund GENERAL/2025-26/009/ROAD/00154-Repair /Maintenance-Bituminous Road009005R0427-GANDHI ROAD SHANKAR NAGAR , | Roads | Bituminous Road | 456/1Dated:25/09/25Road DetailsRoad Length :142 Mts | 2025-26 | 960000 | 960000 |  |  |  | 0 | 13/08/25 | 0 |  | 0 | Work In Progress | 75 |  |  |  |  | 0 |  |  |  | 960000 | 0 | 0 | - |  | 960000 | No | No
114 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00155 |  |  | General Fund GENERAL/2025-26/009/ROAD/00155-Repair /Maintenance-Bituminous Road009007R0525-7TH CROSS STREET ANNA NAGAR , | Roads | Bituminous Road | 456/3Dated:25/09/25Road DetailsRoad Length :82.5 Mts | 2025-26 | 640000 | 640000 |  |  |  | 0 | 13/08/25 | 0.06 |  | 0 | Work In Progress | 75 |  |  |  |  | 0 |  |  |  | 640000 | 0 | 0 | - |  | 640000 | No | No
115 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2024-25/009/BUILDING/00006 | Zone I | 4 | Kalaignar Nagarpura Mempatu Thittam KNMT/2024-25/009/BUILDING/00006-Construction of Daily Market at Anakaputhur Bazaar street ward No.04 Survey No. 309/1,309/2 and 309/3 zone I in Tambaram City Municipal Corporation | Buildings | Market | 13th CPSMC G.O.No.(4D).28Dated:09/09/24 | 2024-25 | 7100000 | 7100000 |  |  |  | 0 | 31/01/25 | 0.06 | Electrical Work And Plastering Work In Progress | 70 | Plastering Work In Progress | 75 |  |  |  |  | 0 |  |  | 0 | 7100000 | 0.32 | 45.01 | - |  | 7100000 | No | Yes
116 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WB/00153 | Zone I | 31 | General Fund GENERAL/2024-25/009/WB/00153-Raising Existing Toe wall , packing for Rough stone in Mukalathamman kulam ward no.31 zone-1 TCMC | WaterBodies | Improvement of Water Bodies | 610Dated:30/12/24 | 2024-25 | 3000000 | 3000000 |  |  |  | 0 | 25/02/25 | 0 |  | 0 | Work In Progress | 75 |  |  |  |  | 0 |  |  |  | 3000000 | 0 | 0 | - |  | 3000000 | No | No
117 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00156 | Zone II | 20 | General Fund GENERAL/2025-26/009/SWD/00156-Construction of SWD and Culvert at mk nagar main road in ward no-20 Zone II, TCMC | Storm Water Drain | Construction of Drain | 37-14/2025-26Dated:25/08/25 | 2025-26 | 820000 | 820000 |  |  |  | 0 | 29/09/25 | 0.08 | Pcc 1:2:4 | 75 | Pcc !:4:8 | 75 |  |  |  |  | 0 |  |  |  | 820000 | 0 | 0 | 29/12/25 |  | 820000 | No | Yes
118 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00005 | Zone II | 13 | Elementary Education Fund EE/2024-25/009/BUILDING/00005-Construction of additional school building at essa pallavaram middle school in wd no 13 Zone-2 | Buildings | Buildings | 446-2Dated:21/10/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 2024-08-11 | 0.6 | Plastering | 70 | Plastering | 75 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 2025-08-05 |  | 6000000 | No | Yes
119 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00124 | Zone II | 17 | Elementary Education Fund EE/2024-25/009/BUILDING/00124-Repair and maintance of floor, Toilet and tiles work at balaji salai anganwadi in ward no-17 Zone II, TCMC | Buildings | Anganwadi | 202-6/2024-25Dated:18/11/24 | 2024-25 | 950000 | 950000 |  |  |  | 0 | 13/11/24 | 0.1 | Roof Level | 50 | Roof Laid | 75 |  |  |  |  | 0 |  |  |  | 950000 | 0 | 0 | 13/02/25 |  | 950000 | No | Yes
120 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00120 | Zone II | 20, 21 | Elementary Education Fund EE/2024-25/009/BUILDING/00120-Renovation of anganvadi at PV Vaithiyalingam road , Ayothidasa pandithar street in ward no-20 & 21 Zone II, TCMC | Buildings | Anganwadi | 527-3/2024-25Dated:30/12/24 | 2024-25 | 2100000 | 2100000 |  |  |  | 0 | 21/03/25 | 0.21 | Plastering | 75 | Roof Laid | 75 |  |  |  |  | 0 |  |  |  | 2100000 | 0 | 0 | 21/06/25 |  | 2100000 | No | Yes
121 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2025-26/009/BUILDING/00367 | Zone IV |  | Elementary Education Fund EE/2025-26/009/BUILDING/00367-Construction of Muthalvar Padippagam at Perungalathur Higher Secondary school zone IV in Tambaram City Municipal Corporation | Buildings | Library | 12511/2025/A3Dated:05/06/25 | 2025-26 | 25000000 | 25000000 |  |  |  | 0 | 21/07/25 | 2.02 | 1St Floor Roof Laid | 70 | 2Nd Floor Roof Laid | 75 |  |  |  |  | 0 |  |  | 0 | 25000000 | 0 | 0 | 26/01/26 |  | 25000000 | No | Yes
122 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00129 | Zone V | 45 | General Fund GENERAL/2025-26/009/BUILDING/00129-Construction of GYM Building Ranga street at Ward no 45 Zone 5 at Tambaram City Municipal Corporation | Buildings | Construction of GYM | 611-1Dated:25/08/25 | 2025-26 | 4600000 | 4600000 |  |  |  | 0.46 | 17/09/25 | 0 | Plastering | 75 | Plastering | 75 |  |  |  |  | 0 |  |  |  | 4600000 | 0 | 0 | 24/01/26 |  | 4600000 | No | Yes
123 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2024-25/009/BUILDING/00156 | Zone I | 4 | Kalaignar Nagarpura Mempatu Thittam KNMT/2024-25/009/BUILDING/00156-Construction of Modern LPG Gasifier Crematorium at ward No.4, S.No.309/1,309/3 and 257/10 Kamarapuram Burial ground in Tambaram City Municipal Corporation | Buildings | Crematorium | 11th Common project sanctioningDated:11/06/24 | 2024-25 | 29400000 | 14700000 |  |  |  | 0.67 | 2024-11-09 | 1.43 | Plastering | 76 | Compound Wall Work In Progress | 76 |  |  |  |  | 0 |  |  | 0 | 14700000 | 0.67 | 45.35 | 2025-11-03 |  | 29400000 | No | Yes
124 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00202 | Zone II | 17 | General Fund GENERAL/2025-26/009/BUILDING/00202-Construction of ward office in subham nagar at ward-17 at zone-II,TCMC | Buildings | Buildings | 492-1 /2025-26Dated:25/08/25 | 2025-26 | 8800000 | 8800000 |  |  |  | 0 | 22/08/25 | 0.88 | Plastering | 80 | Roof Laid | 80 |  |  |  |  | 0 |  |  | 0 | 8800000 | 0 | 0 | 22/11/25 |  | 8800000 | No | Yes
125 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS | CHENGALPATTU | SFCOANDM/2024-25/009/BUILDING/00178 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS SFCOANDM/2024-25/009/BUILDING/00178-Construction of Toilet at Ponniamman CorporationPrimary school in ward No.17 Zone II in Tambaram City Municipal Corporation | Buildings | School Building | 21616/2024/SS2-2Dated:10/09/24 | 2024-25 | 4500000 | 1500000 |  |  |  | 0 | 18/10/24 | 0.15 | Lintel Level | 80 | Plastering | 80 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 4500000 | No | Yes
126 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00084 | Zone I | 5 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00084-Construction of Community Toilet at Fatima Nagar in ward No.05, Zone I in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 21/06/24 | 0.05 | Plastering | 80 | Plastering Work In Progress. | 80 |  |  |  |  | 0 |  |  | 0 | 600000 | 0 | 0 | - |  | 35640000 | No | Yes
127 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00402 | Zone II | 14 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00402-Construction of SWD at P.M.Gopal Street - 009014R0949,St.Mary Street - 009014R0932,Manimegalai Street - 009014R0947,Manimegalai Street Extension - 009014R0948,Dr. Saloman Street - 009014R0944,Sarojini 2St Cross Street - 009014R0937,Dr. Salomon Cross Street - 009014R0945 and Culvert at St.Mary Street - 009014R0932,Manimegalai Street - 009014R0947,Manimegalai Street Extension - 009014R0948,Dr. Saloman Street - 009014R0944 in Ward No.14 Tambaram City Municipal Corporation Zone II (Packag NO.6) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 5000000 |  |  |  | 0 | 2025-12-09 | 0.5 | Vent Flooring Plastering Work | 80 | Work Under Progress | 80 |  |  |  |  | 0 |  |  |  | 5000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
128 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00149 | Zone I | 1, 2, 3, 4 | General Fund GENERAL/2025-26/009/WS/00149-Annual Maintennace and Repairs to water supply mini power and deep bore well work at ward no.1,2,3,4 in TCMC | Water Supply | Repair Works - Water Supply | 262/4Dated:28/04/25 | 2025-26 | 1200000 | 1200000 |  |  |  | 0 | 29/04/25 | 0 |  | 0 | Work In Progress | 80 |  |  |  |  | 0 |  |  |  | 1200000 | 0 | 0 | - |  | 1200000 | No | No
129 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00159 | Zone V | 65 | General Fund GENERAL/2024-25/009/ROAD/00159-Relaying of Road-BT wih SWD009065R5018-SHARMA NAGAR , Zone V, ward No .65 in Tambaram Corporation | Roads | BT,CC,Paver Block wih SWD | 618Dated:25/08/25Road DetailsRoad Length :83 Mts | 2024-25 | 2000000 | 2000000 |  |  |  | 0 | 22/09/25 | 0.2 | Nearing Completion | 80 | Nearing Completion | 80 |  |  |  |  | 0 |  |  |  | 2000000 | 0 | 0 | 30/10/25 |  | 2000000 | No | Yes
130 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00010 | Zone II | 28, 29, 31, 32, 33 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00010-Providing Internal connection between inner premises of resident and chamber for house service connection -6288 nos. Ward covered 28,29,31,32 and 33(p) | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 64500000 |  |  | 0 | 2 | 31/08/18 | 5.68 | Out Of 6288 Hsc, 5299 Nos Of Hsc Connections Given | 79 | Out Of 6288 Hsc, 5299 Nos Of Hsc Connections Given | 80 |  |  |  |  | 0 |  |  |  | 64500000 | 0.29 | 4.52 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
131 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00151 | Zone I | 10 | General Fund GENERAL/2024-25/009/BUILDING/00151-Construction of Additional School Building at Natarajan school in ward no.10 Zone 1 TCMC | Buildings | School Building | 547Dated:30/12/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 16/04/25 | 0 |  | 0 | Work In Progress | 80 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | - |  | 6000000 | No | No
132 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00397 | Zone 01 | 7, 8 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00397-Construction of storm water drain with cover slab from Kamarajar Road to Signal Office Road (via Kamarajar Salai, Nallathambi Road, and Gandhi Road) in Ward No.07 and 08 in Tambaram City Municipal Corporation Zone No.01 (Package No.1) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 45000000 |  |  |  | 0 | 19/09/25 | 4.5 | 500M Cover Slab Completed, 40M Earthwork Completed | 50 | 700M Cover Slab Completed, 20M Earthwork Completed | 80 |  |  |  |  | 0 |  |  | 0 | 45000000 | 2.01 | 44.75 | 18/12/25 |  | 200000000 | No | Yes
133 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00412 | Zone II | 28 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00412-Construction of SWD and Culvert at New Colony 16th Cross Street - 009028R1802,New Colony 16th Cross Street 1st Extn - 009028R1806,New Colony 16th Cross Street 2nd Extn- 009028R1807,New Colony 16th Cross Street 3rd Extn- 009028R1808,Moomrthi Nagar Main Road - 009028R1812,New Colony 6th Cross Street - 009028R1834 in Ward No.28 Tambaram City Municipal Corporation Zone II (Packag NO.16) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3900000 |  |  |  | 0 | 2025-12-09 | 0.39 | 80 % Work Completed,culvert Side Wall Centering Work Progress | 75 | 80 % Work Completed,culvert Side Wall Centering Work Progress | 80 |  |  |  |  | 0 |  |  |  | 3900000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
134 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00276 | Zone III | 44 | General Fund GENERAL/2025-26/009/BUILDING/00276-Construction of Anganwadi Building At THirunavukkarasu Street IN Ward No.44 | Buildings | Anganwadi | 94-6Dated:06/03/25 | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 2025-03-04 | 0.24 |  | 0 | Plastering | 80 |  |  |  |  | 0 |  |  | 0 | 2500000 | 0 | 0 | 2025-10-07 |  | 2500000 | No | Yes
135 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00045 | Zone I | 31 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00045-Water bodies rejuvenation at Uyaliamman koil kulam, Ward No.31, Zone I Survey No. 270 in Thiruneermalai, Tambaram City Municipal Corporation, chengalpattu District | WaterBodies | Improvement of Water Bodies | 26112/2023Dated:03/01/24 | 2023-24 | 11800000 | 4400000 |  | 0 | 0 | 0 | 16/02/24 | 0.44 | Nearing Completion | 80 | Nearing Completion | 80 |  |  |  |  | 0 |  |  |  | 4400000 | 0.26 | 59.61 | - |  | 11800000 | No | Yes
136 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00185 | Zone V | 63 | MLA Fund MLA/2024-25/009/BUILDING/00185-Construction of Public Distribution shop at Balaraman stret in ward No. 63 , Zone No. V in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1070000 |  |  |  | 0 | 29/10/24 | 0.09 | Plastering And Tiles Laying Work Progress | 85 | Plastering And Tiles Laying Work Progress | 85 |  |  |  |  | 0 |  |  |  | 1070000 | 0 | 0 | 26/07/25 |  | 9650000 | No | Yes
137 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00419 | Zone IV | 51, 53 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00419-Construction of Storm Water Drain to BAJANAI KOIL STREET 009051R3639 Ambedhkar street 009051R3640 Rajagopal Nagar 2nd St 009051R3645 SRI RAM NAGAR 6TH STREET 009053R3877 SRI RAM NAGAR 5TH STREET 009053R3876 SRI RAM NAGAR 4TH STREET 009053R3875 MOOVENDAR NAGAR 009055R4008 Jerusulam Nagar David Street 009053R3868 in Ward no.51,53 in Zone-4 (Package No.23) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 9000000 |  |  |  | 0 | 2025-12-09 | 0.9 | Ambedkar St , Rajagopal Nagar & Jerusulam Nagar David St Work Is Under Progress | 82 | Completed | 85 |  |  |  |  | 0 |  |  |  | 9000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
138 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00410 | Zone II | 26 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00410-Construction of SWD and Culvert at BHARATHIYAR STREET-009026R1756,NAIDU SHOP ROAD-009026R1736 in Ward No.26 Tambaram City Municipal Corporation Zone II (Packag NO.14) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3400000 |  |  |  | 0 | 2025-12-09 | 0.34 | Work In Progress | 85 | Work In Progress | 85 |  |  |  |  | 0 |  |  |  | 3400000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
139 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00083 |  |  | TURIP TURIP/2025-26/009/ROAD/00083-Relaying of Road-Bituminous Road009021R1357-ELANGO STREET , 009021R1342-BANGARU NAGAR , 009021R1414-GARDEN WOODROFF NAGAR 3RD CROSS STREET , 009021R1338-R.K.V. AVENUE 6YH STREET , 009021R1385-THIRUTANI NAGAR- PALAR STREET , 009021S0234-THIRUMURUGAN NAGAR 2ND STREET , 009021R5861-Nagalakshmi Salai Extn. , 009021R1349-P.V. Vaithiyalingam Cross Street , 009R0211347-Thirumurugan nagar main road , 009021R1368-Ganesh priyan avenue 2nd Street , 009027S0337-Puduvai Nagar 3rd Street , 009027R1782-CLC IS | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2755 Mts | 2025-26 | 521620000 | 16000000 |  |  |  | 0 | 2025-10-06 | 1.6 | Out Of 17 Roads, 15Nos Of Road Completed, 2 Nos Of Roads Milling Completed | 85 | Out Of 17 Roads, 15Nos Of Road Completed, 2 Nos Of Roads Milling Completed | 85 |  |  |  |  | 0 |  |  |  | 16000000 | 0.74 | 46.13 | 2025-09-08 |  | 521620000 | No | Yes
140 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00399 | Zone I | 31 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00399-Construction of RCC Storm water drain with cover slab at East mada street in ward no.31 Tambaram City Municipal Corporation Zone-1 (Packag NO.3) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 5000000 |  |  |  | 0 | 2025-09-09 | 0.5 | 80M Sidewall Completed. 2 Culvert Completed. 60M Cover Slap Work In Progress | 60 | 140M Sidewall Completed. 50M Wall Reinforement Work In Progress | 85 |  |  |  |  | 0 |  |  | 0 | 5000000 | 0 | 0 | 2025-08-12 |  | 200000000 | No | Yes
141 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00089 |  |  | TURIP TURIP/2025-26/009/ROAD/00089-Relaying of Road-Bituminous Road009051R3672-Thiruneermalai Road Dharges to Mariamman koil street , 009051R3673-Thiruneermalai Road Mariamman koil street to Arputham Nagar , 009051R3639-BAJANAI KOIL STREET , 009049R3548-DURAISWAMY REDDDY STREET , 009053R3829-THIRUVENKADAM NAGAR , 009053R3848-8TH ST KRISHNA NAGAR-MUDICHUR RD , 009053R3820-KULAKKARAI MAIN ROAD , 009053R3822-IST KULAKKARAI ST , 009053R3823-KULAKARAI 1ST CROSS STREET , 009053R3824-KULAKARAI 2ND CROSS STREET , 009053R3826-2ND ST-KULA | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3233 Mts | 2025-26 | 521620000 | 23300000 |  |  |  | 0 | 2025-10-06 | 2.33 | Out Of 15 Roads , 13 Roads Completed , 2 Roads Not Started | 87 | Out Of 15 Roads , 13 Roads Completed , 2 Roads Not Started | 87 |  |  |  |  | 0 |  |  |  | 23300000 | 1.82 | 78.25 | 2025-09-08 |  | 521620000 | No | No
142 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00011 | Zone I | 3 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00011-Construction of New Community Toilet at Bazzar street in ward No.03 , Zone I | Sanitation Work | Constn of Community Toilet | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 600000 |  |  |  | 0 | 2025-06-01 | 0.05 | Tiles Laying Work And Electrical Work In Progress | 85 | Electrical Work In Progress | 87 |  |  |  |  | 0 |  |  | 0 | 600000 | 0 | 0 | 18/01/26 |  | 12070000 | No | Yes
143 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00267 | Zone I |  | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00267-Construction of New Urban PHC at Thiruneermalai Therku Kulakkarai street, Thiruneermalai, Zone I | Buildings | Buildings | 1869/NUHM/SHS/2015-2Dated:03/08/22 | 2023-24 | 24000000 | 12000000 |  |  |  | 1.1 | 2024-10-01 | 1.2 | Door Fixing Work In Progress.tiles Laying Work In Progress | 86 | Ground Floor Tiles Work Completed. 1St Floor Wall Tiles Work In Progress. Paver Block Work In Progress | 88 |  |  |  |  | 0 |  |  | 0 | 12000000 | 0.5 | 41.62 | - |  | 24000000 | No | Yes
144 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/WS/00191 | Zone I | 4 | MLA Fund MLA/2024-25/009/WS/00191-Providing Borewell with Mini power pump syntex at 3 locations in ward No.04 Zone I in Tambaram City Municipal Corporation | Water Supply | Borewell | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 840000 |  |  |  | 0 | 26/10/24 | 0.07 | Out 3Borewell. 2 Borewell Completed, Sintex Tank Fixing Work In Progress | 55 | Finishing Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 840000 | 0 | 0 | - |  | 16540000 | No | Yes
145 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00385 |  |  | TURIP TURIP/2025-26/009/ROAD/00385-Relaying of Road-Bituminous Road009009R0693-ANJANEYAR KOIL STREET WEST , 009015R0966-Zamindar Lane Cross Street , 009015R0965-Zamindhar lane , 009016R1007-PACHAIAMMAN KOIL STREET , 009016R0996-MALAIMAGAL STREET , 009016R1003-Pachaiyappan Colony 1st Street , 009016S0111-Vembuli Nagar 3rd Cross Street , 009016S0112-Vembuli Nagar 1st Cross Street , 009016R1005-Vembuli Nagar 2nd Cross Street , 009016R0989-BHARATHI NAGAR 1ST STREET , 009016R0999-Pachaiyappan Colony 3rd Cross Street , (Package No.IX) | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2611 Mts | 2025-26 | 182896000 | 8600000 |  |  |  | 0 | 18/08/25 | 0.86 | Out Of 11 Roads 10 Roads Completed 1 Roads In Progress . | 90 | Out Of 11 Roads 10 Roads Completed 1 Roads In Progress | 90 |  |  |  |  | 0 |  |  |  | 8600000 | 0 | 0 | 15/05/26 |  | 182896000 | No | Yes
146 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00079 | Zone I |  | TURIP TURIP/2025-26/009/ROAD/00079-Relaying of Road-Bituminous Road009006R0469-7TH STREET M G R NAGAR , 009006S0028-GOWTHAMAN CROSS STREET , 009006R0480-THOLKAPPIYAR STREET PAMMAL , 009006R0503-MA. SURAN STREET , 009006R0507-GOWTHAMAN STREET PASUMPON NAGAR , 009006R0476-THANDHAI PERIYAR CROSS STREET V O C NAGAR , 009006R0451-T R MANI 2ND CROSS STREET , 009006S0032-R.V. SUBRAMANIAM STREET PASUMPON NAGAR , Zone I (Package No.III) | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :876 Mts | 2025-26 | 521620000 | 6500000 |  |  |  | 0 | 2025-10-06 | 0.65 | Out Of 8 Roads , 7 Roads Completed 1 Road Not Started | 90 | Out Of 8 Roads , 7 Roads Completed 1 Road Not Started | 90 |  |  |  |  | 0 |  |  |  | 6500000 | 0.34 | 52.68 | 2025-09-08 |  | 521620000 | No | No
147 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00107 | Zone I | 3 | General Fund GENERAL/2024-25/009/SWD/00107-Construction of Storm water drain to Thiruvalluvar street, KK Sha street, Kattabomman street,ward no.3,zone-1 TCMC) | Storm Water Drain | Construction of Drain | 449Dated:24/06/25 | 2024-25 | 1600000 | 1600000 |  |  |  | 0 | 14/08/25 | 0.16 |  | 0 | Finishing Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 1600000 | 0 | 0 | - |  | 1600000 | No | No
148 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00108 | Zone I | 3 | General Fund GENERAL/2024-25/009/SWD/00108-Construction of Storm water drain and 2 nos culvert to pari nagar kurinji nagar ward no.3 in Anakaputhur zone-1 TCMC | Storm Water Drain | Construction of Drain | 449/3Dated:24/06/25 | 2024-25 | 1200000 | 1200000 |  |  |  | 0 | 14/08/25 | 0.12 |  | 0 | Finishing Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 1200000 | 0 | 0 | - |  | 1200000 | No | No
149 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00190 | Zone I | 31 | General Fund GENERAL/2024-25/009/SWD/00190-Construction of storm water drain to parvathipuram 3rd street, 2nd street, Subraiya nagar 5th cross street, Subraiya nagar 4th cross street and Kasi gardern phase 1 in ward no.31 Zone -1 TCMC | Storm Water Drain | Construction of Drain | 87/3Dated:06/03/25 | 2024-25 | 2410000 | 2410000 |  |  |  | 0 | 23/06/25 | 0 |  | 0 | Nearing Completion | 90 |  |  |  |  | 0 |  |  |  | 2410000 | 0 | 0 | - |  | 2410000 | No | Yes
150 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00226 | Zone I | 4 | General Fund GENERAL/2025-26/009/SWD/00226-Construction of RCC Culvert in Anna nagar main road ,Anna nagar 2nd street, Anna nagar 2nd cross street in ward no.4 Anakaputhur Zone no.1 TCMC | Storm Water Drain | Construction of Drain | 469/2025-26Dated:25/09/25 | 2025-26 | 990000 | 990000 |  |  |  | 0 | 24/10/25 | 0.1 |  | 0 | Work Completed. | 90 |  |  |  |  | 0 |  |  | 0 | 990000 | 0 | 0 | - |  | 990000 | No | No
151 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00126 | Zone II | 30 | General Fund GENERAL/2024-25/009/SWD/00126-Construction of Storm water drain to Durga nagar Thiruvalluvar street,Bhavani amman koil street, nehru street, Thiruvalluvar street, kabilar street culvert in ward no.30 at TCMC | Storm Water Drain | Construction of Drain | 87/4Dated:06/03/25 | 2024-25 | 1500000 | 1500000 |  |  |  | 0 | 18/06/25 | 0.15 |  | 0 | Finishing Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 1500000 | No | Yes
152 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00223 | Zone I |  | General Fund GENERAL/2024-25/009/BUILDING/00223-Construction of Additional school Building at Thiruneermalai Lakshmipuram Padasalai street Primary school at Main road in ward no,29 Zone-1 TCMC | Buildings | Additional school building | 444/2024-25Dated:21/10/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 21/04/25 | 0.6 |  | 0 | Nearing Completion. | 90 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0 | 0 | - |  | 6000000 | No | Yes
153 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/UGSS/00109 |  |  | Namakku Naame Thittam NNT/2022-23/009/UGSS/00109-Providing UGD pipe line arragements in Pumping station at RKV Avenue and providing machine holes from VEls univerisyt to Radial road | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 1120000 |  |  |  | 0.11 | 24/04/23 | 0.09 | Nearly Completed | 80 | Nearly Completed | 90 |  |  |  |  | 0 |  |  |  | 1120000 | 0 | 0 | 19/01/24 |  | 15130000 | No | Yes
154 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00186 | Zone I | 10 | General Fund GENERAL/2025-26/009/BUILDING/00186-Providng Compound wall Fencing at ward no.10 Zone-1 TCMC | Buildings | Construction of Compound Wall | 368//1Dated:24/06/25 | 2025-26 | 2000000 | 2000000 |  |  |  | 0 | 26/06/25 | 0.2 |  | 0 | Nearing Completion | 90 |  |  |  |  | 0 |  |  |  | 2000000 | 0 | 0 | - |  | 2000000 | No | No
155 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WB/00152 | Zone I | 31 | General Fund GENERAL/2025-26/009/WB/00152-Raising Existing Toa wall Packing of Rough stone at ward no.31 Mukalathamman koil street Zone-1 TCMC | WaterBodies | Improvement of Water Bodies | 875Dated:31/10/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 2025-10-11 | 0.15 |  | 0 | Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 1500000 | No | No
156 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00112 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00112-Construction of Public Toilet at Kundumedu MCC in ward No.32 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-12-06 | 0.1 | Plastering Completed White Wash Work Is In Progress | 77 | Completed | 90 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 2024-12-08 |  | 35640000 | No | Yes
157 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00086 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00086-Construction of Community Toilet at Amman kovil MCC in ward No.32, Zone 4 in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 2024-05-07 | 0.06 | Electrical Work And Tiles Laying Complete Colour Wash Work Is Progress | 85 | Completed | 90 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | - |  | 35640000 | No | Yes
158 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00193 | Zone I | 31 | MLA Fund MLA/2024-25/009/BUILDING/00193-Construction of PDS Toilet at ward No. 31 zone-I in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 21/11/24 | 0 | Finishing Work In Progress | 88 | Finishing Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
159 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00028 | Zone I | 6 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00028-Repair and maintaining of Community toilet at Pasumpon Nagar in ward No.06 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 260000 |  |  |  | 0 | 2025-03-01 | 0.02 | White Wash Work In Progress | 82 | Painting Work In Progress | 90 |  |  |  |  | 0 |  |  |  | 260000 | 0 | 0 | - |  | 12070000 | No | Yes
160 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00044 | Zone V |  | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00044-Supply and fixing of 250HP motor with pump at Melachery Head works (River palar) in Zone V | Water Supply Improvement Scheme | Source Augmentation | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 10000000 |  |  |  | 0 | 2025-10-06 | 0.84 | Supplying Of Electromagnetic Flow Meter | 60 | Completed | 90 |  |  |  |  | 0 |  |  |  | 10000000 | 0.64 | 63.74 | - |  | 48950000 | No | Yes
161 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2025-26/009/SWM/00363 | Zone III |  | SBM 2.0 SBM 2.0/2025-26/009/SWM/00363-Construction of Transfer station for Tambaram Corporation at the location near TVK nagar with a capacity of 50 TPD at zone III | Solid Waste Management | SWM | 6450/2024/SBM-1 IIDated:24/03/25 | 2025-26 | 310370000 | 33450000 |  |  |  | 0 | 14/07/25 | 3.35 | Finishing Work | 60 | Finishing Work | 90 |  |  |  |  | 0 |  |  | 0 | 33450000 | 0 | 0 | 2026-10-04 |  | 310370000 | No | Yes
162 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00013 | Zone II | 11, 12, 13, 14, 15, 16, 17, 18 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00013-Providing Internal connection between inner premises of resident and chamber for house service connection -6472 nos. Ward covered 11,12,13,14, 15,16,17 and 18(p) | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 50000000 | 0 |  |  | 4.5 | 31/08/18 | 4.5 | Plastering | 88 | Plastering | 90 |  |  |  |  | 0 |  |  |  | 50000000 | 4.07 | 81.43 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
163 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00023 | Zone II | 18 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00023-Providing Internal connection between inner premises of resident and chamber for house service connection -5635 nos. Ward covered 18(p),22,23,24,25,26 & 27 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 58000000 | 0 |  |  | 1 | 31/08/18 | 5.26 | Plastering | 50 | Out Of 5635 Hsc 5053 Completed | 90 |  |  |  |  | 0 |  |  |  | 58000000 | 1.35 | 23.35 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
164 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2024-25/009/BUILDING/00157 | Zone II | 15 | Kalaignar Nagarpura Mempatu Thittam KNMT/2024-25/009/BUILDING/00157-Construction of Modern LPG Gasifier Crematorium at ward No.15, survey No.87 Jamindar lane Burial ground in Tambaram City Municipal Corporation Zone II | Buildings | Crematorium | 11th Common project sanctioningDated:11/06/24 | 2024-25 | 29400000 | 14700000 |  |  |  | 0 | 2024-11-09 | 1.43 | Weathering Course Tiles And Floor Tiles Completed | 92 | Plastering | 92 |  |  |  |  | 0 |  |  |  | 14700000 | 0.37 | 24.87 | 2025-11-06 |  | 29400000 | No | Yes
165 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00349 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00349-Relaying of Road-Cement Concrete Road009012R0852-M.C. RAJA STREET , 009012R0883-RANI ANNA STREET , 009012L0045-MEENAMBAL STREET , 009012R0893-1ST STREET ESWARI NAGAR , 009012L0048-4TH STREET ESWARI NAGAR , 009012L0046-JAYAMERY STREET , 009012S0087-MOVENDAR STREET NAGAL KENI , 009012L0047-BAJANAI KOIL STREET - NAGALKENI , 009012S0090-KANNAN STREET VEERACHSAMI NAGAR , 009012R0901-KATHAR BHASHA STREET , 009012L0051-PILLAIYAR KOVIL 2ND CROSS STREET , 009012R0870-NAVAMANI CROSS STREET , 80.13 | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1869 Mts | 2025-26 | 237450000 | 8100000 |  |  |  | 0 | 2025-06-06 | 0.81 | Out Of 14 Roads 12 Roads Completed,1 Road In Progress,1 Road To Be Started | 86 | Out Of 14 Roads 13 Roads Completed,1 Road To Be Started | 92 |  |  |  |  | 0 |  |  |  | 8100000 | 0 | 0 | 2025-06-08 |  | 237450000 | No | Yes
166 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00008 | Zone II | 2, 3, 4, 10, 30, 33 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00008-Providing Internal connection between inner premises of resident and chamber for house service connection - 5852 nos. Ward covered 2,3,4,10,30, 33(p),34,35,36 and 37 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 60000000 | 0 |  |  | 2 | 31/08/18 | 5.43 | Pipe Line Supply | 89 | Plastering | 92 |  |  |  |  | 0 |  |  |  | 60000000 | 0.9 | 15.06 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
167 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2025-26/009/SWM/00365 | Zone I |  | SBM 2.0 SBM 2.0/2025-26/009/SWM/00365-Construction of Transfer station for Tambaram Corporation at the Location near Mangalagiri with a capacity of 150 TPD zone I | Solid Waste Management | SWM | 6450/2024/SBM-1 IIDated:24/03/25 | 2025-26 | 310370000 | 97850000 |  |  |  | 0 | 21/07/25 | 9.79 | Finishing Work In Progress. Nearing Completion. | 91 | Finishing Work In Progress . Nearing Completion | 93 |  |  |  |  | 0 |  |  |  | 97850000 | 0 | 0 | 17/04/26 |  | 310370000 | No | Yes
168 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00194 | Zone I | 31 | General Fund GENERAL/2025-26/009/ROAD/00194-Providing Cement Concrete road at Mangeleri Transfer station and Tiruneermalai (M sand plant to Tiruneermalai service road) ward No.31, Zone I in TCMC | Roads | Earthern Road | 870/1Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 11000000 | 5000000 |  |  |  | 0 | 21/01/26 | 0.5 |  | 0 | Nearing Completion | 95 |  |  |  |  | 0 |  |  |  | 5000000 | 0 | 0 | - |  | 11000000 | No | Yes
169 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00199 | Zone I | 6 | MLA Fund MLA/2024-25/009/BUILDING/00199-Construction of PDS Toilet at ward No. 6 zone-I in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 26/10/24 | 0.11 | Tiles Laying Work | 55 | Finishing Work In Progress | 95 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
170 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00408 | Zone II | 20 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00408-Construction of SWD at Ambal Nagar 21St Street - 009020R1228,Thenmozhi Nagar 2Nd Street - 009020R1254,Velusamy Nagar - 009020R1306,Velusamy Nagar - 009020R1307,Velusamy Nagar 6Th St - 009020R5829,Velusamy Nagar 7Th St - 009020R5831,Velusammy Nagar 6Th Cross Street - 009020R5830,Sai Street - 009020R1291,Indian Colony - 009020R1292 and Culvert at Velusamy Nagar - 009020R1306,Velusamy Nagar - 009020R1307 in Ward No.20 Tambaram City Municipal Corporation Zone II (Packag NO.12) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 6000000 |  |  |  | 0 | 2025-12-09 | 0.6 | Nearly Completed | 95 | Nearly Completed | 95 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
171 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00191 | Zone I | 30 | General Fund GENERAL/2024-25/009/BUILDING/00191-Providing Paver block Road, Compound wall and Genset shed to Lakshmi Puram Burial Ground road to ward no.30 Zone-1 TCMC | Buildings | Construction of Compound Wall | 69Dated:06/03/25 | 2024-25 | 2300000 | 2300000 |  |  |  | 0 | 24/03/25 | 0 |  | 0 | Completed | 95 |  |  |  |  | 0 |  |  |  | 2300000 | 0 | 0 | - |  | 2300000 | No | Yes
172 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/PARK/00200 | Zone II | 30 | General Fund GENERAL/2023-24/009/PARK/00200-Improvement to Partk at Thiruneermalai Periyar TNHB Phase -II in ward no.30 TCMC | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 239/6Dated:15/06/23 | 2023-24 | 500000 | 500000 |  |  |  | 0 | 23/08/24 | 0.05 |  | 0 | Nearing Completion | 95 |  |  |  |  | 0 |  |  | 0 | 500000 | 0 | 0 | - |  | 500000 | No | Yes
173 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SL/00136 | Zone I | 8 | General Fund GENERAL/2025-26/009/SL/00136-Supply and Fixing of street lights with new pole single and Double arm in Thiruvalluvar 1st,2nd,3rd,4th,5th,6th,7th cross street, Thiru vi ka 1st to 7th cross street in ward no.08 TCMC | Streetlight | StreetLight | 443Dated:24/06/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 14/08/25 | 0.15 |  | 0 | Work Under Progress | 95 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 1500000 | No | No
174 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00101 |  |  | TURIP TURIP/2025-26/009/ROAD/00101-Relaying of Road-Bituminous Road009059R4391-AMUDHAM NAGAR MAIN ROAD , 009059R4393-SAKTHI NAGAR 6TH STREET , 009059R4404-SAKTHI NAGAR 4TH STREET (SLUM CLEARANCE BOARD HOUSES) , 009059R4452-RAMANUJAM STREET , 009059R4462-VENKATESAN STREET , 009059R4481-KALAIVANI STREET , 009059R4519-VALAYAPATHY STREET , 009059R4521-KUNDALAKESI 2ND STREET , 009059R4522-BHARATHIDASAN STREET , 009059R4533-SRINIVASARAGHAVAN STREET , 009059R4386-SAKTHI NAGAR 1ST STREET , 009059R4385-SAKTHI NAGAR 2ND STREET , 009059R437 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :4190 Mts | 2025-26 | 521620000 | 32000000 |  |  |  | 0 | 2025-10-06 | 2.62 | Out Of 27 Roads ,24 Roads Completed ,1 Roads Is In Progress , 2 Roads To Be Started | 88 | Completed | 95 |  |  |  |  | 0 |  |  |  | 32000000 | 0 | 0 | 2025-09-08 |  | 521620000 | No | Yes
175 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00416 | Zone IV | 57 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00416-Construction of SWD and Culvert from Krishna road to Kalki street in Ward no.57 in Zone-4 (Package No.20) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 5600000 |  |  |  | 0 | 2025-12-09 | 0.56 | Nearing Completion | 95 | Completed | 95 |  |  |  |  | 0 |  |  |  | 5600000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
176 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00126 | Zone IV | 50 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00126-Construction of Urinals at GST Road , ward No.50 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0 | 2024-02-07 | 0.01 | Foundation Work Is In Progress | 15 | Completed | 95 | 28/05/25 |  |  |  | 0 |  |  |  | 130000 | 0 | 0 | - |  | 35640000 | No | Yes
177 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00127 | Zone IV | 49 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00127-Construction of Urinals at Irumbuliyur subway , ward No.49 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0 | 2024-02-07 | 0.01 | Plastering Work Is In Progress | 70 | Completed | 95 |  |  |  |  | 0 |  |  |  | 130000 | 0 | 0 | - |  | 35640000 | No | Yes
178 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00155 | Zone IV |  | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00155-Construction of A 3+3 class room and 3 seats of toilet at ground and first floor building at Kalyan Nagar High school, Zone IV | Buildings | Additional school building | 21615/2024/ss2Dated:22/07/24 | 2024-25 | 29100000 | 14000000 |  |  |  | 0 | 19/09/24 | 1.15 | Painting Work And Electricals Works In Progress | 70 | Completed | 95 |  |  |  |  | 0 |  |  |  | 14000000 | 0.31 | 21.95 | 17/06/25 |  | 29100000 | No | Yes
179 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00042 | Zone IV | 55 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00042-Greenspace Development and improvement to Alwain Garden park in S.No. 419n at Perungalathur ward No.55 zone iv in Tambaram City Municipal Corporation | Parks | Parks | 26112/2023Dated:03/01/24 | 2023-24 | 11800000 | 2500000 |  | 0 | 0 | 0.25 | 2024-12-02 | 0.21 | Compound Wall Work Completed, Path Way Work Is In Progress And Gate Fixing Work Is In Progress | 63 | Completed | 95 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | - |  | 11800000 | No | Yes
180 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00047 | Zone IV | 56 | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00047-Extension of pipe line from Peruratchi mandra street to sitheri GLR in ward NO.56 in Zone IV | Water Supply Improvement Scheme | Laying of Feeder Main and Distribution Main | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 5700000 |  |  |  | 0 | 2025-04-04 | 0.47 | Pipe Laying | 90 | Completed | 95 |  |  |  |  | 0 |  |  |  | 5700000 | 0 | 0 | - |  | 48950000 | No | Yes
181 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00046 | Zone IV | 56 | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00046-Extension of pipe line from Mudichur road to Parvathy Nagar OHT and Mudichur road to Peruratchi Mandra street ward No.56 in zone IV | Water Supply Improvement Scheme | Const OHT & Sump | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 4100000 |  |  |  | 0 | 2025-04-04 | 0.34 | Pipe Laying | 90 | Completed | 95 |  |  |  |  | 0 |  |  |  | 4100000 | 0 | 0 | 30/12/25 |  | 48950000 | No | Yes
182 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00094 |  |  | TURIP TURIP/2025-26/009/ROAD/00094-Relaying of Road-Bituminous Road009033R2117-TNHB PHASE 3 MAIN ROAD , 009033R2118-TNHB PHASE 3 1ST STREET , 009033R2119-TNHB PHASE 3 2ND STREET , 009033R2120-TNHB PHASE 3 1ST CROSS STREET , 009033R2121-TNHB PHASE 3 2ND CROSS STREET , 009033R2122-TNHB PHASE 3 3RD CROSS STREET , 009033R2130-Moulana Nagar Main Road , 009033R2148- JAYA NAGAR 1ST CROSS STREET , 009033R2167-JAYA STREET , 009033R2176-RV GARDEN MAIN ROAD , 009033R2177-RV GARDEN BHUVANESWARI STREET , 009033R2178-JEEVA STREET, R.V.GARDEN | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2319 Mts | 2025-26 | 521620000 | 15700000 |  |  |  | 1.41 | 2025-10-06 | 1.27 | Bituminous Concrete | 83 | Completed | 95 |  |  | 2026-09-01 |  | 15334260 |  |  | 0 | 365740 | 1.41 | 90 | 2025-09-08 |  | 521620000 | No | Yes
183 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SWM/00010 |  |  | SBM 2.0 SBM 2.0/2024-25/009/SWM/00010-Procurement of 2nos of Truck Mounted Road sweeping machine in Tambaram City Municipal Corporation | Solid Waste Management | Procurement of Vehicles /Machineries | 6450/2024/SBM1Dated:22/10/24 | 2024-25 | 17000000 | 17000000 |  |  |  | 1.7 | 17/02/25 | 1.7 | Procurement Of Vehicles/machineries | 95 | Completed | 95 |  |  |  |  | 0 |  |  |  | 17000000 | 1.7 | 99.85 | 18/11/25 |  | 17000000 | No | Yes
184 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2024-25/009/PARK/00005 | Zone IV | 58 | Kalaignar Nagarpura Mempatu Thittam KNMT/2024-25/009/PARK/00005-Construction of Science park in NGO colony park at Perungalathur, ward No.58, Survey NO. 365/A2 , Zone IV in Tambaram City Municipal Corporation | Parks | Parks | G.O.(4D)No.34Dated:04/12/24 | 2024-25 | 18900000 | 18900000 |  |  |  | 1.7 | 2025-05-02 | 1.55 | Completed | 95 | Completed | 95 |  |  |  |  | 0 |  |  |  | 18900000 | 0.96 | 50.77 | 2025-03-11 |  | 18900000 | No | Yes
185 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2023-24/009/PURCHASE/00194 |  |  | 15th CFC 15thCFC/2023-24/009/PURCHASE/00194-Supply and delivery of 6 Nos of MS desilting Machine capacity 250 kg | Purchase of Materials | Purchase of Machineries | 16479/2023/CFC-1Dated:06/07/23 | 2023-24 | 106324000 | 3120000 |  |  |  | 0.31 | 2024-09-01 | 0.31 | Completed | 95 | Completed | 95 |  |  |  |  | 0 |  |  |  | 3120000 | 0.13 | 41.66 | 2024-08-04 |  | 106324000 | No | Yes
186 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00172 | Zone I | 31 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00172-Construction of School building (2+2) and 4nos of Toilet and urinals in Corporation Primary school, ward No. 31 at Thiruneermalai Zone I in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 10250000 |  |  |  | 0 | 24/10/24 | 1.01 | Completed | 95 | Finishing Work In Progress | 95 |  |  |  |  | 0 |  |  | 0 | 10250000 | 0 | 0 | - |  | 40950000 | No | Yes
187 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00101 | Zone II | 21 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00101- Construction of Public Toilet at Highway nagar in ward No.21 Zone II in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0.07 | Completed | 80 | Work Completed. | 95 |  |  |  |  | 0 |  |  | 0 | 1000000 | 0 | 0 | 21/09/24 |  | 35640000 | No | Yes
188 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00459 | Zone II |  | Elementary Education Fund EE/2024-25/009/BUILDING/00459-Construction of Compound wall and providing Paver block,CCTC ,PA system ,Ro plant computer and UPC windows at ponniamman hr sec school in Zone-II | Buildings | Buildings | 446/21.10.2024Dated:21/10/25 | 2024-25 | 24000000 | 6000000 |  |  |  | 0.25 | 2024-08-11 | 0.6 | Plastering | 80 | Painting Work Progress | 95 |  |  |  |  | 0 |  |  |  | 6000000 | 0.25 | 41 | 2025-08-05 |  | 24000000 | No | Yes
189 | Tambaram | Integrated UGSS | CHENGALPATTU | Integrated/2020-21/009/UGSS/00082 |  |  | Integrated UGSS Integrated/2020-21/009/UGSS/00082-Providing Sewerage Collection System with new underground sewer lines, manholes, pumping stations and lifting station, house service sewer connections for pammal (Pacakge - 1) | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | G.O. Ms. No. 126 Municipal Administration and Water Supply Department [MA-3(2)]Dated:16/11/20 | 2020-21 | 2111500000 | 1015800000 |  |  |  | 40 | 26/02/21 | 10.16 | Eot Up To -30.06.2025. Laying Dwc Pipe - Out Of 89.422.00 Km 84.703Km Completed, Laying Of Ci Gravity Main Line Out Of8.957 Km 5.528Km Completed Laying Of Ci Pumping Main Line -Out Of 6.355Km 5.798Km Completed, Hsc Out Of 16244 Nos 16244 Nos Completed, Internal Chamber - Out Of 16244 Nos, 15948 Completed | 91 | Pumping Station-1 | 96 |  |  |  |  | 0 |  |  |  | 1015800000 | 97.8 | 96.28 | 2024-10-06 |  | 2111500000 | No | Yes
190 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00009 | Zone II | 1, 5, 6, 7, 8, 9, 33 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00009-Providing Internal connection between inner premises of resident and chamber for house service connection - 4658 nos. Ward covered 1,5,6,7,8,9, 33(p),37(p),38 and 39 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 48000000 |  |  |  | 1.8 | 31/08/18 | 4.32 | Out Of 4658 Nos Hsc,4524 Nos Hsc Connections Given | 96 | Out Of 4658 Nos Hsc,4524 Nos Hsc Connections Given | 96 |  |  |  |  | 0 |  |  |  | 48000000 | 0.81 | 16.88 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
191 | Tambaram | Integrated UGSS | CHENGALPATTU | Integrated/2020-21/009/UGSS/00083 |  |  | Integrated UGSS Integrated/2020-21/009/UGSS/00083-Providing Sewerage Collection System with new underground sewer lines, manholes, pumping stations and lifting station, house service sewer connections for Anakaputhur (Pacakge - 2) | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | G.O. Ms. No. 126 Municipal Administration and Water Supply Department [MA-3(2)]Dated:16/11/20 | 2020-21 | 2111500000 | 606700000 |  |  |  | 32.6 | 26/02/21 | 61.36 | Pumping Station-1 | 97 | Pumping Station-1 | 97 |  |  |  |  | 0 |  |  |  | 606700000 | 58.75 | 96.83 | 2024-10-06 |  | 2111500000 | No | Yes
192 | Tambaram | Integrated UGSS | CHENGALPATTU | Integrated/2020-21/009/UGSS/00084 |  |  | Integrated UGSS Integrated/2020-21/009/UGSS/00084-Providing 27MLD Capacity (3 x 9MLD) of Integrated Sewerage Treatment plant for Pammal and Anakaputhur on DBOT Basis (Package -III) | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | G.O. Ms. No. 126 Municipal Administration and Water Supply Department [MA-3(2)]Dated:16/11/20 | 2020-21 | 2111500000 | 489000000 |  |  |  | 48.9 | 26/02/21 | 50.2 | Pumping Station-1 | 98 | Trial Commissioning Is To Be Commenced .Finishing Work In Progress | 99 |  |  |  |  | 0 |  |  |  | 489000000 | 45.15 | 92.34 | 27/01/24 |  | 2111500000 | No | Yes
193 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00268 | Zone I |  | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00268-Construction of Additional buildings for Urban Primary Health Centre at Pammal, Zone I | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-3Dated:03/08/23 | 2023-24 | 6000000 | 6000000 |  |  |  | 0 | 28/11/23 | 0.6 | Finishing Work In Progress | 93 | Completed | 99 |  |  |  |  | 0 |  |  |  | 6000000 | 0.07 | 12.05 | - |  | 6000000 | No | Yes
194 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00006 | Zone IV | 33 | MLA Fund MLA Fund/2022-23/009/WS/00006-Providing borewell and Minipower pump at Angan vadi Kadaperi Kullakkarai street in ward No.33 in Tambaram Corporation | Water Supply | Motor PumpSet | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 250000 |  |  |  | 0.03 | 17/04/23 | 0.02 | Work To Be Commenced | 0 | Completed | 100 |  |  | 17/09/24 |  | 250000 |  |  |  | 0 | 0 | 0 | - |  | 7500000 | No | Yes
195 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00007 | Zone IV | 52 | MLA Fund MLA Fund/2022-23/009/WS/00007-Providing sintex tank with motor pumpset at Tambaram Burial ground in ward No.52 in Tambaram Corporation | Water Supply | Motor PumpSet | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 310000 |  |  |  | 0 | 17/04/23 | 0.03 | Work To Be Commenced | 1 | Completed | 100 |  |  | 17/09/24 |  | 163000 |  |  |  | 147000 | 0 | 0 | - |  | 7500000 | No | Yes
196 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00008 | Zone III | 39 | MLA Fund MLA Fund/2022-23/009/WS/00008-Providing RO system at Thirumalai nagar 3rd main road in ward No.39 in Tambaram Corporation | Water Supply | Motor PumpSet | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 700000 |  |  |  | 0 | 28/02/23 | 0.06 | Ro Plant Machine Installation Is In Progress | 70 | Completed | 100 |  |  | 2023-07-07 |  | 698371 |  |  |  | 1629 | 0 | 0 | - |  | 7500000 | No | Yes
197 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00009 | Zone III | 40 | MLA Fund MLA Fund/2022-23/009/WS/00009-Providing RO at Gowriwakkam Kullkkarai street in ward No.40 in Tambaram Corporation | Water Supply | Motor PumpSet | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 700000 |  |  |  | 0.07 | 28/02/23 | 0.06 | Finishing Work Is In Progress | 95 | Completed | 100 |  |  | 2023-07-07 |  | 698371 |  |  |  | 1629 | 0 | 0 | 30/04/23 |  | 7500000 | No | Yes
198 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00010 | Zone III | 42 | MLA Fund MLA Fund/2022-23/009/WS/00010-Providing RO system at Kanagaraj street in ward No.42 in Tambaram Corporation | Water Supply | Motor PumpSet | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 700000 |  |  |  | 0.07 | 28/02/23 | 0.06 | Finishing Work Is In Progress | 95 | Completed | 100 |  |  | 2023-07-07 |  | 699059 |  |  |  | 941 | 0 | 0 | 30/04/23 |  | 7500000 | No | Yes
199 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/PARK/00142 | Zone III | 35 | General Fund GENERAL/2023-24/009/PARK/00142-Renovation of Childrens Park,Supply And Fixing Of Childrens / Senior Citizen Play Equipment And Painting Of Compound Wall At Nallappa Street Park In Ward No.35 In Zone III | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 10Dated:28/03/23 | 2023-24 | 650000 | 650000 |  |  |  | 0 | 27/10/23 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 650000 | 0 | 0 | 2024-03-02 |  | 650000 | No | Yes
200 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00144 | Zone III | 22 | General Fund GENERAL/2024-25/009/PARK/00144-Providing And Laying of Pathway And Supply And Fixing OF Children Play Material And Outdoor Gym Equipment At Jain Nagar in ward No.22 in Zone III | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 347-2Dated:30/08/24 | 2024-25 | 1370000 | 1370000 |  |  |  | 0 | 2024-10-09 | 0.11 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1370000 | 0 | 0 | 17/12/24 |  | 1370000 | No | No
201 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PARK/00290 |  |  | 15th CFC 15th CFC/2020-21/009/PARK/00290-Improvements of Kalaivanar Street Park in Chitlapkakam | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 922/2020/TP2 CH-1Dated:12/08/21 | 2020-21 | 500000 | 500000 |  |  |  | 0.05 | 29/10/21 | 0.04 | Work Completed | 100 | Completed | 100 |  |  | 13/04/23 |  | 500000 |  |  |  | 0 | 0.05 | 100 | 28/12/21 |  | 500000 | Yes | Yes
202 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PARK/00291 |  |  | 15th CFC 15th CFC/2020-21/009/PARK/00291-Improvements to State Bank Colony PArk in Chitlapakkam | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 922/2020/TP2 CH-2Dated:12/08/21 | 2020-21 | 700000 | 700000 |  |  |  | 0 | 29/10/21 | 0.06 | Work Completed | 100 | Completed | 100 |  |  | 19/07/23 |  | 700000 |  |  |  | 0 | 0 | 0 | 28/12/21 |  | 700000 | No | Yes
203 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2020-21/009/PARK/00289 |  |  | MLA Fund MLA Fund/2020-21/009/PARK/00289-Providing Children Play Materials of Reading Room in Sarvamangala Nagar Park at Chitlapakkam | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 1812/2020/A3Dated:24/02/21 | 2020-21 | 1500000 | 1500000 |  |  |  | 0.15 | 2022-08-06 | 0.13 | Nearly Completion | 95 | Completed | 100 |  |  | 2023-10-07 |  | 0 |  |  |  | 1500000 | 0.15 | 100 | 2022-07-08 |  | 1500000 | Yes | Yes
204 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00077 | Zone III | 22 | General Fund GENERAL/2024-25/009/PARK/00077-Improvement and Green Space Development of Park,Children play Material And Outdoor Gym Equipment at Kannammal Nagar Park in Ward 22 in Zone III | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 347Dated:30/08/24 | 2024-25 | 800000 | 800000 |  |  |  | 0 | 2025-11-09 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 800000 | 0 | 0 | 18/12/25 |  | 800000 | No | Yes
205 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00104 | Zone III | 22 | General Fund GENERAL/2024-25/009/PARK/00104-Improvement and Green Space Development of Park, Children play Material And Outdoor Gym Equipment at Kannammal Nagar Park in Ward 22 in Zone III | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 347-1Dated:30/08/24 | 2024-25 | 800000 | 800000 |  |  |  | 0 | 2025-11-09 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 800000 | 0 | 0 | 18/12/25 |  | 800000 | No | Yes
206 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/PARK/00128 | Zone III | 40 | General Fund GENERAL/2023-24/009/PARK/00128-Improvement and green Space development of park, Children Play material and outdoor Gym Equipment At Palaniyappa Nagar Park Ward NO.40 in Zone III | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 78Dated:15/12/23 | 2023-24 | 900000 | 900000 |  |  |  | 0 | 2024-10-06 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 900000 | 0 | 0 | 16/08/24 |  | 900000 | No | Yes
207 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/PARK/00217 | Zone III | 37 | General Fund GENERAL/2023-24/009/PARK/00217-Construction Of Compound Wall Providing Childrens Play Material And Outdoor Gym Equipment At Srinivasa Nagar Park In Ward No.37 In Zone-3 | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 83Dated:15/12/23 | 2023-24 | 750000 | 750000 |  |  |  | 0 | 2024-10-06 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 750000 | 0 | 0 | 17/09/24 |  | 750000 | No | Yes
208 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/PARK/00218 | Zone III | 37 | General Fund GENERAL/2023-24/009/PARK/00218-Construction Of Compound Wall Providing Childrens Play Material And Outdoor Gym Equipment At Sivagami Nagar 2nd Main road Park In Ward No.37 In Zone-3 | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 548Dated:30/11/23 | 2023-24 | 1500000 | 1500000 |  |  |  | 0 | 2024-05-08 | 0.12 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1500000 | 0 | 0 | 2024-12-11 |  | 1500000 | No | Yes
209 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00208 | Zone V |  | General Fund GENERAL/2024-25/009/PARK/00208-Improvement and Green Space Development of Park, Childrens play material and out door GYM Equipment at Avvai nagar park and Varatharaja Nagar Park in ward no: 65 in zone 5 at Tambaram city Municipal corporation | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 463Dated:24/06/25 | 2024-25 | 1165000 | 1165000 |  |  |  | 0 | 17/07/25 | 0.12 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1165000 | 0 | 0 | 24/09/25 |  | 1165000 | No | No
210 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/SL/00151 |  |  | 15th CFC 15thCFC/2022-23/009/SL/00151-Replacement of 139 Nos. Street Lights Poles in GST Main Road, MIT flyover and ponds flyover in Tambaram City Municipal Corporation | Streetlight | StreetLight | 18698/2022/CFC 1Dated:23/03/23 | 2022-23 | 10000000 | 10000000 |  |  |  | 1 | 2023-01-08 | 0.81 | Work Order Issued On 01.08.2023 | 0 | Completed | 100 | 2023-06-09 |  | 2023-06-10 |  | 10000000 |  |  |  | 0 | 0.96 | 96.1 | 2023-01-11 |  | 10000000 | Yes | Yes
211 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00038 | Zone II | 31 | MP Fund MP/2023-24/009/SL/00038-Providing 1nos Mini Highmast Light at ward No.31, Parvathipuram Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Work Completed | 100 | Completed | 100 |  |  | 2025-09-01 |  | 408085 |  |  |  | 11915 | 0 | 0 | - |  | 11435000 | No | Yes
212 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00039 | Zone II | 14 | MP Fund MP/2023-24/009/SL/00039-Providing 1nos Mini Highmast Light at ward No.14, Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone II | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0.04 | 24/01/24 | 0.04 | Work Under Progress | 5 | Completed | 100 |  |  | 2024-09-09 |  | 0 |  |  |  | 420000 | 0.04 | 95.24 | 24/04/24 |  | 11435000 | Yes | Yes
213 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00446 | Zone IV | 52 | MP Fund MP/2024-25/009/SL/00446-Providing 1nos Mini High mast light at Ward No.52 Near Bajanai kovil street junction in Tambaram Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 550000 |  |  |  | 0 | 2025-02-05 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 550000 | 0 | 0 | 2025-01-06 |  | 4400000 | No | Yes
214 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00217 | Zone I | 6 | MP Fund MP/2022-23/009/SL/00217-Providing 1 Nos of Mini Highmast light at Ward No. 6 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Work Completed | 0 | Completed | 100 |  |  | 16/11/23 |  | 420000 |  |  |  | 0 | 0.04 | 95.24 | 2023-12-10 |  | 4200000 | No | Yes
215 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00222 | Zone II | 9 | MP Fund MP/2022-23/009/SL/00222-Providing 1 Nos Mini Highmast Light at Ward No.09 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
216 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00223 | Zone II | 15 | MP Fund MP/2022-23/009/SL/00223-Providing 1 Nos Mini Highmast Light at Ward No.15 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
217 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00224 | Zone II | 16 | MP Fund MP/2022-23/009/SL/00224-Providing 1 Nos Mini Highmast Light at Ward No.16 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
218 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00225 | Zone II | 17 | MP Fund MP/2022-23/009/SL/00225-Providing 1 Nos Mini Highmast Light at Ward No.17 Sara Nagar Main Road Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
219 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00226 | Zone II | 17 | MP Fund MP/2022-23/009/SL/00226-Providing 1 Nos Mini Highmast Light at Ward No.17 Murugesapuram Main Road Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
220 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00227 | Zone II | 27 | MP Fund MP/2022-23/009/SL/00227-Providing 1 Nos Mini Highmast Light at Ward No.27 RBI Colony Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/A3Dated:17/08/23 | 2022-23 | 2520000 | 420000 |  |  |  | 0.04 | 2023-11-09 | 0.03 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 411820 |  |  |  | 8180 | 0.04 | 98.05 | 2023-10-12 |  | 2520000 | Yes | Yes
221 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00076 | Zone III | 41 | General Fund GENERAL/2025-26/009/WS/00076-Providig Deep Borewell With Mini Power Pump At Slum board in Ward No.41 in Zone III | Water Supply | Motor PumpSet | 471Dated:24/06/25 | 2025-26 | 300000 | 300000 |  |  |  | 0 | 16/07/25 | 0.03 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 300000 | 0 | 0 | 23/10/25 |  | 300000 | No | Yes
222 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00454 | Zone I | 10 | MP Fund MP/2024-25/009/SL/00454-Providing 1 no Mini High mast Light at ward No.10 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 | Work Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
223 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00448 | Zone III | 41 | MP Fund MP/2024-25/009/SL/00448-Providing 1 nos Mini High mast Light at ward No.41 Masoothy colony middle of 3rd, 4th and 5thstreet junction Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 600000 |  |  |  | 0 | 24/09/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | 23/12/25 |  | 4400000 | No | Yes
224 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00449 | Zone I | 1 | MP Fund MP/2024-25/009/SL/00449-Providing 1 no Mini High mast Light at ward No.01 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
225 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00450 | Zone I | 4 | MP Fund MP/2024-25/009/SL/00450-Providing 1 no Mini High mast Light at ward No.04 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
226 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00040 | Zone II | 20 | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00040-Supply and Erection of submersible non -clog sewage pump set at Keelkattalai pumping station in ward No.20 at Zone II | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 9000000 | 0 |  |  | 0 | - | 0 | Work Order Issued, Materials Placed To Order | 0 | Work Completed | 100 |  |  | 2025-07-10 |  | 8454592 |  |  |  | 545408 | 0 | 0 | - |  | 48950000 | No | Yes
227 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00244 |  |  | General Fund GENERAL/2025-26/009/ROAD/00244-Formation of New Road-Earthern to CC Road- , | Roads | Earthern to CC Road | 390/2025-26Dated:29/08/25Road DetailsRoad Length :Mts | 2025-26 | 1460000 | 1460000 |  |  |  | 0 | 22/08/25 | 0.15 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1460000 | 0 | 0 | - |  | 1460000 | No | Yes
228 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00017 | Zone II | 13 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00017-Retrofitting and Public Toilet at Kamarajar Nagar in ward No.13 zone II | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 260000 |  |  |  | 0 | - | 0 | Nearly Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 260000 | 0 | 0 | - |  | 12070000 | No | Yes
229 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/UGSS/00204 | Zone V | 45, 47, 62 | General Fund GENERAL/2025-26/009/UGSS/00204-Providing Sewerage line Facilities to Elumalai Street,Eswaran Kovil Street,Vidyalakshmi Street at ward 45, Thirumizhisai Street ward no 47,Ward no 62 Ponnan Nagar and Gayathri Nagar ,Repair and Maintenance of Arul Nagar Pump House Motor at Zone 5 East Tambaram Area in Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Replacement of Old Motors and Other Items | 420-1Dated:04/04/25 | 2025-26 | 980000 | 980000 |  |  |  | 0 | 2025-09-05 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 980000 | 0 | 0 | 2025-12-08 |  | 980000 | No | No
230 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00271 | Zone I | 10 | MLA Fund MLA/2023-24/009/BUILDING/00271-Construction of Public Distribution shop with Toilet facility at ward No .10 zone I in Tambaram Corporation | Buildings | Public Distriibution Shop | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 1250000 |  |  |  | 0 | 14/12/23 | 0.13 | Work Completed | 100 | Work Completed | 100 |  |  | 2024-12-09 |  | 0 |  |  |  | 1250000 | 0 | 0 | - |  | 7430000 | No | Yes
231 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00003 | Zone II | 15 | MLA Fund MLA/2024-25/009/BUILDING/00003-Construction of Public Distribution shop with toilet facilities at ward No. 15 in Zone II , Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1695/2024/A3 24.10.24Dated:24/10/24 | 2024-25 | 1900000 | 1300000 |  |  |  | 0 | - | 0 | Painting And Floor Tiles Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 1900000 | No | Yes
232 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00001 | Zone IV | 58 | MLA Fund MLA/2023-24/009/BUILDING/00001-Construction of Public Distribution shop at NGO colony ,Perungalathur, ward No.58, Zone IV | Buildings | Public Distriibution Shop | 3041/2023/A1Dated:05/10/23 | 2023-24 | 3200000 | 1200000 |  |  |  | 0.11 | 24/11/23 | 0.1 | Completed | 100 | Completed | 100 | 25/10/24 |  | 25/10/24 |  | 1200000 |  |  |  | 0 | 0 | 0 | - |  | 3200000 | No | Yes
233 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00044 | Zone II | 17 | General Fund GENERAL/2025-26/009/WS/00044-Repair and Maintenance of RO Plant at Parthasarathy Street in Ward No.17 Tambaram City Municipal Corporation Zone II | Water Supply | Repair Works - Water Supply | 37-12 and 26/2025-26Dated:29/08/25 | 2025-26 | 1650000 | 700000 |  |  |  | 0 | 26/09/25 | 0.07 |  | 0 | Completed | 100 |  |  | 17/11/25 |  | 707112 |  |  |  | -7112.48 | 0 | 0 | 26/12/25 |  | 1650000 | No | Yes
234 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00045 | Zone II |  | General Fund GENERAL/2025-26/009/WS/00045-Repair and Maintenance of Basement and Galvanizing Sheets at RO Plant in Zone II | Water Supply | Repair Works - Water Supply | 37-12 and 26/2025-26Dated:29/08/25 | 2025-26 | 1650000 | 950000 |  |  |  | 0 | 26/09/25 | 0.1 |  | 0 | Completed | 100 |  |  | 17/11/25 |  | 951847 |  |  |  | -1846.83 | 0 | 0 | 26/12/25 |  | 1650000 | No | Yes
235 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00185 | Zone III | 22, 23, 25, 38 | General Fund GENERAL/2025-26/009/OTHERS/00185-Flood Prepardness During North East Monsoon At Ward No.22,23,25 And 38 in Zone III | Others | Dewatering | 622-1Dated:23/07/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 20/08/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 27/11/25 |  | 1000000 | No | Yes
236 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00131 |  |  | General Fund GENERAL/2024-25/009/BUILDING/00131-Construction of Additional Office Building At Sembakkam | Buildings | Office Building | 452Dated:21/10/24 | 2024-25 | 5800000 | 5800000 |  |  |  | 0 | 28/11/25 | 0.52 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5800000 | 0 | 0 | 2026-05-03 |  | 5800000 | No | Yes
237 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00007 | Zone III |  | General Fund GENERAL/2024-25/009/BUILDING/00007-Repair and Maintenance of Council Hall in Zone-III | Buildings | Office Building | 1/09.01.2025Dated:09/01/25 | 2024-25 | 980000 | 980000 |  |  |  | 0 | 18/02/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 980000 | 0 | 0 | 25/05/25 |  | 980000 | No | Yes
238 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00008 | Zone III |  | General Fund GENERAL/2024-25/009/BUILDING/00008-Construction of Toilet Block in Zone-3 at Office Campus at Tambaram City Municipal Corporation | Buildings | Office Building | 1-1Dated:09/01/25 | 2024-25 | 990000 | 990000 |  |  |  | 0 | 18/02/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | 25/05/25 |  | 990000 | No | Yes
239 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PURCHASE/00116 |  |  | General Fund GENERAL/2025-26/009/PURCHASE/00116-Supply and delivery of toilet cleaning compressor pump to TCMC | Purchase of Materials | Purchase of Materials | 357Dated:24/06/25 | 2025-26 | 2940000 | 2940000 |  |  |  | 0 | 30/07/25 | 0.25 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2940000 | 0 | 0 | 29/08/25 |  | 2940000 | No | Yes
240 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PURCHASE/00079 | Zone II |  | General Fund GENERAL/2025-26/009/PURCHASE/00079-Supply of Precautionerymaterials sand bags, Casurina poles, nylon Ropes etc and for flood affected area during Norh East monsoon in TCMC Zone-2 | Purchase of Materials | Purchase of Materials | 35-13/2025-26Dated:29/08/25 | 2025-26 | 950000 | 950000 |  |  |  | 0 | 18/08/25 | 0.1 |  | 0 | Completed | 100 |  |  | 30/09/25 |  | 947624 |  |  |  | 2376 | 0 | 0 | 18/01/26 |  | 950000 | No | Yes
241 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PURCHASE/00080 | Zone II |  | General Fund GENERAL/2025-26/009/PURCHASE/00080-Supply of Precautionerymaterials and repairs & maintance of water supply motors and power saw for flood affected area during Norh East monsoon in TCMC Zone-2 | Purchase of Materials | Purchase of Materials | 35-12/2025-26Dated:29/08/25 | 2025-26 | 800000 | 800000 |  |  |  | 0 | 18/08/25 | 0.08 |  | 0 | Completed | 100 |  |  | 30/09/25 |  | 797054 |  |  |  | 2946 | 0 | 0 | 18/01/26 |  | 800000 | No | Yes
242 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2022-23/009/SWD/00075 | Zone IV | 50 | General Fund GENERAL/2022-23/009/SWD/00075-Providing RCC Cover Slab in SWD at ranganathapuram 2nd Cross Street Ward no.50 Zone 4 TCMC | Storm Water Drain | Repair and Maintenance of Drain | 231Dated:06/02/23 | 2022-23 | 370000 | 370000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 370000 | 0 | 0 | - |  | 370000 | No | Yes
243 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00074 | Zone IV | 49 | General Fund GENERAL/2024-25/009/SWD/00074-Construction Reparing to Existing SWD & Road in Market Road Near Chicken Stall in Ward No.49 TCMC | Storm Water Drain | Repair and Maintenance of Drain | 421--3Dated:12/03/25 | 2024-25 | 980000 | 980000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 980000 | 0 | 0 | - |  | 980000 | No | Yes
244 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00035 | Zone I | 29 | MP Fund MP/2023-24/009/SL/00035-Providing 1nos Mini Highmast Light at ward No.29, Nagappa Nagar 3rd main road, Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Work Completed | 100 | Completed | 100 |  |  | 2025-09-01 |  | 408085 |  |  |  | 11915 | 0 | 0 | - |  | 11435000 | No | Yes
245 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00069 | Zone IV |  | General Fund GENERAL/2024-25/009/SWD/00069-Providing Beautification of the Rajaji Street to GST Road at Zone 4 in TCMC | Storm Water Drain | Repair and Maintenance of Drain | 109Dated:06/03/25 | 2024-25 | 4050000 | 4050000 |  |  |  | 0 | 2025-12-12 | 0.34 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4050000 | 0 | 0 | 26/01/26 |  | 4050000 | No | Yes
246 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00082 | Zone II | 24, 26 | General Fund GENERAL/2025-26/009/SWD/00082-De silting the existing SWD and culvert at ward-24 & 26 in TCMC Zone-2 | Storm Water Drain | Repair and Maintenance of Drain | 35-6/2025-26Dated:29/08/25 | 2025-26 | 800000 | 800000 |  |  |  | 0 | 18/08/25 | 0.08 |  | 0 | Completed | 100 |  |  | 2025-09-12 |  | 799751 |  |  |  | 249 | 0 | 0 | 18/01/26 |  | 800000 | No | Yes
247 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00083 | Zone II | 27, 28 | General Fund GENERAL/2025-26/009/SWD/00083-De silting the existing SWD and culvert at ward-27 & 28 in TCMC Zone-2 | Storm Water Drain | Repair and Maintenance of Drain | 35-7/2025-26Dated:29/08/25 | 2025-26 | 800000 | 800000 |  |  |  | 0 | 18/08/25 | 0.08 |  | 0 | Completed | 100 |  |  | 2025-10-12 |  | 799857 |  |  |  | 143 | 0 | 0 | 18/01/26 |  | 800000 | No | Yes
248 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00053 | Zone IV | 49 | General Fund GENERAL/2024-25/009/SWD/00053-Manufacturing, Supply and fixing of Precast RCC Cover Slab at Brindavan Avenue, jakir hossain Street Subramani Bharathi Street in Ward no.49 in Zone 4 in TCMC | Storm Water Drain | Repair and Maintenance of Drain | 412-3Dated:30/12/24 | 2024-25 | 680000 | 680000 |  |  |  | 0 | 14/03/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 680000 | 0 | 0 | 13/05/25 |  | 680000 | No | Yes
249 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00055 | Zone IV | 55 | General Fund GENERAL/2024-25/009/SWD/00055-Repair and Reconstruction of strom water drain at Valmigi Street in ward No 55 in Zone IV in Tambaram City Municipal Corporation. | Storm Water Drain | Repair and Maintenance of Drain | 431-6Dated:12/03/25 | 2024-25 | 600000 | 600000 |  |  |  | 0 | 2025-02-05 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | 2025-01-06 |  | 600000 | No | Yes
250 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00056 | Zone III | 41 | General Fund GENERAL/2024-25/009/SWD/00056-Restoration of road and Silt Catch Pit At Sri devi Avenue to tellus avenue 5th main road Disposal At Vengaivasal Eri Via Tellus Avenue Phase-II Main Road, Radheshyam Avenue Main Road, Tellus Avenue 4th Main Road Existing Drain At Ward no.41. in Zone III | Storm Water Drain | Repair and Maintenance of Drain | 94Dated:06/03/25 | 2024-25 | 1970000 | 1970000 |  |  |  | 0 | 14/07/25 | 0.19 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1970000 | 0 | 0 | 21/10/25 |  | 1970000 | No | Yes
251 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00001 |  |  | MLA Fund MLA/2024-25/009/OTHERS/00001-Supply and fixing of CCTV camera under Surveilance to Tambaram Corporation Mudichur road, Gandhi Road, Market Bus stand and railway station junction area in Tambaram City Municipal Corporation | Others | CCTV Installation | 1694/2024/E3Dated:27/09/24 | 2024-25 | 2500000 | 2500000 |  |  |  | 0 | - | 0 | Nearing Completed | 90 | Completed | 100 | 26/02/25 |  | 26/02/25 |  | 2487699 |  |  |  | 12301 | 0 | 0 | - |  | 2500000 | No | Yes
252 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00135 | Zone III |  | General Fund GENERAL/2025-26/009/WS/00135-Construction Of Sump And Pipeline In DuraiSamy Nagar In Ward N0.43 In Zone III | Water Supply | Water supply - Internal Plumbing | 673-2Dated:25/08/25 | 2025-26 | 750000 | 750000 |  |  |  | 0 | 2025-06-10 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 750000 | 0 | 0 | 13/01/26 |  | 750000 | No | Yes
253 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00016 | Zone III |  | General Fund GENERAL/2025-26/009/WS/00016-Laying of Distribution WTER Supply Pipeline at Bashiyam Nagar 2nd Street & 1st Cross Street,Thirumalai Malai Nagar Extn in Ward:22&36 in Zone III | Water Supply | Water supply - Internal Plumbing | 673/25.08.2025Dated:25/08/25 | 2025-26 | 1150000 | 1150000 |  |  |  | 0 | 2025-06-10 | 0.12 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1150000 | 0 | 0 | 2026-12-01 |  | 1150000 | No | No
254 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00178 | Zone III | 25 | MLA Fund MLA/2025-26/009/OTHERS/00178-Supply of CC TV (camera) to Zone III ward No.25 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 500000 |  |  |  | 0 | 2025-10-09 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 500000 | 0 | 0 | 17/12/25 |  | 7100000 | No | Yes
255 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/OTHERS/00469 |  |  | MLA Fund MLA Fund/2022-23/009/OTHERS/00469-SUPPLY AND FIXING CLOSED CIRCUIT CAMERA AT CHITLAPAKKAM POLICE LIMITS IN TCMC | Others | CCTV Installation | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 1000000 |  | 0 |  | 0.1 | 25/11/22 | 0.09 | Work Completed | 100 | Completed | 100 |  |  | 2023-10-10 |  | 997000 |  |  |  | 3000 | 0.09 | 89.3 | 23/02/23 |  | 6280000 | Yes | Yes
256 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00117 |  |  | TURIP TURIP/2023-24/009/ROAD/00117-Relaying of Road-009008R0584-MADHAVAN NAIER STREET , 009008R0594-DURGAI AMMAN KOIL STREET , 009008R0635-2ND STREET ARANGANATHAN NAGAR , 009008R0637-4TH STREET ARAGANATHAN NAGAR , 009008R0640-OTTAKUTTAR STREET MUTHAMIZH NAGAR , 009008R0643-KAMBAR STREET MUTHAMIZH NAGAR , 009008R0646-AVAIAR STREET , 009008R0648-PANDIAN STREET , 009008R0601-RAMANUJAM STREET , 009008R0636-MADHAVI STREET , 009008R0651-DEIVASIGAMANI STREET MUTAMIL NAGAR , 009008R0598-NANDHANAR STREET THIRUVALLUVAR NAGAR | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2423 Mts | 2023-24 | 313620000 | 8150000 |  |  |  | 0.73 | 20/07/23 | 0.82 | Work Completed | 100 | Completed | 100 |  |  | 23/04/24 |  | 814597 |  |  |  | 7335403 | 0.73 | 89.96 | 18/10/23 |  | 313620000 | No | Yes
257 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PARK/00464 |  |  | 15th CFC 15th CFC/2020-21/009/PARK/00464-Improvement to VOC Street Arignar Anna Park in Peerkankaranai | Parks | Parks | 922/2020-TP2Dated:14/09/21 | 2020-21 | 3400000 | 1800000 |  |  |  | 0 | 25/10/21 | 0.18 | Completed | 100 | Completed | 100 |  |  | 30/04/24 |  | 1797868 |  |  |  | 2132 | 0.16 | 91.18 | 24/12/21 |  | 3400000 | Yes | Yes
258 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00186 | Zone IV | 59 | MLA Fund MLA/2024-25/009/BUILDING/00186-Construction of Village Administrative Office building in Kalainger Highways road in ward No. 59 Zone IV in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1040000 |  |  |  | 0.1 | 2024-05-11 | 0.08 | Outer Plastering Work Is In Progress | 81 | Completed | 100 | 28/02/25 |  | 28/02/25 |  | 1038325 |  |  |  | 1675 | 0.1 | 99.84 | 2025-03-08 |  | 9650000 | Yes | Yes
259 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00201 | Zone I | 11 | MLA Fund MLA/2024-25/009/BUILDING/00201-Construction of Anganwadi centre at ward No. 11 zone I in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0.08 | Finising Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 16540000 | No | Yes
260 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00318 | Zone I | 1 | General Fund GENERAL/2025-26/009/CULVERT/00318-Construction of RCC culvert in kasthuribai nagar 2nd street, kasthuribai nagar 1st street and MGR nagar in ward no.1 at Anakaputhur Zone-1 | Culverts | Culverts | 414/1-2025-26Dated:02/04/25 | 2025-26 | 300000 | 300000 |  |  |  | 0 | 16/05/25 | 0.03 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 300000 | 0 | 0 | - |  | 300000 | No | Yes
261 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00182 | Zone III | 43 | General Fund GENERAL/2025-26/009/CULVERT/00182-Construction Of Culvert At Thirumurugan Salai, Kakkapujankar Street And Jegajeevaram In Ward No.43 | Culverts | Culverts | 673-3Dated:25/08/25 | 2025-26 | 500000 | 500000 |  |  |  | 0 | 2025-06-10 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 500000 | 0 | 0 | 13/01/26 |  | 500000 | No | Yes
262 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/CULVERT/00183 | Zone III | 43 | General Fund GENERAL/2024-25/009/CULVERT/00183-Construction Of Culvert At Sabari Street,Kalyana Sundaram Street Near Step Stone Viveakanadhar St, Nisha Avenue To Sudha Avenue And Kalaivanar Salai IN Ward No.43 | Culverts | Culverts | 348-1Dated:30/08/24 | 2024-25 | 930000 | 930000 |  |  |  | 0 | 2024-10-09 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 930000 | 0 | 0 | 17/12/24 |  | 930000 | No | No
263 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/CULVERT/00242 | Zone 03 | 44 | General Fund GENERAL/2024-25/009/CULVERT/00242-Construction of Culvert to Ovvaiyar Street In Ward No.44 In Zone-03 | Culverts | Culverts | 348-4Dated:30/08/24 | 2024-25 | 615000 | 615000 |  |  |  | 0 | 2024-10-09 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 615000 | 0 | 0 | 17/12/24 |  | 615000 | No | Yes
264 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/CULVERT/00243 | Zone 03 | 41 | General Fund GENERAL/2024-25/009/CULVERT/00243-Construction Of Culvert To Radheshyam Avenue In Ward No.41 IN Zone-03 | Culverts | Culverts | 348-5Dated:30/08/24 | 2024-25 | 340000 | 340000 |  |  |  | 0 | 2024-10-09 | 0.03 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 340000 | 0 | 0 | 17/12/24 |  | 340000 | No | Yes
265 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00065 | Zone III | 43 | General Fund GENERAL/2025-26/009/CULVERT/00065-Construction Of Culvert At Lenin Street, muthusamy Nagar Astalakshmi Street And Viswami thrar Street In Ward No.43 in Zone-III | Culverts | Culverts | 84-1Dated:17/02/25 | 2025-26 | 610000 | 610000 |  |  |  | 0 | 15/05/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 610000 | 0 | 0 | 22/08/25 |  | 610000 | No | Yes
266 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/CULVERT/00073 | Zone IV | 55 | General Fund GENERAL/2024-25/009/CULVERT/00073-Construction of Culvert to Bharathi Nagar 7th Street in Ward No.55 Zone 4 TCMC | Culverts | Culverts | 419-17Dated:08/01/26 | 2024-25 | 280000 | 280000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 280000 | 0 | 0 | - |  | 280000 | No | Yes
267 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00289 | Zone I | 6 | General Fund GENERAL/2025-26/009/CULVERT/00289-Construction of RCC culvert at LIC colony 4th street,Panchayat colony street, Subramani street,Sathiyamoorthy street,MGR Nagar 2nd street Nagar 1st street in ward NO.06 Zone NO.1 TCMC | Culverts | Culverts | 469-6Dated:06/10/25 | 2025-26 | 4516000 | 700000 |  |  |  | 0 | 28/11/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 700000 | 0 | 0 | - |  | 4516000 | No | Yes
268 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00196 | Zone I | 1 | MLA Fund MLA/2024-25/009/BUILDING/00196-Construction of Kariya Mandapam at ward No. 1 and Zone I in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0.08 | Finishing Work | 99 | Completed | 100 |  |  | 2025-06-10 |  | 989980 |  |  |  | 10020 | 0.1 | 99.84 | - |  | 16540000 | Yes | Yes
269 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00100 | Zone IV | 50 | General Fund GENERAL/2025-26/009/BUILDING/00100-Providing Additional facilities in dailysis Center in Ranganathapuram Primary Health center Ward no.50 in Zone 4 Tambaram City Municipal Corporation | Buildings | Other Buildings | 351Dated:24/06/25 | 2025-26 | 2420000 | 2420000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2420000 | 0 | 0 | - |  | 2420000 | No | No
270 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/CULVERT/00034 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/CULVERT/00034-Constuction of RCC Culvert at Shanthi Nagar Main Road in Ward No.25 | Culverts | Culverts | 31442/2021/e3Dated:15/12/20 | 2021-22 | 41050000 | 600000 |  |  | 0 | 0.06 | 2022-03-01 | 0.05 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 600000 |  |  |  | 0 | 0.05 | 90.17 | 2022-03-02 |  | 41050000 | No | Yes
271 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00211 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00211-Repair /Maintenance-009/2021/032/R/0000715-8TH ST KRISHNA NAGAR-MUDICHUR RD , 007/2021/021/R/0000442-KRISHNA NAGAR 1ST MAIN ROAD , | Roads | CC Road and Paver Block | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 910000 |  |  |  | 0.09 | 31/12/21 | 0.09 |  | 0 | Completed | 100 |  |  | 20/09/22 |  | 907938 |  |  |  | 2062 | 0.09 | 99.77 | 2022-06-02 |  | 39126000 | Yes | Yes
272 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00212 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00212-Repair /Maintenance-009/2021/001/R/0000765-BURMA COLONY 1ST STREET , 009/2021/001/R/0000766-BURMA COLONY 2ND STREET , 009/2021/001/R/0000767-BURMA COLONY 3RD STREET , 009/2021/032/R/0001064-CHERAN STREET , | Roads | CC Road and Paver Block | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 709000 | 14341000 |  |  | 0.07 | 2022-03-01 | 0.07 |  | 0 | Completed | 100 |  |  | 24/09/22 |  | 7090000 |  |  |  | -6381000 | 0.04 | 53.75 | 2022-06-02 |  | 39126000 | Yes | Yes
273 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WSIS/00088 | Zone I | 7 | 15th CFC 15th CFC/2020-21/009/WSIS/00088-Construction of 1Ltr capacity of Sump in Saravana Nagar Ward No.7 | Water Supply Improvement Scheme | Const OHT & Sump | 7979/2020/LA3SEM-8Dated:30/06/21 | 2020-21 | 2000000 | 2000000 |  |  |  | 0.2 | 2021-12-08 | 0.19 |  | 0 | Completed | 100 |  |  | 20/02/21 |  | 0 |  |  |  | 2000000 | 0.18 | 89.33 | 19/11/21 |  | 2000000 | Yes | Yes
274 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WSIS/00092 | Zone II | 12 | 15th CFC 15th CFC/2020-21/009/WSIS/00092-Ward No.12 Construction of 1 lakh litre capacity of Sump in Ganesh Nagar | Water Supply Improvement Scheme | Const OHT & Sump | 7979/2020/LA3SEM9Dated:30/06/21 | 2020-21 | 2000000 | 2000000 |  |  |  | 0.2 | 2021-12-08 | 0.19 |  | 0 | Completed | 100 |  |  | 13/09/22 |  | 1988848 |  |  |  | 11152 | 0.18 | 89.53 | 2021-10-11 |  | 2000000 | Yes | Yes
275 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PURCHASE/00251 |  |  | General Fund GENERAL/2025-26/009/PURCHASE/00251-Payment made for Purchase of 2 nos Dialysis Machines at Ranganathapuram UHC | Purchase of Materials | Purchase of Machineries | 21648/2025/E1Dated:23/02/26 | 2025-26 | 1950000 | 1950000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1950000 | 0 | 0 | - |  | 1950000 | No | Yes
276 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PURCHASE/00309 | Zone IV | 50 | General Fund GENERAL/2025-26/009/PURCHASE/00309-Supply of 2 nos of diayalisis Machine at Ranganathapuram Urban Primary Health center in Ward No.50 Zone 4 | Purchase of Materials | Purchase of Machineries | 21648Dated:03/03/26 | 2025-26 | 1950000 | 1950000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1950000 | 0 | 0 | - |  | 1950000 | No | Yes
277 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00052 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00052-Supply and delivery of 12nos LCV mounted 0.35 cum capacity mild steel desilting machine | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 18000000 |  |  |  | 0 | 14/07/25 | 1.8 | Chasis Purchased | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 18000000 | 0 | 0 | 2026-10-04 |  | 77422000 | No | Yes
278 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00053 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00053-Supply and delivery of 1no trunk cabin medium capacity commercial mounted water tanker lorry 9000 ltr capacity | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 2820000 |  |  |  | 0 | 14/07/25 | 0.28 | Chasis Purchased | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2820000 | 0 | 0 | 2026-10-04 |  | 77422000 | No | Yes
279 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PURCHASE/00093 |  |  | 15th CFC 15th CFC/2020-21/009/PURCHASE/00093-Supply and Delivery of Battery Operator Vehicle 10 Nos. | Purchase of Materials | Vehicle Purchase | 7979/2020/LA3SEM10Dated:30/06/21 | 2020-21 | 1800000 | 1800000 |  |  |  | 0.18 | 18/03/22 | 0.16 |  | 0 | Completed | 100 |  |  | 2022-09-05 |  | 0 |  |  |  | 1800000 | 0.14 | 79.88 | 2022-02-04 |  | 1800000 | Yes | Yes
280 | Tambaram | SBM | CHENGALPATTU | Swach Bhar/2020-21/009/SWM/00135 |  |  | SBM Swach Bhar/2020-21/009/SWM/00135-Removal of legacy waste dumped in the Vengadamangalam compost yard through bio mining process ( Total 122000 cum) | Solid Waste Management | Bio Mining Work | G.O.(Ms) No. 65Dated:18/06/20 | 2020-21 | 95600000 | 95600000 |  |  |  | 9.56 | 14/12/20 | 9.56 | Out Of 122000 Cu.m/ 117000 Cu.m Reclaimed Balance 5000 Cu.m In Progress | 97 | Completed | 100 | 2025-08-05 |  | 2025-09-05 |  | 89345484 |  |  |  | 6254516 | 8.15 | 85.27 | 18/12/20 | Proposal to be sent to DMA office for additional quantity. | 95600000 | No | Yes
281 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00130 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00130-Supply and delivery of 30nos of 5 Tons, Shredder machine green waste in MCC and RRC | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 27000000 |  |  |  | 2.7 | 27/11/24 | 2.7 | Nearing Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 27000000 | 2.63 | 97.56 | 23/05/26 |  | 118900000 | No | Yes
282 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00131 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00131-Supply and delivery of 35nos sieving machine and conveyor belt in MCC and RRC | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 13650000 |  |  |  | 0 | 26/07/24 | 1.37 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13650000 | 1.11 | 81.28 | 2025-06-05 |  | 118900000 | No | No
283 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00146 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00146-Supply and delivery of 70nos wheel bar in MCC | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 385000 |  |  |  | 0.04 | 31/08/24 | 0 | Tender Extended On 23.08.2024 | 0 | Completed | 100 |  |  | 28/02/25 |  | 384300 |  |  |  | 700 | 0.04 | 99.82 | - |  | 19031000 | Yes | No
284 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00147 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00147-Supply and delivery of 76nos fly catching machine in MCC & ABC centre | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 380000 |  |  |  | 0.04 | 2024-08-10 | 0.04 | Under Tender Evaluation | 0 | Completed | 100 |  |  | 28/02/25 |  | 379240 |  |  |  | 760 | 0.04 | 99.8 | 2025-07-07 |  | 19031000 | Yes | No
285 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00148 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00148-Supply and delivery of 35nos desktop computer including printer for MCC | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 2016000 |  |  |  | 0.2 | 2024-08-10 | 0.2 | Price Negotiation Called On 19.08.2024 | 0 | Completed | 100 |  |  | 28/02/25 |  | 1994125 |  |  |  | 21875 | 0.2 | 98.91 | 2025-12-07 |  | 19031000 | Yes | No
286 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/PURCHASE/00012 |  |  | 15th CFC 15th CFC/2021-22/009/PURCHASE/00012-Purchase of 81 Nos Light Commercial vehicle with capacity between 2.00 to 2.5cum to Tambaram City Municipality Corporation for Solid Waste Management | Purchase of Materials | Vehicle Purchase | 21191/2021/Amrut-1-Tambaram-Untied-1Dated:17/12/21 | 2021-22 | 64800000 | 64800000 |  |  |  | 6.48 | 28/02/22 | 4.85 | All Vehicles Received And Put Into Use. Test Report Awaited | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 64800000 | 5.77Excel | 89.1 | 28/03/22 |  | 64800000 | Yes | Yes
287 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWM/00031 | Zone IV | 52, 70 | General Fund GENERAL/2025-26/009/SWM/00031-Rproviding Ramp and wall For Weight Meachine in Kannadapalayam Ward no.52 Zone 4,Thiruneermalai W.31 Zone1 and Madambakkam Ward no.70 Zone 5 Aera in TCMC (Zone 4) | Solid Waste Management | Micro Composting Center | 285Dated:28/04/25 | 2025-26 | 1070000 | 1070000 |  |  |  | 0 | 28/07/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1070000 | 0 | 0 | 26/09/25 |  | 1070000 | No | Yes
288 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00054 | Zone IV | 56 | SBM 2.0 SBM 2.0/2022-23/009/SWM/00054-Construction of Micro Compost Centre at Kundumedu ward no.56 zone No.4 in Tambaram City Municipal Corporation (Left side) | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.58 | 26/04/23 | 0.48 | Completed | 0 | Completed | 100 |  |  | 17/09/24 |  | 5435522 |  |  |  | 314478 | 0.54 | 94.53 | 26/08/23 |  | 40250000 | Yes | Yes
289 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2023-24/009/ROAD/00191 |  |  | Kalaignar Nagarpura Mempatu Thittam KNMT/2023-24/009/ROAD/00191-Relaying of Road-009032R2088-PULIKORADU EXTN SOUTH EXTN STREET , 009032R2085-PULIKORADU EXTN SOUTH 1ST STREET , 009032R2086-PULIKORADU EXTN SOUTH 2ND STREET , 009032R2087-PULIKORADU EXTN SOUTH 3RD STREET , 009052R3757-Pulikoradu Extn 2nd street , 009052R3759-Pulikoradu Extn , 009052R3758-Pulikoradu Extn 3rd street , 009049R3549-MUTHURANGAM ROAD , | Roads | Bituminous Road | G.O. (4D) No. 20Dated:08/06/23Road DetailsRoad Length :782 Mts | 2023-24 | 16200000 | 4700000 |  |  |  | 0.47 | 19/07/23 | 0.39 | Completed | 100 | Completed | 100 | 2024-12-02 |  | 2024-10-06 |  | 4664336 |  |  |  | 35664 | 0.42 | 89.33 | 27/04/24 |  | 16200000 | Yes | Yes
290 | Tambaram | State Disaster Response Fund | CHENGALPATTU | SDRF/2021-22/009/ROAD/00088 |  |  | State Disaster Response Fund SDRF/2021-22/009/ROAD/00088-Relaying of Road-009/03/039/R/4983-Navaneedham nagar first main road , | Roads | Bituminous Road | 31443/2021/A3-SEm-2Dated:15/12/21Road DetailsRoad Length :196 Mts | 2021-22 | 890000 | 890000 |  |  |  | 0.09 | 31/12/21 | 0.08 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 890000 | 0.09 | 100 | 30/01/22 |  | 890000 | Yes | Yes
291 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00022 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00022-Repair /Maintenance-009/02/009/R/1673-MALLIGA NAGAR 1ST STREET , 009/02/009/R/1672-MALLIGA NAGAR 2ND STREET , 009/02/009/R/1671-MALLIGA NAGAR 3RD STREET , 009/02/009/R/1669-MALLIGA NAGAR 4TH STREET , | Roads | Bituminous Road | 31442/2021/E3 PallavaramDated:18/08/22Road DetailsRoad Length :508 Mts | 2021-22 | 2150000 | 750000 |  |  |  | 0.08 | 2022-09-09 | 0.07 |  | 0 | Completed | 100 | 24/09/22 |  | 2024-09-09 |  | 750000 |  |  |  | 0 | 0.07 | 89.33 | 2022-09-10 |  | 2150000 | Yes | Yes
292 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00023 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00023-Repair /Maintenance-009/02/019/S/0073-KRISHNA COLONY PART I , 009/02/019/R/0979-SAKTHI NAGAR 1ST STREET , | Roads | Bituminous Road | 31442/2021/E3 PallavaramDated:18/08/22Road DetailsRoad Length :220 Mts | 2021-22 | 2150000 | 400000 |  |  |  | 0.04 | 2022-09-09 | 0.04 |  | 0 | Completed | 100 |  |  | 2024-08-08 |  | 400000 |  |  |  | 0 | 0.04 | 89.25 | 2022-09-10 |  | 2150000 | Yes | Yes
293 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00024 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00024-Repair /Maintenance-009/02/020/S/0055-EASWARAN NAGAR 3RD STREET , 009/02/020/R/0664-KALAIVANI STREET , | Roads | Bituminous Road | 31442/2021/E3 PallavaramDated:18/08/22Road DetailsRoad Length :609 Mts | 2021-22 | 2150000 | 850000 |  |  | 0 | 0.09 | 2022-09-09 | 0.08 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 850000 |  |  |  | 0 | 0.08 | 89.18 | 2022-09-10 |  | 2150000 | Yes | Yes
294 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00025 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00025-Repair /Maintenance-009/02/020/R/0730-RANGA NAGAR IST STREET , | Roads | Bituminous Road | 31442/2021/E3 PallavaramDated:18/08/22Road DetailsRoad Length :210 Mts | 2021-22 | 2150000 | 150000 |  |  |  | 0.02 | 2022-09-09 | 0.01 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 150000 |  |  |  | 0 | 0.01 | 89.33 | 2022-09-10 |  | 2150000 | Yes | Yes
295 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00055 | Zone II | 19 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00055-Road Restoration of damaged portion over at Ponniamman Koil Street (007019R717) in Ward No.19 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 850000 |  |  |  | 0.09 | 2022-05-01 | 0.07 |  | 0 | Completed | 100 | 28/06/22 |  | 2023-05-01 |  | 850000 |  |  |  | 0 | 0.08 | 89.41 | 2022-05-02 |  | 41050000 | Yes | Yes
296 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00056 | Zone II | 18 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00056-Road Restoration of damaged portion over at Jain Nagar Main Road (007019R743) in Ward No.18 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 980000 |  |  |  | 0.1 | 2022-05-01 | 0.09 |  | 0 | Completed | 100 | 28/06/22 |  | 28/08/22 |  | 980000 |  |  |  | 0 | 0.09 | 89.18 | 2022-05-02 |  | 41050000 | Yes | Yes
297 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00057 | Zone II | 18 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00057-Road Restoration of damaged portion over at Brhaman Street (007018R666) in Ward No.18 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  | 0 | 0.07 | 2022-05-01 | 0.06 |  | 0 | Completed | 100 | 2022-05-07 |  | 2024-09-09 |  | 700000 |  |  |  | 0 | 0.06 | 90.14 | 2022-05-02 |  | 41050000 | Yes | Yes
298 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00058 | Zone II | 18 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00058-Road Restoration of damaged portion over at AGS Colony West Main Road (007018R624) in Ward No.18 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 350000 |  |  | 0 | 0.04 | 2022-05-01 | 0.03 |  | 0 | Completed | 100 | 2022-05-07 |  | 2024-09-09 |  | 350000 |  |  |  | 0 | 0.03 | 90.14 | 2022-05-02 |  | 41050000 | Yes | Yes
299 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00059 | Zone II | 18 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00059-Road Restoration of damaged portion over at Somu Nagar (007018S194 ) in Ward No.18 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 650000 | 0 |  |  | 0.07 | 2022-05-01 | 0.06 |  | 0 | Completed | 100 | 2022-05-07 |  | 2024-09-09 |  | 650000 |  |  |  | 0 | 0.06 | 90.15 | 2022-05-02 |  | 41050000 | Yes | Yes
300 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00060 | Zone II | 12 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00060-Road Restoration of damaged portion over at Panneer Salai Main Road (007012R228), Panneer Selvam 2nd Street(007012S072) & PV Vaithaiyalingam Cross Street (007012L053) in Ward No. 12 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 930000 | 0 |  | 0 | 0.09 | 2022-05-01 | 0.08 |  | 0 | Completed | 100 | 2022-11-04 |  | 2024-09-09 |  | 900000 |  |  |  | 30000 | 0.08 | 87.2 | 2022-05-02 |  | 41050000 | Yes | Yes
301 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00061 | Zone II | 12 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00061-Road Restoration of damaged portion over at Eswaran Kovil Street (007012S045) & Lingam Rice Mill Road (007012S077) in Ward No. 12 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 750000 | 0 |  |  | 0.08 | 2022-05-01 | 0.07 |  | 0 | Completed | 100 | 22/04/22 |  | 2024-09-09 |  | 750000 |  |  |  | 0 | 0.08 | 100 | 2022-05-02 |  | 41050000 | Yes | Yes
302 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00062 | Zone II | 10, 12 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00062-Road Restoration of damaged portion over at Bharathi Nagar 3rd Street (007010R152) & Arul Murugan Nagar Main Road (007012R216) in Ward No.10 & 12 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 770000 |  |  |  | 0.08 | 2022-05-01 | 0.07 |  | 0 | Completed | 100 | 30/05/22 |  | 2024-09-09 |  | 770000 |  |  |  | 0 | 0.07 | 89.22 | 2022-05-02 |  | 41050000 | Yes | Yes
303 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00063 | Zone II | 9 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00063-Road Restoration of damaged portion over at Bharathi Nagar 2nd Street (007010R151) in Ward No.09 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 | 0 |  |  | 0.09 | 2022-05-01 | 0.08 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 89.22 | 2022-05-02 |  | 41050000 | Yes | Yes
304 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00064 | Zone II | 9 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00064-Road Restoration of damaged portion over at Malaganathapuram 1st Street (007009R130) in Ward No.09 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 550000 |  |  |  | 0.06 | 2022-05-01 | 0.05 |  | 0 | Completed | 100 | 2022-04-04 |  | 2024-09-09 |  | 550000 |  |  |  | 0 | 0.05 | 96.18 | 2022-05-02 |  | 41050000 | Yes | Yes
305 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00048 |  |  | General Fund GENERAL/2025-26/009/ROAD/00048-Repair /Maintenance-Bituminous Road- , | Roads | Bituminous Road | 716-7 / 2025-26Dated:25/08/25Road DetailsRoad Length :Mts | 2025-26 | 2050000 | 2050000 |  |  |  | 0 | 26/09/25 | 0.21 |  | 0 | Completed | 100 |  |  | 17/11/25 |  | 2035878 |  |  |  | 14122 | 0 | 0 | 26/11/25 |  | 2050000 | No | Yes
306 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00070 |  |  | General Fund GENERAL/2025-26/009/ROAD/00070-Repair /Maintenance-Bituminous Road009049R3559-RAJAJI ROAD , | Roads | Bituminous Road | 1005Dated:29/12/25Road DetailsRoad Length :240 Mts | 2025-26 | 2450000 | 2450000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2450000 | 0 | 0 | - |  | 2450000 | No | Yes
307 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00091 | Zone I | 2 | General Fund GENERAL/2024-25/009/ROAD/00091-Providing BT Surface at Damged Potholes in ward no.2 Zone No.o1 TCMC | Roads | Bituminous Road | 454-2Dated:25/08/25Road DetailsRoad Length :112.6 Mts | 2024-25 | 640000 | 640000 |  |  |  | 0 | 21/08/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 640000 | 0 | 0 | 2025-12-12 |  | 640000 | No | No
308 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00221 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00221-Repair /Maintenance-009/2021/033/R/0001423-GANDHI ROAD , 009/2021/039/R/0001167-SUNDARAM COLONY 2ND CROSS ST , 009/2021/039/R/0001168-SUNDARAM COLONY 3RD CROSS ST , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 990000 |  |  |  | 0.1 | 2022-03-01 | 0.1 |  | 0 | Completed | 100 |  |  | 24/09/22 |  | 989027 |  |  |  | 973 | 0.1 | 99.9 | 2022-06-02 |  | 39126000 | Yes | Yes
309 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00222 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00222-Repair /Maintenance-009/2021/002/R/0000815-MOULANA NAGAR 4TH STREET , 009/2021/028/R/0000324-SATHIA SAI NAGAR MAIN STREET , 009/025/R/0014-KALAIMAGAL STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 944000 |  |  |  | 0.09 | 31/12/21 | 0.09 |  | 0 | Completed | 100 |  |  | 17/09/24 |  | 941547 |  |  |  | 2453 | 0.09 | 99.74 | 2022-06-02 |  | 39126000 | Yes | Yes
310 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00223 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00223-Repair /Maintenance-009/2021/033/R/0000723-KULAKKARAI MAIN ROAD CROSS , 009/2021/027/R/0000548-KULAKKARAI STREET , 017/2021/001/R/00001-PILLAIYAR KOIL STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 828000 |  |  |  | 0.08 | 31/12/21 | 0.08 |  | 0 | Completed | 100 |  |  | 22/09/22 |  | 827780 |  |  |  | 220 | 0.08 | 99.97 | 2022-06-02 |  | 39126000 | Yes | Yes
311 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00224 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00224-Repair /Maintenance-009/2021/001/R/0000759-BURMA COLONY MAIN ROAD , 009/2021/028/R/0000941-TAMIL POONGA STREET , 009/2021/028/R/0000958-T.T.K. NAGAR 2ND MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 907000 |  |  |  | 0.09 | 31/12/21 | 0.09 |  | 0 | Completed | 100 |  |  | 23/09/22 |  | 903530 |  |  |  | 3470 | 0.09 | 99.62 | 2022-06-02 |  | 39126000 | Yes | Yes
312 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00225 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00225-Repair /Maintenance-007/2021/022/R/0000124-PANDIYAN STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 934000 |  |  |  | 0.09 | 2022-03-01 | 0.09 |  | 0 | Completed | 100 |  |  | 17/09/24 |  | 930206 |  |  |  | 3794 | 0.09 | 99.59 | 2022-06-02 |  | 39126000 | Yes | Yes
313 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00405 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00405-Repair /Maintenance-009/03/039/R/2885-KALATHUMEDU STREET , 009/03/040/R/2810-SAMRAJ NAGAR 1ST STREET , | Roads | Bituminous Road | 31442/2021/E3 semb-8Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 750000 | 750000 |  |  |  | 0.08 | 31/12/21 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 750000 | 0.07 | 90.88 | 30/01/22 |  | 750000 | Yes | Yes
314 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00406 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00406-Repair /Maintenance-009/03/042/R/2405-Vasuki 1st street , | Roads | Bituminous Road | 31442/2021/E3 semb-9Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 500000 | 500000 |  |  |  | 0.05 | 31/12/21 | 0.04 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 500000 | 0.04 | 88.32 | 30/01/22 |  | 500000 | Yes | Yes
315 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00407 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00407-Repair /Maintenance-009/03/041/R/2574-VGP SRINIVASA NAGAR 5TH CROSS ST , 009/03/043/R/2230-SHA AVENUE , | Roads | Bituminous Road | 31442/2021/E3 semb-10Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 820000 | 820000 |  |  |  | 0.08 | 18/08/22 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 820000 | 0.07 | 90.68 | 17/09/22 |  | 820000 | Yes | Yes
316 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00408 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00408-Repair /Maintenance-009/03/041/R/2546-Saraswathy 3rd street , 009/03/043/R/2230-SHA AVENUE , | Roads | Bituminous Road | 31442/2021/E3 semb-11Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 710000 | 710000 |  |  |  | 0.07 | 18/08/22 | 0.06 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 710000 | 0.06 | 90.49 | 17/09/22 |  | 710000 | Yes | Yes
317 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00409 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00409-Repair /Maintenance-009/03/041/R/2555-VGP SRINIVASA NAGAR 6TH CROSS ST , 009/03/041/R/2511-Koushik avenue main road , | Roads | Bituminous Road | 31442/2021/E3 semb-12Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 830000 | 830000 |  |  |  | 0.08 | 18/08/22 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 830000 | 0.08 | 90.68 | 17/09/22 |  | 830000 | Yes | Yes
318 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00410 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00410-Repair /Maintenance-009/03/041/R/2588-SARAVANA NAGAR 6TH STREET , | Roads | Bituminous Road | 31442/2021/E3 semb-13Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 540000 | 540000 |  |  |  | 0.05 | 18/08/22 | 0.05 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 540000 | 0.05 | 90.2 | 17/09/22 |  | 540000 | Yes | Yes
319 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00411 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00411-Repair /Maintenance-009/03/041/R/2647-SRI DEVI AVENUE , | Roads | Bituminous Road | 31442/2021/E3 semb-14Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 570000 | 570000 |  |  |  | 0.06 | 18/08/22 | 0.05 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 570000 | 0.05 | 90.91 | 17/09/22 |  | 570000 | Yes | Yes
320 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00412 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00412-Repair /Maintenance-009/03/041/R/2648-Sri devi avenue Tellus phase 2 , | Roads | Bituminous Road | 31442/2021/E3 semb-15Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 570000 | 570000 |  |  |  | 0.06 | 18/08/22 | 0.05 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 570000 | 0.05 | 90.93 | 17/09/22 |  | 570000 | Yes | Yes
321 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00413 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00413-Repair /Maintenance-009/03/041/R/2643-TELLUS AVENUE PH-2 DR.ABDULKALAM 1ST CROSS STREET , 009/03/041/R/2636-TELLUS AVENUE 1ST MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 semb-16Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 920000 | 920000 |  |  |  | 0.09 | 18/08/22 | 0.08 | Partially Work Completed | 75 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 920000 | 0.08 | 90.61 | 17/09/22 |  | 920000 | Yes | Yes
322 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00414 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00414-Repair /Maintenance-009/03/041/R/2587-SARAVANA NAGAR 1ST STREET , 009/03/041/R/2582-V.G.P. Srinivasa nagar 1st main road , | Roads | Bituminous Road | 31442/2021/E3 semb-17Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 810000 | 810000 |  |  |  | 0.08 | 15/12/21 | 0.07 |  | 0 | Completed | 100 |  |  | 30/03/22 |  | 0 |  |  |  | 810000 | 0.07 | 90.75 | 14/01/22 |  | 810000 | Yes | Yes
323 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00067 |  |  | State Disaster Response Fund State Disa/2021-22/007/ROAD/00067-Road Restoration of damaged portion over at Hasen basha Street (007002R030) | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 450000 |  |  | 0 | 0.05 | 2022-05-01 | 0.04 |  | 0 | Completed | 100 | 28/04/22 |  | 2024-09-09 |  | 450000 |  |  |  | 0 | 0.04 | 88.89 | 2022-05-02 |  | 41050000 | Yes | Yes
324 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00068 | Zone I | 2 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00068-Road restoration of Damaged portion over at Anajaneyar koil St (007002R034) in Ward No 2 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  |  | 0.07 | 2022-03-01 | 0.06 |  | 0 | Completed | 100 | 28/04/22 |  | 2024-09-09 |  | 638000 |  |  |  | 62000 | 0.06 | 81.14 | 2022-05-02 |  | 41050000 | Yes | Yes
325 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2023-24/009/ROAD/00188 |  |  | Kalaignar Nagarpura Mempatu Thittam KNMT/2023-24/009/ROAD/00188-Relaying of Road-009005R0389-VISWESWAPURAM 3RD STREET , 009005R0414-VISWESWAPURAM 1ST STREET , | Roads | Bituminous Road | G.O. (4D) No. 20Dated:08/06/23Road DetailsRoad Length :497 Mts | 2023-24 | 16200000 | 3900000 |  |  |  | 0.35 | 19/07/23 | 0 | Work Completed | 100 | Completed | 100 | 2024-11-01 |  | 22/01/24 |  | 0 |  |  |  | 3900000 | 0.35 | 90.1 | 19/10/23 |  | 16200000 | No | Yes
326 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00398 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00398-Repair /Maintenance-009/03/042/R/2444-MARUTHI NAGAR 2ND MAIN ROAD , 009/03/042/R/2412-VENUGOPALSAMY STREET , | Roads | Bituminous Road | 31442/2021/E3 Semb-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 780000 | 780000 |  |  |  | 0.08 | 31/12/21 | 0.07 | Partially Completed | 60 | Completed | 100 |  |  | 2022-07-10 |  | 0 |  |  |  | 780000 | 0.07 | 90.99 | 30/01/22 |  | 780000 | Yes | Yes
327 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00399 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00399-Repair /Maintenance-009/03/035/R/0270-HASTHINAPURAM MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 semb-2Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 930000 | 930000 |  |  |  | 0.09 | 31/12/21 | 0.08 |  | 0 | Completed | 100 |  |  | 30/03/22 |  | 0 |  |  |  | 930000 | 0.08 | 88.86 | 30/01/22 |  | 930000 | Yes | Yes
328 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00400 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00400-Repair /Maintenance-009/05/066/R/3343-CHITLAPAKKAM MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 semb-3Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 800000 | 800000 |  |  |  | 0.08 | 31/12/21 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 800000 | 0.07 | 89.23 | 30/01/22 |  | 800000 | Yes | Yes
329 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00401 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00401-Repair /Maintenance-009/05/066/R/3343-CHITLAPAKKAM MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 semb-4Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 800000 | 800000 |  |  |  | 0.08 | 15/12/21 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 800000 | 0.07 | 89.74 | 14/01/22 |  | 800000 | Yes | Yes
330 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00402 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00402-Repair /Maintenance-009/05/066/R/3343-CHITLAPAKKAM MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 semb-5Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 700000 | 700000 |  |  |  | 0.07 | 15/12/21 | 0.06 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 700000 | 0.06 | 89.99 | 14/01/22 |  | 700000 | Yes | Yes
331 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00403 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00403-Repair /Maintenance-009/03/041/R/2654-GURUSAMY NAGAR EXTN. KAVERI STREET , | Roads | Bituminous Road | 31442/2021/E3 semb-6Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 900000 | 900000 |  |  |  | 0.09 | 31/12/21 | 0.08 |  | 0 | Completed | 100 |  |  | 16/09/22 |  | 0 |  |  |  | 900000 | 0.08 | 90.88 | 30/01/22 |  | 900000 | Yes | Yes
332 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00169 | Zone VI |  | TURIP TURIP/2024-25/009/ROAD/00169-Relaying of Road-Bituminous Road009033R2173-SOUTH KULLAKARAI STREET , 009054R3938-JOTHI NAGAR 2ND STREET , 009054R3944-HARITHA ENCLAVE CHERAN STREET , 009054R3948-C.T.O Colony Cross Street , 55R4049-GR AVENUE MEENATCHI NAGAR , 009055R4047-Meenakshi Avenue , 009059R4418-Housing Board , 009059R4499-Soorathamman Kovil Street & Sanathi Street , 009059R4403-VIMAL AVENUE , 009056R4112-GANDHI NAGAR 1ST STREET , 009058R4339-BUDDAR STREET , 009059R4403-VIMAL AVENUE , ZONE VI- PACKAGE NO.XII | Roads | Bituminous Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :1716 Mts | 2024-25 | 197393000 | 6600000 |  |  |  | 0.66 | 26/09/24 | 0 | Out Of 12 Roads 11 Roads Completed 1 Road Is Work In Progress | 92 | Completed | 100 | 24/02/25 |  | 24/02/25 |  | 0 |  |  |  | 6600000 | 0 | 0 | - |  | 197393000 | No | Yes
333 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00030 | Zone II | 1, 2, 3, 31 | SRP SRP/2020-21/009/ROAD/00030-Providing WMM with BT surface to Erikkarai road (From Kalangal street Ward -01 to Dhamodharan Nagar ward -02) ward -01,02 VV Koil Street Ward -03Melandai street , Melandai 1st cross street 2nd cross street Ward -31 Mullai Nagar 1st Main road W-38 | Roads | Bituminous Road | 20557/2020/E3Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 30000000 | 15000000 | 0 |  |  | 1.04 | 2021-01-02 | 1.55 | Out Of 6 Roads, 5 Roads Are 100% Completed, Balance Road Is Work Is In Progress. | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15000000 | 0.13 | 8.63 | 2021-01-08 |  | 30000000 | Yes | Yes
334 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00034 | Zone IV | 32 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00034-Repair and maintaining of Community toilet at Pulikoradu in ward No.32 zone IV | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 650000 |  |  |  | 0 | 2024-03-12 | 0.07 | Nearing Completion | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 650000 | 0 | 0 | 2025-01-09 |  | 12070000 | No | Yes
335 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00036 | Zone V | 68 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00036-Repair and maintaining of Community toilet at Bharath Nagar in ward No.68 zone V | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 250000 |  |  |  | 0 | 13/01/25 | 0 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 250000 | 0 | 0 | - |  | 12070000 | No | Yes
336 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WSIS/00022 | Zone IV | 59 | General Fund GENERAL/2025-26/009/WSIS/00022-Extension of Pipe line from Mudichur road to Krishna Nagar in ward No.59 Zone IV in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Laying of Feeder Main and Distribution Main | 234-1Dated:28/04/25 | 2025-26 | 4400000 | 4400000 |  |  |  | 0 | 30/05/25 | 0.37 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4400000 | 0 | 0 | 28/08/25 |  | 4400000 | No | Yes
337 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WSIS/00023 | Zone IV | 57 | General Fund GENERAL/2025-26/009/WSIS/00023-Extension of pipe line from kamarajar salai to ponniamman koil sump in ward no.57 Zone 4 TCMC | Water Supply Improvement Scheme | Laying of Feeder Main and Distribution Main | 234-2Dated:28/04/25 | 2025-26 | 5730000 | 5730000 |  |  |  | 0 | 30/05/25 | 0.48 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5730000 | 0 | 0 | 28/08/25 |  | 5730000 | No | Yes
338 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00085 | Zone III | 42 | General Fund GENERAL/2025-26/009/PARK/00085-Providing BT Surface in Top of the scating area at Annai Anjugam Park in Ward-42 | Parks | Parks | 905Dated:31/10/25 | 2025-26 | 130000 | 130000 |  |  |  | 0 | 22/09/25 | 0.01 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 130000 | 0 | 0 | 29/12/25 |  | 130000 | No | No
339 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00253 | Zone III | 35 | General Fund GENERAL/2024-25/009/PARK/00253- Improvement of outdoor GYM equipment and Wi-fi zone at MIT Bridge at Ward-35 at Zone-3 in Tambaram City Municipal Corporation. | Parks | Parks | 611-4Dated:30/12/24 | 2024-25 | 4680000 | 4680000 |  |  |  | 0 | 2025-10-02 | 0.46 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 4680000 | 0 | 0 | 17/05/25 |  | 4680000 | No | Yes
340 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00403 | Zone II | 15 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00403-Construction of SWD at Zamindar Lane Cross Street - 009015R0966,Zamindhar lane - 009015R0965,Bajanai Koil 1St Street - 009015R0962,Vembuliamman Koil 1St Street - 009015R0957,Bharathi Nagar 3rd Cross Street - 009016R0988 and Culvert at Zamindhar lane - 009015R0965,Bajanai Koil 1St Street - 009015R0962,Vembuliamman Koil 1St Street - 009015R0957,Bharathi Nagar 3rd Cross Street - 009016R0988 in Ward No.15 Tambaram City Municipal Corporation Zone II(Packag NO.7) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3800000 |  |  |  | 0 | 2025-12-09 | 0.38 | Balance One Culvert Steel Febrication Work Under Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3800000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
341 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00404 | Zone II | 16 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00404-Construction of SWD Elango Vadigal Cross Street - 009016R1006,Bharathi Nagar 1st Street - 009016R0989,Bharathi Nagar 2nd Street - 009016R0990,Bharathi Nagar 3rd Street - 009016R0991,Bharathi Nagar 4th Street - 009016R0992 in Ward No.16 Tambaram City Municipal Corporation Zone II (Packag NO.8) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3800000 |  |  |  | 0 | 2025-12-09 | 0.38 | In Progress | 0 | Completed | 100 |  |  | 29/12/25 |  | 3798079 |  |  | 0 | 1921 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
342 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00405 | Zone II | 17 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00405-Construction of SWD and Culvert at Padmanaban Street - 009017R1009,Kamarajar Nagar 1st Street - 009017R1013 in Ward No.17 Tambaram City Municipal Corporation Zone II (Packag NO.9) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3000000 |  |  |  | 0 | 2025-12-09 | 0.3 | In Progress | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
343 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00114 | Zone I | 29 | General Fund GENERAL/2024-25/009/SWD/00114-Raising Drain wall and Providing cover slab to Doctor Colony (00902R1880) Adiraiyar street (0090029R1878) ward no.29 in Zone-1 TCMC | Storm Water Drain | Retaining Wall of SWD | 349Dated:28/08/24 | 2024-25 | 560000 | 560000 |  |  |  | 0 | 2024-03-10 | 0.06 | Finishing Work In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 560000 | 0.05 | 83.75 | - |  | 560000 | No | Yes
344 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/WS/00181 | Zone III | 34 | MLA Fund MLA/2024-25/009/WS/00181-Providing pipe line at Chitlapakkam lake to pond viz Gandhi street and Nehru street in ward No.34 Zone III in Tambaram City Municipal Corporaton | Water Supply | Water Bodies | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1110000 |  |  |  | 0 | 2025-12-02 | 0.11 | Pipe Supplied | 5 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1110000 | 0.1 | 91.44 | 2025-09-11 |  | 9650000 | No | Yes
345 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00121 | Zone I | 6 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00121-Construction of Urinals at Pozhichalur main road ward No.6 Zone I in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0 | 2024-05-07 | 0 | Work Completed. | 100 | Completed | 100 |  |  | 2025-05-05 |  | 130000 |  |  |  | 0 | 0 | 0 | - |  | 35640000 | No | Yes
346 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00123 | Zone II | 27 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00123-Construction of Urinals at GST road OBERAI Kitchen , ward No.27 Zone II in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0.01 | 21/06/24 | 0.01 | Nearly Completed | 95 | Completed | 100 |  |  | 2025-06-01 |  | 128700 |  |  |  | 1300 | 0.01 | 89.17 | 18/03/25 |  | 35640000 | Yes | Yes
347 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00130 |  |  | General Fund GENERAL/2025-26/009/BUILDING/00130-Providing interior, Furnishing And Air Conditioning Works in additional Office Building III in Sembakkam | Buildings | Office Building | 343Dated:24/07/25 | 2025-26 | 4200000 | 4200000 |  |  |  | 0 | 16/07/25 | 0.39 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4200000 | 0 | 0 | 21/10/25 |  | 4200000 | No | Yes
348 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00160 |  |  | General Fund GENERAL/2024-25/009/BUILDING/00160-Providing Shed Arrangements to Main Office Second Floor in TCMC | Buildings | Office Building | 325/2024-25Dated:30/08/24 | 2024-25 | 2500000 | 2500000 |  |  |  | 0 | 21/10/24 | 0.21 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | - |  | 2500000 | No | Yes
349 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS | CHENGALPATTU | SFCOANDM/2024-25/009/BUILDING/00179 | Zone II |  | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS SFCOANDM/2024-25/009/BUILDING/00179-Construction of Gents Toilet at Ponniaman Corporation Higher Secondary school in ward N. 17, Zone II in Tambaram City Municipal Corporation | Buildings | School Building | 21616/2024/SS2-2Dated:10/09/24 | 2024-25 | 4500000 | 1500000 |  |  |  | 0 | 18/10/24 | 0.15 | Wall Tiles And Closet Fitting Completed | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 4500000 | No | Yes
350 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS | CHENGALPATTU | SFCOANDM/2024-25/009/BUILDING/00180 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS SFCOANDM/2024-25/009/BUILDING/00180-Construction of Girls Toilet at Ponniamman Corporation Higher Secondary school in ward No.17, Zone II in Tambaram City Municipal Corporation | Buildings | School Building | 21616/2024/SS2-2Dated:10/09/24 | 2024-25 | 4500000 | 1500000 |  |  |  | 0 | 18/10/24 | 0.15 | Plastring Completed | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | 18/10/24 |  | 4500000 | No | Yes
351 | Tambaram | CMBFS-COMMON KITCHEN | CHENGALPATTU | CMBFS/2023-24/009/BUILDING/00069 | Zone II |  | CMBFS-COMMON KITCHEN CMBFS/2023-24/009/BUILDING/00069-Construction of Common kitchen building at Maraimalai Aigalar Government Higher secondary school, Pallavapuram zone 2 | Buildings | Buildings | 17404/2022/M1Dated:10/03/23 | 2023-24 | 13750000 | 2750000 |  |  |  | 0.28 | 17/04/23 | 0.24 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 0 |  |  |  | 2750000 | 0.21 | 76.87 | 18/05/23 |  | 13750000 | No | Yes
352 | Tambaram | CMBFS-COMMON KITCHEN | CHENGALPATTU | CMBFS/2023-24/009/BUILDING/00071 | Zone IV |  | CMBFS-COMMON KITCHEN CMBFS/2023-24/009/BUILDING/00071-Construction of Common kitchen building at Corporation Primary school Old Perungalthur zone 4 | Buildings | Buildings | 17404/2022/M1Dated:10/03/23 | 2023-24 | 13750000 | 2750000 |  |  |  | 0.21 | 17/04/23 | 0.24 | Floring Completed , White Wash Completed , Colour Wash Work In Progress | 75 | Completed | 100 |  |  | 17/09/24 |  | 2750000 |  |  |  | 0 | 0.21 | 77.62 | 18/05/23 |  | 13750000 | Yes | Yes
353 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00458 | Zone II |  | Elementary Education Fund EE/2024-25/009/BUILDING/00458-Construction of additional school building at zamin pallavaram primary school in wd no 17 in Zone-II | Buildings | Buildings | 446/21.10.2024Dated:21/10/25 | 2024-25 | 24000000 | 6000000 |  |  |  | 0.32 | 2024-08-11 | 0.6 | Plastering | 90 | Completed | 100 |  |  | 2025-11-11 |  | 5999094 |  |  |  | 906 | 0.32 | 53.96 | 2025-08-05 |  | 24000000 | No | Yes
354 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00428 | Zone II | 17 | General Fund GENERAL/2025-26/009/BUILDING/00428-Providing of AR (AUGUMENTET REALITY) and VR ( VIRTUAL REALITY) Experiance Lab Digitita Initiative for digital class room to develop Expertise Curriculam for teacher and Students in Municipal Higher School , Zamil Pallavaram in Ward no.17, Tambaram City Municipal Corporation Zone II | Buildings | Buildings | 322/2025-26Dated:28/05/25 | 2025-26 | 9200000 | 9200000 |  |  |  | 0 | 2025-08-09 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9200000 | 0 | 0 | - |  | 9200000 | No | No
355 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00026 | Zone V | 64 | MLA Fund MLA/2024-25/009/BUILDING/00026-Construction of Kariya Mandapam work ward No.64, Ambedkar Nagar, Subbarayan park near at Tambaram Corporation, Zone V | Buildings | Buildings | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 1000000 |  |  |  | 0 | 2025-05-02 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 7290000 | No | Yes
356 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00272 | Zone I | 6 | MLA Fund MLA/2023-24/009/BUILDING/00272-Construction of Kariyamandapam at ward No.06, zone I in Tambaram Corporation | Buildings | Buildings | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 1000000 |  |  |  | 0 | 14/12/23 | 0.1 | Completed | 0 | Completed | 100 |  |  | 2024-12-09 |  | 0 |  |  |  | 1000000 | 0.09 | 91.3 | - |  | 7430000 | Yes | Yes
357 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00273 | Zone I | 31 | MLA Fund MLA/2023-24/009/BUILDING/00273-Construction of Kariyamandapam at ward No.31, zone I in Tambaram Corporation | Buildings | Buildings | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 1000000 |  |  |  | 0 | 18/11/23 | 0.1 | Work Completed | 0 | Completed | 100 |  |  | 2024-12-09 |  | 0 |  |  |  | 1000000 | 0.09 | 86.57 | - |  | 7430000 | Yes | Yes
358 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00099 | Zone IV | 50 | General Fund GENERAL/2025-26/009/BUILDING/00099-Providing Additional facilities and Equipments Infrastructure Requirements Works in dailysis Center in Ranganathapuram Primary Health center Ward no.50 in Zone 4 Tambaram City Municipal Corporation | Buildings | Other Buildings | 348Dated:24/06/25 | 2025-26 | 2467000 | 2467000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2467000 | 0 | 0 | - |  | 2467000 | No | No
359 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00198 | Zone I | 30 | MLA Fund MLA/2024-25/009/BUILDING/00198-Construction of Kariyamandapam at ward No.30 zone I in Tambaram City Municipal Corporationi | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0 | Finising Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 16540000 | No | Yes
360 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00101 | Zone IV |  | General Fund GENERAL/2025-26/009/BUILDING/00101-Providing the necessary baisis facilities for Setting up a dialysis center at aerd no.50 Ranganathapuram Urban Primary Health Center in Zone 4 TCMC | Buildings | Other Buildings | 588Dated:25/08/25 | 2025-26 | 1738000 | 1738000 |  |  |  | 0 | 14/08/25 | 0.15 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1738000 | 0 | 0 | 13/10/25 |  | 1738000 | No | Yes
361 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00171 | Zone II | 28 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00171-Construction of urinal near to chrompet railway station , Ward 28, Zone-2 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 120500 |  |  |  | 0.01 | 20/10/22 | 0.01 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 120500 |  |  |  | 0 | 0.01Excel | 100 | 18/01/23 |  | 2160000 | Yes | Yes
362 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00175 | Zone III | 22 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00175-Construction of urinal near hasthinapuram busustand, Ward 22, Zone-3 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0 | 2022-01-09 | 0.01 | Work Completed | 100 | Completed | 100 |  |  | 2023-03-05 |  | 135000 |  |  |  | 0 | 0.01 | 89.89 | 2022-01-12 |  | 2160000 | Yes | Yes
363 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00176 | Zone I | 1 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00176-Construction of urinal at , Ward 1 , Kasturibai nagar, Anakaputhur, Zone-1 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.02 | 2022-01-09 | 0.01 | Work Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 135000 |  |  |  | 0 | 0.01 | 82.96 | 2022-01-12 |  | 2160000 | No | Yes
364 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00323 | Zone III | 22 | General Fund GENERAL/2024-25/009/BUILDING/00323-Construction Of Additional Class Roonm At Second Floor In Hasthinapuram Govt Primary School in Ward No.22 At Zone III | Buildings | Additional school building | 453-1Dated:21/10/24 | 2024-25 | 2000000 | 2000000 |  |  |  | 0 | 29/11/24 | 0.2 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2000000 | 0 | 0 | 2025-06-03 |  | 2000000 | No | Yes
365 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00215 | Zone III | 23 | General Fund GENERAL/2024-25/009/BUILDING/00215-Construction of Additional School Building at Zamin Royapettah Higher Secondary School in Ward No. 23 in Tambaram City Municipal Corporation | Buildings | Additional school building | 375Dated:30/08/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 20/09/24 | 0.5 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0 | 0 | 27/12/24 |  | 6000000 | No | Yes
366 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00220 | Zone III | 23 | General Fund GENERAL/2024-25/009/BUILDING/00220-Construction of Additional (Second Floor ) School Building at Zamin Royapetta Higher Secondary School in Ward No. 23 in Tambaram City Municipal Corporation | Buildings | Additional school building | 94-5Dated:06/03/25 | 2024-25 | 3575000 | 3575000 |  |  |  | 0 | 2025-03-04 | 0.36 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 3575000 | 0 | 0 | 2025-10-07 |  | 3575000 | No | Yes
367 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00121 |  |  | TURIP TURIP/2023-24/009/ROAD/00121-Relaying of Road-009001R0003-THIRU.VE.KA. STREET , 009001R0020-THIRUVALLUVAR PETTAI STREET , 009001R0038-GOWRI AVENUE IST STREET , 009003R0226-DEVARAJ NAGAR EXTN. 3RD STREET , 009003R0225-DEVARAJ NAGAR EXTN, 2ND STREET , 009003R0205-V.O.C. NAGAR 1ST STREET , 009002R0080-VENKATESWARA NAGAR KAMBAR STREET , 009001R0071-Bommai Nagar 1st Street , 009001R0035-KARUNANITHI NAGAR 3RD STREET , 009002R0093-VENKATESWARA NAGAR PALLAVAN ST , 009002R0169-BALAJI NAGAR BRINDHAVAN STREET , 009002R5752-THIRU NAGA | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3473 Mts | 2023-24 | 313620000 | 14000000 |  |  |  | 1.26 | 19/07/23 | 1.4 | Work Completed. | 100 | Completed | 100 |  |  | 26/02/25 |  | 9159778 |  |  | 0 | 4840222 | 0.83 | 59.59 | 14/04/24 |  | 313620000 | No | Yes
368 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00162 |  |  | TURIP TURIP/2024-25/009/ROAD/00162-Relaying of Road-BT and CC Road009001R0013-PILLAIYAR KOIL 1ST LANE , 009001R0014-Iyyapan Street , 009001R0019-SATHYA NAGAR 2ND STREET , 009001R0039-GOWRI AVENUE IIND STREET , 009001R0029-SANJAI GANDHI NAGAR IST STREET , 009001R0046-KASTHURI BAI NAGAR MAIN ROAD , 009001R0062-KULAKARAI STREET , 009001R0063-KULAKARAI 1ST STREET , 009001R0006-SAMUNDEESWARI NAGAR, KAUVERY STREET , 009001S0001-Thiruvalluvar 2nd Street , 009001R0024-BACKTHAVATCHALAM NAGAR IST STREET , 009001R0026-SANJAI GANDHI NAGAR 2N | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :4211 Mts | 2024-25 | 197393000 | 21000000 |  |  |  | 0 | 16/10/24 | 0 | Total 27 Roads. 22 Roads Completed . 5 Roads Work Under Progress | 81 | Completed | 100 |  |  |  |  | 0 |  |  |  | 21000000 | 1.85 | 88.23 | - |  | 197393000 | No | Yes
369 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00163 | Zone I |  | TURIP TURIP/2024-25/009/ROAD/00163-Relaying of Road-BT and CC Road009003R0209-KAMATCHI NAGAR 1ST STREET , 009003R0208-KAMATCHI NAGAR MAIN ROAD , 009003R0200-PETTAI STREET , 009003R0201-PETTAI 1ST STREET , 009003R0199-YADHAVAL STREET , 009003R0236-ADIVASI NAGAR , 009003R0211-KAMATCHI NAGAR 4TH STREET , 009003R0230-KANNIAMMAN KOIL STREET , 009003R0197-THYAGARAJA MUDALI STREET , ZONE I- PACKAGE NO.VIII | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :1725 Mts | 2024-25 | 197393000 | 9150000 |  |  |  | 0.82 | 2024-12-09 | 0 | Work Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9150000 | 0.83 | 90.26 | - |  | 197393000 | No | Yes
370 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00327 |  |  | TURIP TURIP/2024-25/009/ROAD/00327-Relaying of Road-BT and CC Road009029R1857-NAGAPPA NAGAR 2ND CROSS STREET , 009030R1929-DURGA NAGAR KARIKALAN STREET , 009031R2019-Mahalakshmi Nagar 1st Street , 009001R0004-ANGALAPARAMESWARI STREET , 009001R0055-M.G.R. NAGAR IST STREET , 009001R0074-NETHAJI NAGAR 1ST STREET , 009003R0194-BAZAAR STREET , 009004R0299-VINAYAGA NAGAR MAIN ROAD , 009002R0102-GURUSWAMY NAGAR 3RD STREET , 009001R0060-M.G.R. NAGAR 3RD CROSS STREET , 009002R0110-GURUSWAMY NAGAR 4, 3RD CROSS STREET , (Package No.1) Zone | Roads | BT and CC Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2008 Mts | 2024-25 | 130600000 | 14950000 |  |  |  | 0 | 27/05/25 | 1.5 | Work Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 14950000 | 1.12 | 74.78 | 27/08/25 |  | 130600000 | No | Yes
371 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00329 |  |  | TURIP TURIP/2024-25/009/ROAD/00329-Relaying of Road-BT and CC Road009009R0666-MUNVAR AVENUE 3RD STREET , 009009R0667-MUNVAR AVENUE 4TH STREET , 009009R0668-MUNVAR AVENUE 5TH STREET , 009009R0673-ABDUL FAROOK SHAHIB STREET , 009014R0934-THIRUPURA SUNDARI COLONY , 009015L0067-Bajanai koil 2nd Street 1st cross Street , 009015L0242-Bajanai Kovil 1st Cross Street , 009016R0986-BHARATHI NAGAR 1ST CROSS STREET , 009016L0080-Bharathi Nagar Extension , 009016L0081-Bharathi Nagar 2nd Extensio , 009018R1115-GANDHI NAGAR 1ST MAIN ROAD , 009 | Roads | BT and CC Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2128 Mts | 2024-25 | 130600000 | 11950000 |  |  |  | 0 | 27/05/25 | 1.2 | Out Of 20 Roads, 2 Nos Of Road Completed,1 No Work In Progress, 17 Nos Of Road To Be Start | 20 | Completed | 100 |  |  |  |  | 0 |  |  |  | 11950000 | 0 | 0 | 26/07/25 |  | 130600000 | No | Yes
372 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00138 | Zone I |  | TURIP TURIP/2023-24/009/ROAD/00138-Relaying of Road-BT and CC Road009002S0603-Venkateswara nagar kalaimagal 1st cross street , 009003R0242-PARI NAGAR VALLALAR ST , 009004R0277-AYOTHIAMMAN KOIL STREET , 009002R0172-BALAJI NAGAR SUBRAMANIYA BHARATHIYAR ST , 009003R0256-Punniyakotti Nagar , (Package No.01) Zone I | Roads | BT and CC Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :1657 Mts | 2024-25 | 65000000 | 8000000 |  |  |  | 0 | 2025-08-04 | 0.8 | Out Of 5 Roads . 5 Roads Completed. | 100 | Completed | 100 |  |  | 22/12/25 |  | 7998519 |  |  | 0 | 1481 | 0.72 | 89.97 | 18/07/25 |  | 65000000 | No | Yes
373 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00048 |  |  | TURIP TURIP/2022-23/009/ROAD/00048-Relaying of Road-009/01/004/R/0435-THIRUNEERMALAI ROAD BURIAL GROUND , 009/032/R/3900-BURMA COLONY 1ST STREET , 009/04/054/R/2112-BALAKRISHNA NAGAR , 009/04/049/R/3659-GANDHI ROAD , | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :1232 Mts | 2022-23 | 99050000 | 9900000 |  |  |  | 0.89 | 2023-10-04 | 0.89 |  | 0 | Completed | 100 |  |  | 28/02/25 |  | 8582077 |  |  | 0 | 1317923 | 0.83 | 83.9 | 2023-09-07 |  | 99050000 | Yes | Yes
374 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00061 |  |  | TURIP TURIP/2024-25/009/ROAD/00061-Repair /Maintenance-BT and CC Road009009R0704-KANNABIRAN KOIL STREET , 009013R0914-P.P.AMMAN KOIL STREET , 009014R0938-SIVASANKARAN STREET , 009017R1010-LATHIEF COLONY 1ST STREET , 009017R1011-LATHIEF COLONY 2ND STREET , 009017R1012-LATHIEF COLONY 3RD STREET , 009018S0146-BHARATH NAGAR 1ST CROSS STREET , 009018R1123-BHAVANI STREET , 009018R1124-THUNGABATHRA STREET , 009018R1122-BHARATH NAGAR 1ST CROSS STREET , 009018R1120-SINDHU STREET , 009019R1190-ARUL MURUGAN MAIN ROAD , 009020R1282-RANGASAMY | Roads | BT and CC Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :4312.2 Mts | 2024-25 | 169399000 | 20000000 |  |  |  | 1.8 | 27/02/24 | 2 |  | 0 | Completed | 100 |  |  | 19/02/25 |  | 19802148 |  |  |  | 197852 | 1.7 | 84.94 | 27/05/24 |  | 169399000 | No | Yes
375 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/BUILDING/00062 | Zone IV | 56 | CGF CGF/2021-22/009/BUILDING/00062-Construction of Shopping Complex in Kamarajar Salai Main Road in Ward No 56 in Perungalathur | Buildings | Commercial Complex | 19089/2021/E2 -1 TAMBARAM-1Dated:25/03/22 | 2021-22 | 20000000 | 20000000 |  |  |  | 2 | 13/06/22 | 2 | Finishing Work Is In Progress | 96 | Completed | 100 | 19/02/25 |  | 19/02/25 |  | 19977593 |  |  |  | 22407 | 1.2 | 59.86 | - |  | 20000000 | No | Yes
376 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WSIS/00471 | Zone II | 20 | MLA Fund MLA Fund/2022-23/009/WSIS/00471-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell at Ambal Nagar in Ward No.20 | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 970000 |  |  |  | 0.1 | 25/11/22 | 0.09 | Geological Survey Completed | 5 | Completed | 100 | 26/07/23 |  | 2024-09-09 |  | 970000 |  |  |  | 0 | 0.1 | 100 | 23/02/23 |  | 6280000 | Yes | Yes
377 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WSIS/00472 | Zone II | 24 | MLA Fund MLA Fund/2022-23/009/WSIS/00472-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.24 | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 970000 |  |  |  | 0.1 | 25/11/22 | 0.09 | Geological Survey Completed | 5 | Completed | 100 | 26/05/23 |  | 2024-09-09 |  | 970000 |  |  |  | 0 | 0.1 | 100 | 23/02/23 |  | 6280000 | Yes | Yes
378 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WSIS/00473 | Zone II | 26 | MLA Fund MLA Fund/2022-23/009/WSIS/00473-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell at Ambal Nagar in Ward No.26 | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 970000 |  |  |  | 0.1 | 25/11/22 | 0.09 | Geological Survey Completed | 5 | Completed | 100 | 26/07/23 |  | 2024-09-09 |  | 970000 |  |  |  | 0 | 0.1 | 100 | 23/02/23 |  | 6280000 | Yes | Yes
379 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00049 | Zone IV | 33 | MLA Fund MLA/2023-24/009/WSIS/00049-Providing RO plant to GST road East side Nehru street in ward No.33 in Tambaram Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3041/2023/A3-8Dated:08/01/24 | 2023-24 | 4570000 | 700000 |  |  |  | 0.07 | 20/02/24 | 0.06 | Basement And Shad Work Completed, Machinery Plant To Be Installed | 35 | Completed | 100 | 26/02/25 |  | 26/02/25 |  | 695982 |  |  |  | 4018 | 0 | 0 | 2024-05-04 |  | 4570000 | No | Yes
380 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2021-22/009/ROAD/00053 |  |  | Kalaignar Nagarpura Mempatu Thittam KNMT/2021-22/009/ROAD/00053-Relaying of Road-009/05/065/S/0498-KVN NAGAR 1ST CROSS , 009/05/065/R/5076-KVN NAGAR 2ND CROSS , 009/05/065/S/0497-KVN NAGAR 3RD CROSS , 009/05/065/S/0496-KVN NAGAR 4TH CROSS , 009/05/065/R/5069-GANDHI NAGAR MAIN ROAD CROSS , 009/05/065/R/5066-GANDHI NAGAR MAIN ROAD 3RD STREET , 009/05/063/R/3910-SUDHANANDA BHARATHI AND MSP LANE , 009/05/062/S/0382-BALAJI NAGAR VEDHAVADI ST , 009/05/062/S/0384-BALAJI NAAR NARMADHA STREET 4TH CR , 009/01/029/R/4588-CHANDRAN NAGAR 2ND CROSS STREET , and Constructi | Roads | BT,CC,Paver Block wih SWD | G.O.(Ms) No. 92 MAWS (NS) Dept.Dated:30/10/21Road DetailsRoad Length :647 Mts | 2021-22 | 8910000 | 8910000 |  |  |  | 0.89 | 20/01/22 | 0.89 |  | 0 | Completed | 100 |  |  | 27/02/25 |  | 9045761 |  |  |  | -135761 | 0.83 | 93.34 | 23/10/22 |  | 8910000 | Yes | Yes
381 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/017/ROAD/00003 | Zone II | 5, 7, 13, 14, 16, 17 | SRP SRP/2020-21/017/ROAD/00003-Providing B.T. Road @ Kamachi Nagar 2nd street in Ward No.13, Vallalar main road, Senthamil Salai in Ward No.16, Thirumalai Nagar 5th street, Purachimani street, Ganapathy street in Ward No.17 and Providing C.C. Road @ Balaji Nagar 10th street, Balaji Nagar 11th street, Thiru Nagar Main Road in Ward No.5, Anna nagar 9th cross street in Ward No.7, L.I.C Colony 8th street in Ward No.14, Kurunji Street in Ward No.17 | Roads | BT,CC,Paver Block wih SWD | 20557/2020/E3Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 30000000 | 20000000 |  |  |  | 0.5 | 2021-05-02 | 1.85 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 20000000 | 0.45 | 22.65 | 2021-06-05 |  | 30000000 | No | Yes
382 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/UGSS/00017 | Zone 03 | 22 | General Fund GENERAL/2024-25/009/UGSS/00017-Supply And Laying of 200mm Dia DI Pipeline & Supply And Laying of 300mm Ms pipe Trenchless at Om sakthi Nagar Lifting Station in Ward No.22 in Zone 03 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 559/30.12.2024Dated:30/12/24 | 2024-25 | 3250000 | 3250000 |  |  |  | 0 | 20/12/24 | 0.33 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3250000 | 0 | 0 | 27/03/25 |  | 3250000 | No | Yes
383 | Tambaram | MP Fund | CHENGALPATTU | MP/2021-22/009/SL/00089 | Zone IV | 53 | MP Fund MP/2021-22/009/SL/00089-Providing 16 m Highmast at TTK Nagar Near Selva Vinayagar Kovil Ground Ward no 53 Zone 4 In Tambaram City Municipal Corporation. | Streetlight | Conversion of Existing Lights to LED | 2829Dated:21/01/23 | 2021-22 | 1270000 | 1270000 |  |  |  | 0.13 | 31/03/23 | 0.1 |  | 0 | Completed | 100 |  |  | 23/05/23 |  | 1246080 |  |  |  | 23920 | 0.12 | 98.12 | - |  | 1270000 | Yes | Yes
384 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00141 | Zone III | 44 | General Fund GENERAL/2025-26/009/SWD/00141-Providing And Laying Paver Block Road and SWD to Annai Indhra Nagar Sangam Stree In ward No.44 in Zone III | Storm Water Drain | Construction of Drain | 221-4Dated:28/04/25 | 2025-26 | 700000 | 700000 |  |  |  | 0 | 14/07/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 700000 | 0 | 0 | 21/10/25 |  | 700000 | No | Yes
385 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00088 |  |  | General Fund GENERAL/2024-25/009/SWD/00088-Construction of SWD And Culvert At Punithavathi Colony 5th Street and Saibaba Koil Street | Storm Water Drain | Construction of Drain | 84-4Dated:17/02/25 | 2024-25 | 940000 | 940000 |  |  |  | 0 | 20/05/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 940000 | 0 | 0 | 27/08/25 |  | 940000 | No | Yes
386 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00150 | Zone II | 24 | General Fund GENERAL/2025-26/009/SWD/00150-Construction of SWD and Culvert at Jospth Colony in Ward No.24 Tambaram City Municipal Corporation Zone II | Storm Water Drain | Construction of Drain | 37 - 18/2025-26Dated:29/08/25 | 2025-26 | 960000 | 960000 |  |  |  | 0 | 26/09/25 | 0.1 |  | 0 | Completed | 100 |  |  | 2025-09-12 |  | 958286 |  |  |  | 1714.1 | 0 | 0 | 25/12/25 |  | 960000 | No | Yes
387 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00038 | Zone III | 25 | General Fund GENERAL/2025-26/009/SWD/00038-Construction of storm water drain at Nellaiapper Street in ward no.25 in Zone 3 | Storm Water Drain | Construction of Drain | 673.Dated:25/08/25 | 2025-26 | 700000 | 700000 |  |  |  | 0 | 2025-06-10 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 700000 | 0 | 0 | 13/01/26 |  | 700000 | No | Yes
388 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00092 | Zone 01 | 7 | General Fund GENERAL/2025-26/009/SWD/00092-Construction of Storm water drain with cover slab in Raja Rajan street and Agatheeswaran koil street ward no.7 Zone no.01 TCMC | Storm Water Drain | Construction of Drain | 450/3Dated:24/06/25 | 2025-26 | 2850000 | 2850000 |  |  |  | 0 | 21/08/25 | 0.29 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2850000 | 0 | 0 | - |  | 2850000 | No | Yes
389 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00216 | Zone III | 39 | General Fund GENERAL/2024-25/009/SWD/00216-Construction Of SWD At Bhavandhiyar 1st Street And 9th Street in Ward No.39 In Zone III | Storm Water Drain | Construction of Drain | 84-6Dated:17/02/25 | 2024-25 | 900000 | 900000 |  |  |  | 0 | 15/05/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 900000 | 0 | 0 | 22/08/25 |  | 900000 | No | Yes
390 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00230 | Zone 03 | 44 | General Fund GENERAL/2025-26/009/SWD/00230-Construction Of SWD At Chidambaranar Street In Ward No.44 In Zone-03 | Storm Water Drain | Construction of Drain | 673-4Dated:25/08/25 | 2025-26 | 1150000 | 1150000 |  |  |  | 0 | 2025-06-10 | 0.11 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1150000 | 0 | 0 | 13/01/26 |  | 1150000 | No | Yes
391 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00252 | Zone III | 22 | General Fund GENERAL/2025-26/009/SWD/00252-Construction of Storm Water drain and Culvert to Saraswathy nagar main road, Saraswathy nagar 1st street , Saraswathy nagar2nd street and cross streets in Ward no.22 in Zone-3 | Storm Water Drain | Construction of Drain | 929Dated:31/10/25 | 2025-26 | 4000000 | 4000000 |  |  |  | 0 | 13/01/26 | 0.4 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 4000000 | 0 | 0 | 20/04/26 |  | 4000000 | No | Yes
392 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00090 | Zone III | 40 | General Fund GENERAL/2024-25/009/SWD/00090-Construction of SWD with Cover at Sriramalu Street in Ward.40 In Zone III | Storm Water Drain | Construction of Drain | 84-5Dated:17/02/25 | 2024-25 | 830000 | 830000 |  |  |  | 0 | 20/05/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 830000 | 0 | 0 | 27/08/25 |  | 830000 | No | Yes
393 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00072 | Zone IV | 52 | General Fund GENERAL/2024-25/009/SWD/00072-Construction of SWD to Kannadapalayam Road in Ward No.52 in Zone 4 TCMC | Storm Water Drain | Construction of Drain | 365-2Dated:30/08/24 | 2024-25 | 5150000 | 5150000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5150000 | 0 | 0 | - |  | 5150000 | No | Yes
394 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00240 | Zone III | 44 | General Fund GENERAL/2024-25/009/SWD/00240-Construction of SWD to Ovvaiyar Street In Ward No.44 In Zone III | Storm Water Drain | Construction of Drain | 348-2Dated:30/08/24 | 2024-25 | 955000 | 955000 |  |  |  | 0 | 2024-10-09 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 955000 | 0 | 0 | 17/12/24 |  | 955000 | No | Yes
395 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00241 | Zone 03 | 41 | General Fund GENERAL/2024-25/009/SWD/00241-Construction Of SWD To Radheshyam Avenue In Ward No.41 IN Zone-03 | Storm Water Drain | Construction of Drain | 348-3Dated:30/08/24 | 2024-25 | 740000 | 740000 |  |  |  | 0 | 2024-10-09 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 740000 | 0 | 0 | 17/12/24 |  | 740000 | No | Yes
396 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/SWD/00324 | Zone III | 43 | General Fund GENERAL/2023-24/009/SWD/00324-Construction Of Storm Water Drain At Karunathini Street And Culvert To Sarvamangala Nagar In Ward No.43 IN ZOne III | Storm Water Drain | Construction of Drain | 51Dated:18/08/23 | 2023-24 | 520000 | 520000 |  |  |  | 0 | 15/05/25 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 520000 | 0 | 0 | 22/08/25 |  | 520000 | No | Yes
397 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/UGSS/00037 | Zone III | 38 | General Fund GENERAL/2025-26/009/UGSS/00037-Laying of Damages UGSS 200mm DI Pipe Under Ground Sewerage pipe line at Bhayasham Nagar 1st Street, Purushathaman Nagar 5th Street and Thiru.vi.ka. Nagar Well Machineholes in Ward No.38 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 673Dated:25/08/25 | 2025-26 | 1400000 | 1400000 |  |  |  | 0 | 2025-06-10 | 0.14 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1400000 | 0 | 0 | 13/01/26 |  | 1400000 | No | Yes
398 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00109 | Zone III | 37 | General Fund GENERAL/2024-25/009/SWD/00109-Construction of storm water drain and culvert to Sembakkam chitlapakkam Main road and Kakkan Street in Ward No.37 | Storm Water Drain | Construction of Drain | 94-2Dated:06/03/25 | 2024-25 | 3950000 | 3950000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3950000 | 0 | 0 | - |  | 3950000 | No | Yes
399 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00106 | Zone III | 37 | General Fund GENERAL/2025-26/009/SWD/00106-Construction of storm water drain and culvert to Sembakkam chitlapakkam Main road and Kakkan Street in Ward No.37 | Storm Water Drain | Construction of Drain | 94-1Dated:06/03/25 | 2025-26 | 3950000 | 3950000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3950000 | 0 | 0 | - |  | 3950000 | No | No
400 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00043 | Zone II | 14 | General Fund GENERAL/2024-25/009/SWD/00043-Construction of Culvert and SWD at Thiripura Sundari Street and Ethiraj Street in Ward No.14,Tambaram City Municipal Corporation ,Zone II | Storm Water Drain | Construction of Drain | 20-03/2024-25Dated:19/03/25 | 2024-25 | 1000000 | 1000000 |  |  |  | 0 | 24/04/25 | 0.1 |  | 0 | Completed | 100 |  |  | 2025-07-07 |  | 999148 |  |  |  | 851.88 | 0 | 0 | 25/07/25 |  | 1000000 | No | Yes
401 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00125 |  |  | General Fund GENERAL/2025-26/009/SWD/00125-Construction of storm water drain with cover slab at Guruswamy nagar 4th street in ward no,2 TCMC | Storm Water Drain | Construction of Drain | 86/2Dated:06/03/25 | 2025-26 | 3000000 | 3000000 |  |  |  | 0 | 2025-04-07 | 0.3 | Finishing Work In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3000000 | 0.27 | 90.43 | - |  | 3000000 | Yes | Yes
402 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00052 | Zone IV | 60 | General Fund GENERAL/2024-25/009/SWD/00052-Construction of Storm Water drain at Nithyanandham Nagar Ext in Ward no.60 in Zone-4 | Storm Water Drain | Construction of Drain | 391-28Dated:19/08/24 | 2024-25 | 450000 | 450000 |  |  |  | 0 | 13/09/24 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 450000 | 0 | 0 | 15/11/24 |  | 450000 | No | Yes
403 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00201 | Zone III | 40 | General Fund GENERAL/2024-25/009/SWD/00201-Construction of SWD And Culvert At Mahaganapathy Street In Ward No.40 IN Zone III | Storm Water Drain | Construction of Drain | 94-4Dated:06/03/25 | 2024-25 | 4360000 | 4360000 |  |  |  | 0 | 2025-03-04 | 0.42 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 4360000 | 0 | 0 | 2025-10-07 |  | 4360000 | No | No
404 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00060 | Zone I | 4 | General Fund GENERAL/2024-25/009/SWD/00060-Construction Of RCC Drain with Cover slab in Anna Nagar road at Annakaputhur Ward No.4 in TCMC | Storm Water Drain | Construction of Drain | 449-5Dated:24/06/25 | 2024-25 | 2800000 | 2800000 |  |  |  | 0 | 21/08/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2800000 | 0 | 0 | 29/11/25 |  | 2800000 | No | No
405 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00119 | Zone III | 40 | General Fund GENERAL/2024-25/009/SWD/00119-Construction of storm water drain to Soundarya Nagar In Ward No.40 | Storm Water Drain | Construction of Drain | 384-2Dated:30/08/24 | 2024-25 | 880000 | 880000 |  |  |  | 0 | 2024-10-09 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 880000 | 0 | 0 | 17/12/24 |  | 880000 | No | Yes
406 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00058 | Zone III | 42 | General Fund GENERAL/2025-26/009/SWD/00058-Construction of Storm water Drain And Culvert At Gokul Nagar 4th Street And Gandhi Nagar 2nd Street in Ward No.42 in Zone III | Storm Water Drain | Construction of Drain | 84Dated:17/02/25 | 2025-26 | 930000 | 930000 |  |  |  | 0 | 15/05/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 930000 | 0 | 0 | 22/08/25 |  | 930000 | No | Yes
407 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00062 | Zone III | 42 | General Fund GENERAL/2025-26/009/SWD/00062-Construction of Storm water Drain And Culvert At Sathya Sai Nagar 2nd Cross Street in Ward No.42 in Zone III | Storm Water Drain | Construction of Drain | 84.Dated:17/02/25 | 2025-26 | 920000 | 920000 |  |  |  | 0 | 15/05/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 920000 | 0 | 0 | 22/08/25 |  | 920000 | No | Yes
408 | Tambaram | IUDM | CHENGALPATTU | IUDM/2020-21/009/SWD/00032 |  |  | IUDM IUDM/2020-21/009/SWD/00032-Construction of storm water drain from MES road to Irumbuliyur Eri (Via Sudhanantha barathi street, Senthamiz Senthupillai street, Parali Nellaiappar street Balaraman street, sengeni amman koil street Vijayarangam street) Ward No/ 24 & 26 | Storm Water Drain | Construction of Drain | G.O.(D) 303Dated:09/09/20 | 2020-21 | 98490000 | 18900000 | 0 |  |  | 0.76 | 21/12/20 | 1.71 | Out Of 830 M,510 M Length Completed Balance Work Is In Progress At Present 85 Mtr Centering Work In | 71 | Completed | 100 |  |  |  |  | 0 |  |  |  | 18900000 | 0.63 | 33.51 | 23/05/21 |  | 98490000 | No | Yes
409 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/BUILDING/00064 | Zone I | 30 | CGF CGF/2021-22/009/BUILDING/00064-Construction of LPG Gasifier Crematorium in Thiruneermalai Lakshmipuram Burial Ground at Ward No 30 (S. No. 386/28, Zone-I) | Buildings | Crematorium | 19089/2021/E2 -1 TAMBARAM-3Dated:25/03/22 | 2021-22 | 25000000 | 25000000 |  |  |  | 1.25 | 16/08/22 | 1.94 | All Works Fully Completed , Front Gardening Work In Progress | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 25000000 | 1.27 | 50.98 | 16/02/23 | ... | 25000000 | No | Yes
410 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00111 | Zone III | 40 | General Fund GENERAL/2025-26/009/BUILDING/00111-Construction of Compound Wall and Dry Waste Shed At Micro Compost Center Sembakkam In ward No.40 In Zone III | Buildings | Construction of Compound Wall | 57-1Dated:17/02/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 15/05/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 22/08/25 |  | 1000000 | No | Yes
411 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00164 | Zone IV | 52 | General Fund GENERAL/2024-25/009/BUILDING/00164-Construction of Compound Wall and Paver Block in Vasandham Nagar PHC in Ward No.52 Zone 4 TCMC | Buildings | Construction of Compound Wall | 425Dated:12/03/25 | 2024-25 | 980000 | 980000 |  |  |  | 0 | 2025-12-05 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 980000 | 0 | 0 | 2025-11-07 |  | 980000 | No | Yes
412 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00035 | Zone III | 23 | General Fund GENERAL/2025-26/009/BUILDING/00035-CONSTRUCTION OF RETAINING WALL ACROSS POTHERI LAKE WARD NO.23 IN ZONE III | Buildings | Construction of Compound Wall | 639Dated:25/08/25 | 2025-26 | 990000 | 990000 |  |  |  | 0 | 2025-10-09 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | 2025-10-12 |  | 990000 | No | No
413 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00232 | Zone IV | 56 | MLA Fund MLA/2024-25/009/BUILDING/00232-Construction of Compound wall at ward No.56 Government Higher secondary school , Zone IV in Tambaram Corporation | Buildings | Construction of Compound Wall | 1694/2024/A1Dated:19/12/24 | 2024-25 | 47450000 | 655000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 655000 | 0 | 0 | - |  | 47450000 | No | Yes
414 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00255 | Zone IV |  | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00255-Construction of Urban Health Centre at Bajanai kovil street, West Tambaram zone IV | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 20/11/23 | 0.21 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 2500000 |  |  |  | 0 | 0.13 | 53.56 | 27/02/24 |  | 22500000 | No | Yes
415 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00251 | Zone III | 44 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00251-Construction of Urban Health Centre at Ramakrishnapuram, Chitlapakkam in ward No.44, zone III | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-05-10 | 0.25 | Completed | 100 | Completed | 100 |  |  | 2024-11-09 |  | 0 |  |  |  | 2500000 | 0.25 | 100 | 2024-06-01 |  | 22500000 | No | Yes
416 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00049 | Zone IV | 32 | General Fund GENERAL/2024-25/009/BUILDING/00049-Providing and laying of paver block and colour washing to compound wall and gate fixing in arputham nagar burial ground in ward no.32 in TCMC zone 4 | Buildings | Repair and Maintenance | 414-1Dated:30/12/24 | 2024-25 | 800000 | 800000 |  |  |  | 0 | 2025-05-03 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 800000 | 0 | 0 | 2025-04-04 |  | 800000 | No | Yes
417 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00050 | Zone IV | 56 | General Fund GENERAL/2024-25/009/BUILDING/00050-Maintainance and Repair Works of Primary School in Ward no.56 at old Perungalathur in zone 4 | Buildings | Repair and Maintenance | 457-3Dated:21/10/24 | 2024-25 | 1500000 | 1500000 |  |  |  | 0 | 24/12/24 | 0.12 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | 22/02/25 |  | 1500000 | No | Yes
418 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00288 | Zone I | 4 | General Fund GENERAL/2024-25/009/BUILDING/00288-Repair and Maintenanace of ICDS centre at Ayyothiamman koil street in ward no.4 zone .1 TCMC | Buildings | Repair and Maintenance | 391/2024-25Dated:30/12/24 | 2024-25 | 700000 | 700000 |  |  |  | 0 | 24/02/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 700000 | 0 | 0 | - |  | 700000 | No | Yes
419 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00262 | Zone IV | 58 | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00262-Construction of New Urban Health PHC at RMK Nagar, Pandiyan street, ward No.58, Zone IV | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-1Dated:23/08/23 | 2023-24 | 12000000 | 3000000 |  |  |  | 0.3 | 20/11/23 | 0.3 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 0 |  |  |  | 3000000 | 0.27 | 89.24 | 23/08/24 |  | 12000000 | No | Yes
420 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00325 | Zone III | 34 | General Fund GENERAL/2025-26/009/BUILDING/00325-Restoration of Public Toilet And Changes To Meicine Distribution Center in ward No.34 in Zone III | Buildings | Construction of Toilet | 57-3Dated:17/02/25 | 2025-26 | 500000 | 500000 |  |  |  | 0 | 15/05/25 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 500000 | 0 | 0 | 22/08/25 |  | 500000 | No | Yes
421 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00152 | Zone II | 20 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00152-Construction of Toilet at Corporation middle school in ward No. 20 zone II | Buildings | Construction of Toilet | 21615/2024/ss2Dated:22/07/24 | 2024-25 | 29100000 | 1500000 |  |  |  | 0 | 23/09/24 | 0.15 | Nealy Completed | 90 | Completed | 100 |  |  | 2026-03-02 |  | 1496375 |  |  |  | 3625 | 0 | 0 | 20/06/25 |  | 29100000 | No | Yes
422 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00245 | Zone II | 13 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00245-Restoration and Imrovement of Water Bodies as Rain water Harvesting Structure at ward No.13 S.F.No. 372/1, Ward B, Block No. 5 Ramasamy Chetti Kulam zone II in Pallavapuram area of Tambaram City Municipal Corporation in Zone II | WaterBodies | Improvement of Water Bodies | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 12500000 |  |  |  | 0 | 24/01/24 | 1.21 | Toe Wall Completed | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12500000 | 0.1 | 7.81 | 20/10/24 |  | 80000000 | Yes | Yes
423 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00246 | Zone IV | 56 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00246-Restoration and Improvement of Water Bodies at Mangaleri Kulam, Samathuvapuram salai at ward No.56, S.f. No.533/1, Zone 4 in Perungalathur area of Tambaram City Municipal Corporation in Zone IV | WaterBodies | Improvement of Water Bodies | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 14000000 |  |  |  | 0 | 2024-10-01 | 1.4 | Light Fixing Work Completed, Finishig Work In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 14000000 | 0.86 | 61.6 | - |  | 80000000 | No | Yes
424 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00247 | Zone I | 4 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00247-Rejuvenation of Water Bodies at Kalmadavu, ward No. 04, SF No. 13, Survey No. 399, zone I in Anakaputhur areas of Tambaram City Municipal Corporation in zone I | WaterBodies | Improvement of Water Bodies | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 28500000 |  |  |  | 0 | 2023-02-11 | 2.82 | Finishing Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 28500000 | 1.28 | 44.85 | - |  | 80000000 | Yes | Yes
425 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WB/00046 | Zone IV | 56 | General Fund GENERAL/2024-25/009/WB/00046-Development work in Stone Piching and SS Hand Rails of Mangeleri Kulam in Ward No.56 at Zone 4 TCMC | WaterBodies | Improvement of Water Bodies | 106Dated:06/02/25 | 2024-25 | 2450000 | 2450000 |  |  |  | 0 | 15/04/25 | 0.2 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2450000 | 0 | 0 | 14/06/25 |  | 2450000 | No | Yes
426 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/009/WB/00081 | Zone II | 14 | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/009/WB/00081-Rejunevation and improvement of Thirupanathal Lake TS No.109/1) at Ward no.14 in Tambaram City Municipal Corporation (Pammal) | WaterBodies | Improvement of Water Bodies | G.O.(Ms) No.138 MAWS (NS) DeptDated:27/12/21 | 2021-22 | 9950000 | 9950000 |  |  |  | 0.9 | 21/01/22 | 0.98 | Work Fully Completed. Fund Received 50%, Balance Met Out From General Fund. | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9950000 | 0.9 | 90.93 | 21/04/22 | Latest stage of work photo to be uploaded | 9950000 | No | Yes
427 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00012 | Zone I | 6 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00012-Construction of New Community toilet at Pozhihallur main road zone office back side street in ward no.06 zone I | Sanitation Work | Constn of Community Toilet | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 600000 |  |  |  | 0 | 18/12/24 | 0.05 | Finishing Work In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | - |  | 12070000 | No | Yes
428 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00162 | Zone IV | 51, 57 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00162-Construction of CT (Type-I) at junction of Thiruneermalai road & Dhargas road, ward 51, west Tambaram ( Alternative sight at kundumedu, ward 57), Zone-4 | Sanitation Work | Constn of Community Toilet | 5990/2022/SBMDated:11/04/22 | 2021-22 | 5400000 | 2700000 |  |  |  | 0.27 | 2022-01-09 | 0.22 |  | 100 | Completed | 100 |  |  | 2024-08-08 |  | 2697553 |  |  |  | 2447 | 0.09 | 33.33 | 25/10/22 |  | 5400000 | No | Yes
429 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00087 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00087-Construction of Community Toilet at Thiruneermalai road in ward No.32, Zone 4 in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 2024-02-07 | 0.06 | Finishing Work Is In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | 31/08/24 |  | 35640000 | No | Yes
430 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00088 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00088-Construction of Community Toilet at Mannurankulam MCC in ward No.32, Zone 4 in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 2024-12-06 | 0.06 | Electrical And Tiles Laying Works Completed Colour Wash Work Is In Progress | 86 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0.05 | 75.18 | 2024-11-08 |  | 35640000 | No | Yes
431 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00183 | Zone IV | 59 | MLA Fund MLA/2024-25/009/BUILDING/00183-Construction of Public Distribution shop at Rajan Nagar extension in ward No. 59 , Zone No iv in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1250000 |  |  |  | 0.12 | 2024-05-11 | 0.1 | Roof Concrete Work In Is Progress | 60 | Completed | 100 | 28/02/25 |  | 28/02/25 |  | 1249998 |  |  |  | 2 | 0.12 | 100 | 2025-04-08 |  | 9650000 | Yes | Yes
432 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00024 | Zone V | 67 | MLA Fund MLA/2024-25/009/BUILDING/00024-Construction of Ration shop work in ward NO.67,SAnthi Nikethan Colony at Tambaram Corporation, Zone V | Buildings | Public Distriibution Shop | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 1250000 |  |  |  | 0 | 2025-05-02 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1250000 | 0 | 0 | - |  | 7290000 | No | Yes
433 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00025 | Zone V | 68 | MLA Fund MLA/2024-25/009/BUILDING/00025-Construction of Ration shop work in ward No.68, Bharathi Nagar at Tambaram Corporation , Zone V | Buildings | Public Distriibution Shop | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 1000000 |  |  |  | 0 | 2025-05-02 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 7290000 | No | Yes
434 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00269 | Zone I | 5 | MLA Fund MLA/2023-24/009/BUILDING/00269-Construction of Public Distribution shop with Toilet facility at ward No .05 zone I in Tambaram Corporation | Buildings | Public Distriibution Shop | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 1250000 |  |  |  | 0 | 14/12/23 | 0 | Finishing Work In Progress | 97 | Completed | 100 |  |  | 19/08/24 |  | 1250000 |  |  |  | 0 | 0 | 0 | - |  | 7430000 | No | Yes
435 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00270 | Zone I | 2 | MLA Fund MLA/2023-24/009/BUILDING/00270-Construction of Public Distribution shop with Toilet facility at ward No .02 zone I in Tambaram Corporation | Buildings | Public Distriibution Shop | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 1250000 |  |  |  | 0 | 21/11/23 | 0 | Work Fully Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1250000 |  |  |  | 0 | 0 | 0 | - |  | 7430000 | No | Yes
436 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/SANITATION/00235 | Zone IV | 56 | MLA Fund MLA/2024-25/009/SANITATION/00235-Construction of Toilet at Old Perungalathur Parvathy Nagar and Kamarajar street in ward No.56 ,Zone IV in Tambaram Corporation | Sanitation Work | Constn of Community Toilet | 1694/2024/A1Dated:19/12/24 | 2024-25 | 47450000 | 200000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 200000 | 0 | 0 | - |  | 47450000 | No | Yes
437 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/BUILDING/00053 | Zone IV | 61 | MLA Fund MLA/2022-23/009/BUILDING/00053-Construction of Public Distribution shop at Vijayalakshmi street, Peerkankaranai ward No.61 , Zone IV in Tambaram Corporation | Buildings | Public Distriibution Shop | 4408/2022/A3-2Dated:27/03/23 | 2022-23 | 3370000 | 1200000 |  |  |  | 0 | 14/08/23 | 0.12 | Plastering Work Completed, White Washing Work Is In Progress | 86 | Completed | 100 | 26/02/25 |  | 26/02/25 |  | 1192596 |  |  |  | 7404 | 0 | 0 | - |  | 3370000 | No | Yes
438 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00095 | Zone I | 12 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00095-Construction of Public Toilet a tChozan Nagar at ward No.12 Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0 | Work Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1000000 |  |  |  | 0 | 0 | 0 | - |  | 35640000 | No | Yes
439 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00096 | Zone I | 5 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00096- Construction of Public Toilet at Gandhi main road in ward No.5 Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0.07 | Work Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1000000 |  |  |  | 0 | 0.05 | 45 | - |  | 35640000 | No | Yes
440 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00099 | Zone II | 19 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00099-Construction of Public Toilet at Ganga garden in ward No19 Zone II in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0.07 | Nearly Completed | 95 | Completed | 100 |  |  | 2025-03-03 |  | 1000000 |  |  |  | 0 | 0.1 | 100 | 18/03/25 |  | 35640000 | Yes | Yes
441 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00092 | Zone I | 5 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00092-Construction of Public Toilet at Vishveshpuram Transfer station in ward No.5, Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-01-07 | 0.07 | Finishing Work In Progress | 85 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 35640000 | No | Yes
442 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00104 | Zone III | 43 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00104-Construction of Public Toilet at Balaji avenue in ward No.43 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 16/08/24 | 0.08 | Nearly Completed | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 13/05/25 |  | 35640000 | No | Yes
443 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00107 | Zone III | 35 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00107-Construction of Public Toilet at Nheru nagar in ward No.35 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 16/08/24 | 0.08 | Plastering Work Is In Progress | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 13/05/25 |  | 35640000 | No | Yes
444 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00108 | Zone III | 38 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00108-Construction of Public Toilet at Manikandan nagar in ward No.38 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-01-07 | 0.07 | Nearly Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 28/03/25 |  | 35640000 | No | Yes
445 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00109 | Zone III | 34 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00109-Construction of Public Toilet at Chitlapakkam 2 nd main road OHT in ward No.34 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 16/08/24 | 0 | Nearly Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 13/05/25 |  | 35640000 | No | Yes
446 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00113 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00113-Construction of Public Toilet at Kundumedu RRC in ward No.32 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-02-07 | 0.1 | Finishing Work Is In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0.04 | 44.97 | - |  | 35640000 | No | Yes
447 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00114 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00114-Construction of Public Toilet at Kannadapalayam Transfer station in ward No.32 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-12-06 | 0.1 | Tiles Laying Work And Electrical Work Is In Progress | 81 | Completed | 100 | 2025-10-01 |  | 2025-10-01 |  | 999004 |  |  |  | 996 | 0.1 | 99.9 | 2024-12-08 |  | 35640000 | Yes | Yes
448 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00158 |  |  | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00158-construction of Public Toilet at Sanatorium bus stand | Sanitation Work | Public Toilet | 5990/2022/SBM-2Dated:11/04/22 | 2021-22 | 13000000 | 3250000 | 0 |  |  | 0.33 | 25/07/22 | 0.21 | Completed | 100 | Completed | 100 |  |  | 2024-12-06 |  | 3192489 |  |  |  | 57511 | 0.29 | 88.68 | 2022-01-12 |  | 13000000 | Yes | Yes
449 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00014 | Zone I |  | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00014-Construction of Public Toilet at Anakaputhur Bus stand zone I | Sanitation Work | Public Toilet | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 750000 |  |  |  | 0 | 2025-06-01 | 0.06 | Painting Work Completed. | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 750000 | 0 | 0 | - |  | 12070000 | No | Yes
450 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00015 | Zone I | 31 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00015-Construction of Public Toilet at West Kulakkarai street in ward No.31 Thiruneermalai zone I | Sanitation Work | Public Toilet | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 750000 |  |  |  | 0 | 2025-06-01 | 0.06 | Painting Work Completed. | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 750000 | 0 | 0 | - |  | 12070000 | No | Yes
451 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00066 | Zone III | 44 | General Fund GENERAL/2025-26/009/SWD/00066-Construction of Storm water Drain And Culvert At Sharma Nagar 3rd,4th,5th Street in Ward No.44 in Zone III | Storm Water Drain | Construction of Drain | 84-2Dated:17/02/25 | 2025-26 | 990000 | 990000 |  |  |  | 0 | 14/07/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | 21/10/25 |  | 990000 | No | Yes
452 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00277 | Zone III | 43 | General Fund GENERAL/2025-26/009/SWD/00277-Construction Of Storm Water Drain At Rosily Nagar In Ward No.43 In Zone III | Storm Water Drain | Construction of Drain | 673-6Dated:25/08/25 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 2025-10-10 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 900000 | 0 | 0 | 17/01/26 |  | 900000 | No | Yes
453 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00409 | Zone II | 24 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00409-Construction of SWD and Culvert at Maninayakar Street - 009024R1669,Srinivasapuram - 009024R1651 in Ward No.24 Tambaram City Municipal Corporation Zone II (Packag NO.13) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3200000 |  |  |  | 0 | 2025-12-09 | 0.32 | Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3200000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
454 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00003 | Zone III | 39 | General Fund GENERAL/2024-25/009/SWD/00003-Construction of SWD and Culvert in Navaneetha Nagar Main Road and 4th Street in Ward-39 in Zone III | Storm Water Drain | Construction of Drain | 94/06.03.2025Dated:06/03/25 | 2024-25 | 5710000 | 5710000 |  |  |  | 0 | 2025-03-04 | 0.57 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5710000 | 0 | 0 | 2025-10-07 |  | 5710000 | No | No
455 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00398 | Zone I | 2 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00398-Construction of RCC Strom Water Drain with Cover Slab at Brindhavanam Street and Raghavendra Koil Street in Ward No.2 Tambaram City Municipal Corporation Zone-I (Packag NO.2) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 10000000 |  |  |  | 0 | 18/08/25 | 1 | 300M Wall Rasing And Cover Slap Completed. Finishing Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 10000000 | 0 | 0 | 16/11/25 |  | 200000000 | No | Yes
456 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00415 | Zone IV | 59 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00415-Construction of Storm Waret Drain to AS Rajan Nagar and Bharathidasan Nagar Ward no.59 in Zone-4 (Package No.19) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 2286000 |  |  |  | 0 | 2025-12-09 | 0.23 | In Progress | 40 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2286000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
457 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00204 | Zone I | 12 | MLA Fund MLA/2024-25/009/BUILDING/00204-Construction of Anganwadi centre at ward No. 12 zone I in Tambaram City Municipal Corporation | Buildings | Anganwadi | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0.1 | Finishing Work | 99 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 16540000 | No | Yes
458 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00266 | Zone III | 34, 39, 40, 41, 42, 43, 44 | General Fund GENERAL/2025-26/009/OTHERS/00266-Flood Prepardness During North East Monsoon At Ward No.34,39,40,41,42,43,44 in Zone III | Others | Miscellaneous Works | 622-2Dated:25/08/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 20/08/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1000000 | 0 | 0 | 27/11/25 |  | 1000000 | No | Yes
459 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00268 | Zone III | 34, 39, 40, 41, 42, 43, 44 | General Fund GENERAL/2025-26/009/OTHERS/00268-Engaging JCB,Poclain,Tipper Lorry And Labour At Flood Preparedness Of North East Monsoon At Ward No.34,39,40,41,42,43,44 in Zone III | Others | Miscellaneous Works | 622-3Dated:25/08/25 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 20/08/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 900000 | 0 | 0 | 27/11/25 |  | 900000 | No | Yes
460 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00212 | Zone II |  | General Fund GENERAL/2025-26/009/OTHERS/00212-Providing Generators,Flood Light for Hirer basis on Flood Relief Centre in Zone II Tambaram City Municipal Corporation | Others | Miscellaneous Works | 08/2025-26Dated:28/01/26 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 28/11/25 | 0.09 |  | 0 | Completed | 100 |  |  | 23/12/25 |  | 734995 |  |  | 0 | 165005 | 0 | 0 | 28/02/26 |  | 900000 | No | Yes
461 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00219 | Zone 03 | 34 | General Fund GENERAL/2025-26/009/OTHERS/00219-Painting To Chitlapakkam 3rd Main Road Over Head Tank In Ward No.34 in Zone-03 | Others | Miscellaneous Works | 57-2Dated:17/02/25 | 2025-26 | 600000 | 600000 |  |  |  | 0 | 15/05/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 600000 | 0 | 0 | 22/08/25 |  | 600000 | No | Yes
462 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/009/ROAD/00203 |  |  | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/009/ROAD/00203-Relaying of Road-009/04/055/R/0002-Sri Venkadeshwara Nagar 2nd Street , 009/04/055/R/0008-Sri Venkadeshwara Nagar Main Road , 009/04/055/R/0007-Sri Venkadeshwara Nagar 1 st Street , 009/04/055/R/0006-AGS Colony Main Road , 009/04/055/R/0005-Samathuva Periyar Nagar main Road Extension , | Roads | Earthern Road | G.O.(Ms) No.73 MAWS (NS) Dept.Dated:13/05/22Road DetailsRoad Length :Mts | 2021-22 | 12350000 | 6150000 | 19475000 |  |  | 0.62 | 2022-06-07 | 0.62 | Work Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6150000 | 0.6 | 97.69 | 2022-06-10 |  | 12350000 | Yes | Yes
463 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/009/ROAD/00204 |  |  | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/009/ROAD/00204-Relaying of Road-009/04/055/R/0004-Good will nagar main Road , 009/04/055/R/0003-RK Nagar main Road , | Roads | Earthern Road | G.O.(Ms) No.73 MAWS (NS) Dept.Dated:13/05/22Road DetailsRoad Length :Mts | 2021-22 | 12350000 | 6200000 |  |  |  | 0.56 | 2022-05-07 | 0.62 | Concrete Work In Progress | 80 | Completed | 100 | 2025-04-03 |  | 2025-04-03 |  | 3524000 |  |  |  | 2676000 | 0.44 | 70.78 | 2022-07-10 |  | 12350000 | No | Yes
464 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00193 | Zone I | 31 | General Fund GENERAL/2025-26/009/ROAD/00193-Providing Cement Concrete road at Mangeleri Transfer station and Tiruneermalai (M sand plant to RS reaymix plant) ward No.31, Zone I in TCMC | Roads | Earthern Road | 870/1Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 11000000 | 6000000 |  |  |  | 0 | 21/01/26 | 0.6 | Nearing Completion | 90 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 6000000 | 0.45 | 75.31 | - |  | 11000000 | No | Yes
465 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00064 | Zone IV | 59 | General Fund GENERAL/2024-25/009/BUILDING/00064-Construction of 2 class room School building Peerkankarani Primary School at (Raj Kamal Street) in Ward No.59 in Zone-4 | Buildings | Construction of Schools | 458-2Dated:21/10/24 | 2024-25 | 3500000 | 3500000 |  |  |  | 0 | 13/12/24 | 0.27 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3500000 | 0 | 0 | 13/03/25 |  | 3500000 | No | Yes
466 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00321 |  |  | General Fund GENERAL/2025-26/009/ROAD/00321-Repair /Maintenance-Other Roads009010R0718-MOSES STREET IYAPPA NAGAR , 009010R0707-1ST STREET AYYAPPA NAGAR , | Roads | Other Roads | 456/2025-26Dated:25/09/25Road DetailsRoad Length :124 Mts | 2025-26 | 800000 | 800000 |  |  |  | 0 | 13/08/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 800000 | 0 | 0 | - |  | 800000 | No | Yes
467 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00047 |  |  | General Fund GENERAL/2025-26/009/ROAD/00047-Repair /Maintenance-Other Roads- , | Roads | Other Roads | 767/2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 6400000 | 6400000 |  |  |  | 0 | 23/10/25 | 0.64 |  | 0 | Completed | 100 |  |  | 21/11/25 |  | 6158530 |  |  |  | 241470 | 0 | 0 | 23/12/25 |  | 6400000 | No | Yes
468 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00290 | Zone I | 5, 6, 7, 8 | General Fund GENERAL/2025-26/009/ROAD/00290-Providing and laying WMM for ward NO.5,6,7 and 8 in zone I in Tambaram City Municipal Corporation | Roads | Other Roads | 469-6Dated:06/10/25Road DetailsRoad Length :Mts | 2025-26 | 4516000 | 790000 |  |  |  | 0 | 28/11/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 790000 | 0 | 0 | - |  | 4516000 | No | Yes
469 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00196 | Zone III | 41 | General Fund GENERAL/2025-26/009/ROAD/00196-Providing and laying Paver Block To Arulneri Nagar 2nd Cross Street And Krishna Nagar 2nd Street in Ward No.41 in Zone III | Roads | Other Roads | 471-3Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 900000 | 900000 |  |  |  | 0 | 18/07/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 900000 | 0 | 0 | 25/10/25 |  | 900000 | No | Yes
470 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00228 | Zone 03 | 22 | General Fund GENERAL/2025-26/009/ROAD/00228-Providing And Laying Paver Block Road To Sriram Nagar Main Road In Ward No.22 In Zone-03 | Roads | Other Roads | 471-4Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 2000000 | 2000000 |  |  |  | 0 | 18/07/25 | 0.2 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2000000 | 0 | 0 | 25/10/25 |  | 2000000 | No | Yes
471 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00295 |  |  | General Fund GENERAL/2025-26/009/ROAD/00295-Repair /Maintenance-Other Roads- , - , - , - , - , | Roads | Other Roads | 12-1/2025-26Dated:23/02/26Road DetailsRoad Length :Mts | 2025-26 | 850000 | 850000 |  |  |  | 0 | 28/11/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 850000 | 0 | 0 | - |  | 850000 | No | Yes
472 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00089 | Zone I | 3 | General Fund GENERAL/2024-25/009/SWD/00089-Rising of Strom water drain & providing Precast RCC slab at kamatchi nagar 3rd cross to ramalingamadam street ward no 3 zone 1 | Storm Water Drain | Reconstruction of Drain | 349-8Dated:28/08/24 | 2024-25 | 900000 | 900000 |  |  |  | 0 | 19/09/24 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 900000 | 0 | 0 | 25/11/24 |  | 900000 | No | No
473 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00030 | Zone V | 66 | General Fund GENERAL/2024-25/009/SWD/00030-Construction of Storm Water Drain to Rajaji Nagar Main Road in Ward No.66 at Zone V in Tambaram City Municipal Corporation | Storm Water Drain | Reconstruction of Drain | 611Dated:25/08/25 | 2024-25 | 2200000 | 2200000 |  |  |  | 0 | 22/09/25 | 0.22 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2200000 | 0 | 0 | 29/11/25 |  | 2200000 | No | No
474 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00249 | Zone V | 45 | General Fund GENERAL/2025-26/009/PARK/00249-Construction of open GYM at zone 5 Thirupoor kumaran park in ward 45 in Tambaram city Municipal Corporation | Parks | Playground for Sports | 338-1Dated:24/06/25 | 2025-26 | 1600000 | 1600000 |  |  |  | 0 | 24/06/25 | 0.16 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1600000 | 0 | 0 | 30/08/25 |  | 1600000 | No | No
475 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00084 | Zone III |  | General Fund GENERAL/2025-26/009/PARK/00084-Providing Playfield of Roller Skating in Annai Anjugam Park in Ward:42 in Zone III | Parks | Playground for Sports | 597Dated:25/08/25 | 2025-26 | 5250000 | 5250000 |  |  |  | 0 | 2025-07-07 | 0.52 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5250000 | 0 | 0 | 14/10/25 |  | 5250000 | No | No
476 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00322 | Zone III | 43 | General Fund GENERAL/2024-25/009/PARK/00322-Providing Play Field Of Basket Ball Court Bharath Avenue Park Ward No.43 in Zone III | Parks | Playground for Sports | 576Dated:30/12/24 | 2024-25 | 4500000 | 4500000 |  |  |  | 0 | 2025-10-02 | 0.44 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 4500000 | 0 | 0 | 17/05/25 |  | 4500000 | No | Yes
477 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00328 | Zone III | 44 | General Fund GENERAL/2024-25/009/PARK/00328-Providing Play Field Volley Ball,Batminton,Roller Skating At Ramakrishana Nagar Park In Ward No.44 In Zone III | Parks | Playground for Sports | 571Dated:30/12/24 | 2024-25 | 1565000 | 1565000 |  |  |  | 0 | 2025-10-02 | 0.15 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1565000 | 0 | 0 | 17/05/25 |  | 1565000 | No | Yes
478 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00320 | Zone III |  | General Fund GENERAL/2024-25/009/PARK/00320-Providing Playfield of Roller Skating And Improvement of Park in Tellus avenue Phase-2 in Ward:41 in Zone III | Parks | Playground for Sports | 570Dated:30/12/24 | 2024-25 | 5400000 | 5400000 |  |  |  | 0 | 2025-10-02 | 0.53 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 5400000 | 0 | 0 | 17/05/25 |  | 5400000 | No | Yes
479 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/PARK/00028 | Zone V | 69 | MLA Fund MLA/2024-25/009/PARK/00028-Construction of Compound wall work in ward No.69 Pazhathottam park at Tambaram Corporation, Zone V | Parks | Compound Wall Toilet and Security Room | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 830000 |  |  |  | 0 | 2025-05-02 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 830000 | 0 | 0 | - |  | 7290000 | No | Yes
480 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00248 | Zone II | 26 | General Fund GENERAL/2025-26/009/OTHERS/00248-Renovation of Existing OHT,Sump and Providing Paver Block at Shanthi Nagar Water Supply Tank in Ward No.26 Tambaram City Municipal Corporation at Zone II | Others | Infrastructure and Amenities | 716-06/2025-26Dated:25/08/25 | 2025-26 | 2800000 | 2800000 |  |  |  | 0 | 26/09/25 | 0.28 |  | 0 | Completed | 100 |  |  | 16/02/26 |  | 2786608 |  |  | 0 | 13391.79 | 0 | 0 | 26/12/25 |  | 2800000 | No | Yes
481 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00027 | Zone III | 34 | MLA Fund MLA/2024-25/009/OTHERS/00027-Construction of Compound Wall and Toilet work in ward No.34 Sitlapakkam Jothi Nagar VAO Office at Tambaram Corporation, Zone III | Others | Infrastructure and Amenities | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 1210000 |  |  |  | 0 | 24/09/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1210000 | 0 | 0 | 23/12/25 |  | 7290000 | No | Yes
482 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00292 | Zone 01 |  | General Fund GENERAL/2025-26/009/OTHERS/00292-Supply and delivery of Tables,chairs, 1.5 TR split AC and Dismantling the existing wall and Aluminium glazed fixed partition in pammal office zone No.01 TCMC | Others | Infrastructure and Amenities | 469-6Dated:06/10/25 | 2025-26 | 4516000 | 700000 |  |  |  | 0 | 28/11/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 700000 | 0 | 0 | - |  | 4516000 | No | Yes
483 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00293 |  |  | General Fund GENERAL/2025-26/009/OTHERS/00293-Construction of Galvalume sheet shed for SO section in Pammal zone No .1 back side office in Tambaram City Municipal Corporation | Others | Infrastructure and Amenities | 469-6Dated:06/10/25 | 2025-26 | 4516000 | 980000 |  |  |  | 0 | 28/11/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 980000 | 0 | 0 | - |  | 4516000 | No | Yes
484 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00442 |  |  | General Fund GENERAL/2025-26/009/OTHERS/00442-Providing Shamiyana,Chair , Table and additional arrangement for ungaludan stalin Scheme at Ram Seetha Mahal, Sri Padma Ram Ganesh Mahal and Sri ram ganesh mahal | Others | Infrastructure and Amenities | 633/25.08.2025Dated:25/08/25 | 2025-26 | 5260000 | 1000000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 5260000 | No | No
485 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00443 |  |  | General Fund GENERAL/2025-26/009/OTHERS/00443-Providing Shamiyana,Chair , Table and additional arrangement for ungaludan stalin Scheme at CHitlapakkam , Zamin Royapettai School | Others | Infrastructure and Amenities | 633/25.08.2025Dated:25/08/25 | 2025-26 | 5260000 | 1760000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1760000 | 0 | 0 | - |  | 5260000 | No | No
486 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00444 |  |  | General Fund GENERAL/2025-26/009/OTHERS/00444-Providing Shamiyana,Chair , Table and additional arrangement for ungaludan stalin Scheme at Kamarajapuram Community hall | Others | Infrastructure and Amenities | 633/25.08.2025Dated:25/08/25 | 2025-26 | 5260000 | 1000000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 5260000 | No | No
487 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00445 |  |  | General Fund GENERAL/2025-26/009/OTHERS/00445-Providing Shamiyana,Chair , Table and additional arrangement for ungaludan stalin Scheme at Hasthinapuram School , Zamin Royapettai School | Others | Infrastructure and Amenities | 633/25.08.2025Dated:25/08/25 | 2025-26 | 5260000 | 1500000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | - |  | 5260000 | No | No
488 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00020 | Zone III |  | MLA Fund MLA/2023-24/009/BUILDING/00020-Providing Bus shelter at Hasthinapuram bus stand zone III | Buildings | Bus Shelter | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 1000000 |  |  |  | 0 | 2024-09-02 | 0.07 | Work Under Progress | 0 | Completed | 100 |  |  | 2025-02-05 |  | 0 |  |  |  | 1000000 | 0 | 0 | 2024-09-05 |  | 8230000 | No | Yes
489 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00271 | Zone I | 1 | MLA Fund MLA Fund/2021-22/009/WS/00271-Providing 4 Nos. of Borewell with India Mark II Hand Pump at Ward No.1 in Anakaputhur | Water Supply | Borewell | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 600000 |  |  | 0 | 0.06 | 2022-08-06 | 0.05 | Work Completed | 100 | Work Completed | 100 |  |  | 21/12/22 |  | 0 |  |  |  | 600000 | 0.06 | 98.47 | 2022-08-07 |  | 4710000 | Yes | Yes
490 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00001 | Zone I | 4 | MLA Fund MLA Fund/2022-23/009/WS/00001-Providing Deep Borewell with Mini Power Pump and HDPE Tank at (Ward No. 4) | Water Supply | Borewell | 3607/2022/A3Dated:30/11/22 | 2022-23 | 6285000 | 280000 |  |  |  | 0 | 2023-11-01 | 0.02 | Work Completed | 100 | Work Completed | 100 |  |  | 2023-05-04 |  | 280000 |  |  |  | 0 | 0 | 0 | 26/01/23 |  | 6285000 | No | Yes
491 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00157 |  |  | General Fund GENERAL/2025-26/009/WS/00157-Removal of Damaged HDPE tanks and replacing of HDPE Tanks and Pedastal platform East Tambaram Area in Tambaram City Municipality | Water Supply | Borewell | 410Dated:06/01/25 | 2025-26 | 350000 | 350000 |  |  |  | 0 | 2025-07-02 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 350000 | 0 | 0 | 14/04/25 |  | 350000 | No | No
492 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2024-25/009/PARK/00427 | Zone V | 69 | Namakku Naame Thittam NNT/2024-25/009/PARK/00427-Construction of Compound wall to Shiradi sai Nagar park at ward No.69 Zone V | Parks | Parks | 19731/2024/t2Dated:11/03/25 | 2024-25 | 2279000 | 999000 |  |  |  | 0 | 21/04/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 999000 | 0 | 0 | 30/05/25 |  | 2279000 | No | Yes
493 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PARK/00465 |  |  | 15th CFC 15th CFC/2020-21/009/PARK/00465-Improvement of Annai Indra Nagar and AS Nagar Park in Peerkankaranai | Parks | Parks | 922/2020-TP2Dated:14/09/21 | 2020-21 | 3400000 | 1600000 |  |  |  | 0 | 25/10/21 | 0.16 | Work Completed | 100 | Work Completed | 100 |  |  | 17/09/24 |  | 878000 |  |  |  | 722000 | 0 | 0 | 24/12/21 |  | 3400000 | No | Yes
494 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00004 | Zone V | 64 | General Fund GENERAL/2025-26/009/PARK/00004-Construction of Open Gym at Zone 5 Ward No.64 Subburayan Park, Zone V in Tambaram City Municipal Corporation | Parks | Parks | 338Dated:24/06/25 | 2025-26 | 1600000 | 1600000 |  |  |  | 0 | 24/06/25 | 0.16 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1600000 | 0 | 0 | 25/08/25 |  | 1600000 | No | No
495 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00006 | Zone V | 68 | General Fund GENERAL/2025-26/009/PARK/00006-Construction of open gym at zone 5 ward no 68 Mallieswari nagar park in Tambaram City Municipal Corporation | Parks | Parks | 338-2Dated:24/06/25 | 2025-26 | 1600000 | 1600000 |  |  |  | 0 | 24/06/25 | 0.16 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1600000 | 0 | 0 | 30/08/25 |  | 1600000 | No | No
496 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00161 | Zone V | 67 | General Fund GENERAL/2024-25/009/PARK/00161-Construction of Yoga platform at Sridevi Street Ward 67 in Zone 5 Tambaram City Municipal Corporation | Parks | Parks | 369-1Dated:30/08/24 | 2024-25 | 1300000 | 1300000 |  |  |  | 0 | 23/10/24 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | 30/12/24 |  | 1300000 | No | No
497 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00179 | Zone V | 67 | General Fund GENERAL/2025-26/009/CULVERT/00179-Construction of Cut and Cover Box Culvert at Madambakkam Main Road Indian Bank Near in Ward no 67 at Zone 5 Tambaram City Municipal Corporation | Culverts | Culverts | 463-2Dated:24/06/25 | 2025-26 | 700000 | 700000 |  |  |  | 0 | 17/07/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 700000 | 0 | 0 | 24/09/25 |  | 700000 | No | No
498 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/CULVERT/00018 | Zone V | 65 | General Fund GENERAL/2025-26/009/CULVERT/00018-Construction of Slab culvert at ward 65 Ambetkar nagar 3rd, 4th street in zone 5 Tambaram City Municipal Corporation | Culverts | Culverts | 417-2Dated:04/04/25 | 2025-26 | 300000 | 300000 |  |  |  | 0 | 2025-09-05 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 300000 | 0 | 0 | 16/07/25 |  | 300000 | No | No
499 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00051 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00051-Supply and delivery of 2nos 4 wheel drive tractor with MS tractor mounted front dozer | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 2253000 |  |  |  | 0 | 25/07/25 | 0.23 | Tender Extended On 23.05.2025 | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2253000 | 0 | 0 | 21/04/26 |  | 77422000 | No | Yes
500 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00054 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00054-Supply and delivery 1no of 148 Crawler type Hydraulic excavator equipment 1.02 cum capacity | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 7600000 |  |  |  | 0 | 14/07/25 | 0.76 | Loa Issued On 28.04.2025 | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 7600000 | 0 | 0 | 2026-10-04 |  | 77422000 | No | Yes
501 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00055 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00055-Supply and delivery 2no of 148 Crawler type Hydraulic excavator equipment 1.02 cum capacity | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 15200000 |  |  |  | 0 | 14/07/25 | 1.52 | Loa Issued On 28.04.2025 | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15200000 | 0 | 0 | 2026-10-04 |  | 77422000 | No | Yes
502 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00056 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00056-Supply and delivery of 3nos 4 wheel drive tractor with MS tractor mounted front dozer | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 3379000 |  |  |  | 0 | 14/07/25 | 0.34 | Tender Extended On 23.05.2025 | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3379000 | 0 | 0 | 2026-10-04 |  | 77422000 | No | Yes
503 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00057 | Zone I |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00057-Construction of Micro Compost Centre at Anakaputhur zone No.1 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.58 | 26/04/23 | 0.48 | Work Fully Completed | 100 | Work Completed | 100 |  |  | 13/09/24 |  | 5750000 |  |  |  | 0 | 0.58 | 100 | 26/08/23 |  | 40250000 | Yes | Yes
504 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00134 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00134-Supply and delivery of 5nos of backhoe loader fitter with 0.27 cu.m bucket at load end, bucket with bolt on teeth at excavator end, diesel engine of 74HP | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 17450000 |  |  |  | 0 | 14/08/25 | 1.75 | Tender Extended On 23.05.2025 | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 17450000 | 0 | 0 | 2026-11-05 |  | 118900000 | No | Yes
505 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/SWM/00013 | Zone II | 31 | 15th CFC 15th CFC/2021-22/009/SWM/00013-Thiruneermalai Bio mining work (2070 cum) at ward no.31near compost yard (below ground level) | Solid Waste Management | Bio Mining Work | 21191/AMRUT-2-Tambaram-Tied-1 SavingsDated:23/03/22 | 2021-22 | 1650000 | 1640000 |  |  |  | 0.16 | 18/10/21 | 0.15 | Work Completed | 100 | Work Completed | 100 |  |  | 14/12/22 |  | 1640000 |  |  |  | 0 | 0.14 | 84.05 | 18/10/22 |  | 1650000 | Yes | Yes
506 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00283 | Zone II | 7, 12 | 15th CFC 15th CFC/2020-21/009/WS/00283-Ward No.7 Providing deep borewell with power pump at Sundar Avenue, Saravana Nagar 7th street and ward no.12 Bharathidasan street | Water Supply | Borewell | 7979/2020/LAM SEM -3Dated:30/06/21 | 2020-21 | 1000000 | 1000000 | 0 |  |  | 0.1 | 2021-12-08 | 0 | Completed | 100 | Completed | 100 |  |  | 2021-03-11 |  | 974975 |  |  |  | 25025 | Excel0.10 | 97.5 | 2021-10-11 |  | 1000000 | No | Yes
507 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00002 | Zone IV | 58 | MLA Fund MLA/2023-24/009/BUILDING/00002-Construction of Anganwadi center at NGO colony, Perungalathur in ward No.58, Zone IV | Buildings | Anganwadi | 3041/2023/A1Dated:05/10/23 | 2023-24 | 3200000 | 2000000 |  |  |  | 0.2 | 24/11/23 | 0.18 | Finishing Work Is In Progress | 90 | Completed | 100 | 25/10/24 |  | 25/10/24 |  | 278486 |  |  |  | 1721514 | 0 | 0 | 24/05/24 |  | 3200000 | No | Yes
508 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00203 | Zone I | 10 | MLA Fund MLA/2024-25/009/BUILDING/00203-Construction of Anganwadi center at ward No. 10 zone I in Tambaram City Municipal Corporation | Buildings | Anganwadi | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0.08 | Finisihing Work In Progress | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 16540000 | No | Yes
509 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/UGSS/00319 | Zone V | 65 | General Fund GENERAL/2025-26/009/UGSS/00319-Providing Sewerage Line Facilities to Sumaru City at Ward 65 at Zone 5 East Tambaram Area in Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 466Dated:24/06/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 17/07/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1500000 | 0 | 0 | 24/10/25 |  | 1500000 | No | Yes
510 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/UGSS/00034 | Zone V | 64 | General Fund GENERAL/2023-24/009/UGSS/00034-providing sewerage line facilities to incomplete areas at ward 64 at zone 5 East Tambaram at Tambaram City Municipal Corporation | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 566Dated:30/11/25 | 2023-24 | 1540000 | 1540000 |  |  |  | 0 | 14/03/24 | 0.15 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1540000 | 0 | 0 | 21/06/24 |  | 1540000 | No | No
511 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/UGSS/00036 | Zone V | 63 | General Fund GENERAL/2023-24/009/UGSS/00036-Providing Sewerage Facilities and Laying of incomplete 150mm DI Pumping Main and Special from Proposed Sewage Lifting station at Kamakshi Amman kulam to Murugesan street at Ward 63, Zone 5 East Tambaram Area in Tambaram city Municipal Corporation. | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 560Dated:30/11/23 | 2023-24 | 1145000 | 1145000 |  |  |  | 0 | 14/03/24 | 0.11 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 1145000 | 0 | 0 | 21/05/24 |  | 1145000 | No | No
512 | Tambaram | CGF | CHENGALPATTU | CGF/2019-20/009/WS/00189 | Zone II | 17 | CGF CGF/2019-20/009/WS/00189-Restoration and Improvement of water bodies as Rain water harvesting Structure- Pappathi Kuttai in ward 17 of pallavapuram Municipality | Water Supply | Water Bodies | 10586/2019/E1Dated:15/10/19 | 2019-20 | 22300000 | 5600000 |  |  |  | 0.56 | 31/01/20 | 0.51 | Work Completed | 100 | Work Completed | 100 |  |  | 2021-09-04 |  | 5600000 |  |  |  | 0 | 0.42 | 75.54 | 31/10/20 |  | 22300000 | Yes | Yes
513 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00291 | Zone I |  | General Fund GENERAL/2025-26/009/ROAD/00291-Providing and laying Granular sub base at Kalainger roda inward No.07 zone I Tambaram City Municipal Corporation | Roads | Metal Road | 469-6Dated:06/10/25Road DetailsRoad Length :Mts | 2025-26 | 4516000 | 686000 |  |  |  | 0 | 28/11/25 | 0.07 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 686000 | 0 | 0 | - |  | 4516000 | No | Yes
514 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00181 | Zone III | 34 | MLA Fund MLA Fund/2021-22/009/BUILDING/00181-Construction of Public distribution shop at Chitlapakkam Ward No.34 Zone 3 in Tambaram city municipal Corporation | Buildings | Buildings | 4592/2021/A3 ChitlapakkamDated:06/05/22 | 2021-22 | 1000000 | 1000000 | 0 |  |  | 0.1 | 2022-11-07 | 0.09 | Completion Report Claim Proposal Sent To District Collectorate, Chengalpattu Vide Roc No : 498/2022/E1 Date : 23.01.2023 | 100 | Work Completed | 100 |  |  | 2023-02-03 |  | 999956 |  |  |  | 44 | 0.1 | 100 | 2022-09-09 |  | 1000000 | Yes | Yes
515 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/TW013/00063 | Zone III | 37 | MLA Fund MLA/2022-23/009/TW013/00063-Construction of Bus Shelter at Dr.Rajendra Prasad MAin Road and GAyathri Nagar Junction in Ward No.37 | Bus Stand | Others | 3607/2022/A3 - 13Dated:22/10/22 | 2022-23 | 700000 | 700000 | 0 |  |  | 0.07 | 2022-12-12 | 0.06 | Steel Fabrication Work Is In Progress | 20 | Completed | 100 |  |  | 20/07/24 |  | 680399 |  |  |  | 19601 | 0 | 0 | 2023-10-02 |  | 700000 | No | Yes
516 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00239 |  |  | General Fund GENERAL/2025-26/009/ROAD/00239-Repair /Maintenance-Other Roads009007R0560-RADHAKRISHANAN STREET ANNA NAGAR , | Roads | Other Roads | 09/2025-26Dated:23/02/26Road DetailsRoad Length :150 Mts | 2025-26 | 650000 | 650000 |  |  |  | 0 | 31/10/25 | 0.07 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 650000 | 0 | 0 | - |  | 650000 | No | No
517 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00156 | Zone III | 42 | MLA Fund MLA Fund/2021-22/009/BUILDING/00156-Construction of Public distribution shop at Maruthi Nagar Sembakkam at Ward No.42 in Tambaram city Municipal Corporation | Buildings | Buildings | 4592/2021/A3Dated:06/05/22 | 2021-22 | 1000000 | 1000000 |  |  |  | 0.1 | 2022-11-07 | 0.09 | Completion Report Claim Proposal Sent To District Collectorate, Chengalpattu Vide Roc No : 498/2022/E1 Date : 23.01.2023 | 100 | Work Completed | 100 |  |  | 2023-02-03 |  | 781116 |  |  |  | 218884 | 0.08 | 78.11 | 2022-09-09 |  | 1000000 | Yes | Yes
518 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2019-20/009/BUILDING/00276 |  |  | MP Fund MP Fund/2019-20/009/BUILDING/00276-Construction of Community Hall (First Floor) at Nallathambi Road in Pammal | Buildings | Buildings | 4568/2019/E3Dated:15/11/19 | 2019-20 | 5000000 | 5000000 | 0 |  |  | 0.25 | 31/03/20 | 0.46 | Completed | 0 | Work Completed | 100 |  |  | 2023-06-09 |  | 5000000 |  |  |  | 0 | 0.24 | 47.47 | 29/06/20 | ... | 5000000 | No | Yes
519 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00054 | Zone III | 38, 39 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00054-Construction of RCC Strom Water Drain with Cover Slab at New Colony 5th Main Road, New Colony 8th Cross Street ,New Colony 12th Cross Street, New Colony 14th Cross Street and Extn and Grand Palace Lane in Ward No.38,39 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pallavapuram - 2Dated:18/04/22 | 2022-23 | 13900000 | 13900000 |  |  |  | 1.25 | 13/06/22 | 1.13 | 220M Drain Slab Concrete Completed And 250M Drain Side Wall Concrete Completed | 38 | Drain Fully Completed, | 100 |  |  | 30/08/22 |  | 13949762 |  |  |  | -49761.6 | 1.15 | 82.97 | 2022-11-09 |  | 13900000 | Yes | Yes
520 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00015 | Zone V | 70 | General Fund GENERAL/2025-26/009/SWD/00015-Renovation & Construction of Storm water drain at ward no 70 Periyar nagar in zone 5 at Tambaram city Municipal Corporation | Storm Water Drain | Repair and Maintenance of Drain | 417Dated:04/04/25 | 2025-26 | 850000 | 850000 |  |  |  | 0 | 2025-09-05 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 850000 | 0 | 0 | 16/07/25 |  | 850000 | No | No
521 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00255 | Zone I | 4 | General Fund GENERAL/2025-26/009/SWD/00255-Construction of RCC Culvert in Ayyothiamman koil street, Anna nagar street in ward no.4 at Anakaputhur Zone -1 TCMC | Storm Water Drain | Repair and Maintenance of Drain | 414/2025-26Dated:02/04/25 | 2025-26 | 300000 | 300000 |  |  |  | 0 | 16/05/25 | 0 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 300000 | 0 | 0 | - |  | 300000 | No | Yes
522 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00013 | Zone V | 47 | General Fund GENERAL/2025-26/009/SWD/00013-Construction of Storm water drain at ward 47 Nagamai street , Valmegi street , Vasugi street in zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Repair and Maintenance of Drain | 415Dated:04/04/25 | 2025-26 | 950000 | 950000 |  |  |  | 0 | 2025-09-05 | 0.1 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 950000 | 0 | 0 | 16/07/25 |  | 950000 | No | No
523 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00411 | Zone II | 27 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00411-Construction of SWD and Culvert at CLC 1st Main Raod - 009027R1782,CLC 2nd Main Road - 009027R1783 in Ward No.27 Tambaram City Municipal Corporation Zone II (Packag NO.15) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3000000 |  |  |  | 0 | 2025-12-09 | 0.3 | In Progress | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 3000000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
524 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00221 | Zone V |  | General Fund GENERAL/2025-26/009/BUILDING/00221-Providing Digital Initiative for Robotics Lab to develop expert curriculum for teachers and students at corporation Higher secondary school selaiyur in Zone 5 @ Tambaram city municipal corporation | Buildings | Additional school building | 628Dated:25/08/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 25/08/25 | 0.15 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1500000 | 0 | 0 | 30/10/25 |  | 1500000 | No | No
525 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2024-25/009/ROAD/00426 |  |  | Namakku Naame Thittam NNT/2024-25/009/ROAD/00426-Relaying of Road-Bituminous Road009021R5868-English Electric Nagar 1st Main Road , | Roads | Bituminous Road | 19731/2024/t2Dated:11/03/25Road DetailsRoad Length :420 Mts | 2024-25 | 2279000 | 1280000 |  |  |  | 0 | 2025-09-04 | 0 |  | 0 | Completed | 100 |  |  | 25/06/25 |  | 1277972 |  |  |  | 2027.72 | 0 | 0 | 15/07/25 |  | 2279000 | No | Yes
526 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00270 |  |  | General Fund GENERAL/2025-26/009/ROAD/00270-Relaying of Road-Cement Concrete Road009062R4753-SHANTHI NAGAR ST EXTN , 009062S0544-SHANTHI NAGAR 1ST STREET , 009062R4750-SHANTHI NAGAR 2ND STREET , 009062R4751-SHANTHI NAGAR 3RD STREET , | Roads | Cement Concrete Road | 64-7Dated:25/08/25Road DetailsRoad Length :157 Mts | 2025-26 | 2200000 | 2200000 |  |  |  | 0 | 22/09/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2200000 | 0 | 0 | 29/12/25 |  | 2200000 | No | No
527 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2024-25/009/BUILDING/00158 | Zone I | 31 | Kalaignar Nagarpura Mempatu Thittam KNMT/2024-25/009/BUILDING/00158-Construction of Commercial Complex in Thiruneermalai at ward No .31 Survey No .81 Zone I Tambaram City Municipal Corporation | Buildings | Commercial Complex | 12th meeting CPSMCDated:19/07/24 | 2024-25 | 17000000 | 17000000 |  |  |  | 0 | 19/09/24 | 1.61 | White Wash Work Completed. | 85 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 17000000 | 0.83 | 48.93 | 19/12/24 |  | 17000000 | No | Yes
528 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00039 | Zone V | 70 | General Fund GENERAL/2024-25/009/BUILDING/00039-Providing paver block Madambakkam Government school in ward 70 zone 5 Tambaram City Municipal Corporation | Buildings | School Building | 313Dated:08/03/24 | 2024-25 | 540000 | 540000 |  |  |  | 0 | 2024-09-09 | 0.05 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 540000 | 0 | 0 | 16/11/24 |  | 540000 | No | No
529 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/SWD/00019 | Zone V | 48 | General Fund GENERAL/2023-24/009/SWD/00019-Repair and reconstruction of storm water drain at Nalvar street and Kambar street in ward 48 in zone 5 in Tambarm City Municipal Corporation | Storm Water Drain | Reconstruction of Drain | 256Dated:11/11/23 | 2023-24 | 380000 | 380000 |  |  |  | 0 | 30/08/24 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 380000 | 0 | 0 | 2024-06-11 |  | 380000 | No | No
530 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00020 | Zone V | 65 | General Fund GENERAL/2024-25/009/SWD/00020-Construction of storm water drain Palayathamman kovil street at ward no 65 in zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 369Dated:23/08/24 | 2024-25 | 610000 | 610000 |  |  |  | 0 | 21/04/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 610000 | 0 | 0 | 21/06/25 |  | 610000 | No | No
531 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00021 | Zone V | 45 | General Fund GENERAL/2025-26/009/SWD/00021-Construction of storm water drain at Eswaran kovil street ward no 45 at zone 5 in Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 466-2Dated:24/06/25 | 2025-26 | 460000 | 460000 |  |  |  | 0 | 17/07/25 | 0.05 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 460000 | 0 | 0 | 24/09/25 |  | 460000 | No | No
532 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00267 |  |  | General Fund GENERAL/2025-26/009/ROAD/00267-Relaying of Road-Cement Concrete Road009062R4737-ROJA THOTTAM 1ST CROSS EXTN 8TH STREET , 009062S0543-ROJA THOTTAM 1ST CROSS EXTN 7TH CROSS STREET , 009062R4751-SHANTHI NAGAR 3RD STREET , | Roads | Cement Concrete Road | MCR no. 122-13Dated:06/03/25Road DetailsRoad Length :134 Mts | 2025-26 | 3000000 | 3000000 |  |  |  | 0 | 21/04/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 3000000 | 0 | 0 | 28/07/25 |  | 3000000 | No | Yes
533 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00184 | Zone V |  | General Fund GENERAL/2025-26/009/ROAD/00184-Relaying of Road-Cement Concrete Road009068R5290-Bharath Nagar MGR Street , 009068S0625-Ellai Amman Koil Main Street , 009068R6315-Ellai Amman Koil 2nd Cr St , 009068R6316-Ellai Amman Koil 2nd Cr St , 009068S0626-Ellai Amman Koil 1st Cr St , 009068R5284-Santha Nagar 3rd Street , MGR Nagar 1 St cross street and MGR Nagar 9 cross Street Pandiraj 2 nd street ,Shantha Nagar in zone 5 | Roads | Cement Concrete Road | 611-3Dated:25/08/25Road DetailsRoad Length :401 Mts | 2025-26 | 3250000 | 3250000 |  |  |  | 0 | 17/09/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3250000 | 0 | 0 | 24/12/25 |  | 3250000 | No | No
534 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/SWD/00393 | Zone IV |  | 15th CFC Tied Grant 15thCFC/2024-25/009/SWD/00393-Construction of Storm Water Drain (Peripheral drain) at New Corporation office building Out side of Compound wall at Zone IV in Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 28485/2022/EA2-iiiDated:24/02/25 | 2024-25 | 74000000 | 39500000 |  |  |  | 0 | 26/06/25 | 3.95 | Steel Work Is In Progress | 52 | Completed | 100 |  |  |  |  | 0 |  |  |  | 39500000 | 0 | 0 | 24/10/25 |  | 74000000 | No | Yes
535 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00316 | Zone I | 1 | General Fund GENERAL/2025-26/009/SWD/00316-Construction of Storm water drain to Thiruvalluvar pettai street ward no.1 zone-1 TCMC | Storm Water Drain | Construction of Drain | 449/2025-26Dated:24/06/25 | 2025-26 | 1200000 | 1200000 |  |  |  | 0 | 14/08/25 | 0.12 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1200000 | 0 | 0 | - |  | 1200000 | No | Yes
536 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00059 | Zone I | 3 | General Fund GENERAL/2024-25/009/SWD/00059-Construction of Strom Water Drain to Gopal Chetty street & culvert in ward 3 @ Zone I | Storm Water Drain | Construction of Drain | 86-3Dated:06/03/25 | 2024-25 | 2250000 | 2250000 |  |  |  | 0 | 28/04/25 | 0.23 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2250000 | 0 | 0 | 2025-07-08 |  | 2250000 | No | No
537 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00206 | Zone I | 1 | General Fund GENERAL/2024-25/009/SWD/00206-Construction of Storm water drain to VGN Nagar 1st street,2nd street, Bommi nagar and Nethaji street in ward no.1 atAnakaputhur Zone no.1 TCMC | Storm Water Drain | Construction of Drain | 86/1Dated:11/04/25 | 2024-25 | 2000000 | 2000000 |  |  |  | 0 | 28/04/25 | 0.2 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2000000 | 0 | 0 | - |  | 2000000 | No | Yes
538 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00401 | Zone II | 13 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00401-Construction of SWD and Culvert at Thiru.Vi.Ka Street - 009013R0926,Chavadhi Street - 009013R0924,Arnthaipuram 2nd Street - 009013R0919,Valluvar Pattai 1st Street - 009013R0915 in Ward No.13 Tambaram City Municipal Corporation Zone II (Packag NO.5) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3500000 |  |  |  | 0 | 2025-12-09 | 0.35 | Work Completed | 100 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 3500000 | 0.31 | 89.48 | 2025-11-12 |  | 200000000 | Yes | Yes
539 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00420 | Zone IV | 59 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00420-Construction of Storm Waret Drain to Ramanujam Street 009059R4452 Valayapathi Street 009059R4519Bharathidasan Nagar, MANI STREET 009059R4464 KALAINGAR NEDUNCHALAI 009059R4469 in Ward no.59 in Zone-4 (Package No.24) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 5900000 |  |  |  | 0 | 2025-12-09 | 0.59 | In Progress | 12 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 5900000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
540 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | Namakku Na/2021-22/009/SWD/00035 | Zone II | 31 | Namakku Naame Thittam Namakku Na/2021-22/009/SWD/00035-Construction of Storm Water drain and Culvert at Punithavathi Colony Main Road in ward no. 31 Sembakkam in Tambaram Corporation. | Storm Water Drain | Construction of Drain | Roc.No. 28244-18/2021/P2-Storm Water drain - Tambaram CorpnDated:25/01/22 | 2021-22 | 900000 | 900000 |  |  |  | 0.09 | 21/03/22 | 0.08 | Completed | 100 | Work Completed | 100 |  |  | 2022-10-06 |  | 0 |  |  |  | 900000 | 0.08 | 90.93 | 17/09/22 |  | 900000 | Yes | Yes
541 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00011 | Zone II |  | General Fund GENERAL/2024-25/009/SWD/00011-Construction of swd at thiruvalluvar nagar and anna st in wd 21 in zone 2 | Storm Water Drain | Construction of Drain | 341/30-08-2024Dated:30/08/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 23/12/24 | 0.6 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6000000 | 0 | 0 | 23/03/25 |  | 6000000 | No | No
542 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/SWD/00001 | Zone III | 40 | General Fund GENERAL/2023-24/009/SWD/00001-Construction of SWD From Bakkiyam Nagar to VGP Pon Nagar 3rd Street in Ward-40 Zone 3 | Storm Water Drain | Construction of Drain | 588/30.11.2023Dated:30/11/23 | 2023-24 | 2400000 | 2400000 |  |  |  | 0 | 20/12/24 | 0.24 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 2400000 | 0 | 0 | 25/03/25 |  | 2400000 | No | Yes
543 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00406 | Zone II | 18 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00406-Construction of SWD at Yasodha Nagar 2Nd Street - 009018R1156,Yasodha Nagar 3Rd Street - 009018R1157,Bagiyalakshmi Nagar - 009018R1129,Balaji Avenue ,Briundavan Nagar - 009018R1134 and Culvert at Yasodha Nagar 2Nd Street - 009018R1156,Yasodha Nagar 3Rd Street - 009018R1157,Bagiyalakshmi Nagar - 009018R1129,Balaji Avenue ,Briundavan Nagar - 009018R1134 in Ward No.18 Tambaram City Municipal Corporation Zone II (Packag NO.10) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 3900000 |  |  |  | 0 | 2025-12-09 | 0.39 | In Progress | 0 | Completed | 100 |  |  | 19/11/25 |  | 3891785 |  |  |  | 8215.18 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
544 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00227 | Zone I | 11 | General Fund GENERAL/2024-25/009/SWD/00227-Construction of Storm water Drain in Thangiaha street wat ward no.11 zone-1 TCMC | Storm Water Drain | Construction of Drain | 88/06.03.2025Dated:06/03/25 | 2024-25 | 2800000 | 2800000 |  |  |  | 0 | 15/04/25 | 0.28 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2800000 | 0 | 0 | - |  | 2800000 | No | No
545 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00118 | Zone V | 46 | General Fund GENERAL/2024-25/009/SWD/00118-Construction of strom water drain to kamarajar street ward no 46 zone 5 in Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 122-7Dated:06/03/25 | 2024-25 | 2500000 | 2500000 |  |  |  | 0 | 21/04/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 28/06/25 |  | 2500000 | No | No
546 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00124 |  |  | TURIP TURIP/2023-24/009/ROAD/00124-Relaying of Road-009007R0528-RAJARAJAN STREET , 009007R0509-SIGNAL OFFICE ROAD , 009007R0538-AAKTHESHWARAR KOIL STREET A NAGAR , 009007R0527-MEAYR CITYBABU 1ST STREET , 009007R0557-ELANGO STREET ANNA NAGAR , 009007R0611-DEVARAJAN STREET MUTHAMIZH NAGAR , 009007R0564-RAJAJI STREET ANNA NAGAR , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :839 Mts | 2023-24 | 313620000 | 3300000 |  |  |  | 0.3 | 2023-04-09 | 0.33 | Work Completed | 100 | Work Completed | 100 | 13/03/24 |  | 28/03/24 |  | 30 |  |  |  | 3299970.31 | 0.3 | 89.98 | 18/10/23 |  | 313620000 | No | Yes
547 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00098 |  |  | TURIP TURIP/2025-26/009/ROAD/00098-Relaying of Road-Bituminous Road009055R4043-KANNAN AVENUE 3RD STREET , 009055R4045-KANNAN AVENUE 5TH STREET , 009055R4035-BHARATHI NAGAR 6TH STREET , 009055R4037-BHARATHI NAGAR 8TH STREET , 009055R4070-THANGARAJ NAGAR 2ND STREET , 009055R4072-THANGARAJ NAGAR 3RD STREET , 009055R4081-VISHNU NAGAR- EB COLONY 5TH STREET , 009055R4032-BHARATHI NAGAR 3RD STREET , 009055R4018-Kurinji Malar Street , 009055R4076-VISHNU NAGAR 1ST STREET , 009055R4008-ANNAI ANJUGAM NAGAR EXTN 1ST STREET , | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :5321 Mts | 2025-26 | 521620000 | 26400000 |  |  |  | 0 | 2025-10-06 | 2.18 | Out Of Roads 19 , 18 Roads Completed , 1Roads Work Not Started | 90 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 26400000 | 0 | 0 | 2025-09-08 |  | 521620000 | No | Yes
548 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00086 | Zone V | 69 | General Fund GENERAL/2024-25/009/SWD/00086-Construction of Storm Water Drain and Culvert at Padmavathi Nagar 12,14th Street Extn ,Padmavathi nagar 15th street,Bhuvaneswari Nagar 2 nd and 4th street Ward No 69 in Zone 5 Tambaram City MUNICIPAL corporation | Storm Water Drain | Construction of Drain | 646Dated:30/12/24 | 2024-25 | 3200000 | 3200000 |  |  |  | 0 | 16/07/25 | 0 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 3200000 | 0 | 0 | 23/09/25 |  | 3200000 | No | No
549 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/SWD/00146 | Zone V | 66 | General Fund GENERAL/2023-24/009/SWD/00146-Construction of storm water drain and providing RCC cover slab to Gandhi nagar 1st main road ward -66 in tambaram city municipal corporation at zone 5 | Storm Water Drain | Construction of Drain | 110Dated:23/11/22 | 2023-24 | 500000 | 500000 |  |  |  | 0 | 27/10/23 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 500000 | 0 | 0 | 31/12/23 |  | 500000 | No | No
550 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00032 | Zone V | 47 | General Fund GENERAL/2025-26/009/SWD/00032-Construction of storm drain at ward no 47 iyyapan (part) street in zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 417-3Dated:04/04/25 | 2025-26 | 350000 | 350000 |  |  |  | 0 | 2025-09-05 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 350000 | 0 | 0 | 16/07/25 |  | 350000 | No | No
551 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00033 | Zone V | 48 | General Fund GENERAL/2025-26/009/SWD/00033-Construction of storm water drain at ward no 48 nagamai street, valmegi street, and vasuki street in zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 417-4Dated:04/04/25 | 2025-26 | 800000 | 800000 |  |  |  | 0 | 2025-09-05 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 800000 | 0 | 0 | 16/07/25 |  | 800000 | No | No
552 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00224 | Zone V | 62 | General Fund GENERAL/2025-26/009/SWD/00224-Renuvation of Strom Water Drain at Ward no 62 Yamuna Street ,Narmatha Street 3 rd & 4 th Street in Zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 417-5Dated:04/04/25 | 2025-26 | 980000 | 980000 |  |  |  | 0 | 2025-09-05 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 980000 | 0 | 0 | 16/08/25 |  | 980000 | No | No
553 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00225 | Zone V | 62 | General Fund GENERAL/2025-26/009/SWD/00225-Construction of Strom Water Drain at Ward no 62 Vaigai st,Arul Nagar Extn in Zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 417-6Dated:04/04/25 | 2025-26 | 700000 | 700000 |  |  |  | 0 | 2025-09-05 | 0.07 |  | 0 | Compleded | 100 |  |  |  |  | 0 |  |  | 0 | 700000 | 0 | 0 | 16/08/25 |  | 700000 | No | No
554 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00165 | Zone V | 66, 67 | General Fund GENERAL/2025-26/009/SWD/00165-Construction of SWD at Roja thottom and Shanthinekettan colony main Road Ward no 66 and 67 in Zone 5 at Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 463-1Dated:24/06/25 | 2025-26 | 1140000 | 1140000 |  |  |  | 0 | 17/07/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1140000 | 0 | 0 | 24/09/25 |  | 1140000 | No | No
555 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00275 | Zone V | 66 | General Fund GENERAL/2025-26/009/SWD/00275-Construction of Storm Water Drain to Metha Nagar Ward no 66 Zone 5 in Tambaram City Municipal Corporation | Storm Water Drain | Construction of Drain | 415-2Dated:04/04/25 | 2025-26 | 450000 | 450000 |  |  |  | 0 | 30/05/25 | 0 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 450000 | 0 | 0 | 2025-02-09 |  | 450000 | No | No
556 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00203 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00203-Relaying of Road-Bituminous Road009066R5110-SILAPATHIGARAM STREET , 009067R5175-KARUMARIAMMAN NAGAR 2ND STREET , 009067R5130-BRINDAVAN NAGAR MAIN ROAD , 009067R5213-THIRUMALAI NAGAR 1ST MAIN ROAD , 009068R5309-BALAJI NAGAR EAST MAIN ROAD , 009068R6333-Padmavathi Nagar Main Road(51K Bus route ) , 009068R5294-BALAJI NAGAR 1ST STREET , 009069R6369-Padmavathi Nagar Main Road(51K Bus Route) , 009069R6339-Secretariat Colony Phse2 vivekanandhar street , 009069R5470-Secretariat Colony Brindhavan Street | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :3792 Mts | 2022-23 | 98900000 | 20000000 |  |  |  | 1.8 | 19/06/23 | 2 |  | 0 | Completed | 100 |  |  | 26/02/25 |  | 19513561 |  |  |  | 486439 | 1.87 | 93.5 | 17/09/23 |  | 98900000 | No | Yes
557 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00156 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00156-Relaying of Road-009019R1216-SOUNDARAJAN NAGAR MAIN ROAD , 009019R1185-RAJENDRAN NAGAR MAIN ROAD , 009019R5794-Jaya Nagar , 009019R5798-SENDHUR VEEDHI , 009019R1192-SRVS Main road , 009019R1193-NANDHI NAGAR , 009019R5793-RAJENDRAN NAGAR EXTENSION , 009019R1211-BOOPATHY NAGAR EXTN , 009020R1221-AMBAL NAGAR 11TH STREET , 009020R1320-NATESAN SALAI , 009020S0218-AMBAL NAGAR 9TH STREET , 009020R5810-Ayyothidasa Pandidar Road , 009020R5820-Eswaran Nagar 6th Street , 009020R1312-Kamatchi Nagar 1st Mai | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :4319 Mts | 2023-24 | 319260000 | 8900000 |  |  |  | 0.8 | 2024-02-01 | 0.89 | Work To Be Started | 0 | Completed | 100 |  |  | 26/02/25 |  | 8893305 |  |  |  | 6695 | 0.78 | 88.12 | - |  | 319260000 | Yes | Yes
558 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00127 |  |  | General Fund GENERAL/2025-26/009/ROAD/00127-Repair /Maintenance-Bituminous Road009031R2029-EAST MADA STREET, THIRUNEERMALAI, CHENNAI-44 , 009031R1977-1ST STREET, SRIPURAM, THIRUNEERMALAI, CHENNAI-600 044. , | Roads | Bituminous Road | 455/3Dated:25/09/25Road DetailsRoad Length :127.9 Mts | 2025-26 | 960000 | 960000 |  |  |  | 0 | 13/08/25 | 0.1 | Finishing Work In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 960000 | 0 | 0 | - |  | 960000 | No | Yes
559 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00368 |  |  | General Fund GENERAL/2025-26/009/ROAD/00368-Relaying of Road-Bituminous Road009020R1249-AMBAL NAGAR 20TH STREET , 009020S0202-SIVARAJ STREET , 009020R1303-VELSAMY NAGAR IST STREET , 009020S0207-BALAMURUGAN NAGAR 1ST ST , 009020R1228-AMBAL NAGAR 21ST STREET , 009020R1229-AMBAL NAGAR 19TH STREET , 009020R1254-THENMOZHI NAGAR 2ND STREET , 009020S0188-SAI IST CROSS STREET , 009020R5832-BAKKIAMMAL NAGAR 2ND STREET , 009020R1279-THIRUVENGADAMUDAIYAN KOIL STREET , 009020S0204-BAKKIAMMAL NAGAR 2ND STREET , 009020R5834-Balamurugan Nagar 8th Cros | Roads | Bituminous Road | 13146/2025/MA3Dated:19/06/25Road DetailsRoad Length :2335 Mts | 2025-26 | 67200000 | 13300000 |  |  |  | 0 | 2025-04-08 | 1.33 | Out Of 19 Roads , 15 Roads Completed ,4 Roads Is In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13300000 | 0 | 0 | 2025-02-11 |  | 67200000 | No | No
560 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00369 |  |  | General Fund GENERAL/2025-26/009/ROAD/00369-Relaying of Road-Bituminous Road00920R1255-THENMOZHI NAGAR 3RD STREET , 009020S0209-Pallavan colony 5th cross , 009020R1264-Pallavan Colony 3rd Cross , 009020R1263-Pallavan Colony 2nd Cross , 009020R1283-ANNAMMAL NAGAR , 009020R5838-Pallavan Nagar 6th Cross Street , 009020R1290-Thiruveethi amman koil street , 009020R5829-VELUSAMY NAGAR 6TH ST , 009021R1378-PERUMAL NAGAR 10TH CROSS STREET , 009021R1369-PERUMAL NAGAR 2ND MAIN ROAD , 009021R1377-PERUMAL NAGAR 8TH CROSS STREET , 009016R0988-BHARAT | Roads | Bituminous Road | 13146/2025/MA3Dated:19/06/25Road DetailsRoad Length :1824.8 Mts | 2025-26 | 67200000 | 11100000 |  |  |  | 0 | 2025-04-08 | 1.11 | Out Of 12 Roads , 10 Roads Completed ,2 Roads Is In Progress | 83 | Completed | 100 |  |  |  |  | 0 |  |  |  | 11100000 | 0 | 0 | 2025-02-11 |  | 67200000 | No | No
561 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00370 |  |  | General Fund GENERAL/2025-26/009/ROAD/00370-Relaying of Road-Bituminous Road009039R2457-PRASANTH COLONY 1ST STREET , 009039R2523-KALATHUMEDU STREET , 009039R2527-SENTHIL AVENUE 2ND STREET , 009039R2528-SENTHIL AVENUE 3RD STREET , 009039R2529-MANAVALAN NAGAR , 009039R2542-MYLAI RAMAMURTHY STREET , 009039R2500-ERIKARAI STREET , 009039R2481-Vijayakumar avenue , 009039R2479-THIRUMALAI NAGAR 17TH STREET , 009039R2474-Thirumalai nagar 13th street extn , 009040T2575-R B AVENUE 2ND STREET , 009040R2606-SAMRAJ NAGAR 7TH STREET , 009040R2613-Samra | Roads | Bituminous Road | 13146/2025/MA3Dated:19/06/25Road DetailsRoad Length :4736 Mts | 2025-26 | 67200000 | 19500000 |  |  |  | 0 | 2025-04-08 | 0 | Out Of 24 Roads ,12 Roads Completed , 12 Roads In Progress | 50 | Completed | 100 |  |  |  |  | 0 |  |  |  | 19500000 | 0 | 0 | - |  | 67200000 | No | No
562 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00371 |  |  | General Fund GENERAL/2025-26/009/ROAD/00371-Relaying of Road-Bituminous Road009064R4816-CHRIST KING SCHOOL ST , 009064R4825-ARIGNAR ANNA STREET , 009064R4835-INDIAN AIR FORCE STATION MAIN ROAD , 009064R4847-ANNAI THERASA ST , 009065R4910-MUTHUSWAMY STREET , 009065R5031-RAJKUMAR AVENUE , 009065S0561-MURUGESAN STREET , 009065R4891-NEW BALAJI NAGAR MAIN ROAD , 009065R4875-NEW BALAJI NAGAR 2ND STREET , 009065R4876-NEW BALAJI NAGAR 3RD STREET , 009065R4877-NEW BALAJI NAGAR 3RD STREET , 009065R4879-NEW BALAJI NAGAR 5TH STREET , 009065R5006-NATA | Roads | Bituminous Road | 13146/2025/MA3Dated:19/06/25Road DetailsRoad Length :2544 Mts | 2025-26 | 67200000 | 23300000 |  |  |  | 0 | 14/07/25 | 2.33 | Out Of 13 Roads,7 Roads Completed,5 Roads In Progress,1roads To Be Started. | 53 | Completed | 100 |  |  |  |  | 0 |  |  |  | 23300000 | 0 | 0 | 2025-12-10 |  | 67200000 | No | No
563 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00372 |  |  | General Fund GENERAL/2025-26/009/ROAD/00372-Relaying of Road-Bituminous Road009005R0385-SHANKAR NAGAR 36TH STREET , 009005R0394-SHANKAR NAGAR 3RD CROSS STREET , 009005R0404-SHANKAR NAGAR 16TH STREET , 009005R0399-SHANKAR NAGAR 42ND STREET , 009005R5768-SRINIVASAN STREET LIC COLONY , 009005R5774-LIC Colony Jayatheertha Rao Cross street , 009005R0334-GANAPATHI NAGAR 1ST STREET , 009005R0349-Thiruvalluvar Cross Street , | Roads | Bituminous Road | 13146/2025/MA3-2Dated:19/06/25Road DetailsRoad Length :1662 Mts | 2025-26 | 61444000 | 15000000 |  |  |  | 0 | 2025-04-08 | 1.5 | Out Of 8 Roads , 2 Roads Completed ,5 Roads Is In Progress | 25 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15000000 | 0 | 0 | 2025-02-11 |  | 61444000 | No | No
564 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00373 |  |  | General Fund GENERAL/2025-26/009/ROAD/00373-Relaying of Road-Bituminous Road009012R0873-THANTHAI PERIYAR STREET CHOZHAVARAM NAGAR , 009012R0904-PILLAIYAR KOVIL STREET , 009012R0867-NALLATHAMBI STREET CHOZHAVARAM NAGAR , 009012R0894-NALATHURAI SCHOOL STREET , | Roads | Bituminous Road | 13146/2025/MA3-2Dated:19/06/25Road DetailsRoad Length :946 Mts | 2025-26 | 61444000 | 8944000 |  |  |  | 0 | 2025-04-08 | 0.89 | 3 Roads Is In Progress | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 8944000 | 0 | 0 | 2025-02-11 |  | 61444000 | No | No
565 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00374 |  |  | General Fund GENERAL/2025-26/009/ROAD/00374-Relaying of Road-Bituminous Road009012R0912-ABDUL KALAM CROSS STREET , 009012R0856-MUTHU STREET VEERACHSAMI NAGAR , 009012R0853-KUPPAMMAL STREET , 009012R0862-NAVAMANI 1ST STREETCENTRAL BANK COLONY , 009012R0885-ENNAIRAM STREET SAMUNDEESWARI NAGAR , 009012R0888-ADAM NAGAR MAIN ROAD,NAGELKENI , 009012R0877-MGR CROSS STREET , 009012R0876-THANDHAI PERIYAR 1ST CROSS STREET , 009012R0848-ERATTAIMALAI SINIVASAN STREET , 009012R0858-MUNUSAMY STREET VEERACHSAMI NAGAR , 009012R0909-PILLAIYAR KOV | Roads | Bituminous Road | 13146/2025/MA3-2Dated:19/06/25Road DetailsRoad Length :1798 Mts | 2025-26 | 61444000 | 12000000 |  |  |  | 0 | 2025-04-08 | 1.2 | Out Of 11 Roads ,3 Roads Completed 8 Roads Is In Progress | 27 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12000000 | 0 | 0 | 2025-02-11 |  | 61444000 | No | No
566 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00375 |  |  | General Fund GENERAL/2025-26/009/ROAD/00375-Relaying of Road-Bituminous Road009011R0783-PONNINAGAR , 009011R0839-NEELA KANDAN STREET - GANAPATHI NAGAR , 009011R0836-PALAIYAPPAN STREET GANDHI NAGAR , 009011R0832-BALASUBRAMANI STREET , 009011R0812-JAYARMAN STREET , 009011R0888-ADHAM NAGAR MAIN ROAD NAGALKENI , 009011R0816-NAGA RATHINAM STREET - GANDHI NAGAR , 009010R0772-RAMANUJAM STREET PERIYAR NAGAR , 009011R0782-ANNA SALAI CROSS STREET , 009011R0809-KANNAGI STREET , | Roads | Bituminous Road | 13146/2025/MA3-2Dated:19/06/25Road DetailsRoad Length :2095 Mts | 2025-26 | 61444000 | 14900000 |  |  |  | 0 | 2025-04-08 | 1.49 | Out Of 10 Roads , 3 Roads Completed ,3 Roads Is In Progress | 30 | Completed | 100 |  |  |  |  | 0 |  |  |  | 14900000 | 0 | 0 | 2025-02-11 |  | 61444000 | No | No
567 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00376 |  |  | General Fund GENERAL/2025-26/009/ROAD/00376-Relaying of Road-Bituminous Road009006R0460-2ND STREET M.G.R NAGAR , 009006R0445-SINTHALAMAN KOIL STREET , 009006R0462-GOKALA STREET V O C NAGAR , 009006R0473-KANNAGI STREET V O C NAGAR , 009006R0502-DEIVANAYAGAM STREET PASUMPON NAGAR , 009007R0612-5TH CROSS STREET ANNA NAGAR , 009007R0563-KIRUPA STREET ANNA NAGAR , 009010R0771-RANGASAMY STREET THIRU NAGAR , 009012R0875-ARKESWARAR COLONY MAIN ROAD , 009012R0862-NAVAMANI 1ST STREETCENTRAL BANK COLONY , 009012R0909-PILLAIYAR KOVIL 1S | Roads | Bituminous Road | 13146/2025/MA3-2Dated:19/06/25Road DetailsRoad Length :1720 Mts | 2025-26 | 61444000 | 10600000 |  |  |  | 0 | 2025-04-08 | 1.06 | Out Of 12 Roads ,6 Roads Completed,1 Road In Progress,5 Roads To Be Started | 50 | Completed | 100 |  |  |  |  | 0 |  |  |  | 10600000 | 4 | 377.46 | 2025-02-11 |  | 61444000 | Yes | No
568 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00210 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00210-Relaying of Road-Bituminous Road009033R2142-Vedhantham Colony Main Road , 009033R2147- JAYA NAGAR 2ND MAIN ROAD , 009049R3569-RATHINAM ST , 009052R3722-KALAIMAGAL 1ST STREET , 009053R809-OIL MILL STREET , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :663 Mts | 2022-23 | 98900000 | 3129000 |  |  |  | 0.31 | 16/06/23 | 0.31 | Completed | 100 | Completed | 100 | 2023-01-11 |  | 2024-10-05 |  | 3129000 |  |  | 0 | 0 | 0.31 | 100 | 2024-12-03 |  | 98900000 | Yes | Yes
569 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00001 | Zone II | 17 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00001-Road Restoration of damaged portion over at Perumal Nagar 5th Main Road( Dhansin Street to 200 Feet Road) (007017R551) (007017R551) in Ward No.17 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 |  |  |  | 0.1 | 2022-03-01 | 0.08 |  | 0 | Completed | 100 | 17/01/22 |  | 2024-09-09 |  | 950000 |  |  |  | 0 | 0.08 | 89.16 | 2022-03-02 |  | 41050000 | Yes | Yes
570 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00013 | Zone II | 17 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00013-Road Restoration of damaged portion over at Perumal Nagar 5th Main Road( Garden Woodraff Nagar 2nd Street to Dhansin Street) (007017R551) (007017R551) in Ward No.17 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 |  |  |  | 0.1 | 2022-03-01 | 0.08 |  | 0 | Completed | 100 |  |  | 16/08/24 |  | 947539 |  |  |  | 2461.15 | 0.09 | 89.89 | 2022-03-02 |  | 41050000 | Yes | Yes
571 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00014 | Zone II | 17 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00014-Road Restoration of damaged portion over at Perumal Nagar 5th Main Road ( Perumal Nagar 3rd Main Road to Garden Woodraff Nagar 2nd Street) (007017R551) in Ward No.17 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 |  |  |  | 0.1 | 2022-03-01 | 0.08 |  | 0 | Completed | 100 | 27/04/22 |  | 2024-09-09 |  | 945500 |  |  |  | 4500 | 0.08 | 88.74 | 2022-03-02 |  | 41050000 | Yes | Yes
572 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00015 | Zone II | 17 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00015-Road Restoration of damaged portion over at Perumal Nagar 5th Main Road ( Kamatchi Nagar 1st Street to Perumal Nagar 3rd Main Road) (007017R551) in Ward No.17 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 |  |  |  | 0.1 | 2022-03-01 | 0.08 |  | 0 | Completed | 100 | 27/04/22 |  | 2024-09-09 |  | 845000 |  |  |  | 105000 | 0.08 | 79.11 | 2022-03-02 |  | 41050000 | Yes | Yes
573 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00019 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00019-Road Restoration of damaged portion over at M.K Nagar Main Road (Bharath Nagar to Swamy malai Nagar Cross Street) (007016R527) in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 | 2022-10-01 |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 88.78 | 2022-03-02 |  | 41050000 | Yes | Yes
574 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00201 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00201-Relaying of Road-Bituminous Road009019R1218-THANGAI STREET , 009019R1182-GANGA GARDEN , 009019R1163-ALAMELUMANGAPURAM 1ST MAIN ROAD , 009019R1166-ALAMELUMANGAPURAM 2ND MAIN ROAD , 009019R1165-ALAMELUMANGAPURAM 2ND CROSS STREET , 009020R1322-DURAIKANNU SALAI , 009020R1251-BIG STREET , 009020R1280-Thiruvengadamudaiyan Koil cross , 009021S0256-MAlliga Nagar Padmanaban street , 009021R1379-PERUMAL NAGAR 5TH MAIN RD , 009024R1637-GANAPATHIPURAM MAIN ROAD , 009024R1631-Bujanka Rao 1st Cross Street , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2428 Mts | 2022-23 | 98900000 | 9990000 |  |  |  | 0.9 | 19/06/23 | 1 | Out Of 19 Roads, 7 Roads Are Completed, Balance Work Is In Progress | 37 | Completed | 100 | 30/09/23 |  | 29/04/24 |  | 9883251 |  |  | 0 | 106748.81 | 0.9 | 90 | 15/03/24 |  | 98900000 | Yes | Yes
575 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00023 | Zone III | 40 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00023-Road Restoration of damaged portion over at New Colony 6th Cross Street West Side (007040R1270) in Ward No.40 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 |  |  |  | 0.1 | 2022-03-01 | 0.1 |  | 0 | Completed | 100 |  |  | 2024-09-09 |  | 950000 |  |  |  | 0 | 0.09 | 90.21 | 2022-03-02 |  | 41050000 | Yes | Yes
576 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00025 | Zone III | 40 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00025-Road Restoration of damaged portion over at New Colony 3rd Main Road (007040R1261) Office Campus in Ward No.40 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 800000 |  |  |  | 0.08 | 2022-03-01 | 0.07 |  | 0 | Completed | 100 | 13/01/22 |  | 2024-09-09 |  | 800000 |  |  |  | 0 | 0.07 | 89.19 | 2022-03-02 |  | 41050000 | Yes | Yes
577 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00026 | Zone III | 35 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00026-Road Restoration of damaged portion over at Thiruvalluvar Street South(007035R1197) in Ward No.35 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 710000 |  |  |  | 0.07 | 2022-03-01 | 0.06 |  | 0 | Completed | 100 | 23/06/22 |  | 2024-09-09 |  | 698500 |  |  |  | 11500 | 0.06 | 87.75 | 2022-03-02 |  | 41050000 | Yes | Yes
578 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00027 | Zone III | 35 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00027-Road Restoration of damaged portion over at Thiruvalluvar Street North(007035R1197) in Ward No.35 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  |  | 0.07 | 2022-03-01 | 0.06 |  | 0 | Completed | 100 | 20/06/22 |  | 2024-09-09 |  | 693500 |  |  |  | 6500 | 0.06 | 88.29 | 2022-03-02 |  | 41050000 | Yes | Yes
579 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00028 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00028-Road Restoration of damaged portion over at Shanthi Nagar 3rd Street West (007025R983) in Ward No.25 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  |  | 0.07 | 2022-03-01 | 0.06 |  | 0 | Completed | 100 | 2022-06-08 |  | 2024-09-09 |  | 700000 |  |  |  | 0 | 0.06 | 90.14 | 2022-03-02 |  | 41050000 | Yes | Yes
580 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00029 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00029-Road Restoration of damaged portion over at Shanthi Nagar 3rd Street East (007025R983) in Ward No.25 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 600000 |  |  |  | 0.06 | 2022-03-01 | 0.05 |  | 0 | Completed | 100 | 2022-06-08 |  | 2024-09-09 |  | 600000 |  |  |  | 0 | 0.05 | 90.17 | 2022-03-02 |  | 41050000 | Yes | Yes
581 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00030 | Zone II | 20 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00030-Road Restoration of damaged portion over at Vinobaji Nagar 12th Street South (007020R773) in Ward No.20 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 |  | 0 | Completed | 100 |  |  | 18/10/22 |  | 900000 |  |  |  | 0 | 0.08 | 90.22 | 2022-03-02 |  | 41050000 | Yes | Yes
582 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00031 | Zone II | 20 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00031-Road Restoration of damaged portion over at Vinobaji Nagar 12th Street North (007020R773) in Ward No.20 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.06 |  | 0 | Completed | 100 |  |  | 18/10/22 |  | 900000 |  |  |  | 0 | 0.08 | 90.22 | 2022-03-02 |  | 41050000 | Yes | Yes
583 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00378 |  |  | TURIP TURIP/2025-26/009/ROAD/00378-Relaying of Road-Bituminous Road009004R0285-VINAYAGA NAGAR 2ND MAIN ROAD , 009004R0271-LABOUR SCHOOL STREET , 009004R0316-VINAYAGA NAGAR THIRUVALLUVAR ST , 009004R0272-MAHATHMA NAGAR 1ST STREET , 009004R0273-Moorthi Nagar Main Road , 009004R0277-AYOTHIAMMAN KOIL STREET , 009004R0280-BAKTHAVACHALAM STREET , 009004R0281-BAKTHAVACHALAM 1ST STREET , 009004R0282-BAKTHAVACHALAM 2ND STREET , (Package No.II) | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2430 Mts | 2025-26 | 182896000 | 16200000 |  |  |  | 0 | 18/08/25 | 1.62 | Out Of 9 Roads ,8 Roads Completed,1 Road Work In Progress | 88 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 16200000 | 1.19 | 73.45 | 16/11/25 |  | 182896000 | No | No
584 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00379 |  |  | TURIP TURIP/2025-26/009/ROAD/00379-Relaying of Road-Bituminous Road009005R0326-KAMARAJAPURAM WEST RADHA VEETHI CROSS , 009005R0336-GANAPATHY NAGAR 3RD ST , 009005R0337-GANAPATHY NAGAR 4TH STREET , 009005R0360-THENDRAL NAGAR THIRU.VI. KA SALAI , 009005R0348-Anthoniyar Koil Street , 009008R0645-PARTHASARATHY STREET MUTHAMIZH NAGAR , 009008R0636-MADHAVI STREET , 009008R0648-PANDIAN STREET , 009008R0568-1ST CROSS STREET KRISHNA NAGAR , 009008R0620-VEERAMAMUNIVAR STREET MUTHAMIZH NAGAR , 009008R0635-2ND STREET ARANGANATHAN NAGAR | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :1285 Mts | 2025-26 | 182896000 | 9000000 |  |  |  | 0 | 14/07/25 | 0.9 | Out Of 11 Roads 10 Roads Completed 1 Road In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 9000000 | 0.63 | 70.03 | 2025-12-10 |  | 182896000 | No | Yes
585 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00081 |  |  | TURIP TURIP/2025-26/009/ROAD/00081-Relaying of Road-Bituminous Road009014R0938-SIVASANKARAN STREET , 009017R1070-SIDHIVINAYAGAR SALAI CROSS , 009017R1056-VARADHARAJAN AVENUE , 009017R1044-VEERAKUMAR SALAI , 009018R1106-TIRUVALLUVAR NAGAR 1ST STREET , 009018R1105-TIRUVALLUVAR NAGAR 2ND STREET , 009018R1104-TIRUVALLUVAR NAGAR 3RD STREET , 009018R1103-TIRUVALLUVAR NAGAR 4TH STREET , 009018R1131-GANAPATHY AVENUE , 009018R1149-GANDHI STREET , 009019R1169-GANESH NAGAR 1ST MAIN ROAD , 009019R5796-SOUNDARAJAN NAGAR 2ND STREET , 009019R12 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3461 Mts | 2025-26 | 521620000 | 22000000 |  |  |  | 1.98 | 2025-10-06 | 2.2 | Out Of 22 Roads , 18 Road Completed, 4 Roads Is In Progress | 85 | Completed | 100 |  |  |  |  | 0 |  |  |  | 22000000 | 1.98 | 90 | 2025-09-08 |  | 521620000 | No | Yes
586 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00095 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00095-Relaying of Road-Bituminous Road009032R2068-NAGARATHINAM NAGAR 2ND STREET , 009032R2071-LENIN STREET , 009049R3577-MUTHULINGAM STREET , 009049R3578-TIRUPUR KUMARAN STREET , 009051R3629-SADASIVAM ST , 009051R3640-AMBEDKAR STREET , 009051R3645-RAJAGOPAL NAGAR 2ND ST , ZONE IV-Package No.25 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1203 Mts | 2025-26 | 521620000 | 10600000 |  |  |  | 0 | 2025-10-06 | 0.87 | Out Of 7 Roads ,6 Roads Completed , 1 Roads Is In Progress | 85 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 10600000 | 0.93 | 87.62 | 2025-09-08 |  | 521620000 | No | Yes
587 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00096 |  |  | TURIP TURIP/2025-26/009/ROAD/00096-Relaying of Road-Bituminous Road009052R3675-2ND MAIN RD-LAKSHMIPURAM , 009052R3677-LAKSHMI PURAM 1ST STREET , 009052R3674-1ST MAIN ROAD LAKSHMIPURAM , 009052R3689-Vaigai nagar 1st cross , 009052R3725-MULLAI NAGAR 1ST STREET , 009052R3727-MULLAI NAGAR 3RD STREET , 009052R3728-MULLAI NAGAR 4TH STREET , 009052R3731-MULLAI NAGAR 3RD CROSS STREET , 009052R3732-SAKTHI NAGAR I STREET , 009052R3737-TNHB MIG 1ST STREET , 009052R3740-AMBAL NAGAR 2ND STREET , 009052R3760-RAJ,MOHAN NAGAR , 009053R3864-RAM | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3642 Mts | 2025-26 | 521620000 | 30600000 |  |  |  | 0 | 2025-10-06 | 2.5 | Out Of 25 Roads , 20 Roads Completed, 1 Roads Work Is In Progress,4 Roads Not Started | 80 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 30600000 | 2.07 | 67.71 | 2025-09-08 |  | 521620000 | No | No
588 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00388 |  |  | TURIP TURIP/2025-26/009/ROAD/00388-Relaying of Road-Bituminous Road009023R1578-CHOKKALINGAM STREET , 009023R1621-NATESAN NAGAR RAJAGOPALAN STREET , 009023R1622-NATESAN NAGAR , 009023R1617-BIG STREET , 009023R1582-RANGANATHAN STREET , 009023R1605-DHANALAKSHMI STREET , 009023R1623-NATESAN NAGAR 1ST STREET , 009023R1598-Murugesan Naicker Street , 009023R1625-NATESAN NAGAR 3RD STREET , 009023R1600-VEMBULIAMMAN NAGAR , 009023R1614-CHINNA STREET - A , 009023R1624-NATESAN NAGAR 2ND STREET , 009023R1612-NELLIPETTAI HIGH ROAD , 009025R169 | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :3797.2 Mts | 2025-26 | 182896000 | 18945000 |  |  |  | 0 | 2025-12-08 | 1.89 | Out Of 18 Roads,14 Roads Completed 4 Roads In Process | 80 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 18945000 | 1.11 | 58.58 | 18/11/25 |  | 182896000 | No | Yes
589 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00386 |  |  | TURIP TURIP/2025-26/009/ROAD/00386-Relaying of Road-Bituminous Road009021R1403-PALLAVA GARDEN 6TH AVENUE , 009021R1395-PALLAVA GARDEN 5TH STREET , 009021R1394-PALLAVA GARDEN 1ST STREET , 009021R1434-BHARATH NAGAR CROSS STREET , 009021R1440-BHARATH NAGAR CROSS STREET , 009021R1400-PALLAVA GARDEN 3RD AVENUE , 009021R5856-KUMARAN NAGAR , 009021S0222-AGS Nagar 1st street , 009021R1432-AGS Nagar 3rd street , 009021R1415-GARDEN WOODROFF NAGAR 4TH CROSS STREET , 009021S0220-BHARATH NAGAR 1ST CROSS STREET , 009021S0223-Swamymalai Nagar | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2611 Mts | 2025-26 | 182896000 | 14600000 |  |  |  | 1.08 | 14/07/25 | 1.46 | Work Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 14600000 | 1.08 | 73.68 | 18/10/25 |  | 182896000 | No | Yes
590 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00067 |  |  | TURIP TURIP/2024-25/009/ROAD/00067-Relaying of Road-Bituminous Road009032R2067-NAGARATHINAM NAGAR 1ST STREET , 009032R2068-NAGARATHINAM NAGAR 2ND STREET , 009033R2172-THOMAS STREET , 009033R2165-KANNAN STREET 7M BT 3M PB , 009051R3646-RAJAGOPAL NAGAR 3RD STREET , 009054R3920-Thiruvalluvar 2nd Main Road , 009054R3954-C.T.O.COLONY 4TH ST CROSS , 009054R3921-Thiruvalluvar 1st Main Road , 009060R4543-PERUMAL KOIL STREET , 009061R4626-Sambangi 1st Street , 009061R4651-DEVANESAN NAGAR 1ST STREET , 009061R4623-MALLI STREET , 009058R4354 | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :2770.05 Mts | 2024-25 | 169399000 | 19200000 |  |  |  | 1.73 | 28/02/24 | 0 | Out Of 14 Roads 13 Roads Completed Balance 1 Road Work Under Progress | 95 | Completed | 100 | 2025-07-05 |  | 2025-07-05 |  | 19134460 |  |  |  | 65540 | 1.72 | 89.83 | - |  | 169399000 | No | Yes
591 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00126 |  |  | TURIP TURIP/2023-24/009/ROAD/00126-Relaying of Road-009020R5816-Thiruveethi Amman Kovil 2nd Cross Street , 009023L0100-PILLAIYAR KOIL 1ST CROSS STREET , 009020R1242-Baskar Nagar 3rd Cross Street , 009020R1250-AMBAL NAGAR MAIN ROAD , 009020R5826-Kalaivani Main Road , 009028R1823-NEW COLONY 1ST MAIN ROAD , 009028R1833-NEW COLONY 5TH CROSS STREET , 009021R5863-VALLALAR STREET , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1798.5 Mts | 2023-24 | 313620000 | 7250000 |  |  |  | 0.73 | 19/07/23 | 0.73 | Out Of 8 Roads 2 Roads Completed 6 Roads Under Progress | 30 | Completed | 100 |  |  | 2025-03-03 |  | 7189323 |  |  |  | 60677 | 0.63 | 87.35 | 31/10/23 |  | 313620000 | Yes | Yes
592 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00129 |  |  | TURIP TURIP/2023-24/009/ROAD/00129-Relaying of Road-009053R3804-VGN MORA ST , 009053R3790-VGN AVENUE CRANBERRY STREET , 009053R3803-VGN HERCULES ST , 009053R3778-VGN AVENUE CHELSFIELD STREET , 009053R3781-VGN AVENUE HAMPTON STREET , 009053R3806-VGN PONDER ST , 009053R3792-VGN CABLE STREET , 009053R3788-VGN AVENUE MORDEN PARK STREET , 009053R3802-VGN KEMPT ST , 009053R3793-VGN BROS STREET , 009053R3785-VGN AVENUE RAMFORT STREET , 009053R3791-VGN AVENUE COSSER STREET , 009053R3780-VGN AVENUE TRUMAN 1ST STREET , 009053R3796-VGN RU | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3998 Mts | 2023-24 | 313620000 | 12200000 |  |  |  | 1.22 | 31/08/23 | 1.22 |  | 0 | Completed | 100 | 2025-11-02 |  | 2025-11-02 |  | 12170000 |  |  |  | 30000 | 1.1 | 90 | 27/05/24 |  | 313620000 | Yes | Yes
593 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00122 |  |  | TURIP TURIP/2023-24/009/ROAD/00122-Relaying of Road-009004R0262-L.I.C. COLONY NEELAMEGAM STREET , 009004R0281-BAKTHAVACHALAM 1ST STREET , 009004R0285-VINAYAGA NAGAR 2ND MAIN ROAD , 009004R0290-THIRUNEERMALAI ROAD 1ST STREET , 009004R0294-ANNAI MARY 1ST STREET , 009004R0295-ANNAI MARY 2ND STREET , 009004R0296-ANNAI MARY 3RD STREET , 009004R0299-VINAYAGA NAGAR MAIN ROAD , 009004R0303-VINAYAGA NAGAR 3RD STREET , 009004R0307-VINAYAGA NAGAR 6TH STREET , 009004R0317-AMARESAN NAGAR 1ST STREET , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2395 Mts | 2023-24 | 313620000 | 8500000 |  |  |  | 1.4 | 19/07/23 | 0.85 | Work Completed. | 100 | Completed | 100 |  |  | 26/02/25 |  | 0 |  |  | 0 | 8500000 | 0.76 | 89.13 | 14/04/24 |  | 313620000 | No | Yes
594 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00209 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00209-Relaying of Road-007/2021/026/R/0000251-KATTABOMMAN STREET , 007/2021/026/R/0000261-KATTABOMMAN CROSS STREET , 007/2021/029/R/0000308-PURUSOTHAMAN NAGAR 2ND MAIN ROAD , 007/2021/029/R/0000801-BASHIYAM NAGAR 2ND STREET , 009/03/036/R/0013-DEVARAJAN STREET , 009/025/R/0014-KALAIMAGAL STREET , 007/2021/031/R/0000938-KRISHNAMACHARI STREET , 007/2021/033/R/000094-GAJALAKSHMI NAGAR MAIN ROAD , 007/2021/034/R/0000755-DEEKSHITHAR NAGAR (RAMASAMY STREET) , 007/2021/035/R/0000453-AGANANOORU STREET , 007/ | Roads | Bituminous Road | Go.(Ms)No.2Dated:07/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.03 | 2021-11-08 | 1.83 |  | 0 | Completed | 100 |  |  | 2023-02-02 |  | 0 |  |  |  | 20000000 | 0 | 0 | 2022-11-02 |  | 100000000 | No | Yes
595 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00131 |  |  | TURIP TURIP/2023-24/009/ROAD/00131-Relaying of Road-009045R3351-DHANALAKSHMI NAGAR MAIN ROAD , 009045R3335-ANNAI NAGAR 2ND MAIN ROAD , 009062R4760-OLD G.S.T ROAD , 009062R4777-ARUL NAGAR IAF GATE STREET , 009048R3515-KAMBAR STREET (BHARATHMADHA STREET TO BHARATHWAJAR STREET) , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1708 Mts | 2023-24 | 313620000 | 9300000 |  |  |  | 0.93 | 18/07/23 | 0.9 |  | 0 | Completed | 100 |  |  | 26/02/25 |  | 0 |  |  |  | 9300000 | 0.92 | 98.53 | 23/10/23 |  | 313620000 | Yes | Yes
596 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00282 |  |  | General Fund GENERAL/2025-26/009/ROAD/00282-Relaying of Road-Bituminous Road- , | Roads | Bituminous Road | 909-2 / 2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 8600000 | 8600000 |  |  |  | 0 | 13/01/26 | 0.86 |  | 0 | Completed | 100 |  |  | 2026-06-03 |  | 8377000 |  |  | 0 | 223000 | 0 | 0 | 13/04/26 |  | 8600000 | No | Yes
597 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00229 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00229-Repair /Maintenance-009/2021/036/R/0001092-MUTHURANGAM ROAD , 009/2021/006/R/0000903-RANGANATHAPURAM 4TH STREET , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 900000 | 0 |  |  | 0.09 | 31/12/21 | 0.09 |  | 0 | Completed | 100 |  |  | 22/09/22 |  | 611916 |  |  |  | 288084 | 0.06 | 67.99 | 2022-06-02 |  | 39126000 | Yes | Yes
598 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00230 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00230-Repair /Maintenance-009/2021/035/R/0001089-ABDUL RAJAK STREET , 009/2021/035/R/0000758-SHANMUGAM ROAD , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 950000 |  |  |  | 0.1 | 31/12/21 | 0.1 |  | 0 | Completed | 100 |  |  | 21/09/22 |  | 950000 |  |  |  | 0 | 0.05 | 57.03 | 2022-06-02 |  | 39126000 | No | Yes
599 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00231 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00231-Repair /Maintenance-009/2021/001/R/0000768-BURMA COLONY 4TH STREET , 009/2021/001/R/0000806-KK PALAYAM BAJANAI KOIL STREET , 009/2021/001/R/0000804-KK PALAYAM GANGAIAMMAN KOIL STREET , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 550000 |  |  |  | 0.06 | 31/12/21 | 0.06 |  | 0 | Completed | 100 |  |  | 22/09/22 |  | 522527 |  |  |  | 27473 | 0.05 | 95 | 2022-06-02 |  | 39126000 | Yes | Yes
600 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00232 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00232-Repair /Maintenance-009/2021/001/R/0000769-BURMA COLONY 5TH STREET , 009/2021/029/R/0000970-PILLAIYAR KOIL STREET , 021/2021/016/R/0000616-GANDHI NAGAR EXTN 2ND STREET , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 422000 |  |  |  | 0.04 | 2022-03-01 | 0.04 |  | 0 | Completed | 100 |  |  | 22/09/22 |  | 422900 |  |  |  | -900 | 0.04 | 100.21 | 2022-06-02 |  | 39126000 | Yes | Yes
601 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00233 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00233-Repair /Maintenance-009/2021/030/R/0001374-KALYAN NAGAR MAIN ROAD , 009/2021/028/R/0000943-PERUMAL KOIL STREET , 009/2021/028/R/0001348-T.T.K. NAGAR 1ST MAIN ROAD , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 979000 |  |  |  | 0.1 | 2022-03-01 | 0.1 |  | 0 | Completed | 100 |  |  | 24/09/22 |  | 977679 |  |  |  | 1321 | 0.1 | 99.87 | 2022-06-02 |  | 39126000 | Yes | Yes
602 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00234 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00234-Repair /Maintenance-009/2021/032/R/0000659-C.T.O.COLONY MAIN ROAD , 009/2021/032/R/0001065-CHOLAN STREET , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 944000 |  |  |  | 0.09 | 31/12/21 | 0.08 |  | 0 | Completed | 100 |  |  | 24/09/22 |  | 943613 |  |  |  | 387 | 0.09 | 99.96 | 2022-06-02 |  | 39126000 | Yes | Yes
603 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00235 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00235-Repair /Maintenance-009/2021/001/R/0000760-BURMA COLONY 1ST CROSS STREET , 009/2021/001/R/0000761-BURMA COLONY 2ND CROSS STREET , 009/2021/001/R/0000762-BURMA COLONY 3RD CROSS STREET , 009/2021/001/R/0000763-BURMA COLONY 4TH CROSS STREET , 009/2021/001/R/0001453-BURMA COLONY 5TH CROSS STREET , 009/2021/001/R/0000764-BURMA COLONY 6TH CROSS STREET , | Roads | Cement Concrete Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 420000 | 0 | 0 |  | 0.04 | 31/12/21 | 0.04 |  | 0 | Completed | 100 |  |  | 24/09/22 |  | 419098 |  |  |  | 902 | 0.04 | 99.79 | 2022-06-02 |  | 39126000 | Yes | Yes
604 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00063 | Zone I | 7 | General Fund GENERAL/2025-26/009/ROAD/00063- Providing and Laying Cement concrete Road at Muthusamy Street in Ward 7 zone 1 TCMC | Roads | Cement Concrete Road | 390-2Dated:29/08/25Road DetailsRoad Length :Mts | 2025-26 | 1750000 | 1750000 |  |  |  | 0 | 22/09/25 | 0.18 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1750000 | 0 | 0 | 26/10/25 |  | 1750000 | No | No
605 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00067 | Zone I | 12 | General Fund GENERAL/2025-26/009/ROAD/00067-Providing and Laying Cement concrete Road at Prasanthi nagar Bharathiyar Street in Ward 12 zone 1 TCMC | Roads | Cement Concrete Road | 390-3Dated:29/08/25Road DetailsRoad Length :Mts | 2025-26 | 2800000 | 2800000 |  |  |  | 0 | 2025-05-11 | 0.28 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2800000 | 0 | 0 | 2026-09-01 |  | 2800000 | No | No
606 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00356 | Zone I |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00356-Relaying of Road-Bituminous Road009007R0517-6TH MAIN ROAD 1ST LANE , 009007R0521-BENJAMIN STREET H L COLONY , 009007R0510-VADIVEL STREET H L COLONY , 009007R0555-KALAINGER ROAD ANNA NAGAR , 009007R0590-KARUPPAN STREET H L COLONY , 009007R0630-A K DURAI STREET MUTHAMIZH NAGAR , 009007R0602-ANNAI VELANKANNI STREET I LE COLONY , 009007R0532-6TH CROSS STREET ANNA NAGAR , (Package No.II) Zone I | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :1360 Mts | 2025-26 | 85700000 | 9000000 |  |  |  | 0 | 14/07/25 | 0.9 | Out Of 8 Roads 6 Roads Completed, 2 Roads To Be Started | 75 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9000000 | 0.62 | 69.14 | 2025-12-10 |  | 85700000 | No | Yes
607 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00332 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00332-Relaying of Road-Cement Concrete Road009047R3484-IYAPPAN STREET , 009047R3491-ANNAI SATHYA STREET , 009046R6029-Kandasamy Colony 1st Cross Street , 009046R6030-Kandasamy Colony 2nd Cross Street , 009048R3528-GOWTHAMAR STREET , 009048S0449-KAMBAR CROSS STREET , 009062R4706-MAHALAKSHMI STREET , 009062R4707-MAHALAKSHMI 1ST CROSS ST , 009062R4708-MAHALAKSHMI 2ND CROSS ST , 009062R4709-MAHALAKSHMI 3RD CROSS ST , 009062R4694-CHELLIYAMMAN KOIL MAIN STREET , 009062R4695-CHELLIAMMAN KOIL ST-IST ST , 009 | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2549 Mts | 2025-26 | 237450000 | 12400000 |  |  |  | 0 | 2025-06-06 | 1.24 | Out Of 24 Roads 21 Roads Completed 3Roads Is In Progress | 87 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12400000 | 0 | 0 | 2025-05-08 |  | 237450000 | No | Yes
608 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00171 | Zone IV |  | TURIP TURIP/2024-25/009/ROAD/00171-Relaying of Road-Cement Concrete Road009055R4011-Samatthu Periyar Nagar Main Road , ZONE IV- PACKAGE NO.XIII | Roads | Cement Concrete Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :1040 Mts | 2024-25 | 197393000 | 10300000 |  |  |  | 0 | 26/09/24 | 0 |  | 0 | Completed | 100 | 2025-07-05 |  | 2025-07-05 |  | 10297846 |  |  |  | 2154 | 0.93 | 89.98 | - |  | 197393000 | No | Yes
609 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00207 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00207-Relaying of Road-007/2021/014/R/0000343-AMBAL NAGAR 14TH STREET , 007/2021/014/S/0001306-AMBAL NAGAR 15TH STREET , 007/2021/014/R/0000344-AMBAL NAGAR 16TH STREET , 007/2021/014/R/0000342-AMBAL NAGAR 17TH STREET , 007/2021/014/R/0000765-PILLAIYAR KOIL STREET , 007/2021/024/R/0001044-STATION BORDER ROAD , 007/2021/024/S/0001043-SANJAI GANDHI NAGAR 2ND STREET , | Roads | Bituminous Road | Go.(Ms)No.2Dated:07/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 0.54 | 2021-11-08 | 1.84 | Out Of 8 Roads, Completed -7 And Dropped-1. | 100 | Completed | 100 |  |  | 2022-07-11 |  | 16385867 |  |  |  | 3614132.58 | 1.47 | 73.53 | 2022-11-02 |  | 100000000 | Yes | Yes
610 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00110 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00110-Relaying of Road-Cement Concrete Road009057R4304-ANNA STREET , 009057R4285-KAVERY STREET , 009060R4587-DHARMATHOTTAM , 009060R4577-THANTHAI PERIAR 2ND STREET , 009060R4581-THIRUVALLUVARPURAM 1ST STREET , 009060R4607-PATEL NAGAR 1ST ST LANE , 009060R4610-1ST STREET DEIVANAGAR , 009060R4611-2ND STREET DEIVA NAGAR , 009060R4612-3RD STREET DEIVA NAGAR , 009060R4602-KALYAN NAGAR MAIN ROAD , 009060R4586-PILLAIYAR KOIL STREET , 009060R4601-KALYAN NAGAR 4TH CROSS STREET , ZONE IV-Package No..35 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1278 Mts | 2025-26 | 521620000 | 8150000 |  |  |  | 0.73 | 2025-10-06 | 0.67 | Out Of 13 Roads, 12 Roads Completed 1 Roads Works Is In Progress | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 8150000 | 0.66 | 80.82 | 2025-09-08 |  | 521620000 | No | Yes
611 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00184 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00184-Relaying of Road-009001R0069-VINOBA NAGAR 4TH STREET , 009001R0033-KARUNANITHI NAGAR IIND STREET , 009001R0034-KARUNANITHI NAGAR 1ST LANE , 009003R0204-VIJAYALAKSHMI PANDIT STREET , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :670 Mts | 2023-24 | 319260000 | 1930000 |  |  |  | 0.17 | 2023-05-08 | 0.19 | Out Of 4 Roads 3 Roads Completed, Balance 1 Road Under Ugss Work. | 80 | Completed | 100 |  |  | 2024-12-04 |  | 1904388 |  |  |  | 25612 | 0.07 | 35.56 | - |  | 319260000 | No | Yes
612 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2023-24/009/ROAD/00256 | Zone III | 41 | General Fund GENERAL/2023-24/009/ROAD/00256-Providing CC Pavement To Durga Colony 1st And 2nd Street In Ward No.41 in Zone III | Roads | Cement Concrete Road | 497Dated:29/09/23Road DetailsRoad Length :Mts | 2023-24 | 1450000 | 1450000 |  |  |  | 0 | 18/07/25 | 0.14 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1450000 | 0 | 0 | 25/10/25 |  | 1450000 | No | Yes
613 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00123 | Zone III | 43 | General Fund GENERAL/2025-26/009/ROAD/00123-Providing and Laying Paver Block Road to Babu 1st Cross St Ward NO.43 in Zone III | Roads | Paver Block Road | 221-2Dated:28/04/25Road DetailsRoad Length :Mts | 2025-26 | 540000 | 540000 |  |  |  | 0 | 14/07/25 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 540000 | 0 | 0 | 21/07/28 |  | 540000 | No | Yes
614 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00112 | Zone III |  | General Fund GENERAL/2024-25/009/ROAD/00112-Providing and Laying Paver Block Road To Kanagaraj Cross Street in War No.42 in Zone-III | Roads | Paver Block Road | 75-1Dated:05/03/25Road DetailsRoad Length :Mts | 2024-25 | 590000 | 590000 |  |  |  | 0 | 14/07/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 590000 | 0 | 0 | 21/10/25 |  | 590000 | No | Yes
615 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00113 | Zone III | 41 | General Fund GENERAL/2025-26/009/ROAD/00113-Providing And Laying Paver Block Road to Masuthi Colony 2nd St And 3rd Cross Street in Ward No.41. in ZoneIII | Roads | Paver Block Road | 221-1Dated:28/04/25Road DetailsRoad Length :Mts | 2025-26 | 990000 | 990000 |  |  |  | 0 | 14/07/25 | 0.1 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | 21/10/25 |  | 990000 | No | Yes
616 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00093 | Zone III | 42 | General Fund GENERAL/2025-26/009/ROAD/00093-Relaying of Road-Paver Block Road-Sathiya sai Nagar 3rd Cross street Extn in Ward-42 Zone III | Roads | Paver Block Road | 221Dated:28/04/25Road DetailsRoad Length :Mts | 2025-26 | 800000 | 800000 |  |  |  | 0 | 14/07/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 800000 | 0 | 0 | 21/10/25 |  | 800000 | No | Yes
617 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00098 | Zone III | 36 | General Fund GENERAL/2025-26/009/ROAD/00098-Providing and Laying Paver Block Road to Kamala street in Ward NO.36 in Zone III | Roads | Paver Block Road | 471-1Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 710000 | 710000 |  |  |  | 0 | 18/07/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 710000 | 0 | 0 | 25/10/25 |  | 710000 | No | Yes
618 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00257 | Zone 03 |  | General Fund GENERAL/2025-26/009/WS/00257-Providing Deep borewell With Power Pump at ASK Nagar Sump 1LL In Zone-03 | Water Supply | Borewell | 471-6Dated:20/06/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 16/07/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1000000 | 0 | 0 | 21/10/25 |  | 1000000 | No | Yes
619 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00008 | Zone III | 25 | MLA Fund MLA/2023-24/009/WS/00008-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at ward No.25, zone III | Water Supply | Borewell | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 20/02/24 | 0.09 | Work Under Progress | 0 | Completed | 100 |  |  | 30/03/25 |  | 0 |  |  |  | 970000 | 0 | 0 | 20/05/24 |  | 5820000 | No | Yes
620 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00279 | Zone II | 7, 15 | 15th CFC 15th CFC/2020-21/009/WS/00279-Ward No.7 Providing deep borewell with power pump at Koushik Avenue street, Sha Avenue and ward no.15 Kamarajapuram Main road-Emmanuel street | Water Supply | Borewell | 7979/2020/LA3 SEM -1Dated:30/06/21 | 2020-21 | 1000000 | 1000000 | 0 |  |  | 0.1 | 2021-12-08 | 0.1 | Completed | 100 | Completed | 100 |  |  | 14/09/21 |  | 999002 |  |  |  | 998 | Excel0.10 | 99.9 | 2021-10-11 |  | 1000000 | Yes | Yes
621 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00280 |  |  | 15th CFC 15th CFC/2020-21/009/WS/00280-Providing deep borewell with power pump at Sangothiamman Koil street and Durga Colony 1st street | Water Supply | Borewell | 7979/2020/LA3 SEM -2Dated:30/06/21 | 2020-21 | 700000 | 700000 | 0 |  |  | 0.07 | 2021-12-08 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2021-03-11 |  | 664402 |  |  |  | 35598 | Excel0.07 | 94.91 | 2021-10-11 |  | 700000 | No | Yes
622 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00014 | Zone II | 17 | MLA Fund MLA/2023-24/009/WS/00014-Providing Borewell with Minipower pump at ward No.17, zone II | Water Supply | Borewell | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 280000 |  | 0 | 0 | 0.03 | 29/12/23 | 0.03 | Drilling Of Bore Well Completed,tank Stage Work Progress | 75 | Completed | 100 |  |  | 2024-09-09 |  | 280000 |  |  |  | 0 | 0.03 | 100 | 29/03/24 |  | 8230000 | Yes | Yes
623 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00012 | Zone II | 21 | MLA Fund MLA/2023-24/009/WS/00012-Providing Borewell with Minipower pump(3location) at ward No.21, Zone II | Water Supply | Borewell | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 840000 |  |  |  | 0.08 | 29/12/23 | 0.08 | Drilling Of Bore Well Completed, Tank Stage Plastering Work Progress | 60 | Completed | 100 |  |  | 2024-09-09 |  | 840000 |  |  |  | 0 | 0.08 | 100 | 29/03/24 |  | 8230000 | Yes | Yes
624 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00422 | Zone II | 9 | MLA Fund MLA Fund/2021-22/009/WS/00422-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.9 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 845000 |  |  |  | 0.08 | 25/05/22 | 0.08 | 2 Nos Mini Oht Completed,1 Nos Pipe Line Work Progress | 75 | Completed | 100 |  |  | 2024-09-09 |  | 831000 |  |  |  | 14000 | 0.08 | 88.76 | 25/07/22 |  | 14858000 | Yes | Yes
625 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00012 | Zone II |  | General Fund GENERAL/2024-25/009/WS/00012-Providing deep borewell and construction of mini over head tank Dr.soloman street in wd 14 in zone-2 | Water Supply | Borewell | 20-5/19-03-2025Dated:19/03/25 | 2024-25 | 300000 | 300000 |  |  |  | 0 | 25/04/25 | 0.03 |  | 0 | Completed | 100 |  |  | 27/11/25 |  | 290029 |  |  |  | 9971 | 0 | 0 | 25/06/25 |  | 300000 | No | Yes
626 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00311 | Zone IV | 60 | MLA Fund MLA Fund/2021-22/009/WS/00311-Providing borewell with minipower pump at Thiruvallurvar 1st, 3rd street,Mangalapuram 1st street, Pillaiyar kovil street,Dhamathottam 1st street in ward no.60 | Water Supply | Borewell | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 1021000 |  |  |  | 0.1 | 2022-08-06 | 0.1 | Work Completed | 100 | Completed | 100 |  |  | 2023-12-05 |  | 1012130 |  |  |  | 8870 | 0.1 | 99.13 | 2022-09-09 |  | 5038000 | Yes | Yes
627 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00466 | Zone II | 9 | MLA Fund MLA Fund/2022-23/009/WS/00466-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.09 | Water Supply | Borewell | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 560000 |  | 0 |  | 0.06 | 25/11/22 | 0.05 | Geological Survey Completed | 5 | Completed | 100 |  |  | 2023-07-07 |  | 0 |  |  |  | 560000 | 0.05 | 89.16 | 23/02/23 |  | 6280000 | Yes | Yes
628 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00467 | Zone II | 13 | MLA Fund MLA Fund/2022-23/009/WS/00467-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.13 | Water Supply | Borewell | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 280000 |  |  |  | 0.03 | 25/11/22 | 0.02 | Geological Survey Completed | 5 | Completed | 100 |  |  | 2023-12-06 |  | 280000 |  |  |  | 0 | 0.02 | 88.11 | 23/02/23 |  | 6280000 | Yes | Yes
629 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00427 | Zone II | 16 | MLA Fund MLA Fund/2021-22/009/WS/00427-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.16 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 845000 |  |  |  | 0.07 | 25/05/22 | 0.07 | Work Under Progress | 50 | Completed | 100 | 26/09/22 |  | 2024-09-09 |  | 825000 |  |  |  | 20000 | 0.07 | 88.17 | 25/07/22 |  | 14858000 | Yes | Yes
630 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00428 | Zone II | 17 | MLA Fund MLA Fund/2021-22/009/WS/00428-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.17 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 845000 |  |  |  | 0.08 | 25/05/22 | 0.07 | Bore Drilling Work Completed | 45 | Completed | 100 |  |  | 2024-09-09 |  | 844500 |  |  |  | 500 | 0.08 | 90.24 | 25/07/22 |  | 14858000 | Yes | Yes
631 | Tambaram | WATER SUPPLY IMPROVEMENT SCHEME | CHENGALPATTU | WATER SUPP/2014-15/009/WS/00117 |  |  | WATER SUPPLY IMPROVEMENT SCHEME WATER SUPP/2014-15/009/WS/00117-Providing New Water Supply Improvement Scheme in Anakaputhur | Water Supply | Water Supply Improvement Works | G.O MS. No. 162 Municipal Administration and water supply departmentDated:19/12/14 | 2014-15 | 187800000 | 180800000 |  |  |  | 17.68 | 2016-01-03 | 18.41 | Execution By Cmwssb 1. Oht 2 Nos. Completed, Out Of 2 Nos. (Each 17.00 Ll) 2.Conveying Main 0.115 Km Completed Out Of 0.115 Km 3. Feeder Main 0.580 Km Completed Out Of 0.580Km 4.Hsc 5186 Nos Completed Out Of 5206 Nos 5. Electrical Work Completed 6.Trial Run Under Progress | 98.85 | Completed | 100 |  |  |  |  | 0 |  |  |  | 180800000 | 17.68 | 97.8 | 2018-01-03 | Date of completion 28.2.2023 | 187800000 | No | Yes
632 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/WS/00182 | Zone IV | 33 | MLA Fund MLA/2024-25/009/WS/00182-Providing and Drilling of borewell with Mini power motor pump with Syntex tank in Dhamodharan Nagar in ward No. 33 Zone IV in Tambaram City Municipality | Water Supply | Borewell | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 280000 |  |  |  | 0 | 2024-05-11 | 0.03 | Physical Surveying Is In Progress | 1 | Completed | 100 |  |  |  |  | 0 |  |  |  | 280000 | 0 | 0 | 2024-07-12 |  | 9650000 | No | Yes
633 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00242 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00242-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 700000 | 0 |  |  | 0 | 2022-03-01 | 0.07 |  | 0 | Completed | 100 |  |  | 16/09/24 |  | 699000 |  |  |  | 1000 | 0 | 0 | 2022-05-04 |  | 39126000 | No | Yes
634 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2022-23/009/WS/00195 | Zone V | 67 | General Fund GENERAL/2022-23/009/WS/00195-CONSTRUCTION OF 2.00LL SR16 M STAGING OHT (BALANCE WORK)AT ARAVIND NAGAR WARD-67 ZONE 5 IN TAMBARAM CITY MUNICIPAL CORPORATION | Water Supply | Water Supply Improvement Works | 911Dated:30/12/22 | 2022-23 | 1100000 | 1100000 |  |  |  | 0 | 2023-06-03 | 0.11 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1100000 | 0 | 0 | - |  | 1100000 | No | No
635 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00040 | Zone IV | 52, 54 | 15th CFC 15thCFC/2022-23/009/WS/00040-Providing DI Pipe line (755m 150mm dia DI K7) for Pumping main from CTO Colony sump to Thiruneermalai road OHT sump, ward no52,54 ,zone iv in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 2200000 |  |  |  | 0.22 | 21/04/23 | 0 | Work Order Issued On 31.01.2023 | 0 | Completed | 100 |  |  | 17/09/24 |  | 2200000 |  |  |  | 0 | 0.22 | 100 | - |  | 28650000 | Yes | Yes
636 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00041 | Zone III | 37 | 15th CFC 15thCFC/2022-23/009/WS/00041-Extension of pipe line (365m, 150mm dia DI K7) (feeder Main) from Nethaji Nagar OHT to hastinapuram area (Rajendraprasath Salai) upto BBR Nagar, zone III ward No.37 in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 1100000 |  |  |  | 0.11 | 21/04/23 | 0.11 | Work Completed | 100 | Completed | 100 |  |  | 2024-10-05 |  | 1100000 |  |  |  | 0 | 0.11 | 100 | 21/07/23 |  | 28650000 | Yes | Yes
637 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00041 | Zone III | 22 | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00041-Construction of Lifting stations at Kannammal Nagar, Om sakthi Nagar in ward No.22 Zone III | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 5800000 |  |  |  | 0 | 2024-12-12 | 0.58 | Nearly Completed | 98 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5800000 | 0 | 0 | 2025-08-09 |  | 48950000 | No | Yes
638 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SL/00041 | Zone V | 65, 66, 67, 68, 69, 70 | General Fund GENERAL/2025-26/009/SL/00041- Supply and Fixing of New LED Light in Zone 5 Ward No.65,66,67,68,69&70 Tambaram City Municipal Corporation | Streetlight | StreetLight | 641Dated:30/12/24 | 2025-26 | 4800000 | 4800000 |  |  |  | 0 | 16/07/25 | 0.48 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4800000 | 0 | 0 | 24/09/25 |  | 4800000 | No | No
639 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/OTHERS/00276 | Zone I | 12 | MLA Fund MLA/2023-24/009/OTHERS/00276-Providing CC TV camera at ward No.12, Zone I in Tambaram Corporation | Others | CCTV Installation | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 600000 |  |  |  | 0 | 18/11/23 | 0 | Work Completed | 100 | Completed | 100 |  |  | 2024-11-05 |  | 0 |  |  |  | 600000 | 0 | 0 | - |  | 7430000 | No | Yes
640 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00274 | Zone I |  | General Fund GENERAL/2025-26/009/OTHERS/00274-Initiative for Robatic LAb to Develop expert curriculum for teachers and Students Padasalai Middle Sch0ol at Thiruneermalai Zone-1 TCMC | Others | Robotics | 628/2025-26Dated:25/08/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 2025-02-09 | 0.15 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1500000 | 0 | 0 | - |  | 1500000 | No | No
641 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00036 | Zone IV | 32 | 15th CFC 15thCFC/2022-23/009/WS/00036-Construction of 1.00 LL capacity 7.50m staging height Overhead Tank at Kadaperi Bajanai Koil street west Tambaram, ward no. 32, zone IV in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 2000000 |  |  |  | 0.2 | 2023-05-05 | 0.17 | Completed | 100 | Completed | 100 | 2025-03-03 |  | 2025-03-03 |  | 1999925 |  |  |  | 75 | 0.09 | 42.5 | 2023-05-11 |  | 28650000 | No | Yes
642 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00034 | Zone IV | 56 | 15th CFC 15thCFC/2022-23/009/WS/00034-Construction of 2.00 LL SR 16 m staging at Perugalathur, Zone No. 4 , ward No.56 in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 5000000 |  |  |  | 0.5 | 21/04/23 | 0.41 | Pipe Line Connection And Finishing Work Is In Progress | 0 | Completed | 100 | 27/01/25 |  | 27/01/25 |  | 4999774 |  |  |  | 226 | 0.38 | 76.16 | 21/07/23 |  | 28650000 | No | Yes
643 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/PARK/00122 | Zone II | 24 | General Fund GENERAL/2024-25/009/PARK/00122-Providing park & play field at suguna Colony in ward no-24 Zone II, TCMC | Parks | Play Ground | 469-8/2024-25Dated:07/10/24 | 2024-25 | 2500000 | 2500000 |  |  |  | 0 | 2024-08-11 | 0.25 | Completed | 100 | Earth Work | 100 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 2025-08-02 |  | 2500000 | No | Yes
644 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/PARK/00029 | Zone IV | 49 | MLA Fund MLA/2024-25/009/PARK/00029-Supply of Gym Equipment in ward No.49, Muthurangam Park Badminton court at Tambaram Corporation ,Zone IV | Parks | Play Ground | 1694/2024/A3-2Dated:06/01/25 | 2024-25 | 7290000 | 2000000 |  |  |  | 0 | 18/02/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2000000 | 0 | 0 | 18/05/25 |  | 7290000 | No | Yes
645 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/PARK/00315 | Zone IV | 33 | MLA Fund MLA Fund/2021-22/009/PARK/00315-Providing Children play materials to AmarNagar park in ward No.33 | Parks | Play Ground | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 345000 |  |  |  | 0 | 2022-08-06 | 0.03 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 314000 |  |  |  | 31000 | 0 | 0 | 2022-08-07 |  | 5038000 | No | Yes
646 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00205 | Zone I | 29 | MLA Fund MLA/2024-25/009/OTHERS/00205-Providing CCTV at ward No. 29 in Zone I in Tambaram City Municipal Corporation | Others | CCTV Installation | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 600000 |  |  |  | 0 | 31/01/25 | 0 |  | 0 | Work Completed | 100 |  |  | 2025-07-04 |  | 599974 |  |  |  | 26 | 0 | 0 | - |  | 16540000 | No | Yes
647 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00034 | Zone I | 11 | MP Fund MP/2023-24/009/SL/00034-Providing 1nos Mini Highmast Light at ward No.11, Adam Nagar Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Work Fully Completed | 0 | Work Completed | 100 |  |  | 21/03/24 |  | 403922 |  |  |  | 16078 | 0 | 0 | - |  | 11435000 | No | Yes
648 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00447 | Zone V | 46 | MP Fund MP/2024-25/009/SL/00447-Providing 1nos Mini High mast light at Ward No.46 Thangalkarai in Tambaram Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 450000 |  |  |  | 0 | 2025-09-05 | 0.05 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 450000 | 0 | 0 | 14/06/25 |  | 4400000 | No | Yes
649 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00429 | Zone II | 9 | MP Fund MP/2025-26/009/SL/00429-Providing 1no Mini High mast light at ward No.09, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/08/25 |  | 4400000 | No | Yes
650 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00430 | Zone II | 14 | MP Fund MP/2025-26/009/SL/00430-Providing 1no Mini High mast light at ward No.14, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/08/25 |  | 4400000 | No | Yes
651 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00431 | Zone II | 15 | MP Fund MP/2025-26/009/SL/00431-Providing 1no Mini High mast light at ward No.15, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/08/25 |  | 4400000 | No | Yes
652 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00432 | Zone II | 16 | MP Fund MP/2025-26/009/SL/00432-Providing 1no Mini High mast light at ward No.16, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/10/25 |  | 4400000 | No | Yes
653 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00433 | Zone II | 17 | MP Fund MP/2025-26/009/SL/00433-Providing 1no Mini High mast light at ward No.17, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/08/25 |  | 4400000 | No | Yes
654 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00434 | Zone II | 24 | MP Fund MP/2025-26/009/SL/00434-Providing 1no Mini High mast light at ward No.24, zone 2 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 25/06/25 | 0.04 |  | 0 | Completed | 100 |  |  | 2025-07-08 |  | 398120 |  |  |  | 1880 | 0 | 0 | 30/08/25 |  | 4400000 | No | Yes
655 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00435 | Zone III | 23 | MP Fund MP/2025-26/009/SL/00435-Providing 1no Mini High mast light at ward No.23, zone 3 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 14/07/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | 21/09/25 |  | 4400000 | No | Yes
656 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00436 | Zone III | 25 | MP Fund MP/2025-26/009/SL/00436-Providing 1no Mini High mast light at ward No.25, zone 3 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 14/07/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | 21/09/25 |  | 4400000 | No | Yes
657 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00437 | Zone III | 37 | MP Fund MP/2025-26/009/SL/00437-Providing 1no Mini High mast light at ward No.37, zone 3 Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 14/07/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | 21/09/25 |  | 4400000 | No | Yes
658 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00438 | Zone III | 42 | MP Fund MP/2025-26/009/SL/00438-Providing 1no Mini High mast light at ward No.42, sathiyasyan nagar, near Pillaiyar kovil street zone 3 sembakkam Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 14/07/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | 21/09/25 |  | 4400000 | No | Yes
659 | Tambaram | MP Fund | CHENGALPATTU | MP/2025-26/009/SL/00439 | Zone III | 42 | MP Fund MP/2025-26/009/SL/00439-Providing 1no Mini High mast light at ward No.42, Maruthi Nagar main road near sub register office zone 3 sembakkam Tambaram City Municipal Corporation | Streetlight | StreetLight | 1237/2025/a3Dated:20/05/25 | 2025-26 | 4400000 | 400000 |  |  |  | 0 | 14/07/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | 21/09/25 |  | 4400000 | No | Yes
660 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00040 |  |  | General Fund GENERAL/2025-26/009/WS/00040-Supply and Delivery of 25 HP Pump Motor and Panal board and Starter at Ambedkar Nagar Sewerage Pumping station at Zon 5 East Tambaram Area Tambaram City Municipal Corporartion | Water Supply | Motor PumpSet | 613Dated:25/08/25 | 2025-26 | 1300000 | 1300000 |  |  |  | 0 | 22/09/25 | 0.13 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | 30/11/25 |  | 1300000 | No | No
661 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00250 | Zone V | 66 | General Fund GENERAL/2024-25/009/WS/00250-PROVIDING OF DEEP BORE WELL WITH MINI POWER PUMP AT WARD NO 66 IN TAMBARAM CITY MUNICIPAL CORPORATION | Water Supply | Motor PumpSet | 617Dated:25/08/25 | 2024-25 | 350000 | 350000 |  |  |  | 0 | 22/09/25 | 0.04 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 350000 | 0 | 0 | 29/11/25 |  | 350000 | No | No
662 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00262 | Zone V | 66 | General Fund GENERAL/2025-26/009/WS/00262-Providing of Deep Bore Well with Mini Power Pump at ward no 66 in Tambaram City Municipal Corporation Zone 5 | Water Supply | Motor PumpSet | 617-2Dated:25/08/25 | 2025-26 | 350000 | 350000 |  |  |  | 0 | 22/09/25 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 350000 | 0 | 0 | 29/12/25 |  | 350000 | No | No
663 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00148 | Zone V | 65 | General Fund GENERAL/2025-26/009/WS/00148-Providing Deep Bore Well with Power pump at Ambedhkar Street Christain Burial Ground Ward 65 Zone 5 in Tambaram City Municipal Corporation | Water Supply | Motor PumpSet | 417-1Dated:04/04/25 | 2025-26 | 250000 | 250000 |  |  |  | 0 | 2025-09-05 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 250000 | 0 | 0 | 16/07/25 |  | 250000 | No | No
664 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00050 | Zone IV | 33 | MLA Fund MLA/2023-24/009/WSIS/00050-Providing RO plant to Kamakshi Nagar in ward No.33 in Tambaram Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3041/2023/A3-8Dated:08/01/24 | 2023-24 | 4570000 | 700000 |  |  |  | 0.07 | 2024-05-02 | 0.06 | Machinery Plant Installation Work Is In Progress | 15 | Completed | 100 | 26/02/25 |  | 26/02/25 |  | 613841 |  |  |  | 86159 | 0 | 0 | 2024-05-04 |  | 4570000 | No | Yes
665 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00263 | Zone II | 31 | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00263-Construction of New Urban Health PHC at Uyaliamman street, Thiruneermalai UPHC, ward No.31 | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-1Dated:23/08/23 | 2023-24 | 12000000 | 3000000 |  |  |  | 0 | 20/11/23 | 0.29 | Work Fully Completed. | 100 | Work Completed | 100 |  |  | 2024-03-06 |  | 3000000 |  |  |  | 0 | 0.06 | 19.4 | 27/02/24 |  | 12000000 | No | Yes
666 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00264 | Zone IV | 54 | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00264-Construction of New Urban Health Sub centre at CTO colony 5th street, ward No.54 zone IV | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-1Dated:23/08/23 | 2023-24 | 12000000 | 3000000 |  |  |  | 0.27 | 20/11/23 | 0.25 | Finessing Work Is In Progress | 97 | Completed | 100 |  |  | 17/09/24 |  | 3000000 |  |  |  | 0 | 0.15 | 49.99 | 27/02/24 |  | 12000000 | No | Yes
667 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00265 | Zone I | 12 | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00265-Construction of New Urban Health Sub centre at Thiru Nagar Moovendar street, Pammal ward No.12 Zone I | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-1Dated:23/08/23 | 2023-24 | 12000000 | 3000000 |  |  |  | 0.27 | 28/11/23 | 0 | Work Fully Completed. | 100 | Work Completed | 100 |  |  | 14/08/24 |  | 1453418 |  |  |  | 1546582 | 0.15 | 48.45 | - |  | 12000000 | No | Yes
668 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SN0012/00081 | Zone V | 69 | General Fund GENERAL/2024-25/009/SN0012/00081-Improvement and Green Space Developement of park, Children's play material and outdoor gym equipment at Paduvencherry Vinayagar kovil street Park in ward.no.69 in (Zone 5) in Tambaram City Municipal Corporation. | Annual Maintenance | Annual Maintenance of Parks | 471-11Dated:21/10/24 | 2024-25 | 1080000 | 1080000 |  |  |  | 0 | 2024-07-11 | 0.11 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1080000 | 0 | 0 | 2025-07-01 |  | 1080000 | No | No
669 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00312 | Zone V | 62 | General Fund GENERAL/2025-26/009/PARK/00312-Providing,Laying Football TURF and Synthitic Multi -Sports Court at Arul Nagar Park Ward no 62 in Zone 5 in Tambaram City Municipal Corporation | Parks | Playground for Sports | 332Dated:24/06/25 | 2025-26 | 11500000 | 11500000 |  |  |  | 0 | 2025-09-09 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 11500000 | 0 | 0 | 16/12/25 |  | 11500000 | No | Yes
670 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00004 | Zone I | 2 | MLA Fund MLA Fund/2022-23/009/BUILDING/00004-Providing Compound wall at Islams Burial Ground (Kabasthanam) at Ward No. 2, TCMC Zone -1 | Buildings | Construction of Compound Wall | 3607/2022/A3Dated:30/11/22 | 2022-23 | 6285000 | 1000000 |  |  |  | 0 | 2023-11-01 | 0.08 | Work Completed | 100 | Work Completed | 100 |  |  | 2023-10-10 |  | 913000 |  |  |  | 87000 | 0.09 | 91.26 | 2023-11-04 |  | 6285000 | Yes | Yes
671 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00238 | Zone I | 10 | General Fund GENERAL/2025-26/009/OTHERS/00238-Providing and Laying WMM Road in Moongil Eri School at Ward no.10 Zone-1 TCMC | Others | Construction of Pathway | 03/2025-26Dated:23/02/26 | 2025-26 | 850000 | 850000 |  |  |  | 0 | 17/10/25 | 0 |  | 0 | Work Completed | 100 |  |  |  |  | 0 |  |  | 0 | 850000 | 0 | 0 | - |  | 850000 | No | No
672 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/BUILDING/00002 | Zone III | 39 | General Fund GENERAL/2024-25/009/BUILDING/00002-Construction of Library Building at Bhavanadhiyar Park in Ward-39,Zone III | Buildings | Library | 452/21.10.2024Dated:21/10/24 | 2024-25 | 4000000 | 4000000 |  |  |  | 0 | 28/11/25 | 0.4 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4000000 | 0 | 0 | 2026-05-03 |  | 4000000 | No | No
673 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00275 | Zone II | 29 | MLA Fund MLA Fund/2021-22/009/BUILDING/00275- Construction of Library @ (Ward No. 29) in Thiruneermalai | Buildings | Library | 4593/A3/2021 (Thiruneermalai)Dated:18/05/22 | 2021-22 | 1500000 | 1500000 |  |  |  | 0.15 | 16/06/22 | 0.13 | Work Completed | 100 | Work Completed | 100 |  |  | 13/01/23 |  | 1500000 |  |  |  | 0 | 0.15 | 100 | 14/09/22 |  | 1500000 | Yes | Yes
674 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/TW013/00062 | Zone III | 38 | MLA Fund MLA/2022-23/009/TW013/00062-Construction of Bus stand at Hasthinapuram in Ward No.38 | Bus Stand | Construction of New Busstand | 3607/2022/A3-1Dated:22/10/22 | 2022-23 | 5000000 | 5000000 |  |  |  | 0.5 | 2023-05-06 | 0.41 | Truss Work Is In Progress | 50 | Work Completed | 100 |  |  | 23/10/23 |  | 0 |  |  |  | 5000000 | 0 | 0 | 2023-10-02 |  | 5000000 | No | Yes
675 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00280 |  |  | General Fund GENERAL/2025-26/009/ROAD/00280-Relaying of Road-Cement Concrete Road- , | Roads | Cement Concrete Road | 326 / 2025-26Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 3200000 | 3200000 |  |  |  | 0 | 20/06/25 | 0.32 | Earth Work | 20 | Completed | 100 |  |  | 21/01/26 |  | 3176428 |  |  | 0 | 23572 | 0 | 0 | 20/09/25 |  | 3200000 | No | Yes
676 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00246 |  |  | General Fund GENERAL/2024-25/009/ROAD/00246-Relaying of Road-Cement Concrete Road- , | Roads | Cement Concrete Road | 20-1 / 2024-25Dated:19/03/25Road DetailsRoad Length :Mts | 2024-25 | 900000 | 900000 |  |  |  | 0 | 25/04/25 | 0.09 | Earth Work | 20 | Completed | 100 |  |  | 29/08/25 |  | 897531 |  |  | 0 | 2469 | 0 | 0 | 25/07/25 |  | 900000 | No | Yes
677 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00245 |  |  | General Fund GENERAL/2025-26/009/ROAD/00245-Relaying of Road-Cement Concrete Road- , | Roads | Cement Concrete Road | 37-2 / 2025-26Dated:29/08/25Road DetailsRoad Length :Mts | 2025-26 | 500000 | 500000 |  |  |  | 0 | 26/09/25 | 0.05 | Plain Cement Concrete 1:4:8 And Centering | 40 | Completed | 100 |  |  | 27/01/26 |  | 460320 |  |  | 0 | 39680 | 0 | 0 | 26/12/25 |  | 500000 | No | Yes
678 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2022-23/009/ROAD/00195 |  |  | General Fund GENERAL/2022-23/009/ROAD/00195-Relaying of Road-009009S0069-MUNUSWAMY MAISTRY STREET , | Roads | Cement Concrete Road | 87Dated:24/08/22Road DetailsRoad Length :174 Mts | 2022-23 | 500000 | 500000 |  |  |  | 0.05 | 14/10/22 | 0.05 | Plain Cement Concrete 1:4:8 And Centering | 50 | Completed | 100 |  |  | 2023-09-06 |  | 0 |  |  |  | 500000 | 0 | 0 | 2023-12-01 |  | 500000 | No | Yes
679 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2022-23/009/ROAD/00196 |  |  | General Fund GENERAL/2022-23/009/ROAD/00196-Relaying of Road-009009R0688-VINAYAGAR KOIL STREET , | Roads | Cement Concrete Road | 104Dated:20/10/22Road DetailsRoad Length :76 Mts | 2022-23 | 500000 | 500000 |  |  |  | 0.05 | 15/03/23 | 0.05 | Plain Cement Concrete 1:4:8 And Centering | 50 | Completed | 100 |  |  | 2023-12-06 |  | 0 |  |  |  | 500000 | 0 | 0 | 13/06/23 |  | 500000 | No | Yes
680 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00113 |  |  | TURIP TURIP/2023-24/009/ROAD/00113-Relaying of Road-009047R3477-ANDAL STREET , 009047R3470-LAL BAHADUR SHASTRI ST , 009045R6039-MUTHALAMMAN KOIL STREET , 009045R3385-I.O.B. COLONY-IST MAIN RD , 009063R4814-VIJAYARANGAM STREET , 009048R3475-ANNADURAI STREET , 009047R3471-PONNUSAMY STREET , | Roads | Cement Concrete Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1601 Mts | 2023-24 | 313620000 | 7250000 |  |  |  | 0.73 | 18/07/23 | 0.69 | Plain Cement Concrete M 20 | 85 | Completed | 100 |  |  | 26/02/25 |  | 7249511 |  |  |  | 489 | 0.65 | 89.28 | 23/10/23 |  | 313620000 | No | Yes
681 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00108 |  |  | TURIP TURIP/2025-26/009/ROAD/00108-Relaying of Road-Cement Concrete Road009052R3714-AMAL NAGAR 1ST STREET , 009052R3715-AMAL NAGAR 2ND STREET , 009051R3626-DHANAPAL STREET , 009051R3638-WELL STREET , 009052R3674-1ST MAIN ROAD LAKSHMIPURAM , 009052R3678-2ND ST-LAKSHMIPURAM , 009052R3679-4TH STREET ,LAKSHMIPURAM , 009052R3680-LAKSHMIPURAM 6TH STREET , 009053R3852-MALLIGA NAGAR 2ND MAIN ROAD , 009053R3869-JERUSALEM NAGAR - NEHRU STREET , 009053R3870-JERUSALEM NAGAR - CHURCH STREET , 009053R3913-REDDY ST (SRINIVASAN ST) , 009053R3868 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1880 Mts | 2025-26 | 521620000 | 12300000 |  |  |  | 1.11 | 2025-10-06 | 1.01 | Plain Cement Concrete M 20 | 78 | Completed | 100 |  |  | 2026-09-01 |  | 12255968 |  |  |  | 44032 | 1.11 | 90 | 2025-09-08 |  | 521620000 | No | Yes
682 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00348 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00348-Relaying of Road-Cement Concrete Road009012S0091-2ND STREET ESWARI NAGAR , 009012R0897-RAMZHAN STREET SAMUNDEESHWARI NAGAR , 009012R0882-MAIN ROAD ESWARI NAGAR , 009012S0084-JEEVA NANDAM STREET , 009012R0905-MG THENNAVAN STREET , 009012L0055-5TH STREET ESWARI NAGAR , 009012L0049-1ST CROSS STREET ESWARI NAGAR , 009012S0093-NARAYANAN PILLAI STREET , 009012L0050-5TH CROSS STREET ESWARI NAGAR , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1276 Mts | 2025-26 | 237450000 | 7000000 |  |  |  | 0 | 2025-06-06 | 0.7 | Plain Cement Concrete M 20 | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 7000000 | 0.63 | 90 | 2025-05-08 |  | 237450000 | No | No
683 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/WS/00019 | Zone IV | 33 | MP Fund MP Fund/2021-22/009/WS/00019-Providing Deep Borewell Power Pump Pipe Line Works at Thiru.Vi Ka Nagar Ward No.33 in Tambaram City Municipal Corporation | Water Supply | Borewell | 2829/2022/A3 4Dated:30/07/22 | 2021-22 | 1070000 | 270000 |  |  | 0 | 0.03 | 16/11/22 | 0.02 | Earth Work/ Drilling Of A Bore | 70 | Completed | 100 |  |  | 17/09/24 |  | 253334 |  |  |  | 16666 | 0.03 | 93.83 | 16/12/22 |  | 1070000 | Yes | Yes
684 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00013 | Zone III | 23 | MLA Fund MLA/2023-24/009/WS/00013-Providing borewell with minipower pump at ward NO.23 (2 locations), zone III | Water Supply | Borewell | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 560000 |  |  |  | 0 | 28/02/24 | 0.05 | Earth Work/ Drilling Of A Bore | 20 | Completed | 100 |  |  |  |  | 0 |  |  |  | 560000 | 0 | 0 | 24/11/24 |  | 8230000 | No | Yes
685 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/WS/00065 | Zone III | 37 | MLA Fund MLA/2022-23/009/WS/00065-Supply and Erection of 2000 LPH Reverse Osmosis water Treatment Plant with Deep Borewell in Ward No.37 | Water Supply | Borewell | 3607/2022/A3-12Dated:22/10/22 | 2022-23 | 970000 | 970000 | 0 |  |  | 0.1 | 2022-12-12 | 0.08 | Earth Work/ Drilling Of A Bore | 20 | Completed | 100 |  |  | 14/03/24 |  | 948267 |  |  |  | 21733 | 0 | 0 | 2023-10-02 |  | 970000 | No | Yes
686 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/WS/00066 | Zone III | 36 | MLA Fund MLA/2022-23/009/WS/00066-Supply and Erection of 2000 LPH Reverse Osmosis Water TReatment Plant with Deep Borewell in Ward No.36 | Water Supply | Borewell | 3607/2022/A3-11Dated:22/10/22 | 2022-23 | 9700000 | 970000 | 0 |  |  | 0.1 | 2022-12-12 | 0.08 | Earth Work/ Drilling Of A Bore | 20 | Compleetd | 100 |  |  | 14/02/24 |  | 948267 |  |  |  | 21733 | 0 | 0 | 2023-10-02 |  | 9700000 | No | Yes
687 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00468 | Zone II | 24 | MLA Fund MLA Fund/2022-23/009/WS/00468-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.24 | Water Supply | Borewell | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 560000 |  | 0 |  | 0.06 | 25/11/22 | 0.05 | Earth Work/ Drilling Of A Bore | 55 | Completed | 100 |  |  | 2024-09-09 |  | 546196 |  |  |  | 13804 | 0.05 | 90.27 | 23/02/23 |  | 6280000 | Yes | Yes
688 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/WS/00064 | Zone III | 35 | MLA Fund MLA/2022-23/009/WS/00064-Supply and Erection of 2000LPH Reverse Osmosis Water TRaetment Plant with Deep Borewell in Ward No.35 | Water Supply | Borewell | 3607/2022/A3- 10Dated:22/10/22 | 2022-23 | 970000 | 970000 | 0 |  |  | 0.1 | 2022-12-12 | 0.08 | Earth Work/ Drilling Of A Bore | 20 | Completed | 100 |  |  | 2024-12-07 |  | 958352 |  |  |  | 11648 | 0 | 0 | 2023-10-02 |  | 970000 | No | Yes
689 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00009 | Zone II | 15 | MLA Fund MLA/2023-24/009/WS/00009-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at ward No.15, zone II | Water Supply | Borewell | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 19/01/24 | 0.1 | Erection Of Pumps And Gensets | 95 | Work Completed | 100 |  |  | 2025-02-05 |  | 980269 |  |  |  | -10269.06 | 0 | 0 | 19/04/24 |  | 5820000 | No | Yes
690 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00011 | Zone II | 27 | MLA Fund MLA/2023-24/009/WS/00011-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at ward No.27, zone II | Water Supply | Borewell | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 19/01/24 | 0.1 | Erection Of Pumps And Gensets | 95 | Completed | 100 |  |  | 2025-02-05 |  | 980269 |  |  |  | -10269.06 | 0 | 0 | 19/04/24 |  | 5820000 | No | Yes
691 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00038 | Zone II |  | 15th CFC 15thCFC/2022-23/009/WS/00038-Construction of 1.00 LL Capacity of ground level service reservoir and motor at Trisoolam Phase I and II, zone 2 in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 5000000 |  |  |  | 0.5 | 25/04/23 | 0.42 | Stage4 | 90 | Completed | 100 |  |  | 2024-09-09 |  | 4348911 |  |  |  | 651089 | 0.44 | 87.94 | 25/07/23 |  | 28650000 | No | Yes
692 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00035 | Zone V | 70 | 15th CFC 15thCFC/2022-23/009/WS/00035-Construction of 2.00 LL SR 16 m staging at Madampakkam Noothancheri, ward No. 70, Zone 5 in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 5000000 |  |  |  | 0.5 | 21/04/23 | 0.42 | Finishing Work | 99 | Completed | 100 |  |  | 24/04/25 |  | 4753422 |  |  |  | 246578 | 0.37 | 73.99 | 2023-11-11 |  | 28650000 | No | Yes
693 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00133 |  |  | TURIP TURIP/2023-24/009/ROAD/00133-Relaying of Road-009046R3427-THIRUVALLUVAR STREET , 009046R3428-MAHALAKSHMI STREET , 009064R4826-MGR STREET , 009045R3411-EASWARAN KOIL STREET , 009045R3410-MUTHALAMMAN KOIL STREET , 009046R3464-ARTHI NAGAR 1ST MAIN ROAD , 009046R3465-ARTHI NAGAR 2ND MAIN ROAD , 009046R3466-ARTHI NAGAR CROSS STREET , 009045R3341-SOWBAGYALAKSHMI STREET , 009064R4852-PROFESSOR COLONY S.O.S. ST , 009065R5014-INDIRA NAGAR EAST , 009068R6319-MUTHUMARIYAMMAN KOIL STREET , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2848 Mts | 2023-24 | 313620000 | 12000000 |  |  |  | 1.08 | 18/07/23 | 1.02 | Bituminous Concrete | 92 | Completed | 100 |  |  | 2025-12-02 |  | 10219710 |  |  |  | 1780290 | 1.02 | 84.92 | - |  | 313620000 | Yes | Yes
694 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00060 | Zone III |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00060-Construction of Micro Compost Centre at Chitlapakkam Balaji avenue zone No.3 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.51 | 26/04/23 | 0.48 | Finishing Works | 98 | Completed | 100 |  |  | 16/02/24 |  | 5749744 |  |  |  | 256 | 0.55 | 95.71 | 26/08/23 |  | 40250000 | No | Yes
695 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00278 |  |  | General Fund GENERAL/2024-25/009/ROAD/00278-Relaying of Road-Bituminous Road- , | Roads | Bituminous Road | 20-11 / 2024-25Dated:19/03/25Road DetailsRoad Length :Mts | 2024-25 | 950000 | 950000 |  |  |  | 0 | 25/04/25 | 0.1 | Picking/earthwork/milling | 30 | Completed | 100 |  |  | 19/11/25 |  | 930488 |  |  | 0 | 19512 | 0 | 0 | 25/07/25 |  | 950000 | No | Yes
696 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00237 |  |  | General Fund GENERAL/2025-26/009/ROAD/00237-Relaying of Road-Bituminous Road- , | Roads | Bituminous Road | 819-2 / 2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 2200000 | 2200000 |  |  |  | 0 | 27/10/25 | 0.22 | Picking/earthwork/milling | 30 | Completed | 100 |  |  | 2026-06-02 |  | 2187900 |  |  | 0 | 12100 | 0 | 0 | 27/01/26 |  | 2200000 | No | Yes
697 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00329 | Zone III | 42 | General Fund GENERAL/2025-26/009/PARK/00329-Renovation of Annai Anjugam Park-Increasing the Height Of Compound Wall,Providing Pathway Lights,seating And Play Accessories In Ward No.42 in Zone III | Parks | Parks | 929-2Dated:31/10/25 | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 13/01/26 | 0.25 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2500000 | 0 | 0 | 20/04/26 |  | 2500000 | No | Yes
698 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/PARK/00117 | Zone III | 42 | General Fund GENERAL/2025-26/009/PARK/00117-Providing BT Surface in Top of the scating area at Annai Anjugam Park in Ward-42 | Parks | Parks | 905-1Dated:31/10/25 | 2025-26 | 1300000 | 1300000 |  |  |  | 0 | 22/09/25 | 0.13 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | 29/12/25 |  | 1300000 | No | No
699 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/ROAD/00106 |  |  | Namakku Naame Thittam NNT/2022-23/009/ROAD/00106-Relaying of Road-009021R5868-English Electric Nagar 1st Main Road , | Roads | Bituminous Road | 8880/2022/p1-2Dated:20/04/23Road DetailsRoad Length :420 Mts | 2022-23 | 15130000 | 6000000 |  |  |  | 0.6 | 29/05/23 | 0.59 | Wet Mix Macadam (Wmm) | 75 | Completed | 100 |  |  | 28/08/24 |  | 5673630 |  |  |  | 326370.2 | 0.51 | 84.49 | - |  | 15130000 | Yes | Yes
700 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/ROAD/00107 |  |  | Namakku Naame Thittam NNT/2022-23/009/ROAD/00107-Relaying of Road-009027R5918-Railway Gate Road , | Roads | Bituminous Road | 8880/2022/p1-2Dated:20/04/23Road DetailsRoad Length :75 Mts | 2022-23 | 15130000 | 800000 |  |  |  | 0.08 | 2023-08-05 | 0.08 | Wet Mix Macadam (Wmm) | 30 | Completed | 100 |  |  | 2024-09-09 |  | 773500 |  |  |  | 26500 | 0.07Excel | 86.56 | 2023-08-08 |  | 15130000 | Yes | Yes
701 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00032 | Zone II | 28 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00032-Road Restoration of damaged portion over at Bharatha Matha Street (007028R1053) in Ward No.28 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 880000 |  |  |  | 0.09 | 2022-03-01 | 0.09 | Wet Mix Macadam (Wmm) | 30 | Completed | 100 |  |  | 21/12/22 |  | 0 |  |  |  | 880000 | 0.08 | 90.86 | 2022-03-02 |  | 41050000 | Yes | Yes
702 | Tambaram | TURIP | CHENGALPATTU | TURIP/2021-22/007/ROAD/00036 |  |  | TURIP TURIP/2021-22/007/ROAD/00036-Providing B.T. Surface at Station Road,Kabaleshwarar Street,Kabaleshwarar Cross Street,Nemilichery High Road in ward No:23,26,28(Package No.04) | Roads | Bituminous Road | 24886/2021/E1Dated:19/11/20Road DetailsRoad Length :Mts | 2021-22 | 50000000 | 10000000 |  |  |  | 0.5 | 2022-04-01 | 0.98 | Wet Mix Macadam (Wmm) | 55 | Completed | 100 |  |  | 2025-03-03 |  | 8802049 |  |  |  | 1197951 | 0.79 | 79 | 2022-02-10 |  | 50000000 | Yes | Yes
703 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00041 | Zone II | 28 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00041-Road Restoration of damaged portion over at Periyar Nagar 1st Street (007028R1063) in Ward No.28 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 780000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Wet Mix Macadam (Wmm) | 30 | Completed | 100 |  |  | 21/12/22 |  | 0 |  |  |  | 780000 | 0.07 | 90.47 | 2022-03-02 |  | 41050000 | Yes | Yes
704 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00042 | Zone II | 28 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00042-Road Restoration of damaged portion over at VOC Street (007028R1055) in Ward No.28 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 400000 |  |  |  | 0.04 | 2022-03-01 | 0.04 | Wet Mix Macadam (Wmm) | 30 | Completed | 100 |  |  | 21/12/22 |  | 0 |  |  |  | 400000 | 0.04 | 90.9 | 2022-03-02 |  | 41050000 | Yes | Yes
705 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00323 | Zone IV |  | TURIP TURIP/2024-25/009/ROAD/00323-Relaying of Road-Bituminous Road009051R3667-THIRUVALLUVAR 2ND ST , 009051R3658-SUNDHARAM COLONY 3RD ST , 009032R2047-Thiruneermalai Road Burma colony to zone 4 limit , 009032R2045-Thiruneermalai Road, Arputha Nagar to Pulikoradu Road Jn , 9032R2046-Thiruneermalai Road, Pulikoradu Road Jn to Amman Kovil 2nd Street , (Package No.08) Zone IV | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :1287 Mts | 2024-25 | 130600000 | 11580000 |  |  |  | 0 | 27/05/25 | 0.92 | Dense Bituminous Macadam (Dbm) | 90 | Completed | 100 |  |  | 28/01/26 |  | 11573641 |  |  | 0 | 6359 | 0.98 | 84.56 | 26/07/25 |  | 130600000 | No | Yes
706 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00158 | Zone III | 39, 40 | General Fund GENERAL/2025-26/009/OTHERS/00158-Desilting Existing Channel And Storm Water Drain Ward No.39&40 in Zone III | Others | Miscellaneous Works | 622Dated:23/07/25 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 20/08/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 900000 | 0 | 0 | 27/11/25 |  | 900000 | No | Yes
707 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/OTHERS/00004 | Zone IV | 53 | MLA Fund MLA/2023-24/009/OTHERS/00004-Providing open space stage at Old Tambaram Kullakkarai in ward No.53, zone iv | Others | Infrastructure and Amenities | 3041/2023/A3-3Dated:15/11/23 | 2023-24 | 2550000 | 350000 |  |  |  | 0.04 | 2024-10-01 | 0.03 | Plastering Work Is In Progress | 65 | Completed | 100 | 20/02/25 |  | 20/02/25 |  | 350000 |  |  |  | 0 | 0.04 | 100 | 2024-10-04 |  | 2550000 | Yes | Yes
708 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00264 | Zone III | 42 | General Fund GENERAL/2025-26/009/ROAD/00264-Providing BT Surface To Vallal Yusuf Street, Vivekanandhar Street, Ovvaiyar Street In Ward No.42 In Zone III | Roads | Earthern to BT Road | 673-5Dated:25/08/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 2025-06-10 | 0.24 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 2500000 | 0 | 0 | 13/01/26 |  | 2500000 | No | Yes
709 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00317 | Zone III | 35 | General Fund GENERAL/2025-26/009/ROAD/00317-Providing BT Surface To New Street in Ward No.35 in Zone III | Roads | Earthern to BT Road | 471-7Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 700000 | 700000 |  |  |  | 0 | 18/07/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 700000 | 0 | 0 | 25/10/25 |  | 700000 | No | Yes
710 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00314 | Zone I | 10 | General Fund GENERAL/2025-26/009/ROAD/00314-Providing BT Surface at Jeevandam street in ward no.10 zone-1 TCMC | Roads | Earthern to BT Road | 1037/2025-26Dated:29/12/25Road DetailsRoad Length :Mts | 2025-26 | 1820000 | 1820000 |  |  |  | 0 | 2026-12-01 | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1820000 | 0 | 0 | - |  | 1820000 | No | Yes
711 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00229 | Zone 03 | 36 | General Fund GENERAL/2025-26/009/ROAD/00229-Providing And Laying Paver Block Road To Pachaiyappan In Ward No.36 In Zone-03 | Roads | Earthern to PaverBlock | 471-5Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 800000 | 800000 |  |  |  | 0 | 18/07/25 | 0.08 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 800000 | 0 | 0 | 25/10/25 |  | 800000 | No | Yes
712 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/ROAD/00087 |  |  | General Fund GENERAL/2024-25/009/ROAD/00087-Formation of New Road-Earthern to PaverBlock- Kanagaraj Cross Street | Roads | Earthern to PaverBlock | 75Dated:15/05/25Road DetailsRoad Length :Mts | 2024-25 | 590000 | 590000 |  |  |  | 0 | 14/07/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 590000 | 0 | 0 | 21/10/25 |  | 590000 | No | Yes
713 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00140 | Zone III | 40 | General Fund GENERAL/2025-26/009/ROAD/00140-Providing And Laying Paver Block Road Shesharam Nagar In Ward No.40 In Zone III | Roads | Earthern to PaverBlock | 221-3Dated:28/04/25Road DetailsRoad Length :Mts | 2025-26 | 910000 | 910000 |  |  |  | 0 | 14/07/25 | 0.09 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 910000 | 0 | 0 | 21/10/25 |  | 910000 | No | Yes
714 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00078 | Zone III | 41 | General Fund GENERAL/2025-26/009/ROAD/00078-Providing And Laying Paver Block Road to Masuthi Colony 2nd St And 3rd Cross Street in Ward No.41. in ZoneIII | Roads | Earthern to PaverBlock | 384Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 990000 | 990000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | - |  | 990000 | No | Yes
715 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00233 | Zone IV | 57 | MLA Fund MLA/2024-25/009/OTHERS/00233-Providing Paverblock road to Kundumedu Tiruvalluvar street in ward No.57 Zone IV Tambaram Corporation | Others | Road Sign | 1694/2024/A1Dated:19/12/24 | 2024-25 | 47450000 | 1600000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1600000 | 0 | 0 | - |  | 47450000 | No | No
716 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00234 | Zone IV | 57 | MLA Fund MLA/2024-25/009/OTHERS/00234-Providing Paver block road at Ambedkar street in ward No.57 Zone IV in Tambaram Corporation | Others | Road Sign | 1694/2024/A1Dated:19/12/24 | 2024-25 | 47450000 | 1230000 |  |  |  | 0 | - | 0 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1230000 | 0 | 0 | - |  | 47450000 | No | No
717 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00294 | Zone I | 12 | General Fund GENERAL/2025-26/009/OTHERS/00294-Providing Paver block at Moovendar Nagar urban wellness sub centre and Eswari Nagar Urban wellness sub centre in ward No.12 zone I in TCMC | Others | Road Sign | 469-6Dated:06/10/25 | 2025-26 | 4516000 | 660000 |  |  |  | 0 | 28/11/25 | 0.07 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 660000 | 0 | 0 | - |  | 4516000 | No | Yes
718 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/OTHERS/00233 | Zone I |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/OTHERS/00233-Supply and fixing of 600nos of new retro reflective name board and s ticking of 5oo nos of retro reflective street on the existing name board for the streets in zone I | Others | Road Sign | 16479/2023/EA2Dated:09/08/23 | 2023-24 | 55600000 | 13200000 |  |  |  | 1.19 | 24/01/24 | 0 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13200000 | 1.11 | 84.07 | - |  | 55600000 | No | Yes
719 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00301 | Zone III | 34 | General Fund GENERAL/2025-26/009/BUILDING/00301-Providing Additional Work To Library Of Primary School In Chitlapakkam 2nd Main Road In Ward No.34 | Buildings | Library | 929-1Dated:31/10/25 | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 13/01/26 | 0.15 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1500000 | 0 | 0 | 20/04/26 |  | 1500000 | No | Yes
720 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00003 | Zone IV | 53 | MLA Fund MLA/2023-24/009/BUILDING/00003-Construction of New Library building at ward No. 53 Near Kone Krishna Over Head tank zone IV | Buildings | Library | 3041/2023/A3-3Dated:15/11/23 | 2023-24 | 2550000 | 2200000 |  |  |  | 0.2 | 2024-02-01 | 0.18 | Completed | 100 | Completed | 100 | 28/02/25 |  | 28/02/25 |  | 2003211 |  |  |  | 196789 | 0.2 | 91.06 | 2024-02-04 |  | 2550000 | Yes | Yes
721 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/TW013/00054 | Zone II | 13 | General Fund GENERAL/2025-26/009/TW013/00054-Construction & Renovation of Pallavaram bustand at in TCMC ward-13 Zone-2 | Bus Stand | Bus Stand | 716-15/2025-26Dated:25/08/25 | 2025-26 | 2000000 | 2000000 |  |  |  | 0 | 26/09/25 | 0.2 |  | 0 | Completed | 100 |  |  | 15/12/25 |  | 1989745 |  |  |  | 10255 | 0 | 0 | 26/12/25 |  | 2000000 | No | Yes
722 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/TW013/00051 | Zone II | 28 | General Fund GENERAL/2025-26/009/TW013/00051-Construction & Renovation of Chromepet bustand at east side in TCMC ward-28 Zone-2 | Bus Stand | Bus Stand | 716-14/2025-26Dated:25/08/25 | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 26/09/25 | 0.25 |  | 0 | Completed | 100 |  |  | 25/11/25 |  | 2499892 |  |  |  | 108 | 0 | 0 | 26/12/25 |  | 2500000 | No | Yes
723 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/TW013/00207 | Zone III | 34 | General Fund GENERAL/2025-26/009/TW013/00207-Proposed Bus Stop At Chitlapakkam 2nd Main Road Near OHT In Ward No.34 Tambaram City Municipal Corporation | Bus Stand | Construction of New Busstand | 341Dated:24/06/25 | 2025-26 | 1400000 | 1400000 |  |  |  | 0 | 2025-03-07 | 0.14 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 1400000 | 0 | 0 | 2025-10-10 |  | 1400000 | No | Yes
724 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2021-22/009/WS/00087 | Zone IV | 52 | MLA Fund MLA/2021-22/009/WS/00087-Providing 1000 ltr Capacity RO plant with water supply and infrastructure facilities at kannadapalayam pilliyar koil street ward no52 zone 4 in TCMC | Water Supply | Combined Water Supply Scheme | 4592Dated:07/12/22 | 2021-22 | 960000 | 960000 |  |  |  | 0 | 31/03/23 | 0.08 | Work Completed | 100 | Completed | 100 |  |  | 30/08/23 |  | 876000 |  |  |  | 84000 | 0 | 0 | 30/04/23 |  | 960000 | No | Yes
725 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00037 | Zone V | 65 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00037-Repair and maintaining of Community toilet at Bharath park in ward No.65 zone V | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 350000 |  |  |  | 0 | 30/05/25 | 0.04 | Column Raised Upto Roof Level | 35 | Completed | 100 |  |  |  |  | 0 |  |  |  | 350000 | 0 | 0 | 2025-01-08 |  | 12070000 | No | Yes
726 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00039 | Zone V | 64 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00039-Repair and maintaining of Community toilet at Subarayan park in ward No.64 zone V | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 430000 |  |  |  | 0 | 13/01/25 | 0 | Painting Work In Progress | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 430000 | 0 | 0 | - |  | 12070000 | No | Yes
727 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00035 | Zone IV | 51 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00035-Repair and maintaining of Community toilet at Thiruneermalai road in ward No.51 zone IV | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 170000 |  |  |  | 0 | 21/01/25 | 0.02 | Finishing Work Is In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 170000 | 0 | 0 | 21/10/25 |  | 12070000 | No | Yes
728 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00020 | Zone IV | 49 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00020-Retrofitting and Public Toilet at Abdul rasak street in ward No.49 zone IV | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 130000 |  |  |  | 0 | 2024-03-12 | 0.01 | Finishing Work Is In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 130000 | 0 | 0 | 2025-01-09 |  | 12070000 | No | Yes
729 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00021 | Zone IV | 33 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00021-Retrofitting and Public Toilet at Kadaperi Anna bus stand in ward No.33 zone IV | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 760000 |  |  |  | 0 | 2024-03-12 | 0.08 | Tiles Laying Work Completed ,Door Fixing Work Is In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 760000 | 0 | 0 | 2025-01-09 |  | 12070000 | No | Yes
730 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00022 | Zone I | 1 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00022-Repair and maintaining of Community toilet at Kasthuri bai nagar in ward NO.01 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 350000 |  |  |  | 0 | 18/12/24 | 0.03 | Finishing Work In Progress | 85 | Completed | 100 |  |  |  |  | 0 |  |  |  | 350000 | 0 | 0 | - |  | 12070000 | No | Yes
731 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00024 | Zone I | 4 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00024-Repair and maintaining of Community toilet at EB colony in ward No.04 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 290000 |  |  |  | 0 | 2025-03-01 | 0.02 | Plumbing Work In Progess | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 290000 | 0 | 0 | - |  | 12070000 | No | Yes
732 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00025 | Zone I | 4 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00025-Repair and maintaining of Community toilet at Kalmaduvu in ward No.04 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 260000 |  |  |  | 0 | 28/03/25 | 0.02 | Painting Work In Progress | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 260000 | 0 | 0 | - |  | 12070000 | No | Yes
733 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00030 | Zone I | 11 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00030-Repair and maintaining of Community toilet at Adam nagar in ward No.11 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 260000 |  |  |  | 0 | 29/12/24 | 0 | Tiles Reaying Work In Progress | 35 | Completed | 100 |  |  |  |  | 0 |  |  |  | 260000 | 0 | 0 | - |  | 12070000 | No | Yes
734 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00031 | Zone III | 23 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00031-Repair and maintaining of Community toilet at Alamaram street in ward No.23 zone III | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 230000 |  |  |  | 0 | 15/07/25 | 0.02 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 230000 | 0 | 0 | 2026-11-04 |  | 12070000 | No | Yes
735 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00032 | Zone III | 23, 41 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00032-Repair and maintaining of Community toilet at Kalainar street, gangaiamman street and Velachery main road in ward No.23 and 41 zone III | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 610000 |  |  |  | 0 | 15/07/25 | 0.06 |  | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 610000 | 0 | 0 | 2026-11-04 |  | 12070000 | No | Yes
736 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00033 | Zone IV | 32 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00033-Repair and maintaining of Community toilet at Arputham Nagar in ward No.32 zone IV | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 1100000 | 0 | 0 |  | 0 | 2024-03-12 | 0.11 | Painting Work Is In Progress | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1100000 | 0 | 0 | 2025-05-09 |  | 12070000 | No | Yes
737 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/PURCHASE/00004 |  |  | 15th CFC 15th CFC/2021-22/009/PURCHASE/00004-Purchase of 3 nos Manhole De-silting Grabbing machine to Tambaram City Municipal Corporation for Under Ground Sewerage Scheme. | Purchase of Materials | Purchase of Machineries | 21191/2021/AMRUT-2-Tambaram-Tied-5Dated:17/12/21 | 2021-22 | 4500000 | 4500000 |  |  |  | 0.45 | 28/02/22 | 0.4 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4500000 | 0.38 | 85.47 | 31/05/22 |  | 4500000 | Yes | Yes
738 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2023-24/009/PURCHASE/00193 |  |  | 15th CFC 15thCFC/2023-24/009/PURCHASE/00193-Supply and delivery of 2 Nos of Truck Chassis mounted Sewer Suction cum Jetting Machine with 8000 litre tank capacity | Purchase of Materials | Purchase of Machineries | 16479/2023/CFC-1Dated:06/07/23 | 2023-24 | 106324000 | 11350000 |  |  |  | 1.14 | 22/11/23 | 1.13 | Completed | 100 |  | 100 |  |  | 2024-05-06 |  | 11254252 |  |  |  | 95748 | 1.13 | 99.16 | 22/02/24 |  | 106324000 | No | Yes
739 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/PURCHASE/00073 | Zone V |  | 15th CFC 15thCFC/2022-23/009/PURCHASE/00073-Procurement of 6000 litres capacity Water tankers Lorry to zone No.5 (2nos) | Purchase of Materials | Vehicle Purchase | 18698/2022/CFC-1/ WSDated:25/01/23 | 2022-23 | 4250000 | 4250000 |  |  |  | 0.43 | 2023-12-05 | 0.42 | Completed | 100 | Complete | 100 |  |  | 13/09/24 |  | 4250000 |  |  |  | 0 | 0.38 | 88.8 | 2024-06-02 |  | 4250000 | No | Yes
740 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2023-24/009/PURCHASE/00192 |  |  | 15th CFC 15thCFC/2023-24/009/PURCHASE/00192-Supply and delivery of 63 Nos of CNG hopper tipper dumper 3.8 cum for Solid Waste Management | Purchase of Materials | Vehicle Purchase | 16479/2023/CFC-1Dated:06/07/23 | 2023-24 | 106324000 | 91854000 |  |  |  | 9.19 | 24/11/23 | 0 | Completed | 100 | Completed | 100 | 20/05/25 |  | 23/05/25 |  | 87771600 |  |  |  | 4082400 | 8.78 | 95.56 | 22/02/24 |  | 106324000 | Yes | Yes
741 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2023-24/009/PURCHASE/00074 |  |  | 15TH CFC-MPC-AAQ MPC/2023-24/009/PURCHASE/00074-Supply and delivery of 4nos 9000 litres capacity truck Mounted Water lorries in Tambaram Corporation | Purchase of Materials | Vehicle Purchase | 18274/2022/EA-2Dated:13/03/24 | 2023-24 | 11281000 | 11281000 |  |  |  | 1.15 | 2024-12-08 | 1.13 | Completed | 100 | Completed | 100 |  |  | 30/12/99 |  | 11276000 |  |  |  | 5000 | 1.11 | 98.14 | 2025-09-05 |  | 11281000 | Yes | Yes
742 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/PURCHASE/00011 |  |  | 15th CFC 15th CFC/2021-22/009/PURCHASE/00011-Purchase of 3nos Jet rodding cum suction 6000 lit to Tambaram City Municipal corporation for UGSS scheme | Purchase of Materials | Vehicle Purchase | 21191/2021/Amrut-1-Tambaram-Tied-8Dated:17/12/21 | 2021-22 | 16500000 | 16500000 |  |  |  | 1.65 | 28/02/22 | 1.07 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 16480500 |  |  |  | 19500 | 1.65 | 99.88 | 29/11/22 |  | 16500000 | Yes | Yes
743 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2024-25/009/PURCHASE/00050 |  |  | 15TH CFC-MPC-SWM MPC/2024-25/009/PURCHASE/00050-Supply and delivery of 1nos truck chassis mounted suction cum jetting machine 8000 tank capacity | Purchase of Materials | Vehicle Purchase | 16479/2023/EA-2Dated:08/01/25 | 2024-25 | 77422000 | 5670000 |  |  |  | 0 | 24/07/25 | 0.57 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5670000 | 0 | 0 | 20/04/26 |  | 77422000 | No | Yes
744 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/017/SWM/00002 |  |  | 15th CFC 15th CFC/2020-21/017/SWM/00002-Remove the Legacy Waste dumped (approximately 7232 cum) on Anakaputhur EB colony, through Bio-Mining process in Anakaputhur Municipality | Solid Waste Management | Bio Mining Work | 205/2021/B1Dated:05/02/21 | 2020-21 | 5600000 | 5600000 | 0 |  | 0 | 0.56 | 2021-05-07 | 0.52 | Completed | 100 | Completed | 100 |  |  | 2022-06-09 |  | 5600000 |  |  |  | 0 | 0.44 | 78.36 | 2021-05-11 |  | 5600000 | Yes | Yes
745 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/SWM/00040 |  |  | 15th CFC 15th CFC/2020-21/009/SWM/00040-Removal of Legacy Waste through Bio-Mining process in kannadapalayam Compost Yard (32,494 cu.m. of legacy waste) | Solid Waste Management | Bio Mining Work | 15890/2021/AMRUT-2 Tambaram SWMDated:18/10/21 | 2020-21 | 25500000 | 23000000 | 0 |  |  | 2.3 | - | 2.36 | Completed | 100 | Completed | 100 | 2025-06-05 |  | 2025-06-05 |  | 23558150 |  |  |  | -558150 | 2.08 | 90.27 | 31/08/22 |  | 25500000 | Yes | Yes
746 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2017-18/009/SWM/00097 |  |  | Chennai River Restoration Trust Chennia Ri/2017-18/009/SWM/00097-Removal of Legacy Waste dumped on the adayar river bank through bio-mining (8600 cu.m) above GL process in thiruneermalai town panchayat | Solid Waste Management | Bio Mining Work | GO MS NO. 72 MAWS DEPARTMENTDated:12/07/17 | 2017-18 | 6000000 | 6000000 |  |  |  | 0.57 | 26/02/20 | 0.52 | Completed | 100 | Completed | 100 |  |  | 23/05/23 |  | 4253000 |  |  |  | 1747000 | 0.43 | 70.88 | 26/02/21 |  | 6000000 | No | Yes
747 | Tambaram | SBM | CHENGALPATTU | Swach Bhar/2017-18/009/SWM/00183 | Zone III | 38 | SBM Swach Bhar/2017-18/009/SWM/00183-Removal of the existing legacy waste dumped at the Kanndapalayam site through Scientific Closure sanctioned under Swacch Bharath Mission (Ward No.38) | Solid Waste Management | Bio Mining Work | G.O. Ms No. 21Dated:14/03/18 | 2017-18 | 76500000 | 76500000 |  |  |  | 7.65 | 2018-02-07 | 7.91 | Completed | 100 | Completed | 100 |  |  | 2020-09-07 |  | 79850600 |  |  |  | -3350600 | 7.09Excel | 92.68 | 2020-09-07 | Final bill to be entered and closed. | 76500000 | No | Yes
748 | Tambaram | SBM | CHENGALPATTU | Swach Bhar/2017-18/009/SWM/00185 |  |  | SBM Swach Bhar/2017-18/009/SWM/00185-REMOVAL OF LEGACY WASTE DUMPED IN THE PERIYA ERI THROUGH BIO- MINING PROCESS | Solid Waste Management | Bio Mining Work | G.O. (Ms) No.21Dated:14/03/18 | 2017-18 | 70000000 | 70000000 | 68035000 |  |  | 7 | 28/09/18 | 7.24 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 73060000 |  |  |  | -3060000 | 6.53 | 93.29 | 21/03/20 | Final bill to be entered and closed. | 70000000 | Yes | Yes
749 | Tambaram | SBM | CHENGALPATTU | SBM/2023-24/009/SWM/00140 |  |  | SBM SBM/2023-24/009/SWM/00140-Remove the Legacy waste dumped (18606.00 cu.m) through Bio Mining Process at Venkadamangalam | Solid Waste Management | Bio Mining Work | 39259/2015/SBMDated:29/05/23 | 2023-24 | 33200000 | 12000000 |  |  |  | 1.2 | 22/12/23 | 1.08 | Completed | 100 | Completed | 100 | 27/03/25 |  | 2025-02-05 |  | 11953575 |  |  |  | 46425 | 1.18 | 98.61 | - |  | 33200000 | No | Yes
750 | Tambaram | SBM | CHENGALPATTU | SBM/2023-24/009/SWM/00141 |  |  | SBM SBM/2023-24/009/SWM/00141-Remove the Legacy waste dumped (32920.00 cu.m) through Bio Mining Process at Perungalathur Kundumedu & Madambakkam Compost yard | Solid Waste Management | Bio Mining Work | 39259/2015/SBMDated:29/05/23 | 2023-24 | 33200000 | 21200000 |  |  |  | 2.12 | 19/10/23 | 1.74 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 21200000 | 1.77 | 83.7 | 19/04/25 |  | 33200000 | No | Yes
751 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2022-23/009/SWM/00486 |  |  | 15th CFC 15th CFC/2022-23/009/SWM/00486-Supply and delivery of backhoe loader with capacity 0.30cum and operating weight of 7630k | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/cfc1Dated:08/11/22 | 2022-23 | 6735000 | 3735000 |  |  |  | 0.37 | 14/04/23 | 0.31 | Completed | 100 | Completed | 100 |  |  | 2023-08-05 |  | 3665151 |  |  |  | 69849 | 0.36 | 97.13 | 14/05/23 |  | 6735000 | Yes | Yes
752 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2022-23/009/SWM/00487 |  |  | 15th CFC 15th CFC/2022-23/009/SWM/00487-Supply and delivery of Sullage Vehicle with 6000 lit capacity | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/cfc1Dated:08/11/22 | 2022-23 | 6735000 | 3000000 |  |  |  | 0.3 | 31/01/23 | 0.3 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 2998000 |  |  |  | 2000 | 0.3 | 99.93 | 2023-02-03 |  | 6735000 | Yes | Yes
753 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/SWM/00186 |  |  | 15th CFC 15th CFC/2020-21/009/SWM/00186-Purchase of Battery Operated vehicle at east west Tambaram | Solid Waste Management | Procurement of Vehicles /Machineries | 37-2Dated:10/11/20 | 2020-21 | 3800000 | 3800000 |  |  |  | 0.38 | 25/02/21 | 0.38 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 3323980 |  |  |  | 476020 | 0.33 | 87.47 | 26/03/21 |  | 3800000 | Yes | Yes
754 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/SWM/00061 |  |  | 15th CFC 15th CFC/2020-21/009/SWM/00061-SUPPLY AND DELIVERY OF BATTERY OPERATED VEHICLES | Solid Waste Management | Procurement of Vehicles /Machineries | 68/2020/e3Dated:22/02/21 | 2020-21 | 1900000 | 1900000 |  |  |  | 0.19 | 2021-01-03 | 0.19 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1889000 |  |  |  | 11000 | 0.19 | 99.42 | 2021-01-03 |  | 1900000 | No | Yes
755 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/SWM/00007 |  |  | 15th CFC 15th CFC/2021-22/009/SWM/00007-Purchase of 4nos JCB(Max) Earth work excavator to Tambaram City Municipal Corporation for Solid Waste Management | Solid Waste Management | Procurement of Vehicles /Machineries | 21191/2021/AMRUT-2-Tambaram-Tied-7Dated:17/12/21 | 2021-22 | 10650000 | 14200000 |  |  |  | 1.42 | 22/04/22 | 1.07 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 13551200 |  |  |  | 648800 | 1.36Excel | 95.43 | 17/01/23 |  | 10650000 | Yes | Yes
756 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00132 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00132-Supply and delivery of 5nos of 10nos compactor vehicle | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 30000000 |  |  |  | 3 | 2024-05-08 | 3 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 25500000 |  |  |  | 4500000 | 2.7 | 90 | 2026-03-02 |  | 118900000 | Yes | Yes
757 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00133 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00133-Supply and delivery of 1nos of Backhoe loader | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 6300000 |  |  |  | 0.63 | 25/10/24 | 0.63 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 6228000 |  |  |  | 72000 | 0.62 | 98.86 | 22/07/25 |  | 118900000 | Yes | Yes
758 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00135 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00135-Supply and delivery of 5nos of backhoe loader fitter with 0.46cu.m bucket capacity with 62 inch standard bucket | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 11750000 |  |  |  | 1.18 | 23/08/24 | 1.18 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 11740000 |  |  |  | 10000 | 1.17 | 99.91 | 27/05/25 |  | 118900000 | Yes | Yes
759 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00141 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00141-Supply and delivery of 10 nos of 5ton weighting machine with printer | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 3330000 | 0 |  |  | 0.33 | 27/08/24 | 0.33 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3330000 | 0.32 | 96.7 | 27/05/25 |  | 19031000 | No | No
760 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00142 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00142-Supply and delivery of 3nos of 50 ton weighing machine with printer | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 2419000 |  |  |  | 0.24 | 2024-07-11 | 0.24 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 2419000 |  |  |  | 0 | 0.23 | 94.96 | 26/08/25 |  | 19031000 | Yes | No
761 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00143 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00143-Supply and delivery of 35nos of capacity of 1000nos per day Napkin Incinerator for MCC | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 7875000 |  |  |  | 0.79 | 2024-08-11 | 0 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 7306000 |  |  |  | 569000 | 0.73 | 92.77 | - |  | 19031000 | Yes | No
762 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00144 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00144-Supply and delivery of 35nos. of capacity of 1000 nos per day Napkin Incinerator for PT/CT/Corp schools | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 844000 |  |  |  | 0.08 | 21/08/24 | 0.08 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 844000 | 0.08 | 97.7 | 2025-07-06 |  | 19031000 | No | No
763 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00145 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00145-Supply and delivery of 26nos of 100 capacity - Napkin Vending macine for PTs only | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 237000 |  |  |  | 0 | 19/08/24 | 0 | Completed | 90 | Completed | 100 |  |  |  |  | 0 |  |  |  | 237000 | 0.02 | 99.83 | - |  | 19031000 | No | No
764 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00140 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00140-Supply and Delivery of 35 nos of 500 kg Weighting machine | Solid Waste Management | Procurement of Vehicles /Machineries | 18698/2022/EA-2.3Dated:15/03/24 | 2023-24 | 19031000 | 298000 | 0 | 0 |  | 0 | 22/09/24 | 0.03 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 298000 | 0.02 | 83.72 | 19/06/25 |  | 19031000 | No | Yes
765 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00137 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00137-Supply and delivery of cattle catching vehicle with lift | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 3000000 |  |  |  | 0.6 | 30/08/24 | 0 | Completed | 100 | Completed | 100 | 20/05/25 |  | 23/05/25 |  | 2700000 |  |  |  | 300000 | 0.27 | 90 | 27/05/25 |  | 118900000 | Yes | Yes
766 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00138 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00138-Supply and delivery of Dog catching vehicle | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 1500000 |  |  |  | 0.15 | 27/08/24 | 0.15 | Completed | 100 | Completed | 100 | 2024-11-11 |  | 2024-09-12 |  | 0 |  |  |  | 1500000 | 0.15 | 98.15 | 30/05/25 |  | 118900000 | No | Yes
767 | Tambaram | 15TH CFC-MPC-SWM | CHENGALPATTU | MPC/2023-24/009/SWM/00139 |  |  | 15TH CFC-MPC-SWM MPC/2023-24/009/SWM/00139-Supply and delivery of 100nos of walkie talkie | Solid Waste Management | Procurement of Vehicles /Machineries | 18274/2022/EA-2-2Dated:15/03/24 | 2023-24 | 118900000 | 1750000 |  |  |  | 0.18 | 28/08/24 | 0 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 1750000 |  |  |  | 0 | 0.18 | 100 | - |  | 118900000 | Yes | No
768 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00058 | Zone IV |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00058-Construction of Micro Compost Centre at Perugalathur Metrocity zone No.4 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.58 | 26/04/23 | 0.48 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 5744000 |  |  |  | 6000 | 0.49 | 85.72 | 21/01/24 |  | 40250000 | Yes | Yes
769 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00059 | Zone I |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00059-Construction of Micro Compost Centre at Pammal Eswari Nagar zone No.1 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.57 | 26/04/23 | 0.56 | Completed | 100 | Completed | 100 |  |  | 29/04/24 |  | 5750000 |  |  |  | 0 | 0.56 | 97.25 | 26/08/23 |  | 40250000 | No | Yes
770 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2022-23/009/SWM/00475 | Zone V | 70 | SBM 2.0 SWACHH BHA/2022-23/009/SWM/00475-Construction of Micro compost centre with 5 tonne capacity at Madambakkam burial ground campus in ward No.70 | Solid Waste Management | Micro Composting Center | 20860/2022/SBMDated:25/05/22 | 2022-23 | 11500000 | 5750000 |  |  |  | 0.57 | 25/11/22 | 0.45 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 5750000 |  |  |  | 0 | 0.56 | 97.56 | 25/05/23 |  | 11500000 | Yes | Yes
771 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2022-23/009/SWM/00476 | Zone IV | 57 | SBM 2.0 SWACHH BHA/2022-23/009/SWM/00476-Construction of Micro Compost centre with 5tonne capapcity at Perungalathur kundumedu in ward no.57 | Solid Waste Management | Micro Composting Center | 20860/2022/SBMDated:25/05/22 | 2022-23 | 11500000 | 5750000 |  |  |  | 0.58 | 25/11/22 | 0.46 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 5381715 |  |  |  | 368285 | 0.54 | 93.6 | 25/05/23 |  | 11500000 | Yes | Yes
772 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00055 | Zone II |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00055-Construction of Micro Compost Centre at Pallavapuram Barathipuram zone No.2 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.26 | 2023-03-05 | 0.48 | Completed | 100 | Completed | 100 |  |  | 2024-05-09 |  | 5744348 |  |  |  | 5652 | 0.57 | 99.9 | 28/01/24 |  | 40250000 | No | Yes
773 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SWM/00056 | Zone I |  | SBM 2.0 SBM 2.0/2022-23/009/SWM/00056-Construction of Micro Compost Centre at Thiruneermalai road zone No.1 in Tambaram City Municipal Corporation | Solid Waste Management | Micro Composting Center | 20860/2022/SBM-05.12.22Dated:05/12/22 | 2022-23 | 40250000 | 5750000 |  |  |  | 0.52 | 2023-05-05 | 0.48 | Completed | 100 | Completed | 100 |  |  | 20/06/24 |  | 57413156 |  |  |  | -51663156 | 0.55 | 95.94 | 2023-05-09 |  | 40250000 | No | Yes
774 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/009/BUILDING/00037 |  |  | 15thCFC-Health 15th CFC/2021-22/009/BUILDING/00037-UPHC Poondi Bazaar Building 1 No | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/ Tambaram CorporationDated:17/12/21 | 2021-22 | 7500000 | 2500000 | 0 |  |  | 0.25 | 25/01/22 | 0.22 | Completed | 100 | Completed | 100 |  |  | 2023-01-03 |  | 2499758 |  |  |  | 242 | 0.24 | 94.43 | 25/04/22 |  | 7500000 | Yes | Yes
775 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/009/BUILDING/00038 |  |  | 15thCFC-Health 15th CFC/2021-22/009/BUILDING/00038-UPHC Renganathapuram, Sundaram Colony Building 1 No | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/ Tambaram CorporationDated:17/12/21 | 2021-22 | 7500000 | 2500000 | 0 |  |  | 0.25 | 25/01/22 | 0.22 | Completed | 100 | Completed | 100 |  |  | 2023-05-05 |  | 2276179 |  |  |  | 223821 | 0.23 | 91.05 | 25/04/22 |  | 7500000 | Yes | Yes
776 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/021/BUILDING/00003 |  |  | 15thCFC-Health 15th CFC/2021-22/021/BUILDING/00003-UPHC Pammal Building 1 No | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/ Tambaram Corporation(Pammal)Dated:17/12/21 | 2021-22 | 2500000 | 2500000 |  |  |  | 0.23 | 20/01/22 | 0.21 | Completed | 100 | Work Completed | 100 |  |  | 2021-04-05 |  | 0 |  |  |  | 2500000 | 0.2 | 80 | 19/07/22 |  | 2500000 | Yes | Yes
777 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/009/PARK/00039 | Zone II | 30 | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/009/PARK/00039-Green space development and Improvements of park at VGN avenue Park 3 Block 41 ward D TS No 11/2 West Tambaram area ward 30 in Tambaram Municipality | Parks | Parks | G.O.(Ms) No. 90 MAWS (NS) Dept.Dated:27/10/21 | 2021-22 | 11700000 | 11700000 | 0 |  |  | 1.17 | 2022-10-01 | 1.08 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 11725267 |  |  |  | -25267 | 1.14 | 97.22 | 18/10/22 |  | 11700000 | No | Yes
778 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00043 | Zone IV | 59 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00043-Greenspace development and improvement to sakthi Nagar park in S. No.12/1A at Peerkanarakani ward No. 59, zone iv in Tambaram City Municipal Corporation | Parks | Parks | 26112/2023Dated:03/01/24 | 2023-24 | 11800000 | 2100000 |  | 0 | 0 | 0.21 | 2024-12-02 | 0.17 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 0 |  |  |  | 2100000 | 0.19 | 88.62 | 2024-12-05 |  | 11800000 | No | Yes
779 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/PARK/00388 | Zone V | 69 | MLA Fund MLA Fund/2021-22/009/PARK/00388-Providing play materials and construction of compound wall at jaihindapuram 6th street Madambakkam ward no.69, | Parks | Parks | 4592/2021/A3-madambakkam-1Dated:02/05/22 | 2021-22 | 1490000 | 1490000 |  |  |  | 0.15 | 2022-08-06 | 0.13 | Completed | 100 | Completed | 100 |  |  | 2023-09-11 |  | 1490000 |  |  |  | 0 | 0.13 | 90 | 2022-09-07 |  | 1490000 | Yes | Yes
780 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00044 | Zone I | 30 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00044-Greenspace development and improvements park at TNHB colony, 2nd cross street, Durga Nagar, ward No.30, zone I in Thiruneermalai Tambaram City Municipal Corporation | Parks | Parks | 26112/2023Dated:03/01/24 | 2023-24 | 11800000 | 2800000 |  | 0 | 0 | 0.09 | 16/02/24 | 0.28 | Completed | 100 | Kerb Wall Work In Progress. | 100 |  |  |  |  | 0 |  |  | 0 | 2800000 | 0.08 | 29 | 2024-12-11 |  | 11800000 | No | Yes
781 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/009/BUILDING/00036 |  |  | 15thCFC-Health 15th CFC/2021-22/009/BUILDING/00036-UPHC Patel Nagar Building 1 No | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/ Tambaram CorporationDated:17/12/21 | 2021-22 | 7500000 | 2500000 | 0 |  | 0 | 0.25 | 25/01/22 | 0.22 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 949181 |  |  |  | 1550819 | 0.23 | 93.38 | 25/04/22 |  | 7500000 | Yes | Yes
782 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/001/BUILDING/00001 |  |  | 15thCFC-Health 15th CFC/2021-22/001/BUILDING/00001-UPHC Sembakkam Building 1 No | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/ Tambaram Corporation(SembakkamDated:17/12/21 | 2021-22 | 2500000 | 2500000 | 0 |  |  | 0.25 | 25/01/22 | 0.23 | Completed | 100 | Completed | 100 |  |  | 29/12/22 |  | 0 |  |  |  | 2500000 | 0.25 | 100 | 25/04/22 |  | 2500000 | Yes | Yes
783 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00197 | Zone I | 3 | MLA Fund MLA/2024-25/009/BUILDING/00197-Construction of VAO office at ward No. 3 zone I in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1000000 |  |  |  | 0 | 26/10/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-05-06 |  | 998390 |  |  |  | 1610 | 0.1 | 99.84 | - |  | 16540000 | Yes | Yes
784 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/007/BUILDING/00072 |  |  | 15thCFC-Health 15th CFC/2021-22/007/BUILDING/00072-UPHC Keezkattalai (old Pallavapuram)- Building- 1 No. | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/Tambaram(Pallavapuram)Dated:17/12/21 | 2021-22 | 10000000 | 2500000 |  |  |  | 0.25 | 25/01/22 | 0.23 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 2500000 |  |  |  | 0 | 0.22 | 89.4 | 25/07/22 |  | 10000000 | Yes | Yes
785 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/CULVERT/00210 | Zone II | 27 | State Disaster Response Fund State Disa/2021-22/009/CULVERT/00210-Construction of RCC culvert at Santhi nagar in ward No.27 | Culverts | Culverts | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 100000 | 0 |  |  | 0.01 | 2022-03-01 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2023-10-05 |  | 94652 |  |  |  | 5348 | 0.01 | 95 | 2022-06-02 |  | 39126000 | Yes | Yes
786 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/CULVERT/00033 | Zone II | 24 | State Disaster Response Fund State Disa/2021-22/007/CULVERT/00033-Constuction of RCC Culvert at Thiruvalluvar Nagar in Ward No.24 | Culverts | Culverts | 31442/2021/e3Dated:15/12/20 | 2021-22 | 41050000 | 450000 |  |  |  | 0.05 | 2022-03-01 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 450000 |  |  |  | 0 | 0.04 | 90.44 | 2022-03-02 |  | 41050000 | Yes | Yes
787 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/CULVERT/00268 | Zone I | 2 | MLA Fund MLA Fund/2021-22/009/CULVERT/00268-Providing Drain and Culvert at Ward No.2 in Anakaputhur | Culverts | Culverts | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 550000 |  |  |  | 0.05 | 2022-08-06 | 0.05 | Completed | 100 | Completed | 100 |  |  | 14/09/24 |  | 550000 |  |  |  | 0 | 0.05 | 98.6 | 2022-08-07 |  | 4710000 | Yes | Yes
788 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2023-24/009/BUILDING/00139 | Zone III | 22 | 15th CFC 15thCFC/2023-24/009/BUILDING/00139-Modernization of Crematorium in GST Road at Hasthinapuram Ponniamman Koil Street in Ward No. 22 | Buildings | Crematorium | 16479/2023/CFCDated:26/05/23 | 2023-24 | 10800000 | 4120000 |  |  |  | 0.41 | 2023-03-11 | 0.4 | Completed | 100 | Completed | 100 |  |  | 2024-10-05 |  | 3853474 |  |  |  | 266526 | 0.38 | 91.1 | 2024-02-03 |  | 10800000 | No | Yes
789 | Tambaram | CGF | CHENGALPATTU | CGF/2019-20/009/BUILDING/00120 |  |  | CGF CGF/2019-20/009/BUILDING/00120-Construction of Gasifier Crematorium in Sembakkam Municipality (Site Changed to Madambakkam) | Buildings | Crematorium | Roc. No.10568/2019/E2Dated:26/04/22 | 2021-22 | 13500000 | 13500000 | 0 |  |  | 0 | 2022-09-05 | 1.28 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13500000 | 1.08 | 79.69 | 2022-10-11 | To be expedited | 13500000 | No | Yes
790 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/007/BUILDING/00073 |  |  | 15thCFC-Health 15th CFC/2021-22/007/BUILDING/00073-UPHC Haridosspuram (Thiru Vi Ka Street) - Building- 1 No. | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/Tambaram(Pallavapuram)Dated:17/12/21 | 2021-22 | 10000000 | 2500000 |  |  |  | 0.23 | 25/01/22 | 0.23 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 2487233 |  |  |  | 12767 | 0.22 | 88.58 | 25/07/22 |  | 10000000 | Yes | Yes
791 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00367 |  |  | MLA Fund MLA Fund/2021-22/009/BUILDING/00367-Construction of Public Distribution shops at Kiskintha road, Samathuva periyar nagar, Annai Anjugam nagar, Indira nagar, Vnkateshwara Nagar extension ,Survey No. 418 in WardNo .55 | Buildings | Other Buildings | 4592/2021/A3-PDS-5Dated:27/04/22 | 2021-22 | 3000000 | 1000000 |  |  |  | 0.1 | 2022-11-07 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 999703 |  |  |  | 297 | 0.1 | 99.97 | 2022-11-10 |  | 3000000 | Yes | Yes
792 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00014 | Zone IV | 33 | MLA Fund MLA Fund/2022-23/009/BUILDING/00014-Construction of VAO building office at Thomas Kulakkarai Street in ward No.33 in Tambaram Corporation | Buildings | Other Buildings | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 1020000 |  | 0 | 0 | 0.1 | 17/04/23 | 0.08 | Completed | 100 | Completed | 100 | 14/02/25 |  | 14/02/25 |  | 1011481 |  |  |  | 8519 | 0 | 0 | 16/06/23 |  | 7500000 | No | Yes
793 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00368 | Zone IV | 59 | MLA Fund MLA Fund/2021-22/009/BUILDING/00368-Construction of PD Shop at Peerkankaranai area in ward No.59 | Buildings | Other Buildings | 4592/2021/A3-PDS-5Dated:27/04/22 | 2021-22 | 3000000 | 1000000 |  |  |  | 0.1 | 2022-11-07 | 0.1 | Completed | 100 | Colour Washing ,Rolling Shutter Fixing ,Electrical Work In Under Progress. | 100 |  |  | 2022-06-12 |  | 998365 |  |  |  | 1635 | 0.1 | 99.84 | 2022-11-10 |  | 3000000 | Yes | Yes
794 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/WSIS/00045 | Zone III | 34 | 15th CFC Tied Grant 15thCFC/2024-25/009/WSIS/00045-Construction of 2.50 LL Capacity Collection well and Motor pump set with Panel board / Operator room at Chitlapakkam 2nd main road OHT near in ward No. 34 in Zone III | Water Supply Improvement Scheme | Const OHT & Sump | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 5150000 |  |  |  | 0 | 2025-11-02 | 0.52 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 5150000 | 0 | 0 | 2025-08-11 |  | 48950000 | No | Yes
795 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/WSIS/00123 | Zone II | 16 | 15th CFC 15th CFC/2021-22/009/WSIS/00123-Construction of 1.00LL Capacity of Ground Level Service Reservoir at Moovarasampettai Abounded Quarry RO Plant in Ward No.16 | Water Supply Improvement Scheme | Const OHT & Sump | ROC No.238Dated:30/09/21 | 2021-22 | 2300000 | 2300000 |  |  |  | 0.23 | 20/12/21 | 0.17 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 2279152 |  |  |  | 20848 | 0.17 | 73.24 | 21/03/22 |  | 2300000 | No | Yes
796 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00189 | Zone II | 14 | General Fund GENERAL/2025-26/009/SWD/00189-Construction of SWD and culvert ar subramanikoil street in ward-14 at zone-II,TCMC | Storm Water Drain | Construction of Drain | 37-4/2025-26Dated:29/08/25 | 2025-26 | 800000 | 800000 |  |  |  | 0 | 26/09/25 | 0.08 | Shuttering | 50 | Completed | 100 |  |  | 23/01/26 |  | 749670 |  |  |  | 50330 | 0 | 0 | 26/12/25 |  | 800000 | No | Yes
797 | Tambaram | IUDM | CHENGALPATTU | IUDM/2020-21/009/SWD/00033 |  |  | IUDM IUDM/2020-21/009/SWD/00033-Construction of Storm water drain with foot path arrangements to krishna Nagar 8th streeet in Tambaram Municipality | Storm Water Drain | Construction of Drain | G.O.(D) 303Dated:09/09/20 | 2020-21 | 98490000 | 29090000 | 0 |  |  | 2.16 | 21/12/20 | 2.64 | Pcc 1:2:4 | 80 | Completed | 100 |  |  | 27/02/25 |  | 23819092 |  |  |  | 5270908 | 3.16 | 108.75 | 14/06/22 |  | 98490000 | No | Yes
798 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2025-26/009/SWD/00414 | Zone IV | 57 | 15th CFC Tied Grant 15thCFC/2025-26/009/SWD/00414-Construction of SWD and Culvert Indira nagar main road in Ward no.57 in Zone-4 (Package No.18) | Storm Water Drain | Construction of Drain | 11919/2022/EA2- DrainDated:11/06/25 | 2025-26 | 200000000 | 1450000 |  |  |  | 0 | 2025-12-09 | 0.15 | Vent Flooring Plastering Work | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1450000 | 0 | 0 | 2025-11-12 |  | 200000000 | No | Yes
799 | Tambaram | National Urban Health Mission | CHENGALPATTU | National U/2021-22/009/BUILDING/00130 | Zone II | 12 | National Urban Health Mission National U/2021-22/009/BUILDING/00130-Construction Additional Block of Primary Health Centre in PV Vaithiyalingam Hospital at Ward No.12 | Buildings | Urban Health And Wellness Center | 157Dated:25/01/22 | 2021-22 | 2500000 | 2500000 |  |  |  | 0.25 | 17/05/22 | 0.22 | Plumbing | 100 | Work Completed | 100 |  |  | 2024-09-09 |  | 2500000 |  |  |  | 0 | 0.22 | 89.24 | 16/11/22 |  | 2500000 | Yes | Yes
800 | Tambaram | CGF | CHENGALPATTU | CGF/2019-20/009/WS/00188 | Zone II | 17 | CGF CGF/2019-20/009/WS/00188-Restoration and Improvement of water bodies as Rain water harvesting Structure- Tiruvengadamudayan Tank in ward 17 of pallavapuram Municipality | Water Supply | Water Bodies | 10586/2019/E1Dated:15/10/19 | 2019-20 | 22300000 | 7500000 |  |  |  | 0.75 | 31/01/20 | 0.68 | Paver Block | 90 | Completed | 100 |  |  | 17/04/23 |  | 7500000 |  |  |  | 0 | 0.65 | 86.4 | 31/10/20 | ... | 22300000 | Yes | Yes
801 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00258 | Zone II | 13 | General Fund GENERAL/2024-25/009/SWD/00258-Construction of drain with culvert and providing cc pavement at kamaraj nagar 5th cross street, 6th cross street in ward-13 at zone-2 , TCMC | Storm Water Drain | Construction of Drain | 538-2 / 2024-25Dated:30/12/24 | 2024-25 | 3500000 | 3500000 |  |  |  | 0 | 21/03/25 | 0.35 | Earth Work | 20 | Completed | 100 |  |  | 2026-05-02 |  | 3453000 |  |  | 0 | 47000 | 0 | 0 | 21/06/25 |  | 3500000 | No | Yes
802 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00259 | Zone II | 17 | General Fund GENERAL/2025-26/009/SWD/00259-Construction of SWD at amman kovil street in ward-17 at zone-2 , TCMC | Storm Water Drain | Construction of Drain | 04-10/2025-26Dated:28/01/26 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 27/10/25 | 0.1 | Earth Work | 20 | Completed | 100 |  |  | 17/02/26 |  | 992640 |  |  | 0 | 7360 | 0 | 0 | 27/01/26 |  | 1000000 | No | Yes
803 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00281 | Zone II | 9 | General Fund GENERAL/2025-26/009/SWD/00281-Construction of SWD and culvert at girfith main road in ward-09 at zone-2 | Storm Water Drain | Construction of Drain | 716-1 / 2025-26Dated:25/08/25 | 2025-26 | 2000000 | 2000000 |  |  |  | 0 | 26/09/25 | 0.2 | Earth Work | 20 | Completed | 100 |  |  | 2026-09-02 |  | 1942260 |  |  | 0 | 57740 | 0 | 0 | 26/12/25 |  | 2000000 | No | Yes
804 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00279 | Zone II | 28 | General Fund GENERAL/2025-26/009/SWD/00279-Raising of drain side wall and providing precast slab at mummurthi nagar 4 th street and 5th street in ward no-28 at zone-2 | Storm Water Drain | Construction of Drain | 271 / 2025-26Dated:28/04/25 | 2025-26 | 850000 | 850000 |  |  |  | 0 | 30/07/25 | 0.09 | Earth Work | 20 | Completed | 100 |  |  | 2026-03-02 |  | 850000 |  |  | 0 | 0 | 0 | 0 | 30/10/25 |  | 850000 | No | Yes
805 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SWD/00010 | Zone II |  | General Fund GENERAL/2024-25/009/SWD/00010-Construction of swd at Rajaji cross st in wd 26 in zone 2 | Storm Water Drain | Construction of Drain | 190-34/19-08-2024Dated:19/08/24 | 2024-25 | 980000 | 980000 |  |  |  | 0 | 16/09/24 | 0.1 | Earth Work | 30 | Completed | 100 |  |  |  |  | 0 |  |  |  | 980000 | 0 | 0 | 16/11/24 |  | 980000 | No | No
806 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00236 | Zone II | 14, 15 | General Fund GENERAL/2025-26/009/SWD/00236-Construction of SWD and culvert at bharathi nagar main road and cc surface at sumbramani koil street in ward 14 & 15 zone-II,TCMC | Storm Water Drain | Construction of Drain | 625-2 / 2025-26Dated:25/08/25 | 2025-26 | 3200000 | 3200000 |  |  |  | 0 | 26/09/25 | 0.32 | Earth Work | 20 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 3200000 | 0 | 0 | 26/12/25 |  | 3200000 | No | Yes
807 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00313 | Zone II | 17 | General Fund GENERAL/2025-26/009/SWD/00313-Construction of RCCdrain at NSK street in ward no-17 in zone-2 | Storm Water Drain | Construction of Drain | 37-11 / 2025-26Dated:29/08/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 26/09/25 | 0.1 | Pcc !:4:8 | 30 | Completed | 100 |  |  | 16/02/26 |  | 801849 |  |  | 0 | 198151 | 0 | 0 | 26/12/25 |  | 1000000 | No | Yes
808 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00180 | Zone II | 14 | General Fund GENERAL/2025-26/009/SWD/00180-Construction of SWD at pathmavathi nagar 1 st street and 2nd street, Nagar street in ward-14 Zone II, TCMC | Storm Water Drain | Construction of Drain | 04-8/2025-26Dated:28/01/26 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 27/10/25 | 0.1 | Pcc !:4:8 | 30 | Completed | 100 |  |  | 23/01/26 |  | 961695 |  |  |  | 38305 | 0 | 0 | 27/01/26 |  | 1000000 | No | Yes
809 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00202 | Zone II | 27 | MLA Fund MLA/2024-25/009/BUILDING/00202-Construction of PDS shop Toilet at ward No. 27 zone II in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0 | 23/10/24 | 0.13 | Plastering | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | - |  | 16540000 | No | Yes
810 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00162 | Zone II | 18, 19 | General Fund GENERAL/2025-26/009/SWD/00162-De-Silting the existing SWD and culvert ar ward 18 & 19 in Zone II, TCMC | Storm Water Drain | Repair and Maintenance of Drain | 35-4/2025-26Dated:29/08/25 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 18/08/25 | 0.09 | M-sand | 50 | Completed | 100 |  |  | 2026-04-02 |  | 895320 |  |  |  | 4680 | 0 | 0 | 18/11/25 |  | 900000 | No | Yes
811 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00163 | Zone II | 16, 17 | General Fund GENERAL/2025-26/009/SWD/00163-De-Silting the existing SWD and culvert ar ward 16 & 17 in Zone II, TCMC | Storm Water Drain | Repair and Maintenance of Drain | 35-3/2025-26Dated:29/08/25 | 2025-26 | 900000 | 900000 |  |  |  | 0 | 18/08/25 | 0.09 | M-sand | 50 | Completed | 100 |  |  | 2026-04-02 |  | 899048 |  |  |  | 952 | 0 | 0 | 18/11/25 |  | 900000 | No | Yes
812 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00048 | Zone V | 63 | MLA Fund MLA/2023-24/009/WSIS/00048-Providing borewell and RO system at Mothilal Nagar, MES Nagar in ward No.63 | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3041/2023/A3-8Dated:08/01/24 | 2023-24 | 4570000 | 1070000 |  |  |  | 0 | 31/01/24 | 0.09 | Electrical Work | 85 | Completed | 100 |  |  | 2025-03-03 |  | 1067441 |  |  |  | 2559 | 0 | 0 | - |  | 4570000 | No | Yes
813 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00010 | Zone II | 20 | MLA Fund MLA/2023-24/009/WS/00010-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at ward No.20, zone II | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 19/01/24 | 0.1 | Electrical Work | 95 | Completed | 100 |  |  | 2025-02-05 |  | 980269 |  |  |  | -10269.06 | 0 | 0 | 19/04/24 |  | 5820000 | No | Yes
814 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00051 | Zone II | 16 | MLA Fund MLA/2023-24/009/WSIS/00051-Providing Borewell with 2000 LPH RO plant at ward NO.16, Zone II, in Tambaram Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3042/2023/A3-7Dated:08/01/24 | 2023-24 | 1940000 | 970000 |  |  |  | 0 | 29/01/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 0 |  |  |  | 970000 | 0 | 0 | 29/04/24 |  | 1940000 | No | Yes
815 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/WSIS/00055 | Zone V | 62 | MLA Fund MLA/2022-23/009/WSIS/00055-Providing RO plant to Irumbuliyur Balaji Nagar Children park in ward No.62, zone V in Tambaram Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 4408/2022/A3-2Dated:27/03/23 | 2022-23 | 3370000 | 1070000 |  |  |  | 0 | - | 0.09 | Completed | 100 | Completed | 100 |  |  | 25/04/24 |  | 1055288 |  |  |  | 14712 | 0 | 0 | - |  | 3370000 | No | Yes
816 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00081 | Zone III | 43 | MLA Fund MLA/2023-24/009/WSIS/00081-Providing RO plant at Chawlas coloney in ward NO.43 Zone III in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 970000 |  |  |  | 0 | 14/06/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 30/04/25 |  | 0 |  |  |  | 970000 | 0 | 0 | 2024-12-09 |  | 11040000 | Yes | Yes
817 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00082 | Zone III | 43 | MLA Fund MLA/2023-24/009/WSIS/00082-Providing RO plant at Bharath avenue in ward NO.43 Zone III in Tambaram City Municipal Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 970000 |  |  |  | 0 | 14/06/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 30/04/25 |  | 0 |  |  |  | 970000 | 0 | 0 | 2024-12-09 |  | 11040000 | Yes | Yes
818 | Tambaram | CGF | CHENGALPATTU | CGF/2019-20/009/WSIS/00121 |  |  | CGF CGF/2019-20/009/WSIS/00121-Construction of 5.00 MLD of Water Treatment Plant 1.50 MLD 2 Nos and 2.00 MLD 1 No from Moovarasampattu and Trisulam Abandoned Quarries | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | G.o.(Ms) No.08,(MAIV)Dated:20/01/20 | 2019-20 | 125000000 | 125000000 |  |  | 0 | 12.5 | 2020-05-08 | 11.6 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 121620790 |  |  |  | 3379210 | 10.33 | 82.62 | 23/01/23 | ... | 125000000 | Yes | Yes
819 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WSIS/00052 | Zone I | 30 | MLA Fund MLA/2023-24/009/WSIS/00052-Providing borewell with RO plant at ward No.30 in Zone I, Tambaram Corporation | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | 3042/2023/A3-7Dated:08/01/24 | 2023-24 | 1940000 | 970000 |  |  |  | 0 | 26/02/24 | 0 | Completed | 100 | Work Completed | 100 |  |  | 2024-08-06 |  | 970000 |  |  |  | 0 | 0 | 0 | - |  | 1940000 | No | Yes
820 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00154 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00154-Construction of 2+2 school building at Ponniamman Corporation Higher secondary school in ward No.17 Pallavaram zone II | Buildings | Additional school building | 21615/2024/ss2Dated:22/07/24 | 2024-25 | 29100000 | 6800000 |  |  |  | 0.41 | 28/10/24 | 0.57 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6800000 | 0.41 | 59.85 | 26/07/25 |  | 29100000 | No | Yes
821 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2017-18/009/BUILDING/00202 |  |  | Chennai River Restoration Trust Chennia Ri/2017-18/009/BUILDING/00202-Construction of Community Toilet in Anakaputhur | Buildings | Construction of Toilet | G,O. Ms. No. 72Dated:12/07/17 | 2017-18 | 3200000 | 3200000 |  |  |  | 0.24 | 2018-01-06 | 0.28 | Completed | 100 | Work Completed | 100 |  |  | 13/12/22 |  | 1300000 |  |  |  | 1900000 | 0.24 | 75.31 | 2018-01-07 |  | 3200000 | Yes | Yes
822 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/PARK/00005 | Zone IV | 56 | MLA Fund MLA/2023-24/009/PARK/00005-Providing Paver block road at Parvathy Nagar, Old Perungalathur, ward No.56, Zone No.IV | Parks | Parks | 3041/2023/A3-4Dated:25/11/23 | 2023-24 | 1100000 | 1100000 |  |  |  | 0.11 | 2024-02-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1042000 |  |  |  | 58000 | 0 | 0 | - |  | 1100000 | No | Yes
823 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00238 | Zone V | 70 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00238-Green Space development at ward No.70, S.F. No. 557/2A , 558/1,2,3,4, 559/2, 3 and 573 Sadhasivam Park at Madambakkam in Tambaram Municipal Corporation in zone V | Parks | Parks | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 3600000 |  |  |  | 0 | 28/11/23 | 0.35 | Completed | 100 | Completed | 100 |  |  | 16/08/24 |  | 3594073 |  |  |  | 5927 | 0 | 0 | - |  | 80000000 | No | Yes
824 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00239 | Zone III | 43 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00239-Green space development at Babu street park ward No.43, S.F. NO. 31/24 of Chitlapakkam area in Tambaram City Municipal Corporation in Zone III | Parks | Parks | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 2800000 |  |  |  | 0 | 28/11/23 | 0.27 | Completed | 100 | Completed | 100 |  |  | 2025-06-02 |  | 0 |  |  |  | 2800000 | 0 | 0 | 24/08/24 |  | 80000000 | No | Yes
825 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00240 | Zone III | 40 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00240-Green space development at Ambedkar street park ward No.40, S.F. No 140/1 of Sembakkam area in Tambaram City Municipal Corporation in Zone III | Parks | Parks | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 4300000 |  |  |  | 0 | 28/11/23 | 0.42 | Completed | 100 | Completed | 100 |  |  | 2024-11-07 |  | 0 |  |  |  | 4300000 | 0 | 0 | 24/08/24 |  | 80000000 | No | Yes
826 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00241 | Zone I | 12 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00241-Development of Green space at Pammal, ward No. 12, S.F. No. 180, 182/1 Mohan street, Samundeswari nagar of Pammal area in Tambaram City Municipal Corporation in zone I | Parks | Parks | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 1100000 |  |  |  | 0.08 | 20/11/23 | 0.11 | Completed | 100 | Completed | 100 |  |  | 22/07/24 |  | 0 |  |  |  | 1100000 | 0.08 | 73.64 | - |  | 80000000 | No | Yes
827 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/PARK/00242 | Zone I | 11 | AMRUT 2.O AMRUT 2.0/2023-24/009/PARK/00242-Development of Green space at Sigamani street ward No.11 S.F.No. 96/1 of Pammal area in Tambaram City Municipal Corporation in Zone I | Parks | Parks | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 1100000 |  |  |  | 0.08 | 20/11/23 | 0.11 | Completed | 100 | Completed | 100 |  |  | 22/07/24 |  | 0 |  |  |  | 1100000 | 0.08 | 73.64 | - |  | 80000000 | No | Yes
828 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/007/PARK/00069 |  |  | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/007/PARK/00069-Providing Park and Play field at Panchayat Market road in Ward No: 27 | Parks | Parks | G.O.(Ms) No.90 MAWS (NS) Dept.Dated:27/10/21 | 2021-22 | 4950000 | 4950000 |  |  |  | 0.5 | 2022-05-01 | 0.44 | Completed | 100 | Completed | 100 | 17/08/22 |  | 2024-09-09 |  | 4431500 |  |  |  | 518500 | 0.41Excel | 82.75 | 2022-06-07 |  | 4950000 | Yes | Yes
829 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2025-26/009/SWM/00366 | Zone IV |  | SBM 2.0 SBM 2.0/2025-26/009/SWM/00366-Construction of Transfer station for Tambaram Corporation at the Location near Kannadapalayam with a capacity of 150 TPD zone IV | Solid Waste Management | SWM | 6450/2024/SBM-1 IIDated:24/03/25 | 2025-26 | 310370000 | 81350000 |  |  |  | 0 | 21/07/25 | 8.14 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 81350000 | 12.4 | 152.48 | 17/04/26 |  | 310370000 | No | Yes
830 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00138 | Zone II | 19 | General Fund GENERAL/2024-25/009/WS/00138-Construction of Sump and Providing Pipe Line with Motor Arrangement at Duraisamy Nagar in Ward No.19 TCMC at Zone-II | Water Supply | Motor PumpSet | 20-13/2024-25Dated:26/03/25 | 2024-25 | 990000 | 990000 |  |  |  | 0 | 25/04/25 | 0.1 | Completed | 100 | Pumpset Purchase | 100 |  |  |  |  | 0 |  |  |  | 990000 | 0 | 0 | 25/07/25 |  | 990000 | No | Yes
831 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/WS/00015 | Zone II | 22, 26 | 15th CFC 15th CFC/2021-22/009/WS/00015-Pallavapuram: Supply and fixing of 35HP,45HP motor, starter, main pipe line connection at santhi Nagar in ward No .26, zone.2, Supply and fixing of 50HP motor, starter at Nanmangalam sub pumping station in ward NO.22, zone No.03 | Water Supply | Motor PumpSet | 21191/AMRUT-2-Tambaram-Tied-2 savingsDated:23/03/22 | 2021-22 | 1910000 | 1910000 |  |  |  | 0.19 | 18/04/22 | 0.17 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 1910000 |  |  |  | 0 | 0.18 | 94.19 | 18/05/22 |  | 1910000 | Yes | Yes
832 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00310 | Zone IV | 50 | MLA Fund MLA Fund/2021-22/009/WS/00310-Providing mini power pump at Rangathapuram 4th street in ward No.50 | Water Supply | Motor PumpSet | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 160000 |  |  |  | 0.02 | 25/05/22 | 0.02 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 151996 |  |  |  | 8004 | 0.02 | 95 | 25/08/22 |  | 5038000 | Yes | Yes
833 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2022-23/009/PARK/00054 | Zone IV |  | MLA Fund MLA/2022-23/009/PARK/00054-Providing Paver block road to Parvathi Nagar park Old Perungalathur inward No.56, Zone IV in Tambaram Corporation | Parks | Foot Path, PlayMaterial and Lighting Arrangement | 4408/2022/A3-2Dated:27/03/23 | 2022-23 | 3370000 | 1100000 |  |  |  | 0.11 | 2024-10-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1042000 |  |  |  | 58000 | 0 | 0 | - |  | 3370000 | No | Yes
834 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2021-22/009/WSIS/00122 |  |  | 15th CFC 15th CFC/2021-22/009/WSIS/00122-Providing and Laying 200 & 160mm PVC Water Supply Pumping Main Line at Moovarasampettai RO Plant to Katcherimalai OHT Tapping Pont | Water Supply Improvement Scheme | Laying of Pumping Main | MCR NO.238 Dt 30.09.2021Dated:30/09/21 | 2021-22 | 2000000 | 2000000 |  |  | 0 | 0.2 | 20/12/21 | 0.16 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 1787953 |  |  |  | 212047 | 0.16 | 80.5 | 21/03/22 |  | 2000000 | Yes | Yes
835 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGD-Intern/2018-19/009/UGSS/00014 | Zone II | 18, 19, 20, 21 | UGD-Internal Plumbing UGD-Intern/2018-19/009/UGSS/00014-Providing Internal connection between inner premises of resident and chamber for house service connection -4825 nos. Ward covered 19,20,21 and 18(p) | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 13531/2018/UGSSDated:07/06/18 | 2018-19 | 345300000 | 64800000 |  |  | 0 | 1.2 | 31/08/18 | 5.87 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 34749987 |  |  |  | 30050013 | 1.1 | 17.01 | 22/02/20 | To be completed by phased manner. | 345300000 | No | Yes
836 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | State Urba/2022-23/009/SL/00460 |  |  | State Urban Infrastructure Development Fund State Urba/2022-23/009/SL/00460-Conversion of existing Street Light into Energy Efficient LED Light - 7636 Nos | Streetlight | Conversion of Existing Lights to LED | Roc No.31757/2022/WB .Dated:04/11/22 | 2022-23 | 96927000 | 96927000 |  |  |  | 6.7 | 23/02/23 | 9.32 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 96927000 | 8.5 | 87.67 | 2024-11-02 | ... | 96927000 | No | Yes
837 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | State Urba/2022-23/009/SL/00461 |  |  | State Urban Infrastructure Development Fund State Urba/2022-23/009/SL/00461-Conversion of existing Street Light into Energy Efficient LED Light - 7582 Nos | Streetlight | Conversion of Existing Lights to LED | Roc No.31757/2022/WBDated:04/11/22 | 2022-23 | 97470000 | 97470000 | 0 |  | 0 | 8.91 | 23/02/23 | 9.37 | Completed | 100 | Completed | 100 | 23/10/23 |  | 26/11/24 |  | 0 |  |  |  | 97470000 | 8.91 | 91.36 | 2024-11-02 | ... | 97470000 | No | Yes
838 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | State Urba/2022-23/009/SL/00462 |  |  | State Urban Infrastructure Development Fund State Urba/2022-23/009/SL/00462-Conversion of existing Street Light into Energy Efficient LED Light - 7080 Nos | Streetlight | Conversion of Existing Lights to LED | Roc No.31757/2022/WB.Dated:04/11/22 | 2022-23 | 99514000 | 99514000 |  |  |  | 8.82 | 23/02/23 | 9.58 | Completed | 100 | Completed | 100 |  |  | 26/11/24 |  | 0 |  |  |  | 99514000 | 8.82 | 88.63 | 2024-11-02 | ... | 99514000 | No | Yes
839 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | State Urba/2022-23/009/SL/00463 |  |  | State Urban Infrastructure Development Fund State Urba/2022-23/009/SL/00463-Conversion of existing Street Light into Energy Efficient LED Light - 7611 Nos | Streetlight | Conversion of Existing Lights to LED | Roc No.31757/2022/WB ,Dated:04/11/22 | 2022-23 | 97028000 | 97028000 |  |  |  | 2.35 | 23/02/23 | 9.33 | Completed | 100 | Completed | 100 | 25/10/24 |  | 26/11/24 |  | 0 |  |  |  | 97028000 | 2.35 | 24.17 | 2024-11-02 | ... | 97028000 | No | Yes
840 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | State Urba/2022-23/009/SL/00459 |  |  | State Urban Infrastructure Development Fund State Urba/2022-23/009/SL/00459-Conversion of existing Street Light into Energy Efficient LED Light - 7894 Nos | Streetlight | Conversion of Existing Lights to LED | Roc No.31757/2022/WB..Dated:04/11/22 | 2022-23 | 92395000 | 92395000 |  |  |  | 4.62 | 23/02/23 | 8.88 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 92395000 | 8.07 | 87.33 | 2024-01-11 | ... | 92395000 | Yes | Yes
841 | Tambaram | IUDM | CHENGALPATTU | IUDM/2020-21/009/SWD/00024 | Zone I | 1, 2 | IUDM IUDM/2020-21/009/SWD/00024-Construction of Intersection and diversion storm water drain from ward no.02 north kulakkarai street to erikkarai street in ward no.01 via w-3,4,5,6,7,8 and 9 in Tambaram Municipality | Storm Water Drain | Construction of Drain | G.O.(D) 303Dated:09/09/20 | 2020-21 | 98490000 | 50500000 | 0 |  |  | 5.05 | 21/12/20 | 4.52 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 35915612 |  |  |  | 14584388 | 5.24 | 103.8 | 14/06/22 |  | 98490000 | Yes | Yes
842 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00055 | Zone II | 21 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00055-Construction of Cut and cover RCC drain at IAF road west side from Agaram main road to IAF gate culvert (Both sides) in ward No.21 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Tambaram - 2Dated:18/04/22 | 2022-23 | 63500000 | 63500000 |  |  |  | 5.72 | 13/06/22 | 4.97 | Completed | 100 | Completed | 100 |  |  | 18/09/24 |  | 64444490 |  |  |  | -944490 | 5.61 | 88.38 | 2023-05-12 |  | 63500000 | Yes | Yes
843 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00048 | Zone II | 21 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00048-Construction of RCC Strom Water Drain with Cover Slab and Culvert at Nethaji Nagar Main Road, Nethaji Nagar 1st,2nd Street, Odai Street and Nethaji Nagar 1st Cross Street in Ward No.21 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pallavapuram - 3Dated:18/04/22 | 2022-23 | 11700000 | 11700000 | 0 |  |  | 1.05 | 13/06/22 | 0.99 | Completed | 100 | Completed | 100 |  |  | 2023-06-01 |  | 11699056 |  |  |  | 944 | 0.99 | 84.62 | 2023-10-03 |  | 11700000 | No | Yes
844 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00053 | Zone II | 18 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00053-Construction of RCC Strom Water Drain with Cover Slab and Culvert at Ganesh Nagar, Muthusamy Nagar Main Road and Sindhu Street in Ward No.18 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pallavapuram - 4Dated:18/04/22 | 2022-23 | 9900000 | 9900000 |  |  |  | 0.89 | 13/06/22 | 0.82 | Completed | 100 | Completed | 100 | 30/06/22 |  | 2023-06-01 |  | 9852836 |  |  |  | 47164 | 0.84 | 85.1 | 2023-10-03 |  | 9900000 | No | Yes
845 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00052 |  |  | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00052-Construction of Retaining Wall @ Nadavai Odai Both Side (320 x 2) | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pammal - 1Dated:18/04/22 | 2022-23 | 12000000 | 12000000 | 0 | 0 |  | 1.08 | 13/06/22 | 1.03 | Completed | 100 | Completed | 100 |  |  | 30/08/23 |  | 11787666 |  |  |  | 212333.87 | 1.03 | 86.2 | 2022-11-09 |  | 12000000 | No | Yes
846 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00057 |  |  | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00057-Construction of Storm Water Drain at 41st street to Sengazhuneermalai abandoned Quarry | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pammal - 2Dated:18/04/22 | 2022-23 | 15000000 | 15000000 |  |  |  | 1.35 | 13/06/22 | 1.29 | Completed | 100 | Completed | 100 | 2022-01-09 |  | 30/08/23 |  | 14286834 |  |  |  | 713166.23 | 1.19 | 79.33 | 2022-11-09 |  | 15000000 | Yes | Yes
847 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00051 |  |  | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00051-Construction of Storm Water Drain @ Bharathidasan Street, Periyar Street, Muthuswamy Street and Kamarajar Salai | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pammal - 3Dated:18/04/22 | 2022-23 | 13000000 | 13000000 |  |  |  | 1.17 | 13/06/22 | 1.12 | Completed | 100 | Completed | 100 |  |  | 30/08/23 |  | 12808852 |  |  |  | 191147.81 | 0.55 | 42.03 | 2022-11-09 |  | 13000000 | No | Yes
848 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00058 |  |  | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00058-Construction of Storm water drain with coverslab at pump houseroad wd. No.2 , mettu street wd.No. 3,Venkateswara Nagar Thiruvalluvar street ,Kasthuribai nagar & Gurusamy Nagar 4thmainroadwd.No.4, Anna Nagar main Road, AnnaNagar 2ndMainRoad and 4thmain roadwd.no 7, Devaraj Nagar wd. No. 13 E.B Colony Wd. No. 15 , Thendralnagar wd.No.16,Paari Nagarganapathy street ,Senguttuvan street and Rajaji street wd.no. 17 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I AnakaputhurDated:18/04/22 | 2022-23 | 45400000 | 45400000 |  |  |  | 4.09 | 13/06/22 | 3.91 | Completed | 100 | Completed | 100 |  |  | 30/08/23 |  | 31504843 |  |  |  | 13895157.1 | 2.72 | 59.92 | 2022-11-09 |  | 45400000 | Yes | Yes
849 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00074 | Zone III | 42 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00074-Construction of RCC Storm Water Drain at Maruthi Nagar main road, Maruthi Nagar 1st main road, Venugopal samy street and Vallal yusuf street (Disposal at Sembakkam lake) in ward No.42, zone no. 3 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 30000000 |  | 0 | 0 | 2.7 | 2023-07-06 | 2.92 | Completed | 100 | Completed | 100 | 13/08/23 |  | 16/05/24 |  | 29998885 |  |  |  | 1115 | 2.7 | 89.99 | 28/11/24 |  | 375900000 | No | Yes
850 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00075 | Zone III | 41 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00075-Construction of RCC storm water drain at Sridevi avenue to Tellus avenue 5th main rod (disposal at Vengaivasal eri) via (Tellus avenue phase II main road, Radhe shyam avanue main road to teelus avenue 4th main road in ward No.41 in zone No. 3 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 36000000 |  |  |  | 3.24 | 2023-07-06 | 3.5 | Completed | 100 | Completed | 100 | 2023-08-12 |  | 15/05/24 |  | 36000000 |  |  |  | 0 | 3.24 | 90 | 2023-04-12 |  | 375900000 | No | Yes
851 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00076 | Zone V | 67 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00076-Construction of RCC Storm Water Drain from Brindhavan Nagar main road to Vengaivasal eri in ward No.67 , Zone No. 5 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 70200000 |  |  |  | 6.32 | 2023-07-06 | 6.71 | Completed | 100 | Completed | 100 | 31/10/23 |  | 19/04/24 |  | 69912798 |  |  |  | 287202 | 6.3 | 89.74 | 2023-06-09 |  | 375900000 | No | Yes
852 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00077 | Zone III | 16, 17, 20 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00077-Construction of RCC Storm Water Drain with Cover slab to Jain Nagar 1st street, Jain Nagar 2nd street, Seetharaman street, jain Nagar main road, Cauveri street, Ganga street, Sriram Nagar 1st main road in ward No.16,17,20 zone No. 3 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 38000000 |  |  |  | 3.42 | 2023-07-06 | 3.7 | Completed | 100 | Completed | 100 |  |  | 14/05/24 |  | 38000000 |  |  |  | 0 | 3.38 | 88.84 | 28/11/24 |  | 375900000 | No | Yes
853 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00078 | Zone II | 17 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00078-Construction of RCC Storm Water Drain at Pallava salai, Amarvathy street, Sankara salai, Balaji salai, Sankaran salai Ext., (subbammal street), Balaji slaai 1st cross street in ward No. 17, Zone No. 2 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 29800000 |  |  |  | 2.68 | 2023-09-06 | 2.88 | Completed | 100 | Completed | 100 | 20/11/23 |  | 24/05/24 |  | 29865658 |  |  |  | -65658.24 | 2.63 | 88.34 | 30/11/24 |  | 375900000 | Yes | Yes
854 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00079 | Zone I | 8 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00079-Construction of RCC storm water drain with cover slab at Manimegalai street, Anandan street and madhvai street in ward No.08, Zone No. I | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 9700000 |  |  |  | 0.87 | 13/06/23 | 0.91 | Completed | 100 | Completed | 100 | 25/02/25 |  | 2025-07-05 |  | 9300000 |  |  |  | 400000 | 0.82 | 84.57 | 2024-09-03 |  | 375900000 | No | Yes
855 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00080 | Zone 01 | 2 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00080-Construction of RCC drain with Cover slab at Gurusamy Nagar main road and Gurusamy nagar 7th street in ward No.02, zone No. 01 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 15600000 |  |  |  | 1.4 | 2023-09-06 | 1.48 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 15600000 |  |  |  | 0 | 1.37 | 87.95 | 2024-05-03 |  | 375900000 | No | Yes
856 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00081 | Zone III |  | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00081-Construction of RCC SWD with Cover slab at Thirumalai Nagar 1st main road in wad No.22 and 39, zone No.3 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 34000000 |  |  |  | 3.06 | 2023-07-06 | 3.31 | Completed | 100 | Completed | 100 |  |  | 14/05/24 |  | 33998176 |  |  |  | 1824 | 3.06 | 89.93 | 28/11/24 |  | 375900000 | No | Yes
857 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00082 | Zone IV | 56 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00082-Construction of Storm water drain to Kurinji Nagar main road Raja Rajeshwari Nagar (via) Gandhi Nagar (near Tambaram Mudichur road) ward No. 56, Zone 4 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 21300000 |  |  |  | 1.92 | 2023-09-06 | 2.04 | Completed | 100 | Completed | 100 |  |  | 2024-05-02 |  | 21242756 |  |  |  | 57244 | 1.79 | 83.8 | 2024-03-12 |  | 375900000 | No | Yes
858 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00083 | Zone V | 65 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00083-Construction of RCC storm water IAF road and Channel from Selaiyur Eri surplus in ward No.65, zone 5 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 28300000 |  |  |  | 2.55 | 2023-07-06 | 2.73 | Completed | 100 | Completed | 100 | 30/08/23 |  | 24/04/24 |  | 26782094 |  |  |  | 1517906 | 2.55 | 90 | 30/11/24 |  | 375900000 | No | Yes
859 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00084 | Zone III | 44 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00084-Construction of cut and cover drain at Subachandrabose street from Vinayagar street, pandiyan street, Bhavani street (disposal of existing cut and cover drain at Maruthupandiar street) in ward No.44 zone No.3 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 32900000 |  |  |  | 2.96 | 2023-07-06 | 2.71 | Completed | 100 | Completed | 100 |  |  | 27/05/24 |  | 32899777 |  |  |  | 223 | 2.96 | 89.95 | 28/11/24 |  | 375900000 | No | Yes
860 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00085 | Zone II | 20, 21 | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00085-Construction of RCC storm water drain at MK Nagar in ward No.20, AGS nagar, Sammy malai Nagarand Nadesan salai in ward No.20,21 , Zone No.2 | Storm Water Drain | Construction of Drain | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 28500000 |  |  |  | 2.85 | 2023-09-06 | 2.73 | Completed | 100 | Completed | 100 |  |  | 2025-12-05 |  | 24469980 |  |  |  | 4030020 | 2.45 | 85.86 | 30/11/24 |  | 375900000 | Yes | Yes
861 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/SWD/00231 | Zone V | 46 | Namakku Naame Thittam NNT/2022-23/009/SWD/00231-Construction of Storm Water Drain at Mahalakshmi street in ward No. 46, zone V | Storm Water Drain | Construction of Drain | 23182/2023/P2-2Dated:17/08/23 | 2022-23 | 10112000 | 4652000 |  |  |  | 0.46 | 17/10/23 | 0.39 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 4599000 |  |  |  | 53000 | 0.43 | 91.67 | - |  | 10112000 | No | Yes
862 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00068 | Zone III | 43 | General Fund GENERAL/2025-26/009/SWD/00068-Construction of Storm water Drain And Culvert To Yamuna Street in Ward No.43 in Zone III | Storm Water Drain | Construction of Drain | 84-3Dated:17/02/25 | 2025-26 | 570000 | 570000 |  |  |  | 0 | 15/05/25 | 0.06 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 570000 | 0 | 0 | 22/08/25 |  | 570000 | No | Yes
863 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00042 | Zone II | 16 | General Fund GENERAL/2025-26/009/SWD/00042-Construction of RCC SWD Rajiv Gandhi Street to Ambedkar Street and Culvert at Thiruvalluvar Street in Ward No.16,Tambaram City Municipal Corporation ,Zone II | Storm Water Drain | Construction of Drain | 716 S.No.03Dated:25/08/25 | 2025-26 | 2550000 | 2550000 |  |  |  | 0 | 26/09/25 | 0.26 | Completed | 100 | Completed | 100 |  |  | 2025-10-12 |  | 2525888 |  |  |  | 24111.51 | 0 | 0 | 26/12/25 |  | 2550000 | No | Yes
864 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00056 | Zone II | 21 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00056-Construction of Cut and cover RCC drain at Ricky garden from IAF road to Thiruvancheri lake in ward No.21 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Tambaram - 4Dated:18/04/22 | 2022-23 | 54500000 | 54500000 |  |  |  | 4.91 | 13/06/22 | 4.45 | Completed | 100 | Completed | 100 | 2023-06-04 |  | 30/08/23 |  | 31159485 |  |  |  | 23340515 | 3.56 | 65.33 | 2022-11-09 |  | 54500000 | Yes | Yes
865 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00050 | Zone III | 39 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00050-Construction of RCC Strom Water Drain with Cover Slab and Culvert at New Colony 13th Cross Street and Extn and Grand Palace Lane in Ward No.39 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Pallavapuram - 1Dated:18/04/22 | 2022-23 | 17650000 | 17650000 |  |  |  | 1.59 | 13/06/22 | 1.43 | Completed | 100 | Completed | 100 |  |  | 30/08/23 |  | 10772410 |  |  |  | 6877589.51 | 0.92 | 52.32 | 2023-10-03 |  | 17650000 | Yes | Yes
866 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00049 | Zone I | 1 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00049-Construction of Cut and cover RCC drain from Kadaperi Kalangal to Idumban Lake in ward No.01 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Tambaram - 1Dated:18/04/22 | 2022-23 | 39000000 | 39000000 |  |  |  | 3.51 | 13/06/22 | 3.12 | Completed | 100 | Completed | 100 | 16/08/22 |  | 30/08/23 |  | 38369098 |  |  |  | 630902 | 3.17 | 81.34 | 2022-11-09 |  | 39000000 | No | Yes
867 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | State Disa/2022-23/009/SWD/00059 | Zone I | 7, 8 | State Disaster Mitigation Fund State Disa/2022-23/009/SWD/00059-Construction of Cut and cover RCC drain at Babuji street to Kadharbai street in ward No.08,07 | Storm Water Drain | Construction of Drain | 10383/2021/E3 I Tambaram - 3Dated:18/04/22 | 2022-23 | 12000000 | 12000000 |  |  |  | 0 | 13/06/22 | 1.2 | Completed | 100 | Completed | 100 | 17/08/22 |  | 30/08/23 |  | 12866741 |  |  |  | -866741 | 1.19 | 99.05 | 2022-11-09 |  | 12000000 | Yes | Yes
868 | Tambaram | State Disaster Mitigation Fund | CHENGALPATTU | SDMF/2023-24/009/SWD/00086 | Zone I |  | State Disaster Mitigation Fund SDMF/2023-24/009/SWD/00086-Construction of Retaining wall at Nadavai odai in Zone No. 1 | Storm Water Drain | Retaining Wall of SWD | 14293/2022/SS3Dated:06/04/23 | 2023-24 | 375900000 | 1600000 |  |  |  | 0.14 | 13/06/23 | 0.15 | Completed | 100 | Completed | 100 |  |  | 2022-09-05 |  | 1439897 |  |  |  | 160103 | 0.14 | 89.99 | 2024-09-03 |  | 375900000 | No | Yes
869 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00269 |  |  | MLA Fund MLA Fund/2021-22/009/WS/00269-Providing Foot path and LED Light at Sooriyamman Lake in Pammal | Water Supply | Water Bodies | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 1000000 | 0 |  |  | 0.1 | 2022-08-06 | 0.09 | Completed | 100 | Completed | 100 | 2022-08-09 |  | 14/10/22 |  | 1534621 |  |  |  | -534621 | 0.1 | 99.29 | 2022-06-09 |  | 4710000 | Yes | Yes
870 | Tambaram | CGF | CHENGALPATTU | CGF/2019-20/009/WS/00187 | Zone II | 12 | CGF CGF/2019-20/009/WS/00187-Restoration and Improvement of water bodies as Rain water harvesting Structure- Palkeni Kulam in ward 12 of pallavapuram Municipality | Water Supply | Water Bodies | 10586/2019/E1Dated:15/10/19 | 2019-20 | 22300000 | 9200000 |  |  |  | 0.92 | 31/01/20 | 0.85 | Completed | 0 | Work Completed | 100 | 2020-07-05 |  | 26/02/25 |  | 9200000 |  |  |  | 0 | 0.73 | 78.97 | 31/10/20 |  | 22300000 | Yes | Yes
871 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00177 | Zone I | 3 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00177-Construction of urinal at Anakaputhur Bazaar st, Ward 3, Zone-1 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 | 0 |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 |  | 100 |  |  | 16/09/24 |  | 135000 |  |  |  | 0 | 0.01 | 82.96 | 2022-01-12 |  | 2160000 | No | Yes
872 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00178 | Zone I | 31 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00178-Construction of urinal at thiruneermalai main road, near Perumal koil , Ward 31, Zone-1 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 | 0 |  |  | 0.02 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 20/03/23 |  | 134810 |  |  |  | 190 | 0.01 | 100 | 2022-01-12 |  | 2160000 | Yes | Yes
873 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00179 | Zone V | 69 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00179-Construction of urinal at Pathuvancherry , Ward 69, Zone-5 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 134000 |  |  |  | 1000 | 0.01 | 90.86 | 2022-01-12 |  | 2160000 | Yes | Yes
874 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00180 | Zone IV | 61 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00180-Construction of urinal at Perungulathur bus stand , Peerkankaranai, Ward 61, Zone-4 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 1 |  |  |  | 134998.68 | 0.01 | 87.43 | 30/12/22 |  | 2160000 | Yes | Yes
875 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00124 | Zone II | 28 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00124-Construction of Urinals at MIT Bridge under , ward No.28 Zone II in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0.01 | 21/06/24 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2025-06-01 |  | 128700 |  |  |  | 1300 | 0.01 | 99 | 21/09/24 |  | 35640000 | Yes | Yes
876 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00125 | Zone II | 20 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00125-Construction of Urinals at Keelkattalai Eri , ward No.20 Zone II in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0.01 | 21/06/24 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2025-06-01 |  | 128700 |  |  |  | 1300 | 0.01 | 99 | 21/09/24 |  | 35640000 | Yes | Yes
877 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00122 | Zone II | 21 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00122-Construction of Urinals at Vels college zone , ward No.21 Zone II in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0.01 | 21/06/24 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2025-06-01 |  | 128700 |  |  |  | 1300 | 0.01 | 99 | 21/09/24 |  | 35640000 | Yes | Yes
878 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00128 | Zone IV | 49 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00128-Construction of Urinals at Near HINDU MISSION , ward No.49 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | URINALS | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 130000 |  |  |  | 0 | 2024-02-07 | 0.01 | Completed | 100 | Completed | 100 |  |  | 16/06/25 |  | 0 |  |  |  | 130000 | 0.01 | 39.52 | - |  | 35640000 | No | Yes
879 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00165 | Zone IV | 49 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00165-Construction of urinal at Rajaji salai, Ward 49 Zone-4 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 | 0 |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2024-11-09 |  | 1 |  |  |  | 134998.93 | 0.01 | 79.55 | 2022-01-12 |  | 2160000 | Yes | Yes
880 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00166 | Zone III | 33 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00166-Construction of urinal at Railway station ( near MCC college) , Ward 33 , Zone-3 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.02 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 134000 |  |  |  | 1000 | 0.01 | 89.35 | 2022-01-12 |  | 2160000 | Yes | Yes
881 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00167 | Zone V | 45 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00167-Construction of urinal at Camp road junction , Ward 45, Zone-5 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.02 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 134000 |  |  |  | 1000 | 0.01 | 99.22 | 2022-01-12 |  | 2160000 | Yes | Yes
882 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00168 | Zone IV | 33 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00168-Construction of urinal at GST Road, near Taluk office , Ward 33, Zone-4 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 1 |  |  |  | 134998.73 | 0.01 | 84.05 | 2022-01-12 |  | 2160000 | Yes | Yes
883 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00169 | Zone V | 48 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00169-Construction of urinal at bharata matha salai , Ward 48, Zone-5 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 134000 |  |  |  | 1000 | 0.01 | 90.45 | 2022-01-12 |  | 2160000 | Yes | Yes
884 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00170 | Zone IV | 49 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00170-Construction of urinal at market road shanmugam salai, Ward 49, Zone-4 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 1 |  |  |  | 134998.92 | 0.01 | 79.99 | 2022-01-12 |  | 2160000 | Yes | Yes
885 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00172 | Zone II | 13 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00172-Construction of urinal near pallavaram bus stand , Ward 13, Zone-2 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 15/03/23 |  | 127666 |  |  |  | 7334 | 0.01 | 83.53 | 29/05/23 |  | 2160000 | Yes | Yes
886 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00173 | Zone II | 28 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00173-Construction of urinal at Chrompet post office , Ward 28, Zone-2 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 | 0 |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 127700 |  |  |  | 7300 | 0.01 | 94.59 | 2022-01-09 |  | 2160000 | Yes | Yes
887 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00174 | Zone III | 26 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00174-Construction of urinal at near radha nagar market , Ward 26, Zone-3 | Sanitation Work | URINALS | 5990/2022/SBM-5Dated:11/04/22 | 2021-22 | 2160000 | 135000 |  |  |  | 0.01 | 2022-01-09 | 0.01 | Completed | 100 | Completed | 100 |  |  | 2023-05-05 |  | 0 |  |  |  | 135000 | 0.01 | 84.4 | 2022-02-12 |  | 2160000 | Yes | Yes
888 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00153 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00153-Construction of 2+2nos of school building at Ponniamman Corporation Primary school in ward No.17,Pallavapuram, zone ii | Buildings | Additional school building | 21615/2024/ss2Dated:22/07/24 | 2024-25 | 29100000 | 6800000 |  |  |  | 0 | 23/09/24 | 0.57 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6800000 | 0.14 | 20.65 | 20/06/25 |  | 29100000 | Yes | Yes
889 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/WS/00181 | Zone II | 20 | General Fund GENERAL/2025-26/009/WS/00181-Providing pipe line at moovarasanpat quarry to RO plant at ward-20 Zone II, TCMC | Water Supply | Water supply - Internal Plumbing | 37-15/2025-26Dated:29/08/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 26/09/25 | 0.1 | Pipe Laid | 50 | Completed | 100 |  |  | 27/10/25 |  | 990946 |  |  |  | 9054 | 0 | 0 | 26/12/25 |  | 1000000 | No | Yes
890 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00199 | Zone 05 | 48 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00199-Providing CCTV surveillance Camera in ward No.48, Zone 05 in Tambaram City Municipal Corporation | Others | CCTV Installation | 8880/2022/P1-3Dated:07/07/23 | 2022-23 | 5325000 | 575000 |  |  |  | 0.06 | 2023-05-09 | 0.05 | Pole Erection | 60 | Completed | 100 |  |  | 2025-05-05 |  | 569922 |  |  |  | 5078 | 0 | 0 | - |  | 5325000 | No | Yes
891 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00174 | Zone II | 14 | MLA Fund MLA/2025-26/009/OTHERS/00174-Supply of CC TV (camera) to Zone II ward No.14 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 500000 |  |  |  | 0 | 2025-04-08 | 0.05 | Laying Of Power Cable And Fixing Of Switches | 50 | Completed | 100 |  |  | 2025-09-10 |  | 495959 |  |  |  | 4041 | 0 | 0 | 2025-04-11 |  | 7100000 | No | Yes
892 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00175 | Zone II | 15 | MLA Fund MLA/2025-26/009/OTHERS/00175-Supply of CC TV (camera) to Zone II ward No.15 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 500000 |  |  |  | 0 | 2025-04-08 | 0.05 | Ctv Camera Fixing | 50 | Completed | 100 |  |  | 2025-07-10 |  | 498776 |  |  |  | 1224 | 0 | 0 | 2025-04-11 |  | 7100000 | No | Yes
893 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/OTHERS/00176 | Zone II | 24 | MLA Fund MLA/2025-26/009/OTHERS/00176-Supply of CC TV (camera) to Zone II ward No.24 in Tambaram Corporation at Pallavaram Constituency | Others | CCTV Installation | 0983/2025/A3Dated:09/06/25 | 2025-26 | 7100000 | 500000 |  |  |  | 0 | 2025-04-08 | 0.05 | Ctv Camera Fixing | 50 | Completed | 100 |  |  | 2025-09-10 |  | 495959 |  |  |  | 4041 | 0 | 0 | 2025-04-11 |  | 7100000 | No | Yes
894 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00103 | Zone III | 43 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00103-Providing CCTV camera arragements to main roads at ward No.43 in zone 3 | Others | CCTV Installation | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 720000 |  |  |  | 0 | 14/06/23 | 0.07 | Ctv Camera Fixing | 10 | Completed | 100 |  |  | 23/03/24 |  | 712415 |  |  |  | 7585 | 0 | 0 | 2023-12-09 |  | 15130000 | No | Yes
895 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00104 | Zone V | 64 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00104-Providing CCTV camera arrangements to main roads at ward No.64 zone 5 | Others | CCTV Installation | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 440000 |  |  |  | 0.04 | 14/06/23 | 0.04 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 427529 |  |  |  | 12471 | 0 | 0 | - |  | 15130000 | Yes | Yes
896 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00260 | Zone I | 8 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00260-Installation of surveillance cameras in major main roads in zone No.I ward No. 08- (5 camera with DVR) | Others | CCTV Installation | 23182/2023/P2-3Dated:09/10/23 | 2022-23 | 2640000 | 540000 |  |  |  | 0 | 24/11/23 | 0.05 | Completed | 100 | Completed | 100 |  |  | 25/03/24 |  | 538170 |  |  |  | 1830 | 0.05 | 89.79 | - |  | 2640000 | Yes | Yes
897 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00004 | Zone II | 28 | MLA Fund MLA/2024-25/009/OTHERS/00004-Providing CCTV camera at ward No.28 @ Zone II in Tambaram City Municipal Corporation | Others | CCTV Installation | 1695/2024/A3 24.10.24Dated:24/10/24 | 2024-25 | 1900000 | 600000 |  |  |  | 0.06 | - | 0.06 | Completed | 100 | Completed | 100 |  |  | 2025-02-05 |  | 599335 |  |  |  | 665 | 0.06 | 99.89 | - |  | 1900000 | Yes | Yes
898 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00228 | Zone I | 3 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00228-Supply and fixing closed circuit camera at ward No.03, Zone No. I | Others | CCTV Installation | 23182/2023/P2-2Dated:17/08/23 | 2022-23 | 10112000 | 450000 |  |  |  | 0 | 16/10/23 | 0 | Completed | 100 | Completed | 100 |  |  | 25/06/24 |  | 420000 |  |  |  | 30000 | 0.04 | 89.82 | - |  | 10112000 | No | Yes
899 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00229 | Zone V | 67 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00229-Providing CCTV camera at Dhenugambal Nagar 1st street and Dhenugambal Nagar 2nd street in ward No.67 zone V | Others | CCTV Installation | 23182/2023/P2-2Dated:17/08/23 | 2022-23 | 10112000 | 300000 |  |  |  | 0.03 | 20/09/23 | 0.02 | Completed | 100 | Completed | 100 |  |  | 2024-09-02 |  | 297882 |  |  |  | 2118 | 0.03 | 90 | - |  | 10112000 | No | Yes
900 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/OTHERS/00102 | Zone V | 45 | Namakku Naame Thittam NNT/2022-23/009/OTHERS/00102-Providing CCTV camera arrangements to main roads at ward No.45 in zone 5 | Others | CCTV Installation | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 1150000 |  |  |  | 0.12 | 2023-12-06 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 1140000 |  |  |  | 10000 | 0.11 | 99.12 | 27/07/23 |  | 15130000 | Yes | Yes
901 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00007 | Zone II | 16 | MLA Fund MLA/2024-25/009/OTHERS/00007-Providing CCTC at ward No.16 , Zone II in Tambaram City Municipal Corporation | Others | CCTV Installation | 1695/2024/A3-2Dated:24/10/24 | 2024-25 | 1550000 | 300000 |  |  |  | 0.03 | - | 0.03 | Completed | 100 | Completed | 100 |  |  | 2025-02-05 |  | 294137 |  |  |  | 5863 | 0.03 | 98.05 | - |  | 1550000 | Yes | Yes
902 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00008 | Zone II | 17 | MLA Fund MLA/2024-25/009/OTHERS/00008-Providing CCTC at ward No.17 , Zone II in Tambaram City Municipal Corporation | Others | CCTV Installation | 1695/2024/A3-2Dated:24/10/24 | 2024-25 | 1550000 | 750000 |  |  |  | 0.08 | - | 0.07 | Completed | 100 | Completed | 100 |  |  | 2025-02-05 |  | 738979 |  |  |  | 11021 | 0.07 | 98.53 | - |  | 1550000 | Yes | Yes
903 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/OTHERS/00009 | Zone II | 21 | MLA Fund MLA/2024-25/009/OTHERS/00009-Providing CCTC at ward No.21 , Zone II in Tambaram City Municipal Corporation | Others | CCTV Installation | 1695/2024/A3-2Dated:24/10/24 | 2024-25 | 1550000 | 500000 |  |  |  | 0.05 | - | 0.05 | Completed | 100 | Completed | 100 |  |  | 2025-02-05 |  | 497807 |  |  |  | 2193 | 0.05 | 99.56 | 25/08/25 |  | 1550000 | Yes | Yes
904 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00326 |  |  | General Fund GENERAL/2025-26/009/ROAD/00326-Repair /Maintenance-BT and CC Road- , | Roads | BT and CC Road | 914-4 / 2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 28/11/25 | 0.25 | Earth Work | 20 | Completed | 100 |  |  | 19/02/26 |  | 2500000 |  |  | 0 | 0 | 0 | 0 | 28/02/26 |  | 2500000 | No | Yes
905 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00327 |  |  | General Fund GENERAL/2025-26/009/ROAD/00327-Repair /Maintenance-BT and CC Road- , | Roads | BT and CC Road | 914-3 / 2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 28/11/25 | 0.25 | Earth Work | 20 | Completed | 100 |  |  | 2026-09-02 |  | 2500000 |  |  | 0 | 0 | 0 | 0 | 28/02/26 |  | 2500000 | No | Yes
906 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00145 |  |  | General Fund GENERAL/2025-26/009/ROAD/00145-Repair /Maintenance-BT and CC Road- , | Roads | BT and CC Road | 627-1/2025-26Dated:25/08/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 18/08/25 | 0 | Earth Work | 50 | Completed | 100 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 18/11/25 |  | 2500000 | No | Yes
907 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00248 |  |  | SRP SRP/2020-21/009/ROAD/00248-Relaying of Road-Providing B.T. Surface at Fathima Manzil Street, Hassan Basha Street, Nagarathinam street, Bharathi Nagar 2nd Cross Street, Pillaiyar Kovil street, Siva Sankaran Street, Nsk Street Kalaivanar Street and CC Road at Metro Pumping Station, Narayanasamy Pillai Street, Nehru street, New Street, Chavadi Street, Arunthathipuram 1st Street, Arunthathipuram 2nd Street, Arasamaram Street , Voc Street, Kulakari Street, Ethiraj street, Thulukathamman Kovil 4th cross street Exth, Thulukatham | Roads | BT and CC Road | 20557Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 70000000 | 20000000 |  |  |  | 2 | 2021-03-02 | 1.84 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 19991157 |  |  |  | 8843 | 1.78 | 89.15 | 2021-06-11 |  | 70000000 | Yes | Yes
908 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00249 |  |  | SRP SRP/2020-21/009/ROAD/00249-Relaying of Road-Providing B.T. Surface at Perumal Nagar 4th Main Road, Big Street, Pudhuvai Nagar 1st street, 2nd Street, 3rd Street, Murugesapuram Road, Periyar street, Adhiparasakthi Koil street, Ragu street, Roja street, Elango 2nd Cross street , Veera Kumara Salai CC Road at New Colony 18th Cross street Extn, New Colony 16th cross street 1st Cross street, New Colony 16th cross street Extn, TS Lakshman Street, Ethiraj Street in ward No: 12, 13, 14, 17, 38, 40 & 42 (Package No.02) | Roads | BT and CC Road | 20557Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 70000000 | 15000000 |  |  |  | 1.11 | 2021-03-02 | 1.38 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 12830137 |  |  |  | 2169863 | 1.12 | 74.84 | 2021-06-11 |  | 70000000 | Yes | Yes
909 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00250 |  |  | SRP SRP/2020-21/009/ROAD/00250-Relaying of Road-007/2021/032/R/0000789-GANGAIAMMAN KOIL STREET , 007/2021/018/R/0000223-BHAVANI NAGAR 4TH STREET , 007/2021/018/R/0000189-ANNAI THERASA STREET , 007/2021/021/R/0000775-SUDAMANI STREET , | Roads | BT and CC Road | 20557Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 70000000 | 20000000 |  |  |  | 2 | 2021-03-02 | 1.84 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 18810506 |  |  |  | 1189494 | 1.68 | 83.79 | 2021-06-11 |  | 70000000 | Yes | Yes
910 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00251 |  |  | SRP SRP/2020-21/009/ROAD/00251-Relaying of Road-Providing B.T. Surface at Purushothaman Nagar 4th main road, Valluvar 1st street, Valluvar 2nd street, Valluvar 3rd street, Valluvar Cross street, Manimagalai street, Raman Street, Gangaiamman Kovil street, Nehru Nagar and CC Road at VN Samy Cross Street, Bangalamalai, Ramachandran Street, Sadagopan Street, Panchayat Colony Road Extn, Dhanapal Street, Arcot Jambulingam Street, Gangaiamman Kovil cross street in ward No:27, 28, 29, 30, 31, 32, 33, 34, & 35 (Package No.04) | Roads | BT and CC Road | 20557Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 70000000 | 15000000 |  |  |  | 1.5 | 2021-03-02 | 1.37 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 14879674 |  |  |  | 120325.86 | 1.33 | 88.47 | 2021-06-11 |  | 70000000 | Yes | Yes
911 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00159 |  |  | TURIP TURIP/2024-25/009/ROAD/00159-Relaying of Road-BT and CC Road009007R0613-1ST CROSS STREET ANNA NAGAR , 009007R0628-2ND CROSS STREET ANNANAGAR , 009007R0522-SATHYAMOORTHY STREET , 009007R0551-1ST STREET LAKSHMI NARYANAN NAGAR , 009007R0558-2ND STREET LAKSHMI NARYANAN NAGAR , 009007R0545-4TH STREET LAKSHMI NARAYANAN NAGAR , 009007R0552-KALAINJAR CROSS STREET ANNA NAGAR , 009007R0556-GANGA STREET ANNA NAGAR , 009007R0553-KAVERI STREET ANNA NAGAR , 009007S0044-6TH MAIN ROAD ANNA NAGAR , 009007R0519-4TH MAIN ROAD | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :2652 Mts | 2024-25 | 197393000 | 15700000 |  |  |  | 1.41 | 26/09/24 | 0 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 15700000 |  |  |  | 0 | 1.41 | 89.98 | - |  | 197393000 | No | Yes
912 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00160 |  |  | TURIP TURIP/2024-25/009/ROAD/00160-Relaying of Road-BT and CC Road009008R0625-CHOZHAN STREET MUTHAMIZH NAGAR , 009008R0569-GANESAN STREET KRISHNA NAGAR , 009008R0580-TEACHER CHINNASAMY STREET , 009008R0606-ELUMALAI STREET THIRUVALLUVAR NAGAR , 009008R0576-BRINIDHAVANAM COLONY , 009008R0658-ELANGO STREET MUTHAMIZH NAGAR , 009008S0050-BABU STREET SAMANTHAR NAGAR , 009008R0577-NEHRU STREET SAMANTHANAR NAGAR , 009008R0579-DURUVAN STREET THIRUVALLUVAR NAGAR , 009007R0509-SIGNAL OFFICE ROAD , 009007R0535-5TH MAIN ROAD | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :1458 Mts | 2024-25 | 197393000 | 12600000 |  |  |  | 1.13 | 26/09/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-03-03 |  | 12600000 |  |  |  | 0 | 1.13 | 89.98 | - |  | 197393000 | No | Yes
913 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00161 |  |  | TURIP TURIP/2024-25/009/ROAD/00161-Relaying of Road-BT and CC Road009010R0768-MURUGESAN STREET NAGALKENI , 009010R0718-MOSES STREET IYAPPA NAGAR , 009011L0041-METTU STREET ADAM NAGAR , 009011R0817-SELVARAJ STREET PERIYAR NAGAR , 009011R0793-2ND STREET SWAMINATHAN NAGAR , 009011R0778-RAJIVGANDHI STREET ESWARAN NAGAR , 009012R0878-AMBEDKAR MAIN ROAD , 009010R0749-PETTER STREET NAGALKENI , 009010R0706-4TH STREET IYYAPPA NAGAR , 009011R0842-2ND STREET ADAM NAGAR , 009010S0072-SABAPATHY STREET THIRU NAGAR , 009010R0709-BHARATH | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :3816 Mts | 2024-25 | 197393000 | 18500000 |  |  |  | 1.67 | 2024-12-09 | 0 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 18500000 |  |  |  | 0 | 1.66 | 89.99 | - |  | 197393000 | No | Yes
914 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00305 |  |  | TURIP TURIP/2024-25/009/ROAD/00305-Relaying of Road-BT and CC Road009017R1030-Kulakarai Street , 009017L0089-KANNABIRAN 1ST CROSS STREET , 009017R1026-Yadhaval athiyaman street , 009017R1027-Yadhaval street , 009017R5782-NSK STREET , 009017R1063-Sankar Salai 2nd Cross Street , 009017R1064-Sankar Salai 3rd Cross Street , 009017R5783-Ragu Colony , 009019R1219-KAMARAJ STREET , 009019S0157-DURAISAMY NAGAR 5TH MAIN ROAD , 009019S0158-DURAISAMY NAGAR 3RD STREET , 009019S0159-DURAISAMY NAGAR 3RD STREET , 009019S0174-PARI COLONY MANICKAM | Roads | BT and CC Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2290 Mts | 2024-25 | 130600000 | 12910000 |  |  |  | 0 | 27/05/25 | 1.29 | Completed | 100 | Completed | 100 |  |  | 21/10/25 |  | 12633978 |  |  | 0 | 276022 | 1.09 | 84.75 | 26/07/25 |  | 130600000 | No | Yes
915 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00060 |  |  | TURIP TURIP/2024-25/009/ROAD/00060-Relaying of Road-BT and CC Road009011R0801-RAJEVE GANDHI NAGAR 1ST STREET , 009011R0799-RAJIV GANDHI NAGAR 3RD STREET , 009011R0807-SABAPATHY NAGAR 1ST STREET , 009011R0805-SABAPATHY NAGAR 3RD STREET , 009011S0080-5TH STREET ESWARAN NAGAR , 009011R0773-10TH STREET ESHWARAN NAGAR , 009011S0081-SABAPATHY NAGAR 2ND STREET , 009011S0079-1ST STREET POOMBUKAR NAGAR , 009011R0776-2ND STREET POOMBUKAR NAGAR , 009011S0078-3RD STREET POOMBUKAR NAGAR , 009011R0826-THIRUVALLUVAR STREET G | Roads | BT and CC Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :1799 Mts | 2024-25 | 65000000 | 11500000 |  |  |  | 0 | 2025-08-04 | 1.09 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 11493182 |  |  | 0 | 6818 | 0.97 | 84.6 | 2025-08-07 |  | 65000000 | No | Yes
916 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00249 |  |  | TURIP TURIP/2024-25/009/ROAD/00249-Repair /Maintenance-BT and CC Road006045R3324-SRIRAM NAGAR 5TH STREET , 009045R3325-ISHTA SIDHI VINAYAGAR KOIL ST , 009046R3438-BUDDAR STREET , 009047R3498-GANAPATHY COLONY , 009047R3499-GANAPATHY COLONY 1ST CROSS STREET , 009048R3532-PORUR STREET , 009062R4730-ROJA THOTTAM 1ST CROSS EXTN STREET , 009062S0542-ROJA THOTTAM 1ST CROSS EXTN 6TH STREET , 009063R4792-NORTH STREET , 009064R4845-BETHELPURAM , 009064R4850-DOUBLE ROAD , 009048R3520-MOOVAR STREET , 009063R4802-PONDS COLONY , (package No.09 | Roads | BT and CC Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2518 Mts | 2024-25 | 130600000 | 12500000 |  |  |  | 1.13 | 27/05/25 | 1.25 | Completed | 100 | Completed | 100 |  |  | 27/01/26 |  | 12497453 |  |  | 0 | 2547 | 1.01 | 81.18 | 26/07/25 |  | 130600000 | No | Yes
917 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00115 |  |  | TURIP TURIP/2023-24/009/ROAD/00115-Relaying of Road-009002R0193-NARACHIMMA CHETTY STREET , 009002R0150-BALAJI NAGAR RAMAKRISHNA 1ST STREET , 009002R5748-BALAJI NAGAR SUB.BHARATHIYAR 2ND ST , 009002R0076-VENKATESWARA NAGAR ANNA 1ST STREET , 009002R0139-Balaji Nagar 14th Street , 009002R0087-VENKATESWARA NAGAR GANGA STREET , 009002R0168-BALAJI NAGAR THIRUVALLUVAR ST , 009002R0094-VENKATESWARA NAGAR KALIMAGAL STREET , 009002R0112-GURUSWAMY NAGAR 9TH STREET , 009002R0140-BALAJI NAGAR 15TH STREET , 009002R0179-BALAJI NAGAR 30 ROAD 1ST | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :4762 Mts | 2023-24 | 313620000 | 15550000 |  |  |  | 1.4 | 19/07/23 | 1.56 | Completed | 100 | Completed | 100 |  |  | 2025-03-03 |  | 15549990 |  |  |  | 10 | 1.4 | 89.96 | 14/04/24 |  | 313620000 | No | Yes
918 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00116 |  |  | TURIP TURIP/2023-24/009/ROAD/00116-Relaying of Road-009005R0363-SHANKAR NAGAR 38TH STREET , 009005R0371-SHANKAR NAGAR 12TH STREET , 009005R0397-20TH STREET SHANKAR NAGAR , 009005R0407-SHANKAR NAGAR 27TH STREET , 009005R0381-SHANKAR NAGAR 31ST STREET , 009005R0394-SHANKAR NAGAR 3RD CROSS STREET , 009005R0400-SHANKAR NAGAR 2ND CROSS STREET , 009005R0409-19TH STREET SANKAR NAGAR , 009005R0393-SHANKAR NAGAR 14TH STREET , 009005R0419-EAST MAIN ROAD SANKAR NAGAR , 009005R0429-SHANKAR NAGAR 17TH STREET , 009005R0384-SHAN | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :4258 Mts | 2023-24 | 313620000 | 16130000 |  |  |  | 1.45 | 19/07/23 | 1.61 | Completed | 100 | Completed | 100 |  |  | 2025-03-06 |  | 15560873 |  |  |  | 569127 | 1.4 | 86.72 | 14/04/24 |  | 313620000 | No | Yes
919 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00147 |  |  | General Fund GENERAL/2025-26/009/ROAD/00147-Repair /Maintenance-BT and CC Road- , | Roads | BT and CC Road | 627-3/2025-26Dated:25/08/25Road DetailsRoad Length :Mts | 2025-26 | 2500000 | 2500000 |  |  |  | 0 | 18/08/25 | 0.25 | Completed | 100 | Earth Work | 100 |  |  |  |  | 0 |  |  |  | 2500000 | 0 | 0 | 18/11/25 |  | 2500000 | No | Yes
920 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00119 |  |  | TURIP TURIP/2023-24/009/ROAD/00119-Relaying of Road-009007R0510-VADIVEL STREET H L COLONY , 009007R0525-7TH CROSS STREET ANNA NAGAR , 009007R0560-RADHAKRISHANAN STREET ANNA NAGAR , 09007R0523-1ST MAIN RAOD H L COLONY , 009007R0532-6TH CROSS STREET ANNA NAGAR , 009007R0530-DEVADAS STREET H L COLONY , 009007R0602-ANNAI VELANKANNI STREET I LE COLONY , 009008R0568-1ST CROSS STREET KRISHNA NAGAR , 009008R0646-AVAIAR STREET , 009008R0605-NAMMAZHVAR STREET THIRUVALLUVAR NAGAR , 009010R0750-PERIYA PALAIYATHAMMAN KOIL STREE | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :7522 Mts | 2023-24 | 313620000 | 29880000 |  |  |  | 2.69 | 20/07/23 | 2.99 | Completed | 100 | Completed | 100 |  |  | 2025-03-03 |  | 19700000 |  |  | 0 | 10180000 | 1.46 | 48.81 | 2025-10-01 |  | 313620000 | No | Yes
921 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00120 |  |  | TURIP TURIP/2023-24/009/ROAD/00120-Relaying of Road-009017R1097-Kannabiran cross Street , 009017R1019-Kamarajar Nagar 3rd Cross Street , 009015R6411-ESWARI NAGAR MAIN ROAD 1 STREET , 009015R0955-Eswari Nagar Main Road Cross Street , 009015R0971-MALANGANANTHAPURAM 4TH STREET , 009015R0973-MALANGANANTHAPURAM 6TH STREET , 009013R0920-CHAVADI STREET , 009017R1050-Jayalakshmi Nagar 1st Street , 009017R1051-JAyalakshmi Nagar 2nd Street , 009017R1052-JEYALAKSHMI NAGAR 3RD STREET , | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1631 Mts | 2023-24 | 313620000 | 6450000 |  |  |  | 0.45 | 2024-02-01 | 0.65 | Completed | 95 | Completed | 100 |  |  | 16/05/25 |  | 4666875 |  |  |  | 1783125 | 0.45 | 69.9 | 2024-01-04 |  | 313620000 | No | Yes
922 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00139 | Zone II |  | TURIP TURIP/2023-24/009/ROAD/00139-Relaying of Road-BT and CC Road009018R1107-THIRUVALLUVAR NAGAR MAIN ROAD , 009020R1240-SUBRAMANIYAM NAGAR , 009021R1433-BHARATH NAGAR MAIN ROAD , 009028R1816-NEW COLONY 12TH CROSS STREET , 009028R1817-NEW COLONY 13TH CROSS STREET , 009017R1024-Anjaneyar Street , 009020R1293-Kalaivani Cross Street , 009021R1436-AGS NAGAR , (Package No.3) Zone II | Roads | BT and CC Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :2091.4 Mts | 2024-25 | 65000000 | 10100000 |  |  |  | 0 | 27/05/25 | 1.01 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 10100000 | 0.91 | 89.91 | 26/07/25 |  | 65000000 | No | Yes
923 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00042 |  |  | TURIP TURIP/2022-23/009/ROAD/00042-Relaying of Road-009/01/002/R/0141-Narmadha Street , 009/05/065/R/4071-KANNADASAN ST , 009/03/022/R/1664-DURAISAMY STREET , 009/01/010/R/1513-KRISHANA STREET , 009/03/022/R/1714-KAVERI STREET , 009/01/002/R/0098-PUTHUTHAMBI NAGAR SIVAJI 1ST STREET , 009/01/002/R/0087-PUTHUTHAMBI NAGAR SIVAJI 2ND STREET , 009/01/002/R/0083-Puthuthambi Nagar Sivaji 3rd Street , 009/01/002/R/0125-GURUSWAMY NAGAR 4TH STREET , 009/01/002/R/0129-GURUSWAMY NAGAR 5TH STREET , 009/01/002/R/1595-GURUSWAMY NAGAR 4, 2ND CR | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :1884 Mts | 2022-23 | 99050000 | 17600000 |  |  |  | 1.58 | 2023-08-02 | 1.45 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 17600000 | 1.1 | 62.64 | 2023-05-11 |  | 99050000 | No | Yes
924 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00043 |  |  | TURIP TURIP/2022-23/009/ROAD/00043-Relaying of Road-009/04/059/R/1785-MANIMEGALAI STREET , 009/01/005/R/1466-SHANKAR NAGAR 34TH STREET , 009/01/005/R/0537-SHANKAR NAGAR 37TH STREET` , 009/03/043/R/1907-VENKATRAMAN STREET , 009/01/005/R/0597-SHANKAR NAGAR 36TH STREET , 009/01/005/R/0566-SHANKARA NARAYANAN STREET V O C NAGAR , 009/01/005/R/0553-SHANKAR NAGAR 40TH STREET , 009/01/006/S/0186-R.V. SUBRAMANIAM STREET PASUMPON NAGAR , 009/01/006/R/0431-GODHANDAN STREET PASUMPON NAGAR , | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :1497 Mts | 2022-23 | 99050000 | 15800000 |  |  |  | 1.42 | 2023-07-02 | 1.28 | Completed | 100 | Completed | 100 | 2023-01-09 |  | 2025-07-05 |  | 14952562 |  |  |  | 847438 | 1.45 | 91.95 | 2023-08-05 |  | 99050000 | No | Yes
925 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00044 |  |  | TURIP TURIP/2022-23/009/ROAD/00044-Relaying of Road-009/01/006/R/0152-SIVAJI STREET V O C NAGAR , 009/01/006/R/0147-SURIYAMMAN KOIL STREET V O C NAGAR , 009/01/006/R/0184-OM BHARASHAKTHI STREET V.O.C NAGAR , 009/04/054/R/2085-PALLAVAN ST , 009/01/006/R/0371-ARAVINDHAR STREET V O C NAGAR , 009/04/059/R/1801-BHARATHIDASAN STREET , 009/04/060/R/1992-KARIKALAN STREET , 009/04/060/R/1995-BARATHIDASAN 1ST STREET , 009/01/006/R/1506-KANNAGI STREET V O C NAGAR , 009/02/024/R/4534-GOPAL STREET , 009/02/020/S/0055-EASWARAN NAGAR | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :2608 Mts | 2022-23 | 99050000 | 18000000 |  |  |  | 1.62 | 2023-07-02 | 1.46 | Completed | 100 | Completed | 100 |  |  | 25/02/25 |  | 16183869 |  |  |  | 1816131 | 1.61 | 89.62 | 2023-04-11 |  | 99050000 | No | Yes
926 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00045 |  |  | TURIP TURIP/2022-23/009/ROAD/00045-Relaying of Road-009/04/060/R/2039-THIRUVALLUVARPURAM MAIN ROAD , 009/04/060/R/1977-DEIVA NAGAR MAIN STREET , 009/04/054/R/2096-15TH STREET LAKSHMIPIURAM , 009/04/054/R/2102-3RD STREET C.T.O. COLONY , 009/04/051/R/3624-KAILASAPURAM MAIN ROAD , 009/04/051/R/3626-KAILASAPURAM 1ST STREET , 009/04/051/R/3623-3RD ST-KAILASAPURAM , 009/04/053/R/3043-2ND STREET KRISHNA NAGAR , 009/04/052/R/3567-OLD SBI COLONY 3RD MAIN ROAD , 009/04/052/R/3569-OLD SBI COLONY 1ST MAIN ROAD , 009/04/052/R/3568-OLD SBI COL | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :2574 Mts | 2022-23 | 99050000 | 17850000 |  |  |  | 1.61 | 2023-08-02 | 1.46 | Completed | 100 | Completed | 100 |  |  | 2024-02-03 |  | 17811849 |  |  |  | 38151 | 1.6 | 89.44 | 2023-05-11 |  | 99050000 | No | Yes
927 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00046 |  |  | TURIP TURIP/2022-23/009/ROAD/00046-Relaying of Road-009/05/048/R/4221-KALAMEGAM STREET , 009/05/048/R/4232-KALIDASAR STREET , 009/05/065/R/3407-BAGAVATHI NAGAR 1ST MAIN ROAD , 009/05/065/R/3414-A.P.N.NAGAR 1ST STREET , 009/05/065/R/3787-GOVINDAPILLAI STREET , 009/05/065/R/3375-RAJKUMAR AVENUE , 009/05/068/R/3309-ANNA STREET BHARATH NAGAR-TAMBARAM , 009/05/068/R/3314-MUTHUMARIYAMMAN KOIL STREET , | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :987 Mts | 2022-23 | 99050000 | 13200000 |  |  |  | 1.19 | 2023-07-02 | 1.06 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 12909411 |  |  |  | 290589 | 1.17 | 88.42 | 2023-07-11 |  | 99050000 | Yes | Yes
928 | Tambaram | TURIP | CHENGALPATTU | TURIP/2022-23/009/ROAD/00047 |  |  | TURIP TURIP/2022-23/009/ROAD/00047-Relaying of Road-009/05/047/R/4278-PONNUSAMY STREET , 009/05/063/S/0392-MUTHAMIZH STREET , 009/05/063/R/4006-BAJANAI KOIL STREET , 009/05/063/S/0391-SUBRAMANIYA SIVA ST , 009/05/063/R/4003-VVS IYER STREET , 009/05/063/R/4005-PARALI NELLAIYAPPAR STREET , | Roads | BT and CC Road | 24826/2022/SS1Dated:26/12/22Road DetailsRoad Length :1030 Mts | 2022-23 | 99050000 | 6700000 |  |  |  | 0.6 | 2023-07-02 | 0.54 | Completed | 100 | Completed | 100 |  |  | 27/05/25 |  | 6700000 |  |  |  | 0 | 0.6 | 89.98 | 2023-11-11 |  | 99050000 | No | Yes
929 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00076 |  |  | TURIP TURIP/2025-26/009/ROAD/00076-Relaying of Road-BT and CC Road009045R3329-GANAPATHY COLONY , 009045R3384-I.O.B. COLONY-IST MAIN RD , 009045R3387-I.O.B.COLONY 1ST MAIN ROAD CROSS , 009045R3390-IOB COLONY 4TH MAIN ROAD , 009045R3392-I.O.B.COLONY CRESENT AVENUE , 009046R3426-KALPANA NAGAR , 009046R3431-CHAKKARAVARTHY STREET , 00946R3432-LAL MAL GARDEN , 009046R3439-BUDDHAR CROSS STREET , 009046R3467-BURIAL GROUND ROAD (KAMARAJAR ROAD) , 009046R3463-SUBRAMANIAM STREET , 009047R3497-L.I.C COLONY , 009047R3500-GANAPATHY COLONY 2ND | Roads | BT and CC Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2565 Mts | 2025-26 | 521620000 | 18000000 |  |  |  | 0 | 2025-10-06 | 1.8 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 18000000 | 0 | 0 | 2025-09-08 |  | 521620000 | No | Yes
930 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00077 |  |  | TURIP TURIP/2025-26/009/ROAD/00077-Relaying of Road-BT and CC Road009062R4692-MURUGESAN ST , 009062R4693-MURUGESAN CROSS ST , 009062R4697-CHELLIAMMAN KOIL 2ND STREET , 009062R4754-GAYATHRI NAGAR 1ST STREET , 009062R4755-GAYATHRI NAGAR 2ND STREET , 009062R4758-GAYATHRI NAGAR 5TH STREET , 009062R4774-ARUL NAGAR 3RD MAIN ROAD 3RD CROSS , 009063R4803-NAALVAR STREET , 009063R4808-SENGANIAMMAN KOIL STREET , 009063R4809-ASHOK NAGAR 1ST STREET , 009063R4810-ASHOK NAGAR NADU STREET , 009063R4812-ASHOK NAGAR EAST STREET , 009063R4813-ASHOK | Roads | BT and CC Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2834 Mts | 2025-26 | 521620000 | 13450000 |  |  |  | 1.11 | 2025-10-06 | 1.35 | Completed | 100 | Completed | 100 |  |  | 20/11/25 |  | 13445492 |  |  | 0 | 4508 | 1.11 | 82.52 | 2025-09-08 |  | 521620000 | No | Yes
931 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00164 |  |  | TURIP TURIP/2024-25/009/ROAD/00164-Relaying of Road-BT and CC Road009004R0316-VINAYAGA NAGAR THIRUVALLUVAR ST , 009002R0137-BALAJI NAGAR 12TH ST 1ST CROSS ST , 009002R0167-SRI SAMUNDEESWARI A.N.PANDIYAN STREET , 009002R0157-THIRU NAGAR MAIN ROAD , 009004R0297-ANNAI MARY 1ST CROSS STREET , 009004R0298-ANNAI MARY 2ND CROSS STREET , 009004R0264-ANNA DURAI STREET , 009004R0278-AYOTHIAMMAN KOIL ST 1ST CROSS ST , 009004R0293-THIRUNEERMALAI ROAD KALMUDUVU ST , 009004R0259-ANNA NAGAR 2ND MAIN ROAD , 009002R0181-BALAJI NAGAR 12TH ST 2ND C | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :2710 Mts | 2024-25 | 197393000 | 13000000 |  |  |  | 0 | 2025-03-06 | 1.27 | Completed | 100 | Completed | 100 |  |  | 28/12/25 |  | 12974353 |  |  | 0 | 25647 | 1.07 | 82.14 | - |  | 197393000 | No | Yes
932 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00165 |  |  | TURIP TURIP/2024-25/009/ROAD/00165-Relaying of Road-BT and CC Road009015R0972-MALANGANANTHAPURAM 5TH STREET , 009015R0974-MALANGANANTHAPURAM 8TH STREET , 009017R1071-BALAJI STREET , 009017R1072-Balaji Salai 1st Cross , 009021R1412-GARDEN WOODROFF NAGAR 2ND STREET , 009021R1429-SWAMYMALAI NAGAR 2ND MAIN ROAD , 009014S0096-Sundarasan 1st Cross Street , 009016S0607-RAJIV GANDHI STREET , 009020R5806-KUMARAN COLONY 1ST CROSS STREET , 009020R1317-Kumaran colony cross , 009020R1316-Kumaran Colony Cross street , 009027S0332-ADAIKALAM NAG | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :3469.4 Mts | 2024-25 | 197393000 | 15100000 |  |  |  | 0 | 2024-12-09 | 0 | Completed | 100 | Completed | 100 | 2024-10-12 |  | 2025-03-03 |  | 14910007 |  |  |  | 189993 | 0 | 0 | - |  | 197393000 | No | Yes
933 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00166 |  |  | TURIP TURIP/2024-25/009/ROAD/00166-Relaying of Road-BT and CC Road009039R2450-THIRUMALAI NAGAR 2ND MAIN ROAD , 009039R2443-THIRUMALAI NAGAR 1ST STREET , 009039R2445-THIRUMALAI NAGAR 3RD STREET , 009039R2539-LAKSHMI NAGAR 2ND STREET , 009039R2462-THIRUMALAI NAGAR 8TH STREET , 009040R2651-HERITAGE JEYANDRA NAGAR 5TH CROSS STREET , 009040R2653-HERITAGE JEYANDRA NAGAR 6TH CROSS STREET , 009040R2655-Jeyandirar nagar 7th cross street extension , 009040R2659-HERITAGE JEYANDRA NAGAR 8TH CROSS ST , 009040R2639-Jeyandirar nagar extension , | Roads | BT and CC Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :5556 Mts | 2024-25 | 197393000 | 25000000 |  |  |  | 0 | 2024-12-09 | 0 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 25000000 | 2.21 | 88.54 | 2024-11-12 |  | 197393000 | No | Yes
934 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00062 |  |  | TURIP TURIP/2024-25/009/ROAD/00062-Relaying of Road-BT and CC Road009001R0054-M.G.R.NAGAR MAIN ROAD , 009003R0247-KARIKALAN NAGAR RAJAJI STREET , 009003R0246-KARIKALAN NAGAR CHENGUTTUVAN STREET , 009003R0243-PARI NAGAR MULLAI STREET , 009003R5762-DEVARAJ NAGAR CHOZHAN ST , 009004R0300-VINAYAGA NAGAR 1ST STREET , 009004R0305-VINAYAGA NAGAR 4TH STREET , 009004R0290-THIRUNEERMALAI ROAD 1ST STREET , 009002R0141-Balaji Nagar Annai Indira Ghandhi Street , 009001R0007-SAMUNDEESWARI NAGAR, SINDHUNATHI STREET , 009001R0047-KASTHURI BAI N | Roads | BT and CC Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :4375 Mts | 2024-25 | 169399000 | 19700000 |  |  |  | 1.77 | 28/02/24 | 1.93 | Completed | 100 | Work Completed. | 100 |  |  | 28/02/25 |  | 0 |  |  |  | 19700000 | 1.46 | 74.02 | - |  | 169399000 | No | Yes
935 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00063 |  |  | TURIP TURIP/2024-25/009/ROAD/00063-Relaying of Road-BT and CC Road009010r0723-SECRETCEYET COLONY MEENACHI NAGAR , 009010R0731-PARASU RAMAN STREET , 009010R0710-PONNI NAGAR AMBEDKAR STREET , 009010R0771-RANGASAMY STREET THIRU NAGAR , 009010R0735-SIVASANKARAN STREET , 009010S0074-NALLATHAMBI STREET THIRU NAGAR , 009011R0777-KANNATHASAN STREET ESWARAN NAGAR , 009005S0013-THIRUVALLUVAR STREET V O C NAGAR , 009011R0835-JAMES STREET , 009011R0818-THANGAIAH STREET - GANDHI NAGAR , 009012R0911-BALAJI NAGAR MAIN ROAD , 00 | Roads | BT and CC Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :2973.2 Mts | 2024-25 | 169399000 | 13900000 |  |  |  | 1.25 | 28/02/24 | 1.35 | Completed | 100 | Work Completed | 100 |  |  | 25/05/24 |  | 12401048 |  |  |  | 1498951.55 | 1.24 | 89.22 | - |  | 169399000 | No | Yes
936 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00118 |  |  | TURIP TURIP/2023-24/009/ROAD/00118-Relaying of Road-009011R0795-1ST STREET SWAMINATHAN NAGAR , 009011R0792-2ND STREET PONNI NAGAR , 009011R0794-6TH STREET ESWARAN NAGAR , 009011R0779-2ND STREET ESWARAN NAGAR` , 009011R0774-9TH STREET ESWARAN NAGAR , 009011R0814-KANDA SAMY STREET , 009011R0833-ARUL PANDIYAN STREET - PERIYAR NAGAR , 009011R0823-BALAGURUSAMY CROSS STREET , 009011R0787-7TH STREET ESWARAN NAGAR , 009011R0841-4TH STREET ADAM NAGAR , 009011R0803-KANNAYRAM STREET NAGALKENI , 009011R0804-MUTHU PLANIAPPA NAGA | Roads | BT and CC Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2983 Mts | 2023-24 | 313620000 | 11750000 |  |  |  | 1.06 | 20/07/23 | 1.18 | Completed | 100 | Work Completed. | 100 |  |  | 28/02/25 |  | 10731459 |  |  |  | 1018541 | 0.97 | 82.45 | 18/10/23 |  | 313620000 | No | Yes
937 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BRIDGE/00166 | Zone II |  | General Fund GENERAL/2025-26/009/BRIDGE/00166-Supply and fixing of new rope LED lights in MIT Flyover in Zone II, TCMC | Bridges and Flyovers | Bridges/Flyovers | 337-1/2025-26Dated:24/06/25 | 2025-26 | 5250000 | 5250000 |  |  |  | 0 | 21/07/25 | 0.53 | Revetment Wall | 50 | Completed | 100 |  |  | 2026-05-02 |  | 5182096 |  |  |  | 67904 | 0 | 0 | 21/10/25 |  | 5250000 | No | Yes
938 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BRIDGE/00167 | Zone II |  | General Fund GENERAL/2025-26/009/BRIDGE/00167-Supply and fixing of new rope LED lights in PONDS Flyover in Zone II, TCMC | Bridges and Flyovers | Bridges/Flyovers | 337-2/2025-26Dated:24/06/25 | 2025-26 | 4350000 | 4350000 |  |  |  | 0 | 21/07/25 | 0.44 | Revetment Wall | 50 | Completed | 100 |  |  | 2026-05-02 |  | 4338476 |  |  |  | 11524 | 0 | 0 | 21/10/25 |  | 4350000 | No | Yes
939 | Tambaram | MP Fund | CHENGALPATTU | MP/2021-22/009/SL/00002 | Zone I | 4 | MP Fund MP/2021-22/009/SL/00002-Providing 1no of Mini High mast light at zone I, ward No.4 JRC Ground, Anna Nagar 7th street, Tambaram Corporation @ Pallavaram Constituency | Streetlight | Lighting | 2829/2022/A3-sDated:15/03/24 | 2021-22 | 400000 | 400000 |  |  |  | 0 | 26/11/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 400000 |  |  |  | 0 | 0 | 0 | - |  | 400000 | No | Yes
940 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WSIS/00470 | Zone II | 17 | MLA Fund MLA Fund/2022-23/009/WSIS/00470-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.17 | Water Supply Improvement Scheme | Installation ofl Water Purifier with Reverse Osmosis | Rocno 3607/2022/a3Dated:22/10/22 | 2022-23 | 6280000 | 970000 |  |  |  | 0.1 | 25/11/22 | 0.09 | G1 Shed | 60 | Completed | 100 | 23/07/23 |  | 2024-09-09 |  | 919000 |  |  |  | 51000 | 0.1 | 100 | 23/02/23 |  | 6280000 | Yes | Yes
941 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2017-18/009/BUILDING/00079 |  |  | Chennai River Restoration Trust Chennia Ri/2017-18/009/BUILDING/00079-Providing Fencing Along the River Adayar in Perungalathur, Tambaram City Municipal Corporation | Buildings | Construction of Compound Wall | Go.No. MS No.72 MA&WS(MC.1) Depart Date : 12.07.2017Dated:12/07/17 | 2017-18 | 162000000 | 162000000 |  |  |  | 1.2 | 2018-05-06 | 14.54 | Plastering | 95 | Completed | 100 | 2025-04-04 |  | 2025-04-04 |  | 91269892 |  |  |  | 70730108 | 2.11 | 13 | 2019-05-06 | ... | 162000000 | No | Yes
942 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2017-18/017/BUILDING/00004 |  |  | Chennai River Restoration Trust Chennia Ri/2017-18/017/BUILDING/00004-Fencing along with Adyar River from Srinivasapuram to Thirumalai Nagar (Anakaputhur Limit) | Buildings | Construction of Compound Wall | GO.MS.No.72 MAWSDated:12/07/17 | 2017-18 | 30000000 | 30000000 | 0 |  |  | 1.96 | 2018-10-09 | 2.64 | Completed | 100 | Completed | 100 |  |  | 21/04/25 |  | 24321884 |  |  |  | 5678116 | 1.26 | 41.93 | 2019-10-09 | ... | 30000000 | No | Yes
943 | Tambaram | Chennai River Restoration Trust | CHENGALPATTU | Chennia Ri/2017-18/009/BUILDING/00078 |  |  | Chennai River Restoration Trust Chennia Ri/2017-18/009/BUILDING/00078-Providing Fencing along the left and right side of the Adayar River in Thiruneermalai, Tambaram City Municipal Corporation | Buildings | Construction of Compound Wall | G.O Ms No. 72 MAWS (MC1)Dated:12/07/17 | 2017-18 | 90200000 | 90200000 |  |  |  | 2.54 | 2018-05-06 | 8.06 | Completed | 100 | Completed | 100 |  |  | 21/04/25 |  | 46211641 |  |  |  | 43988359 | 3.46 | 38.36 | 2019-05-06 | To be completed by February end | 90200000 | No | Yes
944 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00173 | Zone II | 18 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00173-Construction of 2+2 Class room Additional school Building at Keelkattalai Middle school in ward No. 18 Pallavaram Zone II in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 6800000 |  |  |  | 0 | 25/10/24 | 0.68 | Plastering | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6800000 | 0 | 0 | - |  | 40950000 | No | Yes
945 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SL/00197 | Zone II | 14 | General Fund GENERAL/2025-26/009/SL/00197-Providing mini highmast light at sanjai gandhi nagar in ward-14 at zone-II,TCMC | Streetlight | StreetLight | 04-01/2025-26Dated:28/01/26 | 2025-26 | 400000 | 400000 |  |  |  | 0 | 27/10/25 | 0.04 | Fixing Of Lights | 50 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 400000 | 0 | 0 | 27/01/26 |  | 400000 | No | Yes
946 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/SL/00205 | Zone II |  | General Fund GENERAL/2024-25/009/SL/00205-Supply and erection of street light pole at radhanagar subway in zone-II | Streetlight | StreetLight | 337 /2024-25Dated:30/08/24 | 2024-25 | 4000000 | 4000000 |  |  |  | 0 | 2024-05-09 | 0.4 | Fixing Of Lights | 50 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 4000000 | 0 | 0 | 2024-05-12 |  | 4000000 | No | Yes
947 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00036 | Zone I | 29 | MP Fund MP/2023-24/009/SL/00036-Providing 1nos Mini Highmast Light at ward No.29, Near New street Perumal kovil street Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Completed | 100 | Completed | 100 |  |  | 15/03/24 |  | 408085 |  |  |  | 11915 | 0 | 0 | - |  | 11435000 | No | Yes
948 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00455 | Zone I | 11 | MP Fund MP/2024-25/009/SL/00455-Providing 1 no Mini High mast Light at ward No.11 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
949 | Tambaram | State Urban Infrastructure Development Fund | CHENGALPATTU | SUIDF/2022-23/009/SL/00067 |  |  | State Urban Infrastructure Development Fund SUIDF/2022-23/009/SL/00067-PROVIDING NEW STREET LIGHT 3634 NOS INTO ENERGY SAVING LED LIGHTS LEFT OUT AREA ,ADDED AREA AND MAIN ROADS IN ALL ZONES AT TAMBARAM CITY MUNICIPAL CORPORATION | Streetlight | StreetLight | 001/2022/D01Dated:20/03/23 | 2022-23 | 6479600000 | 64796000 |  |  |  | 3.24 | 2023-12-07 | 5.71 | Completed | 100 | Completed | 100 | 2025-02-05 |  | 2025-02-05 |  | 59714176 |  |  |  | 5081824 | 7.44 | 114.88 | 25/06/24 |  | 6479600000 | No | Yes
950 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00451 | Zone I | 29 | MP Fund MP/2024-25/009/SL/00451-Providing 1 no Mini High mast Light at ward No.29 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
951 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00453 | Zone I | 6 | MP Fund MP/2024-25/009/SL/00453-Providing 1 no Mini High mast Light at ward No.06 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
952 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00218 | Zone I | 7 | MP Fund MP/2022-23/009/SL/00218-Providing 1 Nos of Mini Highmast light at Ward No. 7 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.42 | 2023-12-09 | 0 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 0 |  |  |  | 420000 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
953 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00219 | Zone I | 8 | MP Fund MP/2022-23/009/SL/00219-Providing 1 Nos of Mini Highmast light at Ward No. 8 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 420000 |  |  |  | 0 | 0.04 | 95.24 | 2023-12-10 |  | 4200000 | No | Yes
954 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00220 | Zone II | 10 | MP Fund MP/2022-23/009/SL/00220-Providing 1 Nos of Mini Highmast light at Ward No. 10 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 420000 |  |  |  | 0 | 0.04 | 95.24 | 2023-12-10 |  | 4200000 | No | Yes
955 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00221 | Zone II | 11 | MP Fund MP/2022-23/009/SL/00221-Providing 1 Nos of Mini Highmast light at Ward No. 11 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 420000 |  |  |  | 0 | 0.04 | 95.24 | 2023-12-10 |  | 4200000 | Yes | Yes
956 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00440 | Zone II | 17 | MP Fund MP Fund/2021-22/009/SL/00440-Providing One Number Mini High Mast Light at Ward No.17 , Dharga Colony , Azagu Colony (Near Vells School) Tambaram Corporation Zone - II | Streetlight | StreetLight | 2829/2022/A3 PALLAVARAMDated:30/07/22 | 2021-22 | 800000 | 400000 | 0 |  |  | 0.04 | 2022-02-08 | 0.03 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 0 |  |  |  | 400000 | 0.03 | 87 | 2022-02-11 |  | 800000 | Yes | Yes
957 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00441 | Zone II | 17 | MP Fund MP Fund/2021-22/009/SL/00441-Providing One Number Mini High Mast Light at Ward No.17 , Vathiyar Manickam Street Tambaram Corporation Zone - II | Streetlight | StreetLight | 2829/2022/A3 PALLAVARAMDated:30/07/22 | 2021-22 | 800000 | 400000 |  |  |  | 0.04 | 2022-02-08 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 391000 |  |  |  | 9000 | 0.03 | 87 | 2022-02-11 |  | 800000 | Yes | Yes
958 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00213 | Zone I | 2 | MP Fund MP/2022-23/009/SL/00213-Providing 1 Nos of Mini Highmast light at Ward No. 2 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 419225 |  |  |  | 775 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
959 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00214 | Zone I | 3 | MP Fund MP/2022-23/009/SL/00214-Providing 1 Nos of Mini Highmast light at Ward No. 3 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 419225 |  |  |  | 775 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
960 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00215 | Zone I | 4 | MP Fund MP/2022-23/009/SL/00215-Providing 1 Nos of Mini Highmast light at Ward No. 4 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 419225 |  |  |  | 775 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
961 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00216 | Zone I | 5 | MP Fund MP/2022-23/009/SL/00216-Providing 1 Nos of Mini Highmast light at Ward No. 5 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/11/23 |  | 0 |  |  |  | 420000 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
962 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00040 | Zone III | 37 | MP Fund MP/2023-24/009/SL/00040-Providing 1nos Mini Highmast Light at ward No.37, Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone III | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 400000 |  |  |  | 0.04 | 2024-09-02 | 0.03 | Completed | 100 | Completed | 100 |  |  | 24/07/24 |  | 0 |  |  |  | 400000 | 0 | 0 | 2024-09-05 |  | 11435000 | Yes | Yes
963 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00041 | Zone III | 36 | MP Fund MP/2023-24/009/SL/00041-Providing 1nos Mini Highmast Light at ward No.36, Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone III | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 400000 |  |  |  | 0.04 | 2024-09-02 | 0.03 | Completed | 100 | Completed | 100 |  |  | 24/07/24 |  | 0 |  |  |  | 400000 | 0 | 0 | 2024-09-05 |  | 11435000 | Yes | Yes
964 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00020 | Zone IV | 33 | MP Fund MP Fund/2021-22/009/SL/00020-Providing 12M Mini Highmast at south (Tank Bund Road) Kulakarai Street Ward No.33 Zone 4 in Tambaram City Municipal Corporation | Streetlight | StreetLight | 2829/2022/A3 4Dated:30/07/22 | 2021-22 | 1070000 | 400000 |  |  |  | 0.04 | 16/11/22 | 0.03 | Completed | 100 | Completed | 100 |  |  | 2023-06-02 |  | 400000 |  |  |  | 0 | 0.04 | 99.11 | 13/08/23 |  | 1070000 | Yes | Yes
965 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00021 | Zone IV | 33 | MP Fund MP Fund/2021-22/009/SL/00021-Providing 12M Mini Highmast at Thomas Street RV Garden Road Junction Ward No.33 Zone 4 in Tambaram City Municipal Corporation | Streetlight | StreetLight | 2829/2022/A3 4Dated:30/07/22 | 2021-22 | 1070000 | 400000 |  |  |  | 0 | 16/11/22 | 0.03 | Completed | 100 | Completed | 100 |  |  | 2023-07-04 |  | 400000 |  |  |  | 0 | 0.04 | 99.11 | 16/12/22 |  | 1070000 | Yes | Yes
966 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00281 | Zone I | 2 | MP Fund MP Fund/2021-22/009/SL/00281-Providing 12 M Mini Highmast at Babu Chetty Avenue, Kamarajar Salai Junction Ward No 2 Zone -1 in Tambaram City Municipal Corporation | Streetlight | StreetLight | 2829/2022/A3Dated:30/07/22 | 2021-22 | 800000 | 400000 | 0 |  |  | 0.04 | 29/08/22 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2022-11-11 |  | 395838 |  |  |  | 4162 | 0.04 | 98.96 | 28/09/22 |  | 800000 | Yes | Yes
967 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/SL/00282 | Zone I | 12 | MP Fund MP Fund/2021-22/009/SL/00282-Providing 12 M Mini Highmast at Veerasamy Nagar Ward No 12 Zone -1 in Tambaram City Municipal Corporation | Streetlight | StreetLight | 2829/2022/A3Dated:30/07/22 | 2021-22 | 800000 | 400000 |  |  |  | 0.04 | 29/08/22 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2022-01-12 |  | 400000 |  |  |  | 0 | 0.04 | 98.96 | 28/09/22 |  | 800000 | Yes | Yes
968 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00023 | Zone V | 62 | MP Fund MP/2023-24/009/SL/00023-Providing 1nos Mini High mast Light for ward No.62, Irumbuliyur Old GST road, Near Kulakarai Tambaram Constituency, Chengalpattu District, Zone V | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0.04 | 31/01/24 | 0.03 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 0 |  |  |  | 420000 | 0.04 | 96.33 | - |  | 11435000 | Yes | Yes
969 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00024 | Zone V | 62 | MP Fund MP/2023-24/009/SL/00024-Providing 1nos Mini High mast Light for ward No.62, Thilagavathy Nagar, Balaji Nagar, Arul Nagar, Kurinji Nagar, Ponnan Nagar jucntion Tambaram Constituency, Chengalpattu District, Zone V | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0.04 | 31/01/24 | 0.03 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 0 |  |  |  | 420000 | 0.04 | 96.33 | - |  | 11435000 | Yes | Yes
970 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00025 | Zone IV | 51 | MP Fund MP/2023-24/009/SL/00025-Providing 1nos Mini mast Light for ward No.51,Puthangal lake (Rajmohan Nagar) Tambaram Constituency, Chengalpattu District, Zone IV | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 760000 |  |  |  | 0.08 | 29/01/24 | 0.06 | Completed | 100 | Completed | 100 |  |  | 22/08/24 |  | 735955 |  |  |  | 24045 | 0 | 0 | 29/04/24 |  | 11435000 | No | Yes
971 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00026 | Zone IV | 53 | MP Fund MP/2023-24/009/SL/00026-Providing 1nos High mast Light for ward No.53, Kulakkarai street & Chelliamman kovil street junction Tambaram Constituency, Chengalpattu District, Zone IV | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 680000 |  |  |  | 0.07 | 2024-01-02 | 0.06 | Completed | 100 | Completed | 100 |  |  | 2024-08-08 |  | 0 |  |  |  | 680000 | 0.06 | 95.31 | - |  | 11435000 | Yes | Yes
972 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00027 | Zone IV | 33 | MP Fund MP/2023-24/009/SL/00027-Providing 1nos Mini High mast Light for ward No.33, Moulana Nagar & Rail Nagar junction Tambaram Constituency, Chengalpattu District, Zone IV | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-05-02 | 0.03 | Completed | 100 | Completed | 100 |  |  | 23/05/24 |  | 414840 |  |  |  | 5160 | 0 | 0 | 2024-05-05 |  | 11435000 | No | Yes
973 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00028 | Zone IV | 33 | MP Fund MP/2023-24/009/SL/00028-Providing 1nos Mini High mast Light for ward No.33, North Tankbund & West Tank bund street junction Tambaram Constituency, Chengalpattu District, Zone IV | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-05-02 | 0.03 | Completed | 100 | Completed | 100 |  |  | 16/05/24 |  | 414840 |  |  |  | 5160 | 0 | 0 | 2024-05-05 |  | 11435000 | No | Yes
974 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00029 | Zone V | 48 | MP Fund MP/2023-24/009/SL/00029-Providing 1nos Mini High mast Light for ward No.48, Nalvar street & Bharatha madh street junction Tambaram Constituency, Chengalpattu District, Zone V | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0.04 | 31/01/24 | 0.03 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 0 |  |  |  | 420000 | 0.04 | 96.52 | - |  | 11435000 | Yes | Yes
975 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00030 | Zone V |  | MP Fund MP/2023-24/009/SL/00030-Providing 1nos Mini High mast Light at St.Fathima Annai Temple Graveyard , Tambaram Constituency, Chengalpattu District, Zone V | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 700000 |  |  |  | 0 | 22/01/24 | 0.05 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 657625 |  |  |  | 42375 | 0 | 0 | - |  | 11435000 | No | Yes
976 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00031 | Zone V | 48 | MP Fund MP/2023-24/009/SL/00031-Providing 1nos Mini High mast Light at ward No.48, Kalidasan street, Baradwaj street and Kazhamegam street and Sethadevi Mosque junction , Tambaram Constituency, Chengalpattu District, Zone V | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 700000 |  |  |  | 0.07 | 31/01/24 | 0 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 0 |  |  |  | 700000 | 0.07 | 93.95 | - |  | 11435000 | Yes | Yes
977 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00037 | Zone I | 30 | MP Fund MP/2023-24/009/SL/00037-Providing 1nos Mini Highmast Light at ward No.30, Kivaraj estate Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Completed | 100 | Work Completed | 100 |  |  | 25/03/24 |  | 408085 |  |  |  | 11915 | 0 | 0 | - |  | 11435000 | No | Yes
978 | Tambaram | MP Fund | CHENGALPATTU | MP/2022-23/009/SL/00212 | Zone I | 1 | MP Fund MP/2022-23/009/SL/00212-Providing 1 Nos of Mini Highmast light at Ward No. 1 Tambaram Corporation Pallavaram Constituency | Streetlight | StreetLight | 3859/2022/R3Dated:17/08/23 | 2022-23 | 4200000 | 420000 |  |  |  | 0.04 | 2023-12-09 | 0.03 | Completed | 100 | Work Completed | 100 |  |  | 16/11/23 |  | 419225 |  |  |  | 775 | 0.04 | 95.24 | - |  | 4200000 | No | Yes
979 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00032 | Zone I | 5 | MP Fund MP/2023-24/009/SL/00032-Providing 1nos Mini Highmast Light at ward No.5 Fathima Nagar, Tambaram Corporation, Pallavapuram Constituency , Chengalpattu District, Zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | - | 0 | Completed | 100 | Work Completed | 100 |  |  | 27/03/24 |  | 403885 |  |  |  | 16115 | 0 | 0 | - |  | 11435000 | No | Yes
980 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/SL/00033 | Zone I | 5 | MP Fund MP/2023-24/009/SL/00033-Providing 1nos Mini Highmast Light at ward No.5, near Arts School Tambaram Corporation, Pallavapuram Constituency Chengalpattu District, Zone I | Streetlight | StreetLight | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 420000 |  |  |  | 0 | 2024-03-02 | 0.04 | Completed | 100 | Work Completed | 100 |  |  | 27/03/24 |  | 403885 |  |  |  | 16115 | 0 | 0 | - |  | 11435000 | No | Yes
981 | Tambaram | MP Fund | CHENGALPATTU | MP/2024-25/009/SL/00452 | Zone I | 5 | MP Fund MP/2024-25/009/SL/00452-Providing 1 no Mini High mast Light at ward No.05 Zone I Tambaram City Municipal Corporation | Streetlight | StreetLight | 0881/2025/A3Dated:11/04/25 | 2024-25 | 4400000 | 400000 |  |  |  | 0 | 2025-12-05 | 0.04 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 400000 | 0 | 0 | - |  | 4400000 | No | Yes
982 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/ROAD/00152 |  |  | 15th CFC 15th CFC/2020-21/009/ROAD/00152-Relaying of Road-021/2021/012/R/0000239-KENNEDY STREET MUNGIL ERI , 021/2021/012/R/0000242-SASTHIRI STREET MUNGIL ERI , 021/2021/014/R/0000664-EASWARAN NAGAR 1ST CROSS STREET , 021/2021/016/R/0000300-RAMANATHAN STREET - GANDHI NAGAR , 021/2021/016/R/0000307-BALASUBRAMANI STREET , | Roads | Bituminous Road | 17349 / 2019 / E3Dated:14/10/19Road DetailsRoad Length :Mts | 2020-21 | 9818000 | 5110000 |  |  |  | 0.51 | 13/11/19 | 0.47 | Completed | 100 | Completed | 100 |  |  | 14/12/22 |  | 5100000 |  |  |  | 10000 | 0.58 | 112.97 | 2020-12-01 |  | 9818000 | Yes | Yes
983 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/ROAD/00153 |  |  | 15th CFC 15th CFC/2020-21/009/ROAD/00153-Relaying of Road-021/2021/001/R/0000639-VISWESWAPURAM 1ST STREET , 021/2021/001/R/0000432-SHANKAR NAGAR 40TH STREET , 021/2021/002/R/000022-1ST CROSS STREET LIC COLONY , 021/2021/003/R/000035-ARUMUGAM STREET V O C NAGAR , 021/2021/003/R/0000566-ARUMUGAM CROSS STREET , 021/2021/003/R/000029-SUNDHARA VADIVEL STREET , 021/2021/006/R/0000101-DEIVANAYAGAM STREET PASUMPON NAGAR , 021/2021/006/R/0000479-PASUPON NAGAR MANIYAN STREET , 021/2021/007/S/0000526-ELUMALAI CROSS STREET , 021/20 | Roads | Bituminous Road | 17349 / 2019 / E3Dated:14/10/19Road DetailsRoad Length :Mts | 2020-21 | 9818000 | 4708000 |  |  |  | 0.47 | 13/11/19 | 0.43 | Completed | 100 | Completed | 100 |  |  | 14/12/22 |  | 4708000 |  |  |  | 0 | 0.52 | 110.45 | 2020-12-01 |  | 9818000 | Yes | Yes
984 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00438 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00438-Repair /Maintenance-009/05/069/R/3169-SECRETARIAT COLONY 2ND MAIN ROAD , 009/01/010/R/1519-DELLI STREET PERIYAR NAGAR , 009/05/069/R/3172-ERRATTAIMALAI SRINIVASAN STREET , | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 600000 |  |  |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Completed | 100 | 2022-11-03 |  | 22/03/22 |  | 598740 |  |  |  | 1260 | 0.06 | 99.79 | 18/01/22 |  | 4775000 | Yes | Yes
985 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00174 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00174-Relaying of Road-009001R0002-BHARATHIYA DESIYA SANGAM STREET , 009002R0178-BALAJI NAGAR 30 ROAD , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :540 Mts | 2023-24 | 319260000 | 2520000 |  |  |  | 0.23 | 2023-05-08 | 0 | Completed | 100 | Completed | 100 | 20/02/24 |  | 15/03/24 |  | 2522720 |  |  |  | -2719.7 | 0.23 | 90.21 | - |  | 319260000 | No | Yes
986 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00175 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00175-Relaying of Road-009002R0132-BALAJI NAGAR 9TH STREET , 009002R0177-BALAJI NAGAR RADHAKRISHNAN ST , 009002R0095-VENKATESWARA NAGAR KALAIMAGAL CROSS STREET , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :500 Mts | 2023-24 | 319260000 | 1900000 |  |  |  | 0.17 | - | 0 | Completed | 100 | Completed | 100 |  |  | 2023-01-11 |  | 507926 |  |  |  | 1392074 | 0.05 | 26.73 | - |  | 319260000 | No | Yes
987 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/ROAD/00155 |  |  | 15th CFC 15th CFC/2020-21/009/ROAD/00155-Relaying of Road-021/2021/012/R/0000237-NATARAJAN STREET MUNGIL ERI , 021/2021/012/R/0000243-KASTHURI BAI STREET MUNGIL ERI , 021/2021/014/R/0000276-MOSES STREET EASWARAN NAGAR , 001/2021/002/R/00006-RAJIV GANDHI, 1ST CROSS STREET , 001/2021/002/R/0000741-RAJIV GANDHI 3RD CROSS ST , 021/2021/015/S/0000283-SABAPATHY NAGAR 2ND STREET , 021/2021/015/R/0000284-SABAPATHY NAGAR 3RD STREET , 021/2022/021/R/00002-RANI ANNA STREET , 021/2021/015/R/0000502-APPADURAI STREET SIVASANKARAN NAGAR | Roads | Bituminous Road | 12981 / 2018 / E3Dated:10/08/18Road DetailsRoad Length :Mts | 2020-21 | 5000000 | 5000000 |  |  |  | 0.5 | 31/10/18 | 0.46 | Completed | 100 | Completed | 100 |  |  | 13/12/22 |  | 5000000 |  |  |  | 0 | 0.5 | 100.37 | 30/12/18 |  | 5000000 | Yes | Yes
988 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00171 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00171-Relaying of Road-009005R0374-SHANKAR NAGAR 24TH STREET , 009005R0375-SHANKAR NAGAR 23RD STREET , 009005R0376-SHANKAR NAGAR 25TH STREET , 009005R0424-SHANKAR NAGAR 26TH STREET , 009005R0406-SHANKAR NAGAR 28TH STREET , 009005R0391-SANKAR NAGAR 35TH STREET , 009005R0359-Srinivasapuram Extension , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :980 Mts | 2023-24 | 319260000 | 4980000 |  |  |  | 0.45 | 31/08/23 | 0.5 | Completed | 0 | Completed | 100 |  |  | 13/09/24 |  | 4938304 |  |  |  | 41696 | 0.33 | 66.62 | 29/11/23 |  | 319260000 | No | Yes
989 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00172 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00172-Relaying of Road-009012R0861-NEDUJAZHIYAN STREET CHOZHAVARAM NAGAR , 009012R0860-THANGARAJ STREET CHOZHAVARAM NAGAR , 009012R0898-LINGAM STREET , 009012R0913-APPU STREET SAMUNDEESHWARI NAGAR , 009012S0089-NEHRU STREET NAAGAL KENI , 009012R0873-THANTHAI PERIYAR STREET CHOZHAVARAM NAGAR , 009012R0871-THANDHAI PERIYAR 2ND CROSS STREET CHOZHAVARAM NAGAR , 009012R0892-ASHOKAN STREET KAMARAJAR NAGAR , 009012R0881-1ST STREET KAMARAJA NAGAR , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1240 Mts | 2023-24 | 319260000 | 5260000 |  |  |  | 0.4 | 13/09/23 | 0.53 | Completed | 100 | Completed | 100 |  |  | 16/05/25 |  | 5260000 |  |  |  | 0 | 0.51 | 97.44 | - |  | 319260000 | No | Yes
990 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00170 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00170-Relaying of Road-009005R0396-SHANKAR NAGAR 2ND STREET , 009005R0388-SHANKAR NAGAR 4TH STREET , 009005R0377-SHANKAR NAGAR 5TH STREET , 009005R0395-SHANKAR NAGAR 6TH STREET , 009005R0412-11TH STREET SANKAR NAGAR , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :752 Mts | 2023-24 | 319260000 | 3300000 |  |  |  | 0.32 | 13/09/23 | 0.33 | Completed | 100 | Work Completed | 100 |  |  | 2024-12-09 |  | 0 |  |  |  | 3300000 | 0.32 | 97.43 | 2023-12-12 |  | 319260000 | No | Yes
991 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00136 |  |  | TURIP TURIP/2023-24/009/ROAD/00136-Relaying of Road-009005R0365-BASKARAN STREET V.O.C NAGAR , 009005R0367-SHANKAR NAGAR 7TH STREET , 009005R0366-SHANKAR NAGAR 10TH STREET , 009005R0383-9TH STREET SANKAR NAGAR , 009005R0430-5TH CROSS STREET LIC COLONY , 009005R0405-SHANKAR NAGAR 1ST CROSS STREET , 009005R0411-KAMBER STREET V .O .C NAGAR , 009005R0364-BHARATHIYAR STREET V.O.C NAGAR , 009005R0372-3RD STREET SANKAR NAGAR , 009005R5768-SRINIVASAN STREET LIC COLONY , 009005R5774-LIC Colony Jayatheertha Rao Cross s | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :4639 Mts | 2023-24 | 313620000 | 20000000 |  |  |  | 1.8 | 20/07/23 | 2 | Completed | 100 | Work Completed | 100 |  |  | 28/01/25 |  | 19903472 |  |  |  | 96528 | 1.8 | 90 | 18/10/23 |  | 313620000 | No | Yes
992 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00069 |  |  | TURIP TURIP/2024-25/009/ROAD/00069-Relaying of Road-Bituminous Road009045R3383-CAMP ROAD , 009046R3433-MANGAIYARKARASI STREET , 009046R3444-ESWARI NAGAR MAIN ROAD , 009047R3479-THIRUMANGAIMANAN ST , 009047R3489-KASIYAPPAR STREET , 009048R3508-VIYASAR STREET , 009048R3517-VIYASAR STREET (SUGAMAGARISHI ST TO KAMBAR STREET) , 009048R3524-SIVAGNANAM STREET , 009062S0530-BALAJI NAGAR YAMUNA 1ST CROSS ST , 009062S0534-BALAJI NAGAR YAMUNA EXTN 3RDD CR , 009065R4895-PONNIYAMMAN KOIL STREET , 009064R4836-VENKATESAN STREET , | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :2625 Mts | 2024-25 | 169399000 | 12600000 |  |  |  | 1.13 | 27/02/24 | 1.21 | Completed | 100 |  | 100 |  |  | 28/02/25 |  | 12552261 |  |  |  | 47739 | 1.13 | 90 | - |  | 169399000 | No | Yes
993 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00070 |  |  | TURIP TURIP/2024-25/009/ROAD/00070-Relaying of Road-Bituminous Road009063R4796-M.E.S. ROAD , 009065R4947-KVN NAGAR MAIN ROAD , 009066R6265-Ragavendhra nagar 1st cross street , 009067R5157-SHANTHINIKITAN COLONY 3RD STREET , 009068R5361-BAI GARDEN MAIN ROAD , 009069R5386-S R Colony to K Bus Route Link Road , 009069R5387-S R Colony to Prashanthi Colony Link Road , 009070R6357-A.L.S.NAGAR MAIN ROAD , | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :2625 Mts | 2024-25 | 169399000 | 12499000 |  |  |  | 1.13 | 27/02/24 | 1.19 | Completed | 100 |  | 100 |  |  | 28/02/25 |  | 12480656 |  |  |  | 18344 | 1.13 | 90.01 | - |  | 169399000 | No | Yes
994 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00123 |  |  | TURIP TURIP/2023-24/009/ROAD/00123-Relaying of Road-009006R0455-ANNAI THERESA STREET V O C NAGAR , 009006R0486-TEACHER SAMUVEL STREET , 009006R0483-GOKULAM COLONY PAMMAL , 009006R0467-SERAN STREET V.O.C. NAGAR , 009006R0471-T.R. MANI STREET V O C NAGAR , 009006R0494-SAMUVEL STREET , 009006R0506-JAGANATHAN STREET PASUMPON NAGAR , 009006R0507-GOWTHAMAN STREET PASUMPON NAGAR , 009006R0437-1ST CROSS STREET LIC COLONY , 009006R0450-M G R NAGAR 4TH STREET , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1421 Mts | 2023-24 | 313620000 | 5600000 |  |  |  | 0.5 | 20/07/23 | 0.56 | Completed | 100 | Work Completed | 100 |  |  | 2024-03-08 |  | 4936964 |  |  |  | 663036 | 0.49 | 88.16 | 18/10/23 |  | 313620000 | No | Yes
995 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00208 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00208-Relaying of Road-009/03/023/S/0001-AGS COLONY 5TH CROSS STREET , 007/2021/018/R/0000183-AGS COLONY 2ND CROSS STREET , 009/03/023/R/0009-AGS COLONY MAIN ROAD , 007/2021/022/R/0000662-VEMBULIAMMAN KOIL STREET , 007/2021/018/R/0000191-OM SAKTHI NAGAR EXTENSION , 009/03/022/R/0010-Nemilichery Road , | Roads | Bituminous Road | Go.(Ms)No.2Dated:07/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.57 | 2021-11-08 | 1.83 | Completed | 100 | Total Works-8, All 8 Works Fully Completed | 100 |  |  | 28/02/23 |  | 17679000 |  |  |  | 2321000 | 1.57 | 78.65 | 2022-11-02 |  | 100000000 | Yes | Yes
996 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00474 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00474-Repair /Maintenance-009/01/007/R/0454-NALLATHAMI ROAD , 009/01/007/R/0462-INDIRA GANDHI ROAD ANNA NAGAR , | Roads | Bituminous Road | 31442/2021/MAD3 (Pammal)Dated:18/08/22Road DetailsRoad Length :1286 Mts | 2021-22 | 400000 | 400000 |  |  |  | 0.04 | 13/09/22 | 0.03 | Completed | 100 | Work Fully Completed | 100 |  |  | 20/12/21 |  | 400000 |  |  |  | 0 | 0.04 | 90.93 | 28/09/22 |  | 400000 | Yes | Yes
997 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00443 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00443-Repair /Maintenance-009/04/056/R/1399-METTU STREET , 009/01/001/R/0274-ADANCHIYAMMAN KOIL STREET , 009/01/002/R/0079-GURUSWAMY NAGAR MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 384000 |  |  |  | 0.04 | 2022-03-01 | 0.03 | Completed | 100 | Work Completed | 100 |  |  | 2022-11-08 |  | 4 |  |  |  | 383996.16 | 0.04 | 99.99 | 18/01/22 |  | 5357000 | Yes | Yes
998 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00450 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00450-Repair /Maintenance-009/01/004/R/1330-ANNA NAGAR 1ST MAIN ROAD , 009/01/004/R/0456-ANNA NAGAR 9TH STREET , 009/01/003/R/1493-SHANMUGA MUDALI STREET , 009/02/024/R/4529-SANNATHI STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 551000 | 0 | 0 |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Work Completed | 100 |  |  | 2022-08-11 |  | 551000 |  |  |  | 0 | 0.06 | 99.96 | 18/01/22 |  | 5357000 | Yes | Yes
999 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00451 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00451-Repair /Maintenance-009/03/042/L/0114-MGR NAGAR 1ST CROSS STREET , 009/01/002/R/0146-G.K.NAGAR 2ND STREET , 009/01/002/R/0121-VENKATESWARA NAGAR KAMBAR STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 735000 |  |  |  | 0.07 | 2022-03-01 | 0.06 | Completed | 100 | Work Completed | 100 |  |  | 2022-08-11 |  | 7 |  |  |  | 734992.65 | 0.07 | 99.97 | 18/01/22 |  | 5357000 | Yes | Yes
1000 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00452 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00452-Repair /Maintenance-009/01/002/R/0341-BALAJI NAGAR 18TH STREET , 009/03/044/R/2132-RADHAKRISHNAN STREET , 009/03/022/R/0217-KUMARAN STREET , 009/05/064/R/3974-THIRUMURUGAN STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 551000 |  | 0 | 0 | 0.05 | 2022-03-01 | 0.04 | Completed | 100 | Work Completed | 100 |  |  | 2022-11-08 |  | 548209 |  |  |  | 2791 | 0.05 | 99.49 | 18/01/22 |  | 5357000 | Yes | Yes
1001 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00453 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00453-Repair /Maintenance-009/03/034/S/0288-KALAIVANAR STREET , 009/01/002/R/0386-NARACHIMMA CHETTY STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 368000 | 0 |  |  | 0.04 | 2022-03-01 | 0.03 | Completed | 100 | Work Completed | 100 |  |  | 2022-08-11 |  | 4 |  |  |  | 367996.32 | 0.04 | 99.85 | 18/01/22 |  | 5357000 | Yes | Yes
1002 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00439 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00439-Repair /Maintenance-009/01/012/R/0958-4TH STREET ARKESWARN COLONY , 009/01/012/R/1144-BHARATHIYAR STREET CHOLAVARAM NAGAR , 009/01/012/R/1040-SELVA VINAYAGAR KOIL STREET , 009/01/012/R/1147-ARKEESWARAR COLONY 2ND CROSS STREET , | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 960000 |  |  |  | 0.1 | 2022-03-01 | 0.08 | Completed | 100 | Work Completed | 100 |  |  | 2022-11-08 |  | 10 |  |  |  | 959990.4 | 0.1 | 99.88 | 18/01/22 |  | 4775000 | Yes | Yes
1003 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00173 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00173-Relaying of Road-009003R0224-DEVARAJ NAGAR EXTN 1ST STREET , 009003R0227-INDIRA NAGAR LAL.BAGADUR SASTHRI ST , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :370 Mts | 2023-24 | 319260000 | 1370000 |  |  |  | 0.07 | 2023-05-08 | 0.13 | Completed | 100 | Work Completed | 100 |  |  | 19/01/24 |  | 0 |  |  |  | 1370000 | 0.07 | 47.5 | - |  | 319260000 | No | Yes
1004 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00435 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00435-Repair /Maintenance-009/01/006/R/1476-VETHAGIRI MUDALIYAR STREET , 009/01/006/S/0210-IRATTAI PILLAIYAR KOVIL 1ST CROSS STREET , 009/03/025/R/0881-TL RAGUPATHY STREET , 009/01/006/R/0412-GIRIKORI STREET PASUMPON NAGAR , 009/01/006/R/0424-VASUDEVAN STREET PASUMPON NAGAR , 009/01/006/R/0426-GOWTHAMAN STREET PASUMPON NAGAR , 009/01/006/R/0432-MA. SURAN STREET , 009/05/045/R/4340-ELUMALAI CROSS STREET , 009/01/007/R/0444-VADIVEL STREET H L COLONY , 009/01/007/R/0454-NALLATHAMI ROAD , | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 810000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Work Completed | 100 |  |  | 2022-11-08 |  | 8 |  |  |  | 809991.9 | 0.08 | 98.99 | 18/01/22 |  | 4775000 | Yes | Yes
1005 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00436 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00436-Repair /Maintenance-009/01/007/R/0469-KALAINGER ROAD ANNA NAGAR , 009/01/007/R/0462-INDIRA GANDHI ROAD ANNA NAGAR , 009/01/007/R/0460-1ST STREET LAKSHMI NARYANAN NAGAR , 009/01/007/R/0477-GANGA STREET ANNA NAGAR , 009/04/052/R/3566-1ST CROSS STREET SBI COLONY , 009/01/008/R/0846-VEERAMAMUNIVAR STREET MUTHAMIZH NAGAR , 009/01/012/S/0120-NARASIMMAN STREET , 009/01/008/R/0811-TEACHER KRISHNASMAY STREET MUTHAMIZH NAGAR , 009/01/008/R/0800-MADHAVAN STREET MUTHAMIZH NAGAR , 009/01/008/R/0 | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 805000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 0 | Work Completd | 100 |  |  | 2022-11-08 |  | 8 |  |  |  | 804991.95 | 0.08 | 99.48 | 18/01/22 |  | 4775000 | Yes | Yes
1006 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00437 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00437-Repair /Maintenance-009/01/011/R/1256-SIGAMANI STREET , 009/01/011/R/1252-RAMANATHAN STREET GANDHI NAGAR , 009/01/011/R/1230-KULASEKARAN STREET , 009/01/011/R/1269-JAYARMAN STREET , | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 615000 |  |  |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Work Completed | 100 |  |  | 2022-11-08 |  | 6 |  |  |  | 614993.85 | 0.06 | 99.81 | 18/01/22 |  | 4775000 | Yes | Yes
1007 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2023-24/009/ROAD/00190 |  |  | Kalaignar Nagarpura Mempatu Thittam KNMT/2023-24/009/ROAD/00190-Relaying of Road-009030R5938-RAMAKRISHNA STREET, LAKSHMIPURAM, CHENNAI-44 , 009030R5940-Sakthi nagar 2nd street , 009030R5941-Kalaivani street , 009031R5950-Dr.Kalaigar street , 009031R5952-Saraswathipuram 5th street extn , 009031R5953-Saraswathipuram 6th street extn , | Roads | Bituminous Road | G.O. (4D) No. 20Dated:08/06/23Road DetailsRoad Length :615 Mts | 2023-24 | 16200000 | 4100000 |  |  |  | 0.21 | 19/07/23 | 0 | Completed | 100 | Work Fully Completed | 100 | 25/10/23 |  | 16/10/23 |  | 4102875 |  |  |  | -2875.16 | 0.26 | 62.63 | 19/10/23 |  | 16200000 | No | Yes
1008 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00357 |  |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00357-Relaying of Road-Bituminous Road009009R0676-MARIAMMAN KOVIL 1ST CROSS STREET , 009009R0675-MARIAMMAN KOIL STREET , 009009R0665-MUNVAR AVENUE 2ND STREET , 009009R0680-Ramalingam Street , 009009R0661-TANNERY STREET , 009009R0699-KUMARASAMY STREET , 009014R0949-P.M.GOPAL STREET , 009014R0932-ST.MARY STREET , 009014R0947-MANIMEGALAI STREET , 009014R0948-Manimegalai Street Extension , 009014R0944-Dr. Saloman Street , 009014R0937-Sarojini 2st Cross Street , 009014R0945-Dr. Salomon Cross Street , 0090 | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :1952 Mts | 2025-26 | 85700000 | 12300000 |  |  |  | 0 | 14/07/25 | 1.23 | Completed | 100 | Completed | 100 |  |  | 2025-10-09 |  | 10146132 |  |  | 0 | 2153868 | 1.11 | 90.1 | 2025-12-10 |  | 85700000 | No | Yes
1009 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00358 |  |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00358-Relaying of Road-Bituminous Road009019S0183-GANESH NAGAR 4TH CROSS STREET , 009019S0171-ARULMURUGAN NGR PAZHAMUDIT SOLAI VEEDI , 009019R1171-GANESH NAGAR 3RD STREET , 009019R1208-KASI VISALAKSHIPURAM VAIGAI ST , 009019R1172-GANESH NAGAR 3RD CROSS STREET , 009019R1207-KASI VISALAKSHIPURAM GODAVERI ST , 009019R1161-New Street , 009019S0178-KIRUPANANDA VARIAR STREET , 009019R1188-Kumaran Street , 009019R5795-Thirumurugan Street , 009019R5792-Ganesh Nagar 5th Street , 009019R1194-NANDHI NAGAR EXTN , | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :2196 Mts | 2025-26 | 85700000 | 12200000 |  |  |  | 0 | 14/07/25 | 1.22 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12200000 | 0.88 | 71.8 | 2025-12-10 |  | 85700000 | No | Yes
1010 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00359 |  |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00359-Relaying of Road-Bituminous Road009041R2707-SANGOTHIAMMAN KOIL STREET , 009041R2786-Radheshyam avenue main road , 009041R2784-RADHE SHYAM AVENUE MAIN ROAD , 009041R2816-Saravana nagar main road , 009041R2819-ALAVATAMMAN KOIL STREET , 009041R2717-SUDAR VIZHI AVENUE SAMY ST , 009041R6002-KRISHNA NAGAR 2ND MAIN ROAD , 009041R2844-SARASWATHY NAGAR 1ST STREET , 009041R2919-Sri krishna avenue main road , 009041R2836-Shah avenue extension 2nd street , 009041R2750-Sri devi avenue Tellus phase 2 , 009041 | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :2932 Mts | 2025-26 | 85700000 | 15000000 |  |  |  | 0 | 14/07/25 | 1.5 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15000000 | 1.35 | 89.89 | 2025-12-10 |  | 85700000 | No | Yes
1011 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00360 |  |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00360-Relaying of Road-Bituminous Road009047R3495-KANDASWAMY COLONY , 009047R3499-GANAPATHY COLONY 1ST CROSS STREET , 009048R3523-VALMIGI STREET (BHARATHMADHA TO THIRUVALLUVAR ST) , 009048R3535-KALAMEGAM 1ST CROSS STREET , 009062R4730-ROJA THOTTAM 1ST CROSS EXTN STREET , 009062R4772-ARUL NAGAR 3RD MAIN ROAD 1ST CROSS , 009062R4773-ARUL NAGAR 3RD MAIN ROAD 2ND CROSS , 009062R4777-ARUL NAGAR IAF GATE STREET , 009062R4769-ARUL NAGAR 1ST MAIN ROAD , 009062R4770-ARUL NAGAR 2ND MAIN ROAD , 009062R4774-ARUL | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :3494 Mts | 2025-26 | 85700000 | 21500000 |  |  |  | 0 | 14/07/25 | 2.15 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 21500000 | 1.94 | 90 | 2025-12-10 |  | 85700000 | No | Yes
1012 | Tambaram | 15TH CFC-MPC-AAQ | CHENGALPATTU | MPC/2023-24/009/ROAD/00075 |  |  | 15TH CFC-MPC-AAQ MPC/2023-24/009/ROAD/00075-Relaying of Road-Bituminous Road009049R3594-GANDHI ROAD , | Roads | Bituminous Road | 16476/2023/EA-2Dated:13/03/24Road DetailsRoad Length :772 Mts | 2023-24 | 9200000 | 9200000 |  |  |  | 0.92 | 24/06/24 | 0.77 | Completed | 100 | Completed | 100 | 19/02/25 |  | 21/05/25 |  | 9200000 |  |  |  | 0 | 0.92 | 100 | - |  | 9200000 | Yes | Yes
1013 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00134 |  |  | TURIP TURIP/2023-24/009/ROAD/00134-Relaying of Road-009046R3419-CLUB ROAD , 009046R3420-CLUB ROAD , 009047R3492-THIRUVALLUVAR STREET (KASIAPPAR STREET TO KANDASAMY COLONY) , 009048R3529-SUNDARESWARAR KOIL STREET , 009048R3516-AGASTHIAR STREET (SUGAMAHARISHI TO KAMBAR STREET ) , 009048R3507-AGASTHIAR STREET (VALMIGI TO SUGA MAGARISHI STREET) , 009062R4715-BALAJI NAGAR YAMUNA ST , 009062R4716-BALAJI NAGAR YAMUNA 1ST ST , 009064R4824-ARUMUGANAR STREET , 009064R4830-VANJINATHAN ST , 009045R3347-DHAIRIYALAKSHMI ST , 009065R4995-A.P.N. | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :4537 Mts | 2023-24 | 313620000 | 21300000 |  |  |  | 1.92 | 18/07/23 | 2.08 | Completed | 100 | Completed | 100 | 2024-10-01 |  | 29/04/24 |  | 17875876 |  |  |  | 3424124 | 1.79 | 83.92 | 23/10/23 |  | 313620000 | No | Yes
1014 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00135 |  |  | TURIP TURIP/2023-24/009/ROAD/00135-Relaying of Road-009032R2072-KK PALAYAM BAJANAI KOIL STREET , 009033R2133-KAMATCHI NAGAR 1ST CROSS STREET , 009033R2134-KAMATCHI NAGAR 2ND CROSS STREET , 009003R5756-KAMATCHI NAGAR 3RD CROSS ST , 009033R2123-DURGA NAGAR MAIN ROAD , 009033R2131-KAMATCHI NAGAR 1ST MAIN ROAD , 009049R3565-New State Bank Colony 1st Street , 009049R3546-BHAKTHAVATCHALAM ST , 009051R3621-SIVAM ENCLAVE , 009051R3625-BEMASWARAN STREET , 009051R3624-SIVARAJ ST , 009051R3668-THIRUVALLUVAR 3RD ST , 009051R3670-THIRUVALLUV | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2677 Mts | 2023-24 | 313620000 | 9300000 |  |  |  | 0.84 | 19/07/23 | 0.93 | Completed | 100 | Completed | 100 | 20/03/25 |  | 16/05/25 |  | 9300000 |  |  |  | 0 | 0.68 | 73.29 | 17/10/23 |  | 313620000 | No | Yes
1015 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00132 |  |  | TURIP TURIP/2023-24/009/ROAD/00132-Relaying of Road-009065R5029-VEDHACHALAM NAGAR , 009065R4983-MARUTHI AVENUE 2ND STREET , 009065R49997-SARATHA GARDEN 1ST MAIN STREET , 009065R4935-THIRUVALLUR STREET , 009065R4928-AVVAI 1ST STREET , 009065R5002-BAGAVATHI NAGAR 2ND MAIN ROAD , 009065R5007-KVK NAGAR , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1113 Mts | 2023-24 | 313620000 | 3700000 |  |  |  | 0.33 | 18/07/23 | 0.36 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 3508000 |  |  |  | 192000 | 0.33 | 90 | 23/10/23 |  | 313620000 | No | Yes
1016 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/ROAD/00059 | Zone III |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/ROAD/00059-Relaying of Road-Bituminous Road009022R1467-KATTABOMMAN STREET , 009022R1466-VANCHINATHAN STREET , 009022R1543-JAIN NAGAR MAIN ROAD , 009023R1563-SURYA AVENUE , 009023R1610-POSTAL NAGAR , 009025R1703-HANUMAR KOIL STREET , 009025R1715-SRI DEVI AMMAN STREET , Package No.I- Zone III | Roads | Bituminous Road | 11919/2022/EA-2.roadDated:29/01/24Road DetailsRoad Length :1627 Mts | 2023-24 | 17500000 | 7500000 |  |  |  | 0.68 | 28/02/24 | 0.72 | Completed | 100 | Completed | 100 | 2024-03-05 |  | 14/05/24 |  | 0 |  |  |  | 7500000 | 0.67 | 89.11 | 28/05/24 |  | 17500000 | No | Yes
1017 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/ROAD/00060 | Zone III |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/ROAD/00060-Relaying of Road-Bituminous Road009035R2265-PADMANABHAN STREET , 009035R2276-SUBRAMANIYAR STREET , 009035R2279-PATEL STREET , 009036R2281-ANNAMALAI STREET , 009036R2283-PURUSOTHAMAN NAGAR 2ND MAIN ROAD , 009036R2297-BASHIYAM NAGAR 4TH STREET , 009036R2324-V.N.SAMY STREET , 009037R2386-THIRUVALLUVAR STREET , 009037R2350-VENKATRAMAN NAGAR 3RD MAIN ROAD , 009038S0394-VINOBAJI NAGAR 16TH STREET , Package No.II- Zone III | Roads | Bituminous Road | 11919/2022/EA-2.roadDated:29/01/24Road DetailsRoad Length :2076 Mts | 2023-24 | 17500000 | 10000000 |  |  |  | 0.9 | 28/02/24 | 0.96 | Completed | 100 | Completed | 100 | 2024-03-05 |  | 14/05/24 |  | 0 |  |  |  | 10000000 | 0.9 | 89.5 | 28/05/24 |  | 17500000 | No | Yes
1018 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2025-26/009/ROAD/00355 |  |  | 15th CFC UnTied Grant 15thCFCunt/2025-26/009/ROAD/00355-Relaying of Road-Bituminous Road009006R0498-C.V. MOSSES STREET PASUMPON NAGAR , 009006R0448-OM BHARASHAKTHI STREET V.O.C NAGAR , 009006R0508-GODHANDAN STREET PASUMPON NAGAR , 009006R0497-GIRIKORI STREET PASUMPON NAGAR , 009006R0505-VASUDEVAN STREET PASUMPON NAGAR , 009006R0494-SAMUVEL STREET , 009006R0447-T R MANI 1ST CROSS STREET , 009006R0487-ERATAI PILLIYAR KOIL STREET , 009006R0500-T.L. RAGUPATHI STREET PASUMPON NAGAR , 009006R0470-BARTHI DASAN 1ST CROSS STREET , 009006R | Roads | Bituminous Road | 11919/2022/EA2Dated:13/05/25Road DetailsRoad Length :2197 Mts | 2025-26 | 85700000 | 15700000 |  |  |  | 0.97 | 14/07/25 | 1.57 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 15700000 | 0.97 | 61.75 | - |  | 85700000 | No | Yes
1019 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00190 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00190-Relaying of Road-009/2021/016/R/000034-NAGAMMAL STREET , 009/2021/016/R/000062-MUTHURAMALINGA DEVAR ST , 009/2021/032/R/0001002-SALOMAN STREET , 007/2021/008/R/0001276-Dr. Salomon Cross Street , 009/2021/017/R/000076-RAJA RAO ST , 009/2021/018/R/0000146-THANGAL KARAI ST , 009/2021/018/R/0000141-VGN AVENUE , 009/2021/018/R/0001230-RAJAJI STREET , 009/2021/018/R/0000106-ESWARI NAGAR 1ST EXTN CROSS , 007/2021/003/L/0000600-KANNAN STREET , 009/2021/029/R/0000974-SCHOOL ST , 009/2021/018/R/0001232-RA | Roads | Bituminous Road | G.O.(Ms) No. 02Dated:25/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.26 | 2021-09-08 | 1.83 | Completed | 100 | Completed | 100 |  |  | 2025-03-03 |  | 18476531 |  |  |  | 1523469 | 1.61 | 80.31 | 2022-12-02 |  | 100000000 | Yes | Yes
1020 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00191 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00191-Relaying of Road-007/2021/022/R/0000671-DHANALAKSHMI STREET , 007/2021/015/R/0000330-GANESH NAGAR 1ST MAIN ROAD , 009/2021/019/R/0000159-GANESH NAGAR SILAPATHIKARAM STREET , 009/2021/019/R/0000171-RAJESWARI NAGAR MAIN ROAD (100 FEET ROAD) , 009/2021/019/R/0001247-ABIRAMI STREET , 009/2021/019/R/0000169-KANNAN NAGAR , 007/2021/018/R/0000201-GANGAI AMMAN KOIL STREET , 009/2021/020/S/0000244-PONNIAMMAN KOIL ST 2ND CROSS , 009/2021/020/R/0000259-AMBEDKAR NAGAR BURIAL GROUND , 009/2021/021/R/0000427- | Roads | Bituminous Road | G.O.(Ms) No. 02Dated:25/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.63 | 2021-09-08 | 1.76 | Completed | 100 | Completed | 100 |  |  | 21/11/24 |  | 19911931 |  |  |  | 88069 | 1.72 | 86.1 | 2022-12-02 |  | 100000000 | No | Yes
1021 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00192 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00192-Relaying of Road-001/2021/013/R/0000246-JAGAJEEVANRAMAN STREET , 009/2021/021/R/0000384-IAF ROAD (ZION SCHOOL SIDE) , 009/2021/025/R/0000501-M.E.S. 2ND ST , 007/2021/011/R/0000634-THIRUVALLUVAR STREET , 009/2021/026/R/0000516-SUDHANANDA BHARATHI ST CROSS , 001/2021/008/R/0000433-Roja thottam main road , 009/2021/027/R/0000622-ARUL NAGAR , | Roads | Bituminous Road | G.O.(Ms) No. 02Dated:25/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.96 | 2021-09-08 | 2 | Completed | 100 | Completed | 100 |  |  | 24/09/24 |  | 19209563 |  |  |  | 790437 | 1.93 | 96.49 | 2022-09-05 |  | 100000000 | Yes | Yes
1022 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00193 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00193-Relaying of Road-009/2021/038/R/0001197-PULIKORADU 1ST CROSS STREET , 009/2021/038/R/0001212-PULIKORADU EXTN SOUTH 3RD STREET , 009/2021/001/R/0000787-MIDDLE STREET , 009/2021/001/L/0000775-AMMAN KOIL 2ND CROSS STREET , 009/2021/001/R/0001317-ARPUTHAM NAGAR , 009/2021/005/R/0001326-4TH CROSS STREET RANGANATHAPURAM , 001/2021/004/R/0000679-KULAKARAI STREET , | Roads | Bituminous Road | G.O.(Ms) No. 02Dated:25/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  | 0 | 0.92 | 2021-09-08 | 1.83 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 20000000 | 1.02 | 51 | 2021-11-11 |  | 100000000 | Yes | Yes
1023 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00194 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00194-Relaying of Road-009/2021/038/R/0001179-VASANTHAM NAGAR MAIN ROAD , 009/2021/002/R/0000857-DURGA NAGAR MAIN ROAD , | Roads | Bituminous Road | G.O.(Ms) No. 02Dated:25/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 | 37917000 |  |  | 0 | 2021-09-08 | 1.82 | Completed | 100 | Completed | 100 | 13/08/24 |  | 2025-08-05 |  | 12857662 |  |  |  | 7142338 | 0 | 0 | 20/02/22 |  | 100000000 | No | Yes
1024 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00205 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00205-Relaying of Road-007/2021/001/R/0000162-KRISHNASAMY STREET , 007/2021/001/R/0000612-GRIFFITH 4ND STREET , 007/2021/006/R/0000586-RAILWAY STATION ROAD , 007/2021/011/R/0000631-QUARRY ROAD , 009/02/021/R/0001-VELS COLLEGE ROAD , 007/2022/012/R/000064-PONNIAMMAN KOIL STREET , | Roads | Bituminous Road | Go.(Ms)No.2Dated:07/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 1.41 | 2021-11-08 | 1.84 | Completed | 100 | Completed | 100 |  |  | 28/02/23 |  | 0 |  |  |  | 20000000 | 1.41 | 70.35 | 2022-11-02 |  | 100000000 | Yes | Yes
1025 | Tambaram | TNSUDP | CHENGALPATTU | TNSUDP/2020-21/009/ROAD/00206 |  |  | TNSUDP TNSUDP/2020-21/009/ROAD/00206-Relaying of Road-007/2021/013/R/0000272-SANNADHI STREET , 007/2021/014/R/0001288-THENMOZHI NAGAR 5TH STREET , 007/2021/014/R/0000354-AMBAL NAGAR MAIN RD , 007/2021/014/R/0000350-AMBAL NAGAR 5TH STREET , 007/2021/014/R/0000349-AMBAL NAGAR 6TH STREET , 007/2021/014/R/0000346-AMBAL NAGAR 8TH STREET , | Roads | Bituminous Road | Go.(Ms)No.2Dated:07/01/21Road DetailsRoad Length :Mts | 2020-21 | 100000000 | 20000000 |  |  |  | 0.83 | 2021-11-08 | 1.84 | Completed | 100 | Completed | 100 |  |  | 28/02/23 |  | 9472000 |  |  |  | 10528000 | 0.83 | 41.65 | 2022-11-02 |  | 100000000 | No | Yes
1026 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00377 |  |  | TURIP TURIP/2025-26/009/ROAD/00377-Relaying of Road-Bituminous Road009001R0065-MANNAR SWAMY 1ST CROSS STREET , 009002R5748-BALAJI NAGAR SUB.BHARATHIYAR 2ND ST , 009003R0237-Ramalingasamy Madam Saraswathy Street , 009003R0195-GOPAL CHETTY STREET , 009003R0255-Thirumalai Nagar 5th Street , 009003R0206-V.O.C. NAGAR 2ND STREET , 009003R0207-V.O.C. NAGAR 2ND CROSS STREET , 009003R0202-SHANMUGA MUDALI STREET , 009003R0203-SANNATHI STREET , 009003R0229-INDIRA NAGAR KATTABOMMAN ST , (Package No.I) | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2193 Mts | 2025-26 | 182896000 | 15800000 |  |  |  | 0 | 14/07/25 | 1.58 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 15800000 | 1.33 | 84.19 | 18/10/25 |  | 182896000 | No | No
1027 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00097 |  |  | TURIP TURIP/2025-26/009/ROAD/00097-Relaying of Road-Bituminous Road009054R3891-SRI SAI NAGAR 1ST STREET , 009054R3893-SRI SAI NAGAR 3RD STREET , 009054R3294-SRI SAI NAGAR 4TH STREET , 009054R3895-SRI SAI NAGAR 4TH STREET , 009054R3896-SRI SAI NAGAR 6TH STREET , 009054R3929-BHARATHIDASAN NAGAR 3RD STREET , 009054R3930-JOTHI NAGAR 8TH STREET , 009054R3943-SAPTHAGIRI NAGAR , 009054R3949-1ST STREET C.T.O. COLONY , 009054R3952-C.T.O.COLONY 3RD ST CROSS , 009054R3954-C.T.O.COLONY 4TH ST CROSS , 009054R3969-RADHA NAGAR 1ST STREET , 0090 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2972 Mts | 2025-26 | 521620000 | 19000000 |  |  |  | 1.71 | 2025-10-06 | 1.55 | Completed | 100 | Completed | 100 |  |  | 21/01/26 |  | 19000000 |  |  |  | 0 | 1.71 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1028 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00137 |  |  | TURIP TURIP/2023-24/009/ROAD/00137-Relaying of Road-009007R0515-7TH CROSS 1ST LANE , 009007R0526-9TH CROSS STREET ANNA NAGAR , 009007R0531-LOGONATHAN STREET H.L. COLONY , 009007R0551-1ST STREET LAKSHMI NARYANAN NAGAR , 009007R0516-7TH CROSS 2ND LANE , 009007R0511-KAKKAN STREET H.L COLONY , 009007R0512-KAKKAN 2ND CROSS STREET H.L. COLONY , 009007R0535-5TH MAIN ROAD ANNA NAGAR , 009007R0548-MARUTHI STREET , 009007R0563-KIRUPA STREET ANNA NAGAR , 009007R0545-4TH STREET LAKSHMI NARAYANAN NAGAR , 009007R0552-KALAINJAR | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :5181 Mts | 2023-24 | 313620000 | 19100000 |  |  |  | 1.72 | 20/07/23 | 1.91 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 19058449 |  |  |  | 41551 | 1.67 | 87.52 | 15/04/24 |  | 313620000 | No | Yes
1029 | Tambaram | TURIP | CHENGALPATTU | TURIP/2021-22/007/ROAD/00035 |  |  | TURIP TURIP/2021-22/007/ROAD/00035-Providing B.T. Surface at Nellipettai High Road,Kanni Koil Street,Vinobaji Nagar 5th Street in ward No:19,22 (Package No.05) | Roads | Bituminous Road | 24886/2021/E1Dated:19/11/20Road DetailsRoad Length :Mts | 2021-22 | 50000000 | 10000000 |  |  |  | 1 | 2022-04-01 | 0.95 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 10000000 | 0.86 | 86.04 | 2022-05-04 |  | 50000000 | Yes | Yes
1030 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00389 |  |  | TURIP TURIP/2025-26/009/ROAD/00389-Relaying of Road-Bituminous Road009045R3326-SRIRAM NAGAR 1ST CROSS STREET , 009045R3328-SRIRAM NAGAR 3RD CROSS STREET , 009045R3330-GANAPATHY COLONY CROSS STREET , 009045R3331-THIRU-VI-KA-STREET , 009045R3332-KANNAN NAGAR , 009045R3343-VIDYALAKSHMI STREET , 009045R3344-VIDYALAKSHMI 1ST CROSS STREET , 009045R3361-PERIYATHAMBI ST , 009045R3369-KUMARAN STREET , 009045R3377-PILLAIYAR KOIL STREET , 009069R5467-Secretariat Colony Pillaiyar kovil Street , 009066R5077-Brindhavan nagar 3rd cross street , | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2265 Mts | 2025-26 | 182896000 | 13501000 |  |  |  | 0 | 14/07/25 | 1.35 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13501000 | 1.11 | 82.21 | 30/10/25 |  | 182896000 | No | Yes
1031 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00140 | Zone III |  | TURIP TURIP/2023-24/009/ROAD/00140-Relaying of Road-Bituminous Road009022R1542-JAIN NAGAR 2ND STREET , 009022R1482-BRAHMIN STREET , 009023R1609-KULAKARAI STREET , 009023R1605-DHANALAKSHMI STREET , 009023R1604-Dhanalakshmi Nagar Extn Postal Nagar , 009025R1702-SCHOOL STREET , 009025R1700-KRISHNAMACHARI STREET , 009025R1697-RAMASAMY STREET , 009025R1704-RAMASAMY CROSS STREET , 009025R1722-NEHRU STREET (Package No.4) Zone III | Roads | Bituminous Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :2267.7 Mts | 2024-25 | 65000000 | 11000000 |  |  |  | 0 | 27/05/25 | 1.1 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 11000000 | 0.99 | 89.93 | 26/07/25 |  | 65000000 | No | Yes
1032 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00141 | Zone IV |  | TURIP TURIP/2023-24/009/ROAD/00141-Relaying of Road-Bituminous Road009057R4286-MUTHUVELAR STREET , 009058R4323-MUTHIRULANDI STREET , 009058R4327-THIRUVALLUVAR 1 CROSS STREET , 009056R4145-GANDHI STREET , 009056R4213-BHARATHI AVENUE MAIN ROAD , 009055R4026-VEERALAKSHMI NAGAR , 009060R4555-7TH STREET PERIYAR NAGAR , 009059R4505-AVVAI STREET , 009059R4493-SOORATHAMMAN KOIL 1ST STREET , (Package No.5) Zone IV | Roads | Bituminous Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :2092 Mts | 2024-25 | 65000000 | 9900000 |  |  |  | 0 | 27/05/25 | 0.79 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9900000 | 0.89 | 89.98 | 26/07/25 |  | 65000000 | No | Yes
1033 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00142 | Zone V |  | TURIP TURIP/2023-24/009/ROAD/00142-Relaying of Road-Bituminous Road009045R3370-VALLALAR STREET , 009047R3496-L.I.C COLONY , 009048R3533-KAMBAR STREET , 009062R4756-GAYATHRI NAGAR 3RD STREET , 009062R4757-GAYATHRI NAGAR 4TH STREET , 009062R4729-ROJA THOTTAM IST CROSS , 009063R4807-BALARAMAN STREET , 009064R4815-MUTHUMARIAMMAN KOIL ST , (Package No.6) Zone V | Roads | Bituminous Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :1441 Mts | 2024-25 | 65000000 | 6000000 |  |  |  | 0 | 27/05/25 | 0.6 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6000000 | 0.54 | 90.03 | 26/07/25 |  | 65000000 | No | Yes
1034 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00143 | Zone V |  | TURIP TURIP/2023-24/009/ROAD/00143-Relaying of Road-Bituminous Road009066R5060-Thirumagal nagar main road. , 009067R5186-SUDHARSAN NAGAR 1ST MAIN ROAD , 009067R5162-Gayathri Garden 1st Main Road , 009068R6324-KARPAGAM NAGAR 2ND STREET , 009069R5409-YESHWANTH NAGAR 2ND MAIN ROAD , 009069R5439-Shirdi Sai Nagar 3rd Cross Street , 009070R5582-SRI MARUTHI NAGAR 4TH STREET , 009070R5581-SRI MARUTHI NAGAR 3RD STREET , (Package No.6) Zone V | Roads | Bituminous Road | Roc.No. 2459-2024-SS1Dated:20/01/25Road DetailsRoad Length :1539 Mts | 2024-25 | 65000000 | 8500000 |  |  |  | 0 | 27/05/25 | 0.85 | Completed | 100 | Completed | 100 |  |  | 23/01/26 |  | 8441266 |  |  |  | 58734 | 0.76 | 89.6 | 26/07/25 |  | 65000000 | No | Yes
1035 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00250 |  |  | TURIP TURIP/2024-25/009/ROAD/00250-Relaying of Road-Bituminous Road009005R0342-SENTHAMIZH SALAI, THENDRAL NAGAR , 009005R0352-Mosque Street , 009005R0327-THENDRAL NAGAR NALADIYAR ST , 009005R0328-KAMARAJAPURAM VICTORIA SALAI , 009006R0501-VALLALAR STREET PASUMPON NAGAR , 009006R0502-DEIVANAYAGAM STREET PASUMPON NAGAR , 009006R0481-VETHAGIRI MUDALIYAR STREET , 009007R0528-RAJARAJAN STREET , 009007R0554-GIRI SQUARE 2ND STREET , 009008R0570-PILLAYAR KOIL 2ND CORSS STREET K NAGAR , 009008R0574-PADMANABAN STREET KRISHNA NAG | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2365 Mts | 2024-25 | 130600000 | 15540000 |  |  |  | 0 | 27/05/25 | 1.55 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 15539728 |  |  |  | 272 | 1.4 | 89.96 | 26/07/25 |  | 130600000 | No | Yes
1036 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00317 |  |  | TURIP TURIP/2024-25/009/ROAD/00317-Relaying of Road-Bituminous Road009034R2212-State bank colony 1st street , 009034R2213-State bank colony 2nd street , 009034R2218-State bank colony 3rd street extension , 009034R2221-THIRUKURAL STREET , 009034R2220-Thirukural street, bank colony extension , 009034R2184-JOTHI NAGAR 1ST STREET , 009043R3180-BABU STREET, KOWSALYA NAGAR , 009043R3220-G.D. NAIDU STREET , 009043R3147-C.V. RAMAN STREET , 009043R3143-MARTIN LUTHAR STREET , 009043R3137-THIRUMURUGAN SALAI , 009043R3112-SARATHAMBAL STREET | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2274 Mts | 2024-25 | 130600000 | 15600000 |  |  |  | 1.4 | 27/05/25 | 1.56 | Completed | 100 | Completed | 100 |  |  | 29/01/26 |  | 15639303 |  |  | 0 | -39303 | 1.4 | 89.86 | 26/07/25 |  | 130600000 | No | Yes
1037 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00319 | Zone III |  | TURIP TURIP/2024-25/009/ROAD/00319-Relaying of Road-Bituminous Road009044R3247-KRISHNA STREET , 009044R3271-SETHUNARAYANAN STREET , 009044R6061-KANNAGI STREET , 009044R3259-RAMANAR STREET , 009044R6068-MARUTHUPANDIAR STREET , (Package No.6) Zone III | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :1352 Mts | 2024-25 | 130600000 | 9400000 |  |  |  | 0 | 27/05/25 | 0.94 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9400000 | 0.85 | 89.94 | 26/07/25 |  | 130600000 | No | Yes
1038 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00321 | Zone IV |  | TURIP TURIP/2024-25/009/ROAD/00321-Relaying of Road-Bituminous Road009033R2170-LUTHERAN CHURCH STREET , 009052R3675-2ND MAIN RD-LAKSHMIPURAM , 009053R3816-2ND CR ST-MELANDAI STREET , 009055R3983-Balaji Nagar , 009055R4032-BHARATHI NAGAR 3RD STREET , 009056R4160-Manawalan Nagar , 009055R4264-VENKATESHWARA NAGAR 2ND STREET , 009057R4265-VENKATESHWARA NAGAR EXTN , 009058R4353-MOTHILAL STREET , 009061R4676-KATTABOMMAN STREET , (Package No.7) Zone IV | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2673 Mts | 2024-25 | 130600000 | 13670000 |  |  |  | 0 | 27/05/25 | 1.09 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13670000 | 0.69 | 50.48 | 26/07/25 |  | 130600000 | No | Yes
1039 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00325 |  |  | TURIP TURIP/2024-25/009/ROAD/00325-Repair /Maintenance-Bituminous Road009065R4959-GANDHI NAGAR MAIN ROAD , 009065R5053-RICKY GARDEN 5TH CROSS STREET , 009066R5106-VALLALAR 3RD CROSS STREET , 009066R5102-Kambar street main road , 009066R6274-GANESH NAGAR MAIN ROAD , 009067R5145-SHANTHINIKITAN COLONY EXTN 1ST STREET , 009067R5158-SHANTHINIKITAN COLONY 2ND STREET , 009067R5248-MAYANA STREET , 009068R5330-MALLESWARI NAGAR MAIN ROAD , 009068R5360-BAI GARDEN 1ST STREET , 009068R5363-BAI GARDEN 3RD STREET , 009068R5362-Bai Garden Cross | Roads | Bituminous Road | 2459/2024/SS1-Phase-vDated:17/03/25Road DetailsRoad Length :2953 Mts | 2024-25 | 130600000 | 12500000 |  |  |  | 0 | 27/05/25 | 1.25 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12500000 | 1.12 | 89.97 | 26/07/25 |  | 130600000 | No | Yes
1040 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00064 |  |  | TURIP TURIP/2024-25/009/ROAD/00064-Relaying of Road-Bituminous Road009021R1379-PERUMAL NAGAR 5TH MAIN RD , 009021R1326-MALLIGA NAGAR , 009021R1329-ABDUL KALAM STREET KATTABOMMAN NAGAR , 009021R1350-A R G NAGAR , 009021R1351-ARG Nagar 2nd Extension , 009021R1422-4TH MAIN ROAD - GARDEN WOODRAFFEE NGR , 009021R1423-GARDEN WOODROFF NAGAR 5TH MAIN ROAD , 009021R1424-GARDEN WOODROFF NAGAR 5TH CROSS STREET , 009021S0226-GARDEN WOODROFF NAGAR 5TH CROSS STREET , 009021R1409-GARDEN WOODROFF NAGAR 1ST MAIN ROAD , 009024R1669-MANI NAICKER S | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :3582.7 Mts | 2024-25 | 169399000 | 17000000 |  |  |  | 1.53 | 27/02/24 | 1.7 | Completed | 100 | Completed | 100 | 19/04/24 |  | 24/02/25 |  | 16864986 |  |  |  | 135014.41 | 1.52 | 89.39 | 27/05/24 |  | 169399000 | No | Yes
1041 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00065 | Zone III |  | TURIP TURIP/2024-25/009/ROAD/00065-Relaying of Road-Bituminous Road009022R1454-SINDHU STREET , 009022S0284-KUPPUNAYAGAN PETTAI , 009023R1576-TALUK OFFICE ROAD , 009025R1721-RAMASAMY IYER STREET , 009035R2280-IYYASAMY SCHOOL STREET , 009035R2268-RAMACHANDRA STREET , 009036R2290-PURUSOTHAMAN NAGAR 4TH CROSS STREET , 009036R2296-BASHIYAM NAGAR 3RD STREET , 009037R2371-RAMAN STREET , 009037R2388-M.C.NAGAR THIRD MAIN ROAD , 009038R2422-THIRU-VI-KA NAGAR MAIN ROAD , 009038R2405-VINOBAJI NAGAR 10TH STREET , (Package No.5), zone III | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :3342.6 Mts | 2024-25 | 169399000 | 17400000 |  |  |  | 1.57 | 28/02/24 | 1.68 | Completed | 100 | Completed | 100 | 2024-03-05 |  | 15/05/24 |  | 0 |  |  |  | 17400000 | 1.56 | 89.84 | 28/05/24 |  | 169399000 | No | Yes
1042 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00066 |  |  | TURIP TURIP/2024-25/009/ROAD/00066-Relaying of Road-Bituminous Road009039R2483-BAVANANTHIYAR MAIN ROAD , 009039R2442-THIRUMALAI NAGAR MAIN ROAD , 009040R2684-Hasthinapuram link road , 009041R2771-TELLUS AVENUE 4TH MAIN ROAD , 009041R2770-TELLUS AVENUE 3RD MAIN ROAD , 009041R2750-Sri devi avenue Tellus phase 2 , 009042R3048-MARUTHI NAGAR 1ST MAIN ROAD , 009043R3105-U.v.saminathan street sha avenue , 009044R3246-GOTHAVARI STREET , 009044R3248-KAVERI STREET , 009044R3240-THIRUMAGAL NAGAR FIRST STREET , 009044R3275-PERI AZVAR STREET | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :3764 Mts | 2024-25 | 169399000 | 19700000 |  |  |  | 1.77 | 28/02/24 | 1.87 | Completed | 100 | Completed | 100 | 2024-07-05 |  | 14/05/24 |  | 0 |  |  |  | 19700000 | 1.77 | 89.65 | 28/05/24 |  | 169399000 | No | Yes
1043 | Tambaram | TURIP | CHENGALPATTU | TURIP/2021-22/007/ROAD/00037 |  |  | TURIP TURIP/2021-22/007/ROAD/00037-Providing B.T. Surface at Saibaba Street, bharath Nagar Main Road, Ambal Nagar 12th Street, Ambal Nagar 18th Street,Baskar Nagar 2nd Street, Rajendra Nagar Main Road, Arul Murugan Nagar Main Road in ward No:14,15(Package No.03) | Roads | Bituminous Road | 24886/2021/E1Dated:19/11/20Road DetailsRoad Length :Mts | 2021-22 | 50000000 | 10000000 |  |  |  | 1 | 2022-04-01 | 1.01 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 8527625 |  |  |  | 1472375 | 0.76 | 75.58 | 2022-02-10 |  | 50000000 | Yes | Yes
1044 | Tambaram | TURIP | CHENGALPATTU | TURIP/2021-22/007/ROAD/00038 |  |  | TURIP TURIP/2021-22/007/ROAD/00038-Providing B.T. Surface at Sankara Salai, Paratha Sararthy Street, Muthuvellar Salai Cross Street, Amaravathi Street, Ramaswamy 1st Street in ward No:13,14(Package No.02) | Roads | Bituminous Road | 24886/2021/E1Dated:19/11/20Road DetailsRoad Length :Mts | 2021-22 | 50000000 | 10000000 |  |  |  | 1 | 2022-04-01 | 0.99 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 10001640 |  |  |  | -1640 | 0.89 | 89.2 | 2022-02-10 |  | 50000000 | Yes | Yes
1045 | Tambaram | TURIP | CHENGALPATTU | TURIP/2021-22/007/ROAD/00039 | Zone I | 1 | TURIP TURIP/2021-22/007/ROAD/00039-Providing BT Surface at Girifith Main Road Maliga Nagar 1st Street Malliga Nagar Cross Street Mahaveer Salai Muthuvellar Salai in Ward No 1 12, 13 (Package No 01) | Roads | Bituminous Road | 24886/2021/E1Dated:19/11/20Road DetailsRoad Length :Mts | 2021-22 | 50000000 | 10000000 |  |  |  | 1 | 2022-04-01 | 1 | Completed | 100 | Completed | 100 |  |  | 30/05/25 |  | 9860946 |  |  |  | 139054 | 0.99 | 98.6 | 2022-02-10 |  | 50000000 | Yes | Yes
1046 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00130 |  |  | TURIP TURIP/2023-24/009/ROAD/00130-Relaying of Road-009045R3334-ANNAI NAGAR 1ST MAIN ROAD , 009045R3336-ANNAI NAGAR CROSS STREET , 009045R3339-GEORGE AVENUE , 009045R3371-MALAVIKA AVENUE MAIN ROAD , 009063R4806-SUDHANANDA BHARATHI AND MSP LANE , 009062R4743-PONNA NAGAR 1ST ST , 009062R4744-PONNA NAGAR 2ND ST , 009062R4745-PONNA NAGAR 3RD ST , 009064R4818-THANTHAI PERIAR STREET (NEAR ANNA ST) , 009064R4863-AMBEDKAR STREET (S.PARK STREET EXTN) , 009045R3372-MALAVIKA AVENUE 1ST CROSS STREET , 009045R3373-MALAVIKA AVENUE 2ND CROSS ST | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3055 Mts | 2023-24 | 313620000 | 10100000 |  |  |  | 0.91 | 18/07/23 | 0.97 | Completed | 100 | Completed | 100 |  |  | 27/05/25 |  | 10082495 |  |  |  | 17505 | 0.91 | 90 | 23/04/24 |  | 313620000 | No | Yes
1047 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00127 |  |  | TURIP TURIP/2023-24/009/ROAD/00127-Relaying of Road-009054R3946-HARITHA ENCLAVE PANDIAN STREET , 009051R3647-RAJAGOPAL NAGAR 4TH ST , 009052R3723-TNHB MULLAI NAGAR 2ND MAIN ROAD , 009054R3955-5TH STREET C.T.O. COLONY , 009033R2105-MES ROAD 7.0 M BT 2.0 M , 009051R3643-RAMATHILAGAM ST , 009051R3644-RAJAGOPAL NAGAR 1ST ST , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :2119 Mts | 2023-24 | 313620000 | 10360000 |  |  |  | 0 | 20/07/23 | 1.04 | Completed | 100 | Completed | 100 | 2024-10-09 |  | 2025-05-05 |  | 7324621 |  |  |  | 3035379 | 0.66 | 63.63 | 18/10/23 |  | 313620000 | No | Yes
1048 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00128 |  |  | TURIP TURIP/2023-24/009/ROAD/00128-Relaying of Road-009049R3588-KAMARAJ ST , 009049R3577-MUTHULINGAM STREET , 009049R3559-RAJAJI ROAD , 009051R3646-RAJAGOPAL NAGAR 3RD STREET , 009051R3649-IST STREET-RAMESH NAGAR , 009051R3648-RAMESH NAGAR MAIN ROAD , 009052R3763-MULLAI NAGAR 3RD MAIN ROAD , 009054R3950-2ND STREET C.T.O. COLONY , 009053R3827-POORNATHILAGAM STREET , 009060R4548-1ST STREET PERIYAR NAGAR , 009049R3552-AYYASAMY ST , 009049R3570-LOGANATHAN STREET , 009052R3691-OLD SBI COLONY 2ND MAIN ROAD , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3375 Mts | 2023-24 | 313620000 | 12200000 |  |  |  | 1.1 | 20/07/23 | 1.22 | Completed | 100 | Completed | 100 |  |  | 24/02/25 |  | 12200000 |  |  |  | 0 | 1.1 | 90 | 28/04/24 |  | 313620000 | No | Yes
1049 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00068 |  |  | TURIP TURIP/2024-25/009/ROAD/00068-Relaying of Road-Bituminous Road009055R4042-KANNAN AVENUE 2ND STREET , 009055R4025-MOOVENDAR NAGAR EXTN , 009055R4052-SADAGOPAN NAGAR , 009055R4054-PAVITHRA ENCLAVE , 009056R4221-BALAJI NAGAR MAIN ROAD , 009057R4237-SRI BALAJI NAGAR MAIN ROAD , 009057R4254-VIVEK NAGAR 7TH STREET , 009057R4248-VIVEK NAGAR 1ST STREET - CASTLE HOMES , 009057R4251-VIVEK NAGAR 4TH STREET , 009059R4437-A.S. RAJAN NAGAR , 009059R4450-RAJKAMAL STREET , 009059R4509-UMA NAGAR , 009059R4414-G.K.Moopanar street , (P | Roads | Bituminous Road | 2459/2024/SS1Dated:01/02/24Road DetailsRoad Length :3427 Mts | 2024-25 | 169399000 | 17400000 |  |  |  | 0 | 28/02/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2024-11-06 |  | 16610298 |  |  |  | 789702 | 0 | 0 | - |  | 169399000 | No | Yes
1050 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00125 |  |  | TURIP TURIP/2023-24/009/ROAD/00125-Relaying of Road-009005R0353-SRINIVASAPURAM 2ND CROSS ST , 009005R0354-SRINIVASAPURAM MAIN ROAD , 009005R0355-SRINIVASAPURAM 1ST STREET , 009005R0356-SRINIVASAPURAM 2ND STREET , 009010R0762-1ST STREET THIRUMAL NAGAR , 009010R0751-LAKSHMANAN STREET PERIYAR NAGAR , 009012R0870-NAVAMANI CROSS STREET , | Roads | Bituminous Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1208 Mts | 2023-24 | 313620000 | 4100000 |  |  |  | 0.37 | 31/08/23 | 0.41 | Completed | 100 | Completed | 100 |  |  | 13/08/23 |  | 3600000 |  |  |  | 500000 | 0.33 | 80.66 | 20/10/23 |  | 313620000 | No | Yes
1051 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00387 |  |  | TURIP TURIP/2025-26/009/ROAD/00387-Relaying of Road-Bituminous Road009017R1069-MAHAVEER SALAI CROSS , 009017R1042-Mahaveer Salai , 009017R1074-NAGAPILLAI STREET , 009017R1054-Amaravathi Street , 009017R1043-Sankara Salai , 009017R1078-NAGAPILLAI CROSS STREET , 009018R1156-YASODHA NAGAR 2ND STREET , 009017R1053-Jayalakshmi Nagar Main Road , 009018R1126-BHARATH NAGAR 2ND CROSS STREET , 009018R1157-YASODHA NAGAR 3RD STREET , 009018R1129-Bagiyalakshmi nagar , 009018R1135-Brindhavan Nagar , 009018R1134-Balaji Avenue ,Briundavan Nagar | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2957 Mts | 2025-26 | 182896000 | 18200000 |  |  |  | 1.35 | 14/07/25 | 1.82 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 18200000 | 1.55 | 85.32 | 21/10/25 |  | 182896000 | No | Yes
1052 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00040 | Zone III | 42 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00040-Road Restoration of damaged portion over at CLC 1st Main Road (007042R1297) in Ward No.42 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  |  | 0.07 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 | 2022-04-04 |  | 2024-09-09 |  | 700000 |  |  |  | 0 | 0.06 | 90.14 | 2022-03-02 |  | 41050000 | Yes | Yes
1053 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00024 | Zone III | 40 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00024-Road Restoration of damaged portion over at New Colony 6th Cross Street East Side (007040R1270) in Ward No.40 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 0 |  |  |  | 900000 | 0.12 | 137.44 | 2022-03-02 |  | 41050000 | Yes | Yes
1054 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00202 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00202-Relaying of Road-Bituminous Road009009R0698-ABDUL RAZAK STREET , 009009R0692-P.P.AMMAN KOIL STREET , 009014R0933-SAROJINI STREET , 009015R0970-MALANGANANTHAPURAM 3RD STREET , 009017R1017-KAMARAJ NAGAR 3RD STREET , 009017R1084-SARA NAGAR MAIN ROAD , 009018R1117-Jayalakshmi Street (Sai Nagar extn) , 009018R1118-AMARAVATHI STREET , 009015R0969-MALANGANANTHAPURAM 2ND STREET , 009018R1147-DHARMARAJA KOIL STREET , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2978.5 Mts | 2022-23 | 98900000 | 10000000 |  |  |  | 0.9 | 16/06/23 | 1 | Completed | 100 | Completed | 100 | 2023-03-10 |  | 24/05/24 |  | 10000000 |  |  |  | 0 | 0.9 | 90 | 14/09/23 |  | 98900000 | Yes | Yes
1055 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00020 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00020-Road Restoration of damaged portion over at M.K Nagar Main Road ( Velsamy Nagar 1st Street to Bharath Nagar) (007016R527)in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 | 2022-10-01 |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 88.56 | 2022-03-02 |  | 41050000 | Yes | Yes
1056 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00021 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00021-Road Restoration of damaged portion over at M.K Nagar Main Road (Perumal Nagar 2nd Main Road to Velsamy Nagar 1st Street) (007016R527)in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 | 2022-10-01 |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 88.67 | 2022-03-02 |  | 41050000 | Yes | Yes
1057 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00022 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00022-Road Restoration of damaged portion over at M.K Nagar Main Road (Kalavani street to Perumal Nagar 2nd Main Road) (007016R527) in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 | 2022-07-01 |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 88.67 | 2022-03-02 |  | 41050000 | Yes | Yes
1058 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00082 | Zone II |  | TURIP TURIP/2025-26/009/ROAD/00082-Relaying of Road-Bituminous Road009020S0213-BIG STREET , 009020R1251-BIG STREET , 009020R5826-Kalaivani Main Road , 009020R1323-NATESAN SALAI , 009020R1322-DURAIKANNU SALAI , 009021R1366-Kambar Street Main Road , 009021R1367-P.V.VAITHIYALINGAM ROAD , Zone II (package No.VIII) | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2811 Mts | 2025-26 | 521620000 | 24850000 |  |  |  | 2.24 | 2025-10-06 | 2.49 | Completed | 100 | Completed | 100 |  |  | 2025-03-07 |  | 24773583 |  |  | 0 | 76417 | 2.24 | 89.97 | 2025-09-08 |  | 521620000 | No | Yes
1059 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00084 |  |  | TURIP TURIP/2025-26/009/ROAD/00084-Relaying of Road-Bituminous Road009022R1540-MARUTHI NAGAR , 009022R1528-MANIKANDAN NAGAR , 009022R1521-THIRUMALAI NAGAR NORTH EXTN. , 009022R1530-DAMODHARAN NAGAR , 009022R1531-DAMODARAN NAGAR 1ST STREET , 009022R1472-DURAIRAJ SALAI , 009022R1522-Saraswathy Nagar Ist street , 009022R1471-SARASWATHI STREET , 009022R1517-VINOBAJI NAGAR 5TH STREET , 009022S0292-SARASWATHY NAGAR IST CROSS STREET , 009022R1473-RAJA KANNIAMMAN STREET , 009022R1474-SARASWATHY STREET EXTN , 009022R1532-DAMODARAN NAGAR | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3437 Mts | 2025-26 | 521620000 | 14550000 |  |  |  | 0 | 2025-10-06 | 1.46 | Completed | 100 | Completed | 100 |  |  | 29/01/26 |  | 14398222 |  |  | 0 | 151777.96 | 1.31 | 89.95 | 2025-09-08 |  | 521620000 | No | No
1060 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00085 | Zone III |  | TURIP TURIP/2025-26/009/ROAD/00085-Relaying of Road-Bituminous Road009038R2399-4TH ST-MAHESWARI NAGAR , 009038R2395-2ND CROSS ST-MAHESWARI NAGAR , 009038R2396-2ND ST-MAHESWARI NAGAR , 009038R2398-5TH ST-MAHESWARI NAGAR , 009038R2400-MAHESWARI NAGAR , 009038R2418-VALLALAR STREET , 009038R2403-VINOBAJI NAGAR 8TH STREET , 009038S0399-MANICKAM NAGAR , 009038R2419-AVVAIYAR STREET , 009038R2397-3RD ST-MAHESWARI NAGAR , Zone III (Package No.11) | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1083 Mts | 2025-26 | 521620000 | 4990000 |  |  |  | 0.45 | 2025-10-06 | 0.5 | Completed | 0 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4990000 | 0.45 | 89.86 | 2025-09-08 |  | 521620000 | No | Yes
1061 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00086 | Zone III |  | TURIP TURIP/2025-26/009/ROAD/00086-Relaying of Road-Bituminous Road009034R2215-PATTINATHAR STREET , 009034R2216-Rajparis nagar state bank colony extension , 009034S0376-KALAIVANAR STREET , 009034S0374-SARANGAPANI STREET , 009034R2195-ANNA STREET , Zone III (Package No.12) | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1666 Mts | 2025-26 | 521620000 | 11550000 |  |  |  | 0 | 2025-10-06 | 1.16 | Completed | 100 | Completed | 100 |  |  | 29/01/26 |  | 11265680 |  |  | 0 | 284320 | 1.04 | 89.98 | 2025-09-08 |  | 521620000 | No | Yes
1062 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00087 |  |  | TURIP TURIP/2025-26/009/ROAD/00087-Relaying of Road-Bituminous Road009044R3250-GOMATHI STREET , 009044R3295-VAITHYALINGAM STREET , 009044R3256-BHARTHI STREET , 009044R3273-Maraimalai adigal street (ramanar street to pambanswamigal salai) , 009044R3312-JEYENDRAR STREET , 009044R3262-RAVEENDRANATH TAGORE STREET , 009043R3207-SARVAMANGALA NAGAR 1ST CROSS STREET , 009043R6037-RAMALINGA ADIKALAR STREET , 009043R3123-PAMBANSAMIGAL SALAI , 009042R2875-Sathyasai nagar 3rd cross street.. , 009242R3023-VASUGI STREET , 009042R3015-BARATHIDA | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :4432 Mts | 2025-26 | 521620000 | 22450000 |  |  |  | 0 | 2025-10-06 | 2.25 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 22450000 | 0 | 0 | 2025-09-08 |  | 521620000 | No | Yes
1063 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00088 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00088-Relaying of Road-Bituminous Road009058R4335-GANAPATHI SALAI , 009058R4311-V.O.C. STREET , 009058R4333-PERUMAL SALAI , 009058R4370-N.G.O. COONY 4TH STREET , 009058R4326-THIRUVALLUVAR STREET , 009058R4318-RAMADOSS STREET , 009058R4313-BHARATHIYAR STREET Zone IV-Package No.15 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1105 Mts | 2025-26 | 521620000 | 6850000 |  |  |  | 0.62 | 2025-10-06 | 0.66 | Completed | 95 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6850000 | 0.62 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1064 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00090 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00090-Relaying of Road-Bituminous Road009061R4615-KHURINJI STREET , 009061R4624-MALLI CROSS STREET , 009061R4642-SRIRAM NAGAR MAIN ROAD , 009061R4682-Kattabomman 6th cross street , 009061R4688-Gandhi 5th cross street , 009061R4648-DEVANESAN NAGAR 4TH STREET , 009061R4666-ANNA STREET , 009061R4683-GANDHI STREET , 009061R4613-OLD G.S.T. ROAD , Zone IV-Package No.17 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3141 Mts | 2025-26 | 521620000 | 14500000 |  |  |  | 0 | 2025-10-06 | 1.4 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 14500000 | 1.16 | 80.11 | 2025-09-08 |  | 521620000 | No | Yes
1065 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00091 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00091-Relaying of Road-Bituminous Road55R4000-Irtaimalai Srinivasa Street , 009055R4001-RAGAVENDRA GARDEN , 009055R4082-RAGAVENDHRA STREET , 009055R3985-BERLIN ENCLAVE , 009055R4087-PERUMAL KOVIL STREET , 009055R4061-Ganesh Nagar , 009055R4006-Karumariyamman Nagar , 009055R3997-SASIVARADHAN NAGAR 4TH STREET , 009055R3983-Balaji Nagar , 009055R6121-Balaji Nagar 1st Street , , Zone IV-Package No.18 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2090 Mts | 2025-26 | 521620000 | 14000000 |  |  |  | 1.26 | 2025-10-06 | 1.36 | Completed | 100 | Completed | 100 |  |  | 29/01/26 |  | 13999501 |  |  | 0 | 499 | 1.26 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1066 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00092 |  |  | TURIP TURIP/2025-26/009/ROAD/00092-Relaying of Road-Bituminous Road009065R4920-JAGAJEEVA RAMAN COLONY 1ST MAIN ROAD CROSS , 009065R4919-JAGAJEEVA RAMAN COLONY 1ST MAIN ROAD , 009065R4927-AVVAI NAGAR MAIN STREET (MURUGAN KOIL STREET , 009065R4929-AVVAI 2ND STREET , 009065R4930-3RD STREET-AVVAI NAGAR , 009065R4961-GANDHI NAGAR MAIN ROAD 1ST STREET , 009065R4962-GANDHI NAGAR MAIN ROAD 1ST CROSS STREET , 009065R4963-GANDHI NAGAR MAIN ROAD 2ND STREET , 009065R4965-UMA NAGAR , 009065R4966-UMA NAGAR CROSS , 009066R5066-ROJA THOTTAM 2ND | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3790 Mts | 2025-26 | 521620000 | 15700000 |  |  |  | 0 | 2025-10-06 | 1.57 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15700000 | 1.41 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1067 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00093 |  |  | TURIP TURIP/2025-26/009/ROAD/00093-Relaying of Road-Bituminous Road009068R5331-MALLESWARI NAGAR 9TH STREET , 009068R5340-MOHAN NAGAR MAIN ROAD , 009068R5344-MOHAN NAGAR 4TH STREET , 009068R5372-JAIWANTHPURAM 1ST STREET , 009068R5374-JAIWANTHPURAM 3RD STREET , 009068R5375-JAIWANTHPURAM 3RD STREET , 009068R5376-JAIWANTHPURAM 5TH STREET , 009068R5377-JAIWANTHPURAM 6TH STREET , 009069R5395-YESHWANTH NAGAR 1ST STREET , 009069R5401-YESHWANTH NAGAR 3RD STREET , 009069R5419-BHUVANESHWARI NAGAR 1ST STREET , 009069R5430-BHUVANESHWARI NAGAR | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3489 Mts | 2025-26 | 521620000 | 15800000 |  |  |  | 0 | 2025-10-06 | 1.58 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15800000 | 1.42 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1068 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00380 |  |  | TURIP TURIP/2025-26/009/ROAD/00380-Relaying of Road-Bituminous Road009007R0627-2ND MAIN ROAD ANNA NAGAR , 009007R0557-ELANGO STREET ANNA NAGAR , 09007R0523-1ST MAIN RAOD H L COLONY , 009007R0516-7TH CROSS 2ND LANE , 009007R0544-S B I COLONY 3RD STREET , 009007R0610-SENGUTTUVAN STREET MUTAMIL NAGAR , 009007R0518-BHARATHIAR STREET H L COLONY , 009007R0611-DEVARAJAN STREET MUTHAMIZH NAGAR , 009007R0536-10TH CROSS STREET ANNA NAGAR , 009007R0563-KIRUPA STREET ANNA NAGAR , 009008R0622-PARIVALLAL STREET MUTAMIL NAGAR , (P | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :1852 Mts | 2025-26 | 182896000 | 13250000 |  |  |  | 0 | 14/07/25 | 1.33 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13250000 | 1.09 | 82.6 | 2025-12-10 |  | 182896000 | No | Yes
1069 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00381 |  |  | TURIP TURIP/2025-26/009/ROAD/00381-Relaying of Road-Bituminous Road009010R0730-MAHAVEER STREET , 009010R0711-THIRUVALLUVAR 1ST CROSS STREET PONNI NAGAR , 009010R0726-RAJAN STREET MEENACHI NAGAR , 009010R0756-AMBETKAR STREET PREYAR NAGAR , 009010R0712-KANNAKI STREET PONNI NAGAR , 009010R0720-3RD STREET NEHRU NAGAR , 009010R0769-SAKRABANI STREET PREYAR NAGAR , 009010R0728-MUTHUZA STREET , 009010R0768-MURUGESAN STREET NAGALKENI , 009010R0759-NARAYANAN STREET , 009010R0710-PONNI NAGAR AMBEDKAR STREET , 009010S0072-SABA | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2074 Mts | 2025-26 | 182896000 | 12400000 |  |  |  | 0 | 14/07/25 | 1.24 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12400000 | 1.01 | 81.06 | 2025-12-10 |  | 182896000 | No | Yes
1070 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00382 |  |  | TURIP TURIP/2025-26/009/ROAD/00382-Relaying of Road-Bituminous Road009029R1873-MANIMEGALAI STREET, UMAIYALPURAM , 009029R1880-DOCTORS COLONY , 009029R1879-ABDUL KALAM STREET, UMAYALPURAM , 009029R1854-PONNAPPAR STREET , 009029R1858-NAGAPPA NAGAR 1ST MAIN ROAD , 009029R1859-NAGAPPA NAGAR 2ND MAIN ROAD , 009029R1860-NAGAPPA NAGAR 3RD MAIN ROAD , 009029R1861-NAGAPPA NAGAR 4TH MAIN ROAD , 009029R1862-NAGAPPA NAGAR 5TH MAIN ROAD , 009029R1863-NAGAPPA NAGAR 6TH MAIN ROAD , 009029R1855-VENKATRAMAN STREET , 009029R1851-RANGANATHASAMY 1ST | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :4069 Mts | 2025-26 | 182896000 | 16100000 |  |  |  | 0 | 2025-12-08 | 1.61 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 16100000 | 0 | 0 | 2025-10-11 |  | 182896000 | No | Yes
1071 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00383 |  |  | TURIP TURIP/2025-26/009/ROAD/00383-Relaying of Road-Bituminous Road009030R1930-DURGA NAGAR NEHRUJI STREET , 009030R1929-DURGA NAGAR KARIKALAN STREET , 009030R1938-DURGA NAGAR AVAIYAR STREET , 009030R1944-DURGA NAGAR VINOBA STREET EXTN. , 009030R1915-TNHB Colony form GST Road To Flat 294/271 , 009030R1923-DURGA NAGAR MAIN ROAD , 009030R1924-DURGA NAGAR TNHB COLONY , 009030R1943-DURGA NAGAR VINOBA 2ND CROSS STREET , 009030R1893-NEERVANNAN 1ST STREET, LAKSHMIPURAM , 009030R1896-KULAKKARI 1ST CROSS STREET , 009030R5934-Sakthi nagar 1 | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :3273 Mts | 2025-26 | 182896000 | 13400000 |  |  |  | 0 | 14/07/25 | 1.34 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13400000 | 1.01 | 75.34 | 2025-12-10 |  | 182896000 | No | No
1072 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00384 |  |  | TURIP TURIP/2025-26/009/ROAD/00384-Relaying of Road-Bituminous Road009031R2025-WEST KULAKKARI STREET , 009031R1961-Kasi Gardan 3rd Street , 009031R1956-SUBRAYANNAGAR 3RD CROSS STREET, THIRUNEERMALAI, CHENNAI-600 044. , 009031R2012-RISHIKA STREET V G N GRAND HISTORIA , 009031R1975-2ND STREET, SARASWATHIPURAM, THIRUNEERMALAI, CHENNAI-600 044 , 009031R5943-Bharathidasan 3rd street , 009031R1998-THIRUMANGAI AZHVARPURAM, JAGAJEEVAN RAM STREET , 009031R2026-North Kulakkarai Street , 009031R1962-RANGA NAGAR 1ST STREET, THIRUNEERMALAI, | Roads | Bituminous Road | 9730/2025/SS1- PH-IIIDated:30/05/25Road DetailsRoad Length :2537 Mts | 2025-26 | 182896000 | 12900000 |  |  |  | 0 | 14/07/25 | 1.29 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12900000 | 0.89 | 68.95 | 2025-12-10 |  | 182896000 | No | Yes
1073 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00080 |  |  | TURIP TURIP/2025-26/009/ROAD/00080-Relaying of Road-Bituminous Road009008R0584-MADHAVAN NAIER STREET , 009008R0646-AVAIAR STREET , 009008R0652-KAMARAJAR SALAI MUTHAMIZH NAGAR , 009008R0616-V.O.C STREET MUTHAMIZH NAGAR , 009008R0651-DEIVASIGAMANI STREET MUTAMIL NAGAR , 009008R0657-THANTAHI PERYEAR STREET , 009008R0660-MADHAVAN STREET MUTHAMIZH NAGAR , 009008R0605-NAMMAZHVAR STREET THIRUVALLUVAR NAGAR , 009008R0644-1ST STREET ARANGANATHAN NAGAR , 009008R0566-MADHAVANAYAR CROSS STREET , 009008R0578-4TH CROSS STREET KRISH | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2523 Mts | 2025-26 | 521620000 | 17000000 |  |  |  | 0 | 2025-10-06 | 1.7 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 16995643 |  |  | 0 | 4357 | 1.53 | 89.96 | 2025-09-08 |  | 521620000 | No | Yes
1074 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00016 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00016-Road Restoration of damaged portion over at M.K Nagar Main Road (Ambedkar Nagar Cross Street to 200 feet Road) (007016R527)in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 800000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 | 2022-07-01 |  | 2024-09-09 |  | 800000 |  |  |  | 0 | 0.07 | 89 | 2022-03-02 |  | 41050000 | Yes | Yes
1075 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00017 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00017-Road Restoration of damaged portion over at M.K Nagar Main Road (Swamy Malai Nagar 1st Street to Ambekar Nagar Cross Street) (007016R527)in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 88.89 | 2022-03-02 |  | 41050000 | Yes | Yes
1076 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00018 | Zone II | 16 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00018-Road Restoration of damaged portion over at M.K Nagar Main Road (Swamy malai Nagar cross Street to Swami Malai Nagar 1st Street) (007016R527)in Ward No.16 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 | 2022-10-01 |  | 2024-09-09 |  | 900000 |  |  |  | 0 | 0.08 | 89.22 | 2022-03-02 |  | 41050000 | Yes | Yes
1077 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00211 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00211-Relaying of Road-Bituminous Road009056R4235-KALPANA CHAVLA STREET , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :152 Mts | 2022-23 | 98900000 | 750000 |  |  |  | 0.08 | 19/06/23 | 0.08 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 739926 |  |  |  | 10074 | 0.07 | 98.66 | 17/09/23 |  | 98900000 | Yes | Yes
1078 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00152 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00152-Relaying of Road-009007R0533-THIYAGARAJAN STREET H L COLONY , 009007R0559-NEHRU STREET ANNA NAGAR PAMMAL , 009007R0540-S B I COLONY 1ST STREET , 009007R0541-2ND STREET SBI COLONY , 009007R0542-GIRI SQUARE 1ST STREET , 009007R0543-NANCHILAR STREET , 009007R0520-8TH CROSS STREET ANNA NAGAR , 009007R0561-M G R STREET ANNA NAGAR , 009008R0622-PARIVALLAL STREET MUTAMIL NAGAR , 009011R0838-VASU STREET PERIYAR NAGAR NAGALKENI , 009011R0811-MAHIMAIDASAN STREET - PERIYAR NAGAR , 009011R0819 | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :2184 Mts | 2023-24 | 319260000 | 8100000 |  |  |  | 0.66 | 28/11/23 | 0.81 | Completed | 100 | Completed | 100 |  |  | 2025-03-03 |  | 7268976 |  |  |  | 831024 | 0.65 | 80.77 | 30/12/23 |  | 319260000 | No | Yes
1079 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00153 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00153-Relaying of Road-009010R0720-3RD STREET NEHRU NAGAR , 009010R0743-4TH STREET NEHRU NAGAR , 009010R0736-RAJAMANIKKAM STREET MEENACHI NAGAR , 009010R0722-ROSAMMAL STREET MEENACHI NAGAR , 009010R0769-SAKRABANI STREET PREYAR NAGAR , 009010R0753-SRIDHARAN STREET PERIYAR NAGAR , 009010R0752-DELLI STREET PERIYAR NAGAR , 009010R0765-SONGUVEL STREET , 009010R0754-SAHUL AMEED STREET LORD SRINIVASA COLONY , 009010R0758-CHELLAPPA STREET SRINIVASA COLONY , 009010R0708-AYYAPPA NAGAR MAIN ROA | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1410 Mts | 2023-24 | 319260000 | 6150000 |  |  |  | 0.3 | 17/11/23 | 0.61 | Completed | 100 | Completed | 100 |  |  | 2025-04-06 |  | 5574728 |  |  |  | 575272.17 | 0.5 | 81.8 | - |  | 319260000 | No | Yes
1080 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00154 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00154-Relaying of Road-009029R1847-DR. SOLOMAN COLONY, LAKSHMIPURAM , 009029R1866-CHANDRAN NAGAR MAIN ROAD , 009029R1877-AVVAIYAR STREET, UMAYALPURAM, CHENNAI-600 044 , 009030R1909-JAYARAM NAGAR 1ST STREET , 009030R1912-MUTHAMIL STREET , 009030R1935-DURGA NAGAR PILLAYAR KOIL STREET, CHENNAI-600 047 , 009030R5932-Ganga Street 1st street , 009030R5933-Ganga main road , 009030S0623-Ganga 2nd street , 009030R5935-Ganga 3rd street , 009030R5936-Ganga 4th street , 009030R5942-Meenakshi nagar mainroad , 0 | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :2480 Mts | 2023-24 | 319260000 | 9200000 |  |  |  | 0.8 | 28/07/23 | 0.92 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 9198700 |  |  |  | 1300 | 0.79 | 85.98 | 23/04/24 |  | 319260000 | No | Yes
1081 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00155 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00155-Relaying of Road-009009R0700-GANDHI STREET , 009009R0703-Yasin Khan 1st Cross Street , 009015R0952-Eswari Nagar 1st Main Road , 009015R0965-Zamindhar lane , 009015R0968-MALANGANANTHAPURAM 1ST STREET , 009016R0990-BHARATHI NAGAR 2ND STREET , 009016R0991-BHARATHI NAGAR 3RD STREET , 009016R0992-BHARATHI NAGAR 4TH STREET , 009017R1023-CHETTY STREET , 009017R1089-Ambedkar ground road , 009017R1009-Padmanaban Stret , 009017R1013-KAMARAJ NAGAR 1ST STREET , 009017S0124-LINGAM RICE MILL ROAD , 009018R114 | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :3401 Mts | 2023-24 | 319260000 | 9100000 |  |  |  | 0.82 | 2024-02-01 | 0.91 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 8362373 |  |  |  | 737627 | 0.8 | 88.27 | 2024-02-04 |  | 319260000 | Yes | Yes
1082 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00157 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00157-Relaying of Road-009039R2477-THIRUMALAI NAGAR 15TH STREET , 009039R2464-THIRUMALAI NAGAR 10TH STREET , 009039R2444-THIRUMALAI NAGAR 2ND STREET , 009039R2449-THIRUMALAI NAGAR 7TH STREET , 009039R2447-THIRUMALAI NAGAR 5TH STREET , 009039R2467-THIRUMALAI NAGAR 6TH CROSS STREET , 009039R2455-Mahasakthi Colony 1st Street , 009039R2489-BAVANANTHIYAR 5TH STREET , 009039R2491-BAVANANTHIYAR 6TH STREET , 009039R2503-NAVANEETHAM NAGAR 2ND STREET , 009040R2675-Sakthi nagar , 009040R2676-Bakkiyam Nagar exten | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :3978 Mts | 2023-24 | 319260000 | 15300000 |  |  |  | 1.38 | 20/09/23 | 1.49 | Completed | 100 | Completed | 100 | 2024-08-02 |  | 16/05/24 |  | 0 |  |  |  | 15300000 | 1.35 | 88.51 | - |  | 319260000 | No | Yes
1083 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00158 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00158-Relaying of Road-009034R2210-GANDHI STREET , 009034S0373-JOTHI NAGAR 3RD STREET , 009034R2182-EMERALD ESTATE , 009034R2237-JUDGE COLONY 1ST MAIN ROAD , 009034R2238-JUDGE COLONY 2ND MAIN ROAD , 009034R2239-HOME ROAD, JUDGE COLONY , 009034R2234-JUDGE COLONY 1ST STREET , 009034R2235-JUDGE COLONY 2ND STREET , 009034R2236-JUDGE COLONY 3RD STREET , 009034R2250-JUDGE COLONY 4TH STREET , 009034R2240-NATARAJAN STREET , 009034R2224-RAGAVENDRA AVENUE , 009034R2244-SRI RAM COLONY , 009034R2222-KANNAMAMAL ST | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :5889 Mts | 2023-24 | 319260000 | 21100000 |  |  |  | 1.9 | 20/09/23 | 1.92 | Completed | 100 | Completed | 100 |  |  | 2024-10-05 |  | 19531364 |  |  |  | 1568636.16 | 1.9 | 89.97 | 20/12/23 |  | 319260000 | No | Yes
1084 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00159 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00159-Relaying of Road-009039R5966-MANAVALAN NAGAR, LAKSHMI NAGAR EXTN , 009039R2482-Thirumalai nagar north street , 009039R2452-THIRUMALAI NAGAR 3RD MAIN ROAD , 009039R2516-Backiyam nagar extension , 009039R2525-Kalathumedu 2nd street , 009040R2635-SOUNDARYA NAGAR 2ND STREET , 009041R2721-DURGA COLONY 2ND STREET , 009041R2742-West street , 009040R2667-VGP PON NAGAR EXTN. , 009040R2663-VGP PONN NAGAR 1ST MAIN ROAD , 009040R2673-VGP PONN NAGAR 5TH STREET , 009042R3054-VALLAL YUSUF NAGAR 1ST MAIN ROAD , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :4316 Mts | 2023-24 | 319260000 | 16600000 |  |  |  | 1.5 | 19/09/23 | 1.48 | Completed | 100 | Completed | 100 | 29/12/23 |  | 16/05/24 |  | 0 |  |  |  | 16600000 | 1.43 | 86.23 | 19/12/23 |  | 319260000 | No | Yes
1085 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00160 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00160-Relaying of Road-009022R1534-BAJANAI KOIL STREET , 009022R1527-Thirumalai Nagar Main Road , 009022R1519-PONNIAMMAN KOIL STREET , 009022R1535-MOSQUE STREET , 009023R1561-PILLAIYAR KOIL STREET , 009023R1568-ISWARAYA NAGAR 1ST STREET , 009025R1706-NELLAIYAPPAR STREET , 009025R1709-CHIDAMBARAM STREET , 009025R1716-RAVI STREET , 009025R1713-VALLUVAR HIGH ROAD , 009025R1707-Ravi Cross Street , 009025R1687-BALAJI NAGAR MAIN ROAD , 009035R2258-RAMACHANDRA STREET , 009035R2263-PERIYAR ROAD , 009035R2259- | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :8138 Mts | 2023-24 | 319260000 | 29400000 |  |  |  | 2.65 | 28/07/23 | 2.84 | Completed | 100 | Completed | 100 |  |  | 2025-04-03 |  | 29398776 |  |  |  | 1224 | 2.51 | 85.53 | 18/01/25 |  | 319260000 | No | Yes
1086 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00161 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00161-Relaying of Road-009022R1462-GANESH NAGAR MAIN ROAD , 009022R1463-MAHANADHI STREET , 009022r1469-YAMUNA STREET , 009022R1470-NEHRU STREET , 009022R1491-BALASUBRAMANIYAM STREET , 009022R1501-NEHRU STREET , 009022R1502-VOC STREET , 009022R1503-NETHAJI STREET , 00920R1504-ANNA STREET , 009022R1505-GANDHI STREET EXTN , 009022R1506-KRISHNA STREET , 009022R1507-LYYAOOAN STREET , 009022R1508-VENKATESAWARA STREET , 009022R1509-THIRUMALAI STREET , 009022R1510-BHARATHIYAR STREET , 009022R1512-SABARI STREE | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :7645 Mts | 2023-24 | 319260000 | 25000000 |  |  |  | 2.25 | 28/07/23 | 2.44 | Completed | 100 | Completed | 100 |  |  | 2025-02-06 |  | 24776556 |  |  |  | 223444 | 2.14 | 85.51 | 18/01/25 |  | 319260000 | No | Yes
1087 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00162 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00162-Relaying of Road-009036R2285-PURUSOTHAMAN NAGAR 4TH MAIN ROAD , 009036R2287-PURUSOTHAMAN 1ST CROSS STREET , 009036R2305-KAMALA STREET , 009036R2313-VALLIAMMAI STREET VIJAYALAKSHMI NAGAR , 009036R2315-GAJALAKSHMI NAGAR 1ST CROSS STREET , 009036R2316-GAJALAKSHMI NAGAR 2ND MAIN ROAD , 009036R2317-GAJALAKSHMI NAGAR 2ND CROSS STREET , 009036R2318-GAJALAKSHMI NAGAR 3RD CROSS ROAD , 009036R2319-GAJALAKSHMI NAGAR MAIN ROAD , 009037R2327-VENKATRAMAN NAGAR 6TH MAIN ROAD , 009037R2332-VIVEK NAGAR , 009037R | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :7187 Mts | 2023-24 | 319260000 | 24000000 |  |  |  | 2.16 | 28/07/23 | 2.34 | Completed | 100 | Completed | 100 |  |  | 2025-04-03 |  | 23365077 |  |  |  | 634923 | 2.08 | 86.71 | 18/01/25 |  | 319260000 | No | Yes
1088 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00163 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00163-Relaying of Road-009049R3558-VOC STREET , 009049R3576-ELUMALAI STREET , 009049R3549-MUTHURANGAM ROAD , 009049R3550-DURAISAMY PILLAI ST , 009049R3551-ALAGESAN STREET , 009049R3556-VENKATESAN STREET , 009049R3572-SIVANANTHAM STREET , 009054R3945-HARITHA ENCLAVE CHOZHAN STREET , 009060R4605-1ST STREET PATEL NAGAR , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :2075 Mts | 2023-24 | 319260000 | 10000000 |  |  |  | 1 | 28/07/23 | 1 | Completed | 100 | Completed | 100 |  |  | 28/03/24 |  | 9976208 |  |  |  | 23792 | 0.9 | 90 | 31/10/23 |  | 319260000 | No | Yes
1089 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00164 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00164-Relaying of Road-009033R2096-RAIL NAGAR MAIN ROAD , 009033R2166-RANGA STREET , 009032R2074-KK PALAYAM PILLAIYAR KOIL STREE , 009033R2132-KAMATCHI NAGAR 2ND MAIN ROAD , 009052R3676-LAKSHMIPURAM 3RD MAIN ROAD , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :893 Mts | 2023-24 | 319260000 | 5800000 |  |  |  | 0.58 | 28/07/23 | 0.58 | Completed | 100 | Completed | 100 |  |  | 2024-12-06 |  | 5045458 |  |  |  | 754542 | 0.5 | 86.99 | 31/10/23 |  | 319260000 | Yes | Yes
1090 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00165 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00165-Relaying of Road-009055R3982-Good will nagar main Road , 009055R4078-VISHNU NAGAR- EB COLONY 3RD STREET , 009058R4356-RAJAMANIKKAM STREET , 009059R4421-T.T.K. NAGAR 3RD CROSS STREET , 009055R4031-BHARATHI NAGAR 2ND STREET , 009057R4308-KRISHNA ROAD , 009061R4652-ERIKKARAI SALAI , 009055R4094-APPAR STREET , 009055R4066-SUNDHARAR STREET , 009055R4075-VISHNU NAGAR EB COLONY MAIN ROAD , 009055R4034-BHARATHI NAGAR 5TH STREET , 009057R4286-MUTHUVELAR STREET , 009055R4035-BHARATH | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :5720 Mts | 2023-24 | 319260000 | 13900000 |  |  |  | 1.39 | 28/07/23 | 1.39 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 13513469 |  |  |  | 386530.51 | 1.22 | 87.65 | 31/10/23 |  | 319260000 | No | Yes
1091 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00166 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00166-Relaying of Road-009055R6119-Asirvatham Homes Road , 009057R4269-KAMATCHI NAGAR 3RD STREET , 009058R4362-NEHRU NEDUNCHALAI , 009059R4524-THOLKAPPIYAR STREET , 009059R4420-T.T.K. NAGAR 2ND MAIN ROAD , 009061R4672-V.O.C. STREET , 009061R4667-VIJAYALAKSHMI STREET , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :2881 Mts | 2023-24 | 319260000 | 10800000 |  |  |  | 1.08 | 2023-01-09 | 1.08 | Completed | 100 | Completed | 100 |  |  | 19/02/24 |  | 10075025 |  |  |  | 724975 | 1.02 | 94.42 | 2023-03-12 |  | 319260000 | No | Yes
1092 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00167 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00167-Relaying of Road-009046R3443-MANIMEGALAI STREET EAST , 009048R3509-BHARADWAJAR STREET (VALMIGI ST TO NALWAR STREET) , 009048R3518-BHARADWAJAR STREET (SUGAMAHARISHI STREET TO VELACHERY MAIN ROAD) , 009048R3514-KARPAGA VINAYAGAR KOIL ST , 009065R5009-K.V.K. NAGAR 1ST STREET , | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1608 Mts | 2023-24 | 319260000 | 6100000 |  |  |  | 0.55 | 28/07/23 | 0.59 | Completed | 100 | Completed | 100 |  |  | 2023-03-01 |  | 5772372 |  |  |  | 327628 | 0.55 | 90 | 26/10/23 |  | 319260000 | No | Yes
1093 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00168 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00168-Relaying of Road-009066R6294-MANIMEGALAI STREET , 009066R5100-VENUGOPAL STREET , 009067R6313-Sannadi Cross Street , 009067R5177-Dhuwagapuri Main Road , 009067R5178-Dhuwagapuri Ist street , 009068R5373-JAIWANTHPURAM MAIN ROAD , 009068R5365-ALAMELUPURAM 2ND MAIN ROAD , 009068R5317-DEVARAJ NAGAR SHEELA RAJARATHINAM STREET , 009069R5481-Agaram to Madambakkam , 009069R5550-Muthumariyamman kovil Street , 009069R5435-Shirdi Sai Nagar Main Road , 009070R6402-chandraprabu Nagar Main Road , 009070R5653-D | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :3645 Mts | 2023-24 | 319260000 | 9400000 |  |  |  | 0.85 | 28/07/23 | 0.9 | Completed | 100 | Completed | 100 | 2024-10-01 |  | 29/04/24 |  | 9349565 |  |  |  | 50435 | 0.85 | 90 | 26/10/23 |  | 319260000 | No | Yes
1094 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00169 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00169-Relaying of Road-009066R5064-Roja thottam main road , 009066R5093-Vallalar main road , 009066R5105-EZHIL NAGAR 1ST STREET , 009066R2897-Ragavendhra nagar main road , 009066R5112-CHERAN STREET , 009067R5203-ARAVIND NAGAR 5TH STREET , 009067R5179-DWARAGAPURI NAGAR 2ND STREET , 009067R5204-ARAVIND NAGAR EAST MAIN ROAD , 009067R5248-MAYANA STREET , 009067R5139-Prasanthi Colony Main Road , 009067R5142-Prasanthi Colony Main Road , 009069R5438-Shirdi Sai Nagar 5th Cross Street , 009070R6371-Bala Garden | Roads | Bituminous Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :3329 Mts | 2023-24 | 319260000 | 12500000 |  |  |  | 1.13 | 28/07/23 | 1.21 | Completed | 100 | Completed | 100 | 2024-10-01 |  | 29/04/24 |  | 12219914 |  |  |  | 280086 | 1.13 | 90 | 26/10/23 |  | 319260000 | No | Yes
1095 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00204 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00204-Relaying of Road-Bituminous Road009034R2187-JOTHI NAGAR 5TH STREET , 009034R2186-JOTHI NAGAR 4TH STREET , 009034R2185-JOTHI NAGAR 2ND STREET , 009034R2195-ANNA STREET , 009034R2204-Chitlapakkam 3rd main road(anna st t0 seethapathy st) , 009043R3160-CHITLAPAKKAM 3RD MAIN ROAD , 009043R3201-SARVAMANGALA NAGAR FIRST MAIN ROAD , 009043R3227-LAKSHMINAGAR 2ND STREET , 009043R3226-LAKSHMI NAGAR FIRST MAIN ROAD , 009043R3137-THIRUMURUGAN SALAI , 009043R3123-PAMBANSAMIGAL SALAI , 009044R3251-PAMANSAMYGAL | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :3926 Mts | 2022-23 | 98900000 | 10370000 |  |  |  | 0.94 | 22/06/23 | 1.04 | Completed | 100 | Completed | 100 | 13/10/23 |  | 15/05/24 |  | 10352333 |  |  | 0 | 17667 | 1.04 | 99.83 | 18/03/24 |  | 98900000 | Yes | Yes
1096 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00205 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00205-Relaying of Road-Bituminous Road009039R2537-LAKSHMI NAGAR MAIN ROAD , 009039R2526-SENTHIL AVENUE 1ST MAIN ROAD , 009039R2488-BAVANANTHIYAR 4TH STREET , 009039R2469-THIRUMALAI NAGAR 13 TH STREET , 009039R2463-THIRUMALAI NAGAR 9TH STREET , 009039R2492-BAVANANTHIYAR 7TH STREET , 009039R2493-BAVANANTHIYAR 7TH CROSS STREET , 009039R2481-Vijayakumar avenue , 009040R2577-R B AVENUE 1ST STREET , 009040R2593-GAYATHIRI NAGAR MAIN ROAD , 009041R2753-TELLUS AVENUE PH-2 DR.ABDULKALAM 3RD CROSS STREET , 0090 | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2710 Mts | 2022-23 | 98900000 | 10100000 |  |  |  | 0.96 | 19/06/23 | 1.01 | Completed | 100 | Completed | 100 | 17/11/23 |  | 15/05/24 |  | 10068596 |  |  | 0 | 31403.69 | 0.91 | 90 | 15/03/24 |  | 98900000 | No | Yes
1097 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00206 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00206-Relaying of Road-Bituminous Road009055R4007-FCI , 009055R4086-SATHIYAMOORTHY STREET , 009056R6225-Indra Nagar Main Road (Sivasakthi Nagar Main Road) , 009058R4338-JAWAHARLAL NEHRU STREET , 009059R4513-UMA NAGAR , 009059R4388-SAKTHI NAGAR EXTN , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2417 Mts | 2022-23 | 98900000 | 8588000 |  |  |  | 0.86 | 19/06/23 | 0.86 | Completed | 100 | Completed | 100 |  |  | 24/02/25 |  | 8585770 |  |  |  | 2230 | 0.86 | 99.97 | 15/03/24 |  | 98900000 | Yes | Yes
1098 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00207 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00207-Relaying of Road-Bituminous Road009033L0163-Station Border Road (Jaya Nagar 1st Main Road to Apparao Colony) , 009049R3538-ANNA STREET , 009052R3722-KALAIMAGAL 1ST STREET , 009054R3937-JOTHI NAGAR 1ST STREET , 009032R2058-PILLAYAR KOIL STREET , 009051R3636-THIRUVALLUVAR ST , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :906 Mts | 2022-23 | 98900000 | 6150000 |  |  |  | 0.37 | 19/06/23 | 0.62 | Completed | 100 | Completed | 100 |  |  | 23/08/24 |  | 4904094 |  |  |  | 1245906 | 0.45 | 73.09 | 17/09/23 |  | 98900000 | No | Yes
1099 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00208 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00208-Relaying of Road-Bituminous Road009029R1875-NATCHIYAR STREET, UMAYALPURAM , 009029R1848-MADUVAPPAR 1ST STREET , 009029R1849-MADUVAPPAR 2ND STREET , 009029S0346-VELAPPAR STREET, LAKSHMIPURAM, CHENNAI-44 , 009030R1911-MANI STREET , 009030R1926-Perumal Street , 009030R5939-Iyya Govindaswamy street , 009030R1908-JAYARAM NAGAR MAIN ROAD , 009030R1894-NEERVANNAN 2ND STREET, LAKSHMIPURAM , 009031R1960-Kasi Gardan 2nd Street , 009031R1951-SUBRAYANNAGAR 2ND MAIN ROAD, THIRUNEERMALAI, CHENNAI-600 044. , 0 | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2854 Mts | 2022-23 | 98900000 | 9850000 |  |  |  | 0.89 | 16/06/23 | 0.99 | Completed | 100 | Completed | 100 |  |  | 28/02/25 |  | 9822481 |  |  |  | 27519 | 0.8 | 80.73 | 2024-12-03 |  | 98900000 | No | Yes
1100 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2022-23/009/ROAD/00209 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2022-23/009/ROAD/00209-Relaying of Road-Bituminous Road009029R1882-1ST PUTHU STREET , 009029R1846-SANGAM SALAI, LAKSHMIPURAM, CHENNAI , 009030R1914-TNHB Colony form GST Road To Flat 294/271 , 009031R1985-KUMARASAMY STREET, LAKSHMIPURAM, CHENNAI-600 044 , 009030R1917-2ND CROSS STREET, TNHB COLONY, DURGA NAGAR, CHENNAI-47 , | Roads | Bituminous Road | G.O. (D)No. 234-1Dated:28/04/23Road DetailsRoad Length :2083 Mts | 2022-23 | 98900000 | 9973000 |  |  |  | 1 | 22/06/23 | 1 | Completed | 100 | Completed | 100 |  |  |  |  | 9973000 |  |  | 0 | 0 | 1 | 100 | 18/03/24 |  | 98900000 | Yes | Yes
1101 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00078 | Zone I |  | TURIP TURIP/2025-26/009/ROAD/00078-Relaying of Road-Bituminous Road009005R0403-SHANKAR NAGAR 43RD STREET , 009005R0382-39TH STREET SANKAR NAGAR , 009005R0387-32ND STREET SANKAR NAGAR , 009005R0335-GANAPATHI NAGAR 2ND STREET , 009005R0361-THENDRAL NAGAR THIRU.VI. KA SALAI 1ST CROSS ST , 009005R0350-Tholkappiyar Street , Zone I (package No.I) | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1059 Mts | 2025-26 | 521620000 | 9430000 |  |  |  | 0 | 2025-10-06 | 0.94 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 9427662 |  |  | 0 | 2338 | 0.85 | 89.96 | 2025-09-08 |  | 521620000 | No | Yes
1102 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00167 |  |  | TURIP TURIP/2024-25/009/ROAD/00167-Relaying of Road-Bituminous Road009005R5769-ANNAI THERSA STREET L I C COLONY , 009006R0438-NEELAMEGAM STREET LIC COLONY , 009006S0017-6TH STREET M.G.R NAGAR , 009006R0468-NETHAJI STREET V O C NAGAR , 009012R0896-BHARATHIYAR STREET PRASANTHI NAGAR , 009012R0851-TIRUPPUR KUMARAN STREET , 009012S0085-MARIYAMMAN KOIL STREET - NAGALKENI , 009012R0863-5TH STREET AKESWARAN COLONY , 009012R0864-6TH CROSS STREET AKKISHWARAN COLONY , 009012R0874-7TH STREET AREGESWARAN COLONY , 009012R0885-EN | Roads | Bituminous Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :2710 Mts | 2024-25 | 197393000 | 18743000 |  |  |  | 1.69 | 26/09/24 | 0 | Completed | 100 | Completed | 100 |  |  | 24/02/25 |  | 18666151 |  |  |  | 76849.02 | 1.68 | 89.73 | - |  | 197393000 | No | Yes
1103 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00168 |  |  | TURIP TURIP/2024-25/009/ROAD/00168-Relaying of Road-Bituminous Road009002R0105-GURUSWAMY NAGAR 6TH STREET , 009002R0183-Balaji Nagar 14th Cross Street , 009002R0185-KALIVANAR STREET , 009002R0115-G.K.NAGAR 3RD STREET , 009002R0076-VENKATESWARA NAGAR ANNA 1ST STREET , 009002R0077-VENKATESWARA NAGAR BHARATHIDASAN STREET , 009002R0099-GURUSWAMY NAGAR MAIN ROAD , 009002R0090-VENKATESWARA NAGAR KULATHUNGAN STREET , 009002R0086-VENKATESWARA NAGAR THIRUVALLUVAR STREET , 009002R0114-G.K.NAGAR 2ND STREET , 009002R0189-BABUREDDY AVENUE , 0 | Roads | Bituminous Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :2515 Mts | 2024-25 | 197393000 | 13200000 |  |  |  | 1.19 | 2024-12-09 | 0 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 13199895 |  |  | 0 | 105 | 1.19 | 90 | - |  | 197393000 | No | Yes
1104 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00031 | Zone II | 15, 16, 17, 18, 21, 22, 23, 24, 26, 27 | SRP SRP/2020-21/009/ROAD/00031-Providing BT surface to Kambar Street,Ward No 15,Manimegalai west street in ward 16 Manimegalai street Extn in ward 17, Subramanian Street and Annai Sivagami Street in Ward no.18,KVK Nagar in Ward No.21,Kalaignar Street,Vallalar Street and jejajeevanram street in Ward No.22,Lalbagathur Street and Leelavathi Nagar in Ward no 23,Subramaniyasiva Street,Bajanai Kovil street,VVS Iyer Street in Ward No 24 Smith Lane in ward no 26 and Arul Nagar Nagar Main Road ,NK lane 1 & 2nd Street in Ward No 27 | Roads | Bituminous Road | 20557/2020/E3Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 30000000 | 15000000 | 0 |  |  | 0.7 | 2021-01-02 | 1.56 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 8493300 |  |  |  | 6506700 | 0.7 | 46.93 | 2021-01-08 |  | 30000000 | Yes | Yes
1105 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/021/ROAD/0000001 | Zone II | 6, 7, 10 | SRP SRP/2020-21/021/ROAD/0000001-Improvements to (Ward No. 6) Pasumpon Nagar Pulavar Jeganathan Street, Nagalingam Street, Vallalar Street, Prabhudoss Street, (Ward No. 7) Thiruvalluvar Nagar Maniyammaiyar Street, Anandan and Cross Street, Durgai Amman Koil Street, (Ward No. 10) AK Durai Street, Anna Nagar 2nd Street, Anna Nagar 5th Cross Street and Nanchillar Street | Roads | Bituminous Road | 298Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 35000000 | 6300000 | 0 |  |  | 0.6 | 22/01/21 | 0.61 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6300000 | 0.51 | 80.78 | 22/04/21 |  | 35000000 | Yes | Yes
1106 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/021/ROAD/00002 | Zone II | 12, 14, 17, 19, 21 | SRP SRP/2020-21/021/ROAD/00002-Improvements to BT surface at Ward 12, Masoothi Street, Ward 14 Moses Street, Ward 17 Rosammal Street, Masthan sahib street Ward 19, Bajanai koil street and Ward 21 Kamarajan street | Roads | Bituminous Road | 298Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 35000000 | 8500000 |  |  | 0 | 0.9 | 22/01/21 | 0.86 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 8500000 | 0.74 | 87.64 | 26/05/21 |  | 35000000 | Yes | Yes
1107 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00195 |  |  | SRP SRP/2020-21/009/ROAD/00195-Relaying of Road-017/2021/002/R/0000343-Thiruvalluvar Pettai 1st Street , 017/2021/004/R/000062-GURUSWAMY NAGAR 1ST STREET , 017/2021/004/R/000074-GURUSWAMY NAGAR 4TH STREET , 017/2021/004/R/000037-VENKATESWARA NAGAR BHARATHIDASAN STREET , 017/2021/004/R/000080-VENKATESWARA NAGAR RAJAJI STREET , | Roads | Bituminous Road | 20557/E3/2020Dated:11/12/20Road DetailsRoad Length :Mts | 2020-21 | 10000000 | 10000000 | 0 |  |  | 0.9 | 2021-12-01 | 0.89 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 10000000 | 0.8 | 80 | 13/03/21 |  | 10000000 | Yes | Yes
1108 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00133 |  |  | SRP SRP/2020-21/009/ROAD/00133-Relaying of Road-021/2021/009/R/0000183-KALAINJAR CROSS STREET ANNA NAGAR , 021/2021/009/R/0000191-GANDHI ROAD ANNA NAGAR , 021/2021/010/S/0000198-PAARI VALLAL STREET , 021/2021/010/R/0000490-SENGUTTUVAN STREET MUTAMIL NAGAR , 021/2021/011/R/0000493-PARTHASARATHY STREET MUTHAMIZH NAGAR , 021/2021/010/R/0000485-S.G. NATARAJAN STREET MUTHAMIZH NAGAR , | Roads | Bituminous Road | 805-3Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 7900000 | 7900000 |  |  |  | 0.76 | 22/01/21 | 0.78 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 7900000 | 0.67 | 85.37 | 22/05/21 |  | 7900000 | Yes | Yes
1109 | Tambaram | SRP | CHENGALPATTU | SRP/2020-21/009/ROAD/00134 |  |  | SRP SRP/2020-21/009/ROAD/00134-Relaying of Road-021/2021/020/R/0000610-THANDHAI PERIYAR 1ST CROSS STREET , 021/2021/020/R/0000371-THANTHAI PERIYAR 3RD CROSS STREET CHOZHAVARAM NAGAR , 021/2021/020/R/0000368-NAVAMANI STREET , 021/2021/020/R/0000608-AMBEDKAR MAIN ROAD , 021/2021/021/R/0000581-KM ADAM SALAI , 021/2021/021/R/0000383-SARGUNAR SALAI , | Roads | Bituminous Road | 20557/2018/E3Dated:14/12/20Road DetailsRoad Length :Mts | 2020-21 | 6500000 | 6500000 |  |  |  | 0.64 | 22/01/21 | 0.61 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6500000 | 0.57 | 87.69 | 22/04/21 |  | 6500000 | Yes | Yes
1110 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00404 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00404-Repair /Maintenance-009/05/047/R/4274-ERIKARAI STREET , | Roads | Bituminous Road | 31442/2021/E3 semb-7Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 950000 | 950000 |  |  |  | 0.1 | 31/12/21 | 0.08 | Completed | 100 | Completed | 100 |  |  | 16/09/22 |  | 949892 |  |  |  | 108 | 0.09 | 90.92 | 30/01/22 |  | 950000 | Yes | Yes
1111 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2023-24/009/ROAD/00189 |  |  | Kalaignar Nagarpura Mempatu Thittam KNMT/2023-24/009/ROAD/00189-Relaying of Road-009001R5734-V.G.A.NAGAR 1ST STREET , 009001R5735-V.G.A.NAGAR 2ND STREET , 009002R5737-venkateswara Nagar kalimagal 3rd cross street , 009002R5742-BALAJI NAGAR V.O.C STREET , 009002R5749-Balaji Nagar A.N.Pandian 2nd Cross Street , | Roads | Bituminous Road | G.O. (4D) No. 20Dated:08/06/23Road DetailsRoad Length :435 Mts | 2023-24 | 16200000 | 3500000 |  |  |  | 0.32 | 19/07/23 | 0 | Completed | 0 | Completed | 100 | 25/10/22 |  | 24/01/24 |  | 3518407 |  |  |  | -18406.88 | 0.32 | 90.57 | 19/10/23 |  | 16200000 | No | Yes
1112 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00277 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00277-Repair /Maintenance-009/05/067/R/0018-Brinthavan Nagar Main Road , 007/2022/014/R/00006-BALAJI NAGAR 1ST STREET , | Roads | Bituminous Road | 31442/2021/E3-Madambakkam-Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 1500000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.09 | Completed | 100 | Completed | 100 |  |  | 30/03/22 |  | 884157 |  |  |  | 15843 | 0.09 | 98.24 | 2022-06-02 |  | 1500000 | Yes | Yes
1113 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00278 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00278-Repair /Maintenance-009/05/070/R/0017-Padhuvanchery Main Road , 007/2021/017/R/0000892-GANAPATHY NAGAR , | Roads | Bituminous Road | 31442/2021/E3-Madambakkam-Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 1500000 | 600000 | 0 |  |  | 0.06 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 |  |  | 30/03/22 |  | 589400 |  |  |  | 10600 | 0.06 | 98.17 | 2022-06-02 |  | 1500000 | Yes | Yes
1114 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00434 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00434-Repair /Maintenance-009/01/005/R/1205-SHANKAR NAGAR 26TH STREET , 009/01/005/R/0556-SHANKAR NAGAR 27TH STREET , 009/01/005/R/0579-SHANKAR NAGAR 1ST MAINROAD , 009/01/006/R/0093-4TH CROSS STREET LIC COLONY , 009/01/006/R/1509-T.R. MANI STREET V O C NAGAR , | Roads | Bituminous Road | DMA Proc Roc.No.31442 / 2021 / E3 / Pammal-1Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 4775000 | 985000 |  |  |  | 0.1 | 2022-03-01 | 0.09 | Completed | 100 | Completed | 100 |  |  | 2022-08-11 |  | 10 |  |  |  | 984990.15 | 0.1 | 99.48 | 18/01/22 |  | 4775000 | Yes | Yes
1115 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00444 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00444-Repair /Maintenance-009/01/003/R/0406-Punniyakotti Nagar , 009/04/061/R/1777-THIRUVALLUVAR ROAD , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 532000 |  |  |  | 0.05 | 2022-03-01 | 0.05 | Completed | 100 | Completed | 100 |  |  | 2022-12-04 |  | 532000 |  |  |  | 0 | 0.05 | 99.95 | 18/01/22 |  | 5357000 | Yes | Yes
1116 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00445 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00445-Repair /Maintenance-009/04/058/R/0757-RAMALINGA ADIGALAR STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 560000 |  |  |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Completed | 100 |  |  | 2022-08-11 |  | 6 |  |  |  | 559994.4 | 0.06 | 99.93 | 18/01/22 |  | 5357000 | Yes | Yes
1117 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00446 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00446-Repair /Maintenance-009/04/056/R/1420-GANDHI STREET , 009/01/003/R/1374-ADIVASI NAGAR , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 392000 |  |  |  | 0.01 | 2022-03-01 | 0.03 | Completed | 100 | Completed | 100 |  |  | 2022-08-11 |  | 136000 |  |  |  | 256000 | 0.01 | 34.81 | 18/01/22 |  | 5357000 | Yes | Yes
1118 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00447 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00447-Repair /Maintenance-009/01/004/R/0486-BAKTHAVACHALAM STREET , 009/01/004/R/0497-LIC COLONY 8TH CROSS STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 420000 |  |  |  | 0.04 | 2022-03-01 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2024-11-09 |  | 4 |  |  |  | 419995.8 | 0.04 | 99.92 | 18/01/22 |  | 5357000 | Yes | Yes
1119 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00448 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00448-Repair /Maintenance-009/01/003/R/1478-KAMATCHI NAGAR 4TH STREET , 009/01/003/R/1461-KAMATCHI NAGAR 5TH CROSS STREET , 009/01/003/R/1465-KAMATCHI NAGAR 6TH STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 350000 |  | 0 | 0 | 0.03 | 2022-03-01 | 0.03 | Completed | 100 | Completed | 100 | 2022-04-05 |  | 2024-09-09 |  | 4 |  |  |  | 349996.5 | 0.03 | 99.9 | 18/01/22 |  | 5357000 | Yes | Yes
1120 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00449 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00449-Repair /Maintenance-009/03/023/R/0732-MAHATMA GANDHI STREET , 009/01/003/R/1505-BAZAAR STREET , 009/03/034/R/2713-KULAKKARAI STREET , | Roads | Bituminous Road | 31442/2021/E3 (Anakaputhur)Dated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 5357000 | 514000 |  |  |  | 0.05 | 2022-03-01 | 0.04 | Completed | 100 | Completed | 100 |  |  | 2022-08-11 |  | 514000 |  |  |  | 0 | 0.05 | 99.9 | 18/01/22 |  | 5357000 | Yes | Yes
1121 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00099 |  |  | TURIP TURIP/2025-26/009/ROAD/00099-Relaying of Road-Bituminous Road009056R4099-KURINJI NAGAR MAIN ROAD , 009056R4102-KURINJI NAGAR 3RD MAIN ROAD , 009056R4106-KURINJI NAGAR 4TH MAIN ROAD EXTN , 009056R4107-KURINJI NAGAR 5TH MAIN ROAD , 009056R4117-RAJA RAJESWARI NAGAR 3RD STREET , 009056R4119-SRI RAM NAGAR 1ST MAIN ROAD , 9056R4121-RAJARAJESHWARI NAGAR EXTN , 009056R4122-KURINJI NAGAR EXTN , 009056R4128-SENTHIL NAGAR 2ND STREET , 009056R4161-Thiruvenkatapuram , 009056R4175-PARVATHI NAGAR , 009056r4176-SELLIAMMAN KOIL STREET | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :3426 Mts | 2025-26 | 521620000 | 18100000 |  |  |  | 1.63 | 2025-10-06 | 1.49 | Completed | 100 | Completed | 100 |  |  | 18/12/25 |  | 18079086 |  |  |  | 20914 | 1.63 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1122 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00100 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00100-Relaying of Road-Bituminous Road009057R4239-SRI BALAJI NAGAR 2ND STREET , 009055R4246-RAGHAVENDRA NAGAR , 009057R4267-KAMATCHI NAGAR 1ST STREET , 009057R4275-ELUMALAIYAR STREET , 009057R4270-KAMATCHI NAGAR 4TH STREET , 009057R4249-VIVEK NAGAR 2ND STREET , 009057R4248-VIVEK NAGAR 1ST STREET - CASTLE HOMES , 009057R4282-ANJUGAM STREET , 009057R4297-PERIYALWAR STREET , 009057R6234-Angalamman Kovil Street , 009057R4299-TIRUMAZHAI ALWAR STREET , ZONE IV-Package No..30 | Roads | Bituminous Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :970.13 Mts | 2025-26 | 521620000 | 9400000 |  |  |  | 0.85 | 2025-10-06 | 0.77 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9400000 | 0.85 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1123 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00226 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00226-Repair /Maintenance-009/2021/027/R/0000621-OLD G.S.T ROAD , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 1000000 |  |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1000000 |  |  |  | 0 | 0.1 | 99.96 | 2022-05-02 |  | 39126000 | Yes | Yes
1124 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00227 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00227-Repair /Maintenance-009/2021/021/R/0000384-IAF ROAD (ZION SCHOOL SIDE) , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 920000 | 0 |  |  | 0.09 | 2022-03-01 | 0.08 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 920000 |  |  |  | 0 | 0.09 | 99.95 | 2022-05-02 |  | 39126000 | Yes | Yes
1125 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00228 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00228-Repair /Maintenance-009/2021/021/R/0000406-IAF MAIN ROAD , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 1290000 |  |  |  | 0.13 | 2022-03-01 | 0.13 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1290000 |  |  |  | 0 | 0.06 | 50.23 | 2022-05-02 |  | 39126000 | Yes | Yes
1126 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00213 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00213-Repair /Maintenance-009/2021/021/R/0000424-RICKY GARDEN 1ST MAIN ROAD CROSS , 009/2021/021/R/0000425-RICKY GARDEN 2ND MAIN ROAD , 009/2021/021/R/0000431-RICKY GARDEN 5TH CROSS STREET , 009/2021/021/R/0000339-VIGNESH AVENUE MAIN ROAD , 009/2021/021/R/0000340-VIGNESH AVENUE 1ST STREET , 009/2021/021/R/0000341-VIGNESH AVENUE 1ST CROSS STREET , 009/2021/021/R/0000342-VIGNESH AVENUE 2ND CROSS STREET , 009/2021/021/R/0000343-VIGNESH AVENUE 3RD CROSS STREET , 009/2021/021/R/0000344-VIGNESH AVENUE 4TH C | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 960000 |  |  |  | 0.1 | 31/12/21 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 959000 |  |  |  | 1000 | 0.1 | 99.93 | 2022-06-02 |  | 39126000 | Yes | Yes
1127 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00214 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00214-Repair /Maintenance-009/2021/011/R/000025-BHARATHA MADHA ST , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 7259000 |  |  |  | 0.73 | 31/12/21 | 0.73 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 7225000 |  |  |  | 34000 | 0.72 | 99.53 | 2022-05-02 |  | 39126000 | Yes | Yes
1128 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00215 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00215-Repair /Maintenance-009/2021/019/R/0001248-DHANALAKSHMI 1ST STREET , 009/2021/019/R/0000190-DHANALAKSHMI 1ST STREET 5TH CROSS , 009/2021/019/R/0001250-PERIYATHAMBI ST , 009/2021/019/R/0000172-RAJESWARI NAGAR MAIN ROAD (100 FEET ROAD) , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 990000 |  |  |  | 0.1 | 31/12/21 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 990000 |  |  |  | 0 | 0.1 | 99.97 | 2022-06-02 |  | 39126000 | Yes | Yes
1129 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00216 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00216-Repair /Maintenance-009/2021/027/R/0000632-ARUL NAGAR 2ND MAIN ROAD , 017/2021/001/R/0000235-ARUL NAGAR 3RD STREET , 009/2022/027/R/00003-ARUL NAGAR 3RD MAIN ROAD 1ST CROSS , 009/2022/027/R/00007-ARUL NAGAR 3RD MAIN ROAD 2ND CROSS , 009/2022/027/R/00006-ARUL NAGAR 3RD MAIN ROAD 3RD CROSS , 009/2021/024/R/0000496-VVS IYER STREET , 009/2021/024/R/0001307-BAJANAI KOIL STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 850000 |  |  |  | 0.09 | 31/12/21 | 0.09 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 849000 |  |  |  | 1000 | 0.08 | 99.88 | 2022-06-02 |  | 39126000 | Yes | Yes
1130 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00217 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00217-Repair /Maintenance-009/2021/027/R/0001313-BALAJI NAGAR NARMADHA STREET , 009/2021/027/S/0000571-BALAJI NAGAR NARMADHA STREET 1ST CR , 009/2021/027/R/0000572-BALAJI NAGAR NARMADHA STREET 2ND CR , 009/2021/027/R/0000573-BALAJI NAGAR NARMADHA STREET 3RD CR , 009/2021/027/R/0000575-BALAJI NAGAR NARMADHA STREET 5TH CR , 009/2021/027/R/0000576-BALAJI NAGAR NARMADHA STREET 6TH CR , 009/2021/027/S/0000577-BALAJI NAGAR NARMADHA STREET 7TH CR , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 940000 |  |  |  | 0.09 | 31/12/21 | 0.09 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 940000 |  |  |  | 0 | 0.09 | 99.95 | 2022-06-02 |  | 39126000 | Yes | Yes
1131 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00218 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00218-Repair /Maintenance-009/2021/027/S/0000578-BALAJI NAGAR NARMADHA STREET 8TH CR , 009/2021/023/R/0000466-BETHELPURAM , 009/2021/031/R/0000988-VENKATESAN STREET , 009/2021/020/S/0000284-MADHA KOIL 1ST CROSS STREET , 009/2021/020/S/0000285-MADHA KOIL 2ND CROSS STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 880000 |  |  |  | 0.09 | 31/12/21 | 0.09 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 0 |  |  |  | 880000 | 0.09 | 99.96 | 2022-06-02 |  | 39126000 | Yes | Yes
1132 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00219 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00219-Repair /Maintenance-009/2021/020/R/0001254-NEW BALAJI NAGAR MAIN ROAD , 009/2021/020/R/0000216-NEW BALAJI NAGAR 1ST STREET , 009/2021/020/R/0000217-NEW BALAJI NAGAR 2ND STREET , 009/2021/020/R/0000219-NEW BALAJI NAGAR 3RD STREET , 009/2021/020/R/0000220-NEW BALAJI NAGAR 3RD STREET , 009/2021/020/R/0000218-NEW BALAJI NAGAR 2ND STREET , 009/2021/020/R/0000215-NEW BALAJI NAGAR 1ST STREET , 009/2021/020/R/0000227-NEW BALAJI NAGAR EXTN 4TH STREET , 009/2021/020/R/0000222-NEW BALAJI NAGAR 5TH STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 990000 |  |  |  | 0.1 | 31/12/21 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 989000 |  |  |  | 1000 | 0.1 | 99.87 | 2022-06-02 |  | 39126000 | Yes | Yes
1133 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/ROAD/00220 |  |  | State Disaster Response Fund State Disa/2021-22/009/ROAD/00220-Repair /Maintenance-009/2021/021/R/0000371-BAGAVATHI NAGAR 1ST MAIN ROAD , 009/2021/021/R/0000372-BAGAVATHI NAGAR 1ST MAIN ROAD CROSS , 009/2021/021/R/0000373-BAGAVATHI NAGAR 2ND MAIN ROAD , 009/2021/021/R/0000357-A.P.N.NAGAR 1ST STREET , 009/2021/021/R/0000358-A.P.N.NAGAR 2ND ST , 009/2021/021/R/0000359-A.P.N.NAGAR CROSS STREET , 001/2021/012/R/0000276-MARUTHI NAGAR 2ND CROSS STREET , | Roads | Bituminous Road | 31442/2021/E3-TambaramDated:15/12/21Road DetailsRoad Length :Mts | 2021-22 | 39126000 | 960000 |  |  |  | 0.1 | 31/12/21 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 959000 |  |  |  | 1000 | 0.1 | 99.9 | 2022-06-02 |  | 39126000 | Yes | Yes
1134 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00065 | Zone I | 3, 5 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00065-Road Restoration of damaged portion over at Kannabiran Kovil Street (007003R051) & Ranganathan Street (007005R066) in Ward No.03 & 05 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 950000 | 0 |  |  | 0.08 | 2022-05-01 | 0.1 | Completed | 100 | Completed | 100 | 2022-10-05 |  | 2022-08-06 |  | 950000 |  |  |  | 0 | 0.08 | 84.21 | 2022-05-02 |  | 41050000 | Yes | Yes
1135 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00044 | Zone II | 26 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00044-Road Restoration of damaged portion over at Nammalwar Street (007026R1008),Fernando Street (007026S265) in Ward No.26 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 750000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 | 2022-02-05 |  | 2024-09-09 |  | 750000 |  |  |  | 0 | 0.07 | 89.33 | 2022-03-02 |  | 41050000 | Yes | Yes
1136 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00045 | Zone II | 26 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00045-Road Restoration of damaged portion over at Dr.Colony (007026R1007) in Ward No.26 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 600000 |  |  |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Completed | 100 | 21/07/22 |  | 2024-09-09 |  | 586791 |  |  |  | 13209 | 0.05 | 88.17 | 2022-03-02 |  | 41050000 | Yes | Yes
1137 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00046 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00046-Road Restoration of damaged portion over at Shanthi Nagar 5th Street (007025R987) in Ward No.25 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 500000 |  |  |  | 0.05 | 2022-03-01 | 0.04 | Completed | 100 | Completed | 100 | 2022-06-08 |  | 2024-09-09 |  | 500000 |  |  |  | 0 | 0.05 | 90 | 2022-03-02 |  | 41050000 | Yes | Yes
1138 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00047 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00047-Road Restoration of damaged portion over at Shanthi Nagar 1st Cross Street (007025R981) in Ward No.25 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 600000 |  |  | 0 | 0.06 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 | 2022-06-08 |  | 2024-09-09 |  | 600000 |  |  |  | 0 | 0.05 | 90.17 | 2022-03-02 |  | 41050000 | Yes | Yes
1139 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00048 | Zone III | 25 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00048-Road Restoration of damaged portion over at Shanthi Nagar 2nd Street 2nd Cross Street (007025R985) in Ward No.25 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 600000 | 0 |  |  | 0.06 | 2022-03-01 | 0.05 | Completed | 100 | Completed | 100 | 2022-06-08 |  | 2024-09-09 |  | 600000 |  |  |  | 0 | 0.05 | 90.17 | 2022-03-02 |  | 41050000 | Yes | Yes
1140 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00049 | Zone II | 21 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00049-Road Restoration of damaged portion over at Kannan Nagar 2nd Street (007024S260),Kannabiran Street (007023S259) in Ward No.21 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 680000 |  |  |  | 0.07 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 680000 |  |  |  | 0 | 0.06 | 89.12 | 2022-03-02 |  | 41050000 | Yes | Yes
1141 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00050 | Zone III | 23 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00050-Road Restoration of damaged portion over at Kannabiran Street (007023S259) in Ward No.23 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 800000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 800000 |  |  |  | 0 | 0.07 | 89.13 | 2022-03-02 |  | 41050000 | Yes | Yes
1142 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00051 | Zone III | 22 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00051-Road Restoration of damaged portion over at Big Street (007022R903) in Ward No.22 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 700000 |  |  | 0 | 0.07 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 | 18/05/22 |  | 2024-09-09 |  | 700000 |  |  |  | 0 | 0.06 | 90.14 | 2022-03-02 |  | 41050000 | Yes | Yes
1143 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00052 | Zone II | 21 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00052-Road Restoration of damaged portion over at NGO Colony 2nd Street (007021R813),Shamuga Street (007021R828) in Ward No.21 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 800000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 | 25/06/22 |  | 2024-09-09 |  | 777000 |  |  |  | 23000 | 0.07 | 87.5 | 2022-03-02 |  | 41050000 | Yes | Yes
1144 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/007/ROAD/00054 | Zone II | 21 | State Disaster Response Fund State Disa/2021-22/007/ROAD/00054-Road Restoration of damaged portion over at Karumariamman Kovil 2nd Street (007021R815) in Ward No.21 | Roads | Bituminous Road | 31442/2021/e3Dated:15/12/20Road DetailsRoad Length :Mts | 2021-22 | 41050000 | 750000 |  |  |  | 0.08 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 | 26/05/22 |  | 2024-09-09 |  | 750000 |  |  |  | 0 | 0.07 | 90.13 | 2022-03-02 |  | 41050000 | Yes | Yes
1145 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2021-22/009/ROAD/00061 |  |  | Namakku Naame Thittam NNT/2021-22/009/ROAD/00061-Relaying of Road-009/05/070/R/5663-SADASIVA NAGAR 3RD MAIN ROAD , | Roads | Cement Concrete Road | 28244-44/2021Dated:08/11/22Road DetailsRoad Length :185 Mts | 2021-22 | 2000000 | 2000000 |  |  |  | 0.2 | 2023-10-01 | 0.2 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 2000000 |  |  |  | 0 | 0.2 | 100 | 2023-10-04 |  | 2000000 | Yes | Yes
1146 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/ROAD/00259 |  |  | Namakku Naame Thittam NNT/2022-23/009/ROAD/00259-Relaying of Road-Cement Concrete Road- Venkateswara Nagar main road (00955R4092) -160m | Roads | Cement Concrete Road | 23182/2023/P2-3Dated:09/10/23Road DetailsRoad Length :Mts | 2022-23 | 2640000 | 2100000 |  |  |  | 0.21 | 28/11/23 | 0.17 | Completed | 100 | Completed | 100 |  |  | 28/05/24 |  | 2099949 |  |  |  | 51 | 0.19 | 90.03 | 24/08/24 |  | 2640000 | No | Yes
1147 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00176 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00176-Relaying of Road-009032R2057-SCHOOL STREET , 009032R2070-KK PALAYAM GANGAIAMMAN KOIL STREET , 009033R2137-Siddhivinayak Temple Street , 009049R3537-JEEVA STREET , 009049R3543-SUBRAMANIYAN BHARATHI STREET , 009050R3609-KADHARBAI STREET , 009051R3619-MEENAMBAL STREET , 009051R3663-SUNDARAM COLONY 3RD CROSS ST , 009051R3661-SUNDARAM COLONY 1ST CROSS STREET , 009053R3764-DEVARAJ PILLAI STREET , 009054R3901-VETRI NAGAR MAIN ROAD , 009054R3902-VETRI NAGAR 1ST STREET , 009054R3903-VETRI NAGAR 2ND STREE | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :2494 Mts | 2023-24 | 319260000 | 13000000 |  |  |  | 1.3 | 2023-05-08 | 1.3 | Completed | 100 | Completed | 100 |  |  | 2025-05-02 |  | 11087643 |  |  |  | 1912357 | 1.16 | 89.07 | 2024-05-05 |  | 319260000 | No | Yes
1148 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00177 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00177-Relaying of Road-009049R3574-SHANMUGAM ROAD , 009049R3593-KATTABOMMAN STREET , 009049R3586-AYYASWAMY STREET , 009049R3542-BAGAVATH SINGH STREET , 009049R3544-SINGARAVELAN STREET , 009049R3539-ZAHIR HUSSAIN STREET , 009049R3553-GOVINDARAJAN ST , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1696 Mts | 2023-24 | 319260000 | 13900000 |  |  |  | 1.39 | 2023-05-08 | 1.29 | Completed | 100 | Completed | 100 | 2025-02-05 |  | 2025-06-05 |  | 9805599 |  |  |  | 4094401 | 0.89 | 63.71 | 2023-07-11 |  | 319260000 | No | Yes
1149 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00178 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00178-Relaying of Road-009050R3606-6TH CROSS STREET RANGANATHAPURAM , 009050R3611-KALYANA SUNDARAM STREET , 009060R4597-KALYAN NAGAR 1ST STREET , 009060R4598-Kalyan Nagar 1st Cross St , 009060R4603-2ND STREET KALYAN NAGAR , 009060R4599-2ND CR.ST -KALYAN NAGAR , 009060R4600-KALYAN NAGAR 3RD CROSS STREET , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1261 Mts | 2023-24 | 319260000 | 8100000 |  |  |  | 0.81 | 2023-05-08 | 0.81 | Completed | 100 | Completed | 100 |  |  | 23/05/24 |  | 7384751 |  |  |  | 715249 | 0.73 | 90 | 2023-07-11 |  | 319260000 | Yes | Yes
1150 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00179 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00179-Relaying of Road-009033S0368-Station Border Road (Station Road To Jaya Nagar 1st Main Rpad , 009032R2055-EAST STREET , 009060R4587-DHARMATHOTTAM , 009060R4595-BHARATHIYAR STREET , 009054R3960-2nd MAIN ROAD LAKSHMIPURAM EXTN , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :900 Mts | 2023-24 | 319260000 | 4100000 |  |  |  | 0.28 | 2023-01-09 | 0.41 | Completed | 100 | Completed | 100 |  |  | 23/05/24 |  | 3335335 |  |  |  | 764665.47 | 0.28 | 68.08 | 2023-03-12 |  | 319260000 | No | Yes
1151 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00180 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00180-Relaying of Road-009059R4441-MURUGAN STREET , 009056R4227-SHARMILA NAGAR MAIN ROAD , 009056R4123-SARANGAN AVENUE 1ST STREET , 009056R4226-SRI LINGAM NAGAR , 009059R4425-T.T.K. NAGAR 4TH STREET , 009058R4330-VARUN AVENUE 1ST STREET , 009056R4126-DINAGAR STREET , 009058S0503-LALBHAGATHUR SASTHRI STREET , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :1307 Mts | 2023-24 | 319260000 | 6100000 |  |  |  | 0.61 | 28/07/23 | 0.61 | Completed | 100 | Completed | 100 |  |  | 2024-06-06 |  | 5286503 |  |  |  | 813497 | 0.48 | 78.22 | 2023-07-11 |  | 319260000 | No | Yes
1152 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00346 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00346-Relaying of Road-Cement Concrete Road009010R0727-VIVEKA NANDHA STREET - VIJAYA NAGAR , 009010R0724-JANAKHI RAMAN STREET , 00901S0070-1ST STREET - INDRA NAGAR , 009010R0734-9TH STREET MUNGIL ERI , 009010R0737-2ND STREET - NEHRU NAGAR , 009010R0761-VALLI AMMAL STREET LORD SRINIVASAN COLONY , 009010R0763-SABAPATHY STREET , 009010L0037-THIRUVALLUR 3RD CROSS STREET , 009010R0719-N S K STREET ESHWARAN NAGAR , 009010R0748-12TH STREET MOONGIL ERI , 009010R0766-KUMARA SAMY STREET , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :836 Mts | 2025-26 | 237450000 | 4800000 |  |  |  | 0 | 2025-06-06 | 0.48 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4800000 | 0.43 | 90 | 2025-06-08 |  | 237450000 | No | Yes
1153 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00347 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00347-Relaying of Road-Cement Concrete Road009011R0823-BALAGURUSAMY CROSS STREET , 009011R0826-THIRUVALLUVAR STREET GANDHI NAGAR , 009011R0834-RAMADAS STREET GANDHI NAGAR , 009011R0778-RAJIVGANDHI STREET ESWARAN NAGAR , 009011L0041-METTU STREET ADAM NAGAR , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :900 Mts | 2025-26 | 237450000 | 4600000 |  |  |  | 0 | 2025-06-06 | 0.46 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4600000 | 0.41 | 90 | 2025-05-08 |  | 237450000 | No | Yes
1154 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00109 |  |  | TURIP TURIP/2025-26/009/ROAD/00109-Relaying of Road-Cement Concrete Road009054R3913-MOOGAMBIGAI NAGAR 2ND STREET , 009054R3914-MOOGAMBIGAI NAGAR 3RD STREET , 009054R3916-MOOGAMBIGAI NAGAR EXTN , 009054R3925-BHARATHIDASAN NAGAR, GANDHI STREET , 009054R3905-VETRI NAGAR 3RD STREET , 009055R4005-METRO CLSSIC CITY , 009055R4089-KANNAKI STREET , 009055R4004-RAGHAVENDRA AVENUE , 009055R3984-Medovilas - Plu Sagar , 009055R4014-MGR STREET , 009055R6091-M.G.R Street to Bethol 1st Cross Street Link Road , 55R3999-Seguwara Street , 00905 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2234 Mts | 2025-26 | 521620000 | 16700000 |  |  |  | 1.5 | 2025-10-06 | 1.38 | Completed | 95 | Completed | 100 |  |  | 2026-08-01 |  | 16700000 |  |  |  | 0 | 1.5 | 90 | 2025-09-08 |  | 521620000 | No | Yes
1155 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00102 |  |  | TURIP TURIP/2025-26/009/ROAD/00102-Relaying of Road-Cement Concrete Road009005R0338-MANIMEGALAI ST, THENDRAL NAGAR , 009005R0325-KAMARAJAPURAM NORTH RADHA VEETHI , 009005S0010-CHANDRAN STREET , 009005R0415-CHECKPOST STREET RAJIV GANDHI NAGAR , 009005R5772-THIRUNEERMALAI ROAD PATHIMA NAGAR , 009005R0330-KAMARAJAPURAM NESAMANY STREET , 009005R0331-KAMARAJAPURAM GANDHI STREET , 009005R0425-DASAN CROSS STREET , 009005R0345-Silapathikaram 2nd Street, 1st Cross Street , 009005R0339-KAMARAJAPURAM KUTTI NADAR ST , 009005S0009-V.O.C | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1138 Mts | 2025-26 | 521620000 | 7570000 |  |  |  | 0 | 2025-10-06 | 0.76 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 7568638 |  |  |  | 1362 | 0.68 | 89.95 | 2025-09-08 |  | 521620000 | No | Yes
1156 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00103 |  |  | TURIP TURIP/2025-26/009/ROAD/00103-Relaying of Road-Cement Concrete Road009006L0008-N.T. KRISHANA STREET PASUMPON NAGAR , 009006L0009-K.M. MANJON STREET PASUMPON NAGAR , 009006S0030-NAGALINGAM STREET , 009006L0011-DHANAPAL STREET PASUMPON NAGAR , 009006L003-VEDAKIRI 1ST STREET , 009006R0449-N.S.K STREET V.O.C NAGAR , 009006S0016-MARIYADASAN STREET , 009006R0441-SURIYAMMAN KOIL STREET V O C NAGAR , 009006R0482-MA PO. SI. STREET PAMMAL , 009006S0023-RAMAKRISHNA CROSS STREET , 009006L0005-IYAN THIRUVALLUVAR STREET , 00 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2172 Mts | 2025-26 | 521620000 | 10600000 |  |  |  | 0 | 2025-10-06 | 1.06 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 10290448 |  |  |  | 309552 | 0.93 | 87.62 | 2025-09-08 |  | 521620000 | No | Yes
1157 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00104 |  |  | TURIP TURIP/2025-26/009/ROAD/00104-Relaying of Road-Cement Concrete Road009008R0581-THIRUVALLUVAR STREET PAMMAL , 009008R0604-SIVASANKARAN STREET ERATTAIMALAI SINIVASAN COLONY , 009008S0058-BAJANAI KOIL STREET PAMMAL , 009008R0639-VAITHIYALINGAM STREET , 009008S0057-THIRU VI KA 4TH STREET LANE , 009008R0592-THRUVEDHIYAN STREET , 009008R0573-5TH CROSS STREET KRISHNA NAGAR , 009008R0600-ANANDHAN STREET THRIUVALLUER NAGAR PAMMAL , 009008S0056-THERUVETHYAMMAN KOIL STREET , 009008R0656-MARAIMALAI ADIKALAR STREET , 0 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :2242 Mts | 2025-26 | 521620000 | 12350000 |  |  |  | 0 | 2025-10-06 | 1.24 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12350000 | 0 | 0 | 2025-09-08 |  | 521620000 | No | Yes
1158 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00105 | Zone III |  | TURIP TURIP/2025-26/009/ROAD/00105-Relaying of Road-Cement Concrete Road009044R3253-MUGAMBIGAI STREET , 009044R3270-NELSON MANDELA STREET , 009044R3269-MURUGESAN STREET , 009044R3242-VALAL EBRAHIM STREET , 009044R3249-SANGAM STREET , 009044R3281-CHOKKANATHAR STREET , 009043R3150-ELIZABETH RANI STREET , 009043R3139-BOOMPUGAR STREET , 009043S0420-CHAKRAPANI STREET , 009043R3168-ADVOCATE JANAKIRAMAN STREET , 009042R2931-VENKATACHALAPATHY STREET , 009042R3033-SOUTH SANNATHI STREET , Zone III (Package No.14) | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1746 Mts | 2025-26 | 521620000 | 8830000 |  |  |  | 0 | 14/07/25 | 0.87 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 8830000 | 0.72 | 82.09 | 2025-07-09 |  | 521620000 | No | Yes
1159 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00106 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00106-Relaying of Road-Cement Concrete Road009058R4316-O.VI.AZHAGESHAN STREET , 009058R4319-SANJAI GANDHI STREET , 009058R4328-THIRUVALLUVAR 3 CROSS STREET , 009058R4320-VIVEKANANDAR STREET , 009051R3650-RAMESH NAGAR, 2ND ST , 009051R3653-PERIYAR ST , Zone IV-Package No.19 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :754 Mts | 2025-26 | 521620000 | 4500000 |  |  |  | 0 | 2025-10-06 | 0.44 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4500000 | 0.34 | 74.49 | 2025-09-08 |  | 521620000 | No | Yes
1160 | Tambaram | TURIP | CHENGALPATTU | TURIP/2025-26/009/ROAD/00107 | Zone IV |  | TURIP TURIP/2025-26/009/ROAD/00107-Relaying of Road-Cement Concrete Road009032R2083-PULIKORADU GANGAI AMMAN KOIL STREET , 009049R3575-SIVA SHANMUGAM ROAD , 009050R3599-2ND CROSS STREET RANGANATHAPURAM , 009050L0197-V.O.C. 5TH CROSS STREET , 009050R3612-VOC STREET , 009050R3606-6TH CROSS STREET RANGANATHAPURAM , ZONE IV-Package No..32 | Roads | Cement Concrete Road | 9730/2025/SS1Dated:02/04/25Road DetailsRoad Length :1255 Mts | 2025-26 | 521620000 | 7900000 |  |  |  | 0.71 | 2025-10-06 | 0.77 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 7573252 |  |  |  | 326748 | 0.64 | 81.01 | 2025-09-08 |  | 521620000 | No | Yes
1161 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00114 |  |  | TURIP TURIP/2023-24/009/ROAD/00114-Relaying of Road-009032R2039-BURMA COLONY 6TH CROSS STREET , 009032R2038-BURMA COLONY 5TH CROSS STREET , 009032R2042-BURMA COLONY 3RD STREET , 009032R2041-BURMA COLONY 2ND STREET , 009032R2034-BURMA COLONY 1ST CROSS STREET , 009032R2043-BURMA COLONY 4TH STREET , 009032R2037-BURMA COLONY 4TH CROSS STREET , 009032R2035-BURMA COLONY 2ND CROSS STREET , 009032R2036-BURMA COLONY 3RD CROSS STREET , 009032R2075-KK PALAYAM PILLAIYAR KOIL CROSS STREE , 009032R2053-AMMAN KOIL 3RD CROSS STREET , 009032R2 | Roads | Cement Concrete Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3473 Mts | 2023-24 | 313620000 | 8000000 |  |  |  | 0.64 | 19/07/23 | 0.8 | Completed | 100 | Completed | 100 | 2025-07-05 |  | 2025-07-05 |  | 7841992 |  |  |  | 158008 | 0.72 | 90.08 | - |  | 313620000 | No | Yes
1162 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/ROAD/00230 |  |  | Namakku Naame Thittam NNT/2022-23/009/ROAD/00230-Relaying of Road-Cement Concrete Road009017R5784-Dharga Road (Vel's School Road) , | Roads | Cement Concrete Road | 23182/2023/P2-2Dated:17/08/23Road DetailsRoad Length :220 Mts | 2022-23 | 10112000 | 4500000 |  |  |  | 0.45 | 25/10/23 | 0.36 | Completed | 100 | Completed | 100 | 2024-09-02 |  | 2024-09-02 |  | 4199780 |  |  |  | 300220 | 0.42 | 93.33 | 25/01/24 |  | 10112000 | Yes | Yes
1163 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00183 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00183-Relaying of Road-009001R0009-SAMUNDEESWARI NAGAR, VAIKAI STREET , 009001R0010-SATHIYA NAGAR, ANNA STREET , 009001R0032-KARUNANITHI NAGAR IST STREET , 009001R0040-V.G.A NAGAR , 009001R0042-ADANCHIYAMMAN KOIL STREET , 009001R0064-MANNAR SWAMY KOLI STREET , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :954 Mts | 2023-24 | 319260000 | 3000000 |  |  |  | 0.24 | 2023-03-08 | 0.3 | Completed | 100 | Completed | 100 | 14/08/23 |  | 13/03/24 |  | 2994031 |  |  |  | 5969 | 0.1 | 34.32 | 2023-01-11 |  | 319260000 | No | Yes
1164 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00110 |  |  | TURIP TURIP/2023-24/009/ROAD/00110-Relaying of Road-009004R0261-L.I.C.COLONY 2ND STREET , 009004R0264-ANNA DURAI STREET , 009004R0278-AYOTHIAMMAN KOIL ST 1ST CROSS ST , 009004R0279-AYOTHIAMMAN KOIL ST 2ND CROSS ST , 009004R0283-LIC COLONY 8TH CROSS STREET , 009004R0288-L.I.C.COLONY KOTHANDAPANI STREET , 009004R0292-THIRUNEERMALAI ROAD BURIAL GROUND , | Roads | Cement Concrete Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1685 Mts | 2023-24 | 313620000 | 6500000 |  |  |  | 0.71 | 19/07/23 | 0.65 | Completed | 100 | Completed | 100 |  |  | 20/05/24 |  | 0 |  |  |  | 6500000 | 0.58 | 89.96 | 17/10/23 |  | 313620000 | No | Yes
1165 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00111 |  |  | TURIP TURIP/2023-24/009/ROAD/00111-Relaying of Road-009004R0310-VINAYAGA NAGAR 7TH STREET , 009004R0311-VINAYAGA NAGAR 8TH STREET , 009004R0312-VINAYAGA NAGAR 9TH STREET , 009004R0313-VINAYAGA NAGAR 10TH STREET , 009004R0314-Vinayaga Nagar 13th Street , 009004R0318-AMARESAN NAGAR 2ND STREET , 009004R0319-AMARESAN NAGAR 3RD STREET , 009004R0320-E.B.COLONY 1ST STREET , 009004R0321-E.B.COLONY 2ND STREET , 009004R0322-VINAYAGA NAGAR 11TH STREET , | Roads | Cement Concrete Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :1560 Mts | 2023-24 | 313620000 | 6100000 |  |  |  | 0.61 | 19/07/23 | 0 | Completed | 100 | Completed | 100 |  |  | 27/02/25 |  | 3607918 |  |  |  | 2492082 | 0.32 | 53.23 | 14/04/24 |  | 313620000 | No | Yes
1166 | Tambaram | TURIP | CHENGALPATTU | TURIP/2023-24/009/ROAD/00112 |  |  | TURIP TURIP/2023-24/009/ROAD/00112-Relaying of Road-009046R3440-C.S.T. NAGAR , 009046R3462-ANNAI SIVAGAMI STREET , 009045R3405-ELUMALAI ST , 009047R3474-ANTHONY PILLAI STREET , 009047R3501-VALMIGI STREET (THIRUVALLUVAR STREET TO SEMBAKKAM) , 009048R3527-MOHAN STREET , 009063R4787-SENTHAMIZH SETHUPILLIAR STREET , 009063R4788-SENTHAMIZH SETHUPILLAI CROSS ST , 009063R4804-SMITHLANE STREET , 009063R4795-SHARMA STREET , 009064R4849-PROFESSOR COLONY EXTN ST , 009065R5008-K.V.K. NAGAR CROSS STREET , 009065R5036-MADHAKOIL 1ST CROSS STREE | Roads | Cement Concrete Road | 4548/2023/SS1Dated:31/05/23Road DetailsRoad Length :3327 Mts | 2023-24 | 313620000 | 15550000 |  |  |  | 1.4 | 18/07/23 | 0.36 | Completed | 100 | Completed | 100 | 2024-10-01 |  | 29/04/24 |  | 15542505 |  |  |  | 7495 | 1.4 | 89.97 | 23/10/23 |  | 313620000 | No | Yes
1167 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00350 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00350-Relaying of Road-Cement Concrete Road009010S0071-MEENAKSHI SUNDARAM STREET KALYANI PURAM , 009007R0628-2ND CROSS STREET ANNANAGAR , 009010R0767-KRISHNAN STREET KALYANI PURAM , 009012L0049-1ST CROSS STREET ESWARI NAGAR , 009012S0091-2ND STREET ESWARI NAGAR , 009010R0763-SABAPATHY STREET , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :816 Mts | 2025-26 | 237450000 | 4000000 |  |  |  | 0 | 2025-06-06 | 0.4 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4000000 | 0.36 | 90 | 2025-05-08 |  | 237450000 | No | Yes
1168 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00351 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00351-Relaying of Road-Cement Concrete Road009003R0241-PARI NAGAR LAKSHMI CROSS STREET , 009003R0252-THIRUMALAI NAGAR 2ND STREET , 009003R0232-PURATCHIMANI STREET , 009003R0233-K.K.SHA 1ST STREET , 009003R0239-Pari Nagar Ganapathy Street , 009003R0240-PARI NAGAR LAKSHMI STREET , 009003R0253-Thirumalai Nagar 3rd Street , 009003R5757-INDIRA NAGAR VIVEKANANDAR ST , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1275 Mts | 2025-26 | 237450000 | 9100000 |  |  |  | 0 | 2025-06-06 | 0.91 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 9100000 | 0.82 | 89.99 | 2025-06-08 |  | 237450000 | No | Yes
1169 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00352 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00352-Relaying of Road-Cement Concrete Road009004R0265-ANNA DURAI 1ST CROSS STREET , 009004R0269-ANNA DURAI 5TH CROSS STREET , 009004R0270-Annadurai VIth Cross Street , 009004R0292-THIRUNEERMALAI ROAD BURIAL GROUND , 009004S0006-LABOUR SCHOOL STREET 3RD CROSS ST , 009004R0258-ANNA NAGAR 1ST MAIN ROAD , 009004R0266-ANNA DURAI 2ND CROSS STREET , 009004R0278-AYOTHIAMMAN KOIL ST 1ST CROSS ST , 009004R0279-AYOTHIAMMAN KOIL ST 2ND CROSS ST , 009004R0308-SRI BALAJI NAGAR MAIN ROAD , 009004R0309-SRI BALAJI NA | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :3335 Mts | 2025-26 | 237450000 | 22500000 |  |  |  | 1.85 | 2025-06-06 | 2.25 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 22493310 |  |  | 0 | 6690 | 1.85 | 82.13 | 2025-05-08 |  | 237450000 | No | No
1170 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00353 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00353-Relaying of Road-Cement Concrete Road009001R0048-KASTHHURI BAI NAGAR 2ND STREET , 009001R0057-M.G.R.NAGAR 3RD STREET , 009001R0034-KARUNANITHI NAGAR 1ST LANE , 009001R0052-M.G.R. NAGAR, RAMALINGAM STREET , 009001S0002-NETHAJI NAGAR 2ND STREET , 009001R0053-M.G.R NAGAR RAMALINGAM CROSS ST , 009001R0059-M.G.R.NAGAR 2ND CROSS STREET , 009002R0166-THIRU NAGAR BHARAHIDASAN ST , 009002R0146-BALAJI NAGAR RAJIV GANDHI STREET , 009002R5738-VENKATESWARA NAGAR RAJARAJAN STREET , 009002R5750-A.N.pandiyan 1s | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2280 Mts | 2025-26 | 237450000 | 15900000 |  |  |  | 0 | 2025-06-06 | 1.59 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15900000 | 0 | 0 | 2025-05-08 |  | 237450000 | No | Yes
1171 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00354 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00354-Relaying of Road-Cement Concrete Road009023S0305-ODAI STREET , 009039R2458-Airport Colony M.N Grace , 009039R2459-AIRPORT COLONY , 009039R2460-Airport colonyy , 009039R2509-NAVANEETHAM NAGAR EXTN , 009039R2533-PRASANTH COLONY 3RD STREET , 009039R2451-Prasanth Colony Extend , 009039R2520-Karpagam avenue main road , 009039R2538-LAKSHMI NAGAR 1ST STREET , 009040R2578-R B AVENUE MAIN ROAD , 009040R2614-PUNITHAVATHY COLONY MAIN ROAD , 009040R2615-PUNITHAVATHY COLONY 1ST STREET , 009040R2616-PUNITHAVA | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :5308 Mts | 2025-26 | 237450000 | 24100000 |  |  |  | 0 | 14/07/25 | 1.99 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 24100000 | 0 | 0 | 21/10/25 |  | 237450000 | No | Yes
1172 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00331 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00331-Relaying of Road-Cement Concrete Road009045R3319-SRIRAM NAGAR 1ST STREET , 009045R3320-SRIRAM NAGAR 2ND STREET , 009045R3322-SRIRAM NAGAR 4TH STREET , 009045R3323-SRIRAM NAGAR 4TH CROSS STREET , 009045R3327-SRIRAM NAGAR 2ND CROSS STREET , 009045R3345-SANTHANA LAKSHMI ST , 009045R6045-Thiru.Vi.Ka Street 1st street , 009045R6048-Thiru.Vi.Ka Street Cross Street , 009045R3317-GANESH NAGAR ATHIYAMAN STREET , 009046R3416-ANTHONY STREET , 009046R3417-ANTHONI 1ST CROSS STREET , 009046R3418-ANTHONI 2ND C | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2549 Mts | 2025-26 | 237450000 | 12500000 |  |  |  | 0 | 2025-06-06 | 1.25 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12500000 | 1.47 | 117.48 | 2025-05-08 |  | 237450000 | No | Yes
1173 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00333 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00333-Relaying of Road-Cement Concrete Road009063L0225-VIJAYARANGAM STREET , 009063S0550-ASHOK NAGAR 2ND STREET , 009063S0551-ASHOK NAGAR CROSS STREET , 009063S0628-Naalvar Cross Street , 009064R4827-VOC STREET , 009064R4838-LEELA COLONY KAVERI STREET , 009064R4839-LEELA COLONY KAVERI CROSS STREET , 009064R4840-LEELA COLONY VAIGAI STREET , 009064R4861-ANNAI SIVAGAMI ST CROSS , 009064R6263-Senpaga Poo Street , 009065R4889-MULLAI STREET , 009065R4890-KANNADASAN ST , 009065R4903-MULLAI STREET , 009065R50 | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2749 Mts | 2025-26 | 237450000 | 13800000 |  |  |  | 0 | 2025-06-06 | 1.38 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13800000 | 1.13 | 82.17 | 2025-05-08 |  | 237450000 | No | Yes
1174 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00334 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00334-Relaying of Road-Cement Concrete Road009066R5096-SUNDARAM COLONY MAIN ROAD , 009066R5095-Selali nagar main road , 009066R6276-GANDHI NAGAR 2ND STREET , 009066R6277-GANDHI NAGAR 1ST STREET , 009067R5264-BHARATHIYAR STREET , 009067R5269-THIRUVALLUVAR CROSS STREET , 009067R6306-Gnanandha Nagar Main Road( 107-260M) , 009068R5287-KARPAGAM NAGAR 3RD STREET , 009068R5341-MOHAN NAGAR 1ST STREET , 009068R6327-KARPAGAM NAGAR 5TH STREET , 009069R5392-YESHWANTH NAGAR 3RD STREET , 009069R5394-YESHWANTH NAGAR | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2249 Mts | 2025-26 | 237450000 | 12600000 |  |  |  | 0 | 2025-06-06 | 1.26 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 12600000 | 1.13 | 90 | 2025-05-08 |  | 237450000 | No | Yes
1175 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00335 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00335-Relaying of Road-Cement Concrete Road009009R0697-ANJANEYAR KOIL B STREET , 009009L0028-Kannabiran Kovil 2nd Cross Street , 009009L0030-Kannabiran Kovil 4th Cross Street , 009009S0066-Hassan Basha 2nd Cross Street , 009009S0068-Kannabiran Koil 10th Cross Street , 009009L0029-Kannabiran Kovil 3rd Cross Street , 009009L0033-Kannabiran Koil 7th Cross Street , 009009L0035-KAMBAR STREET , 009009L0032-Kannabiran Koil 6th Cross Street , 009015R0964-VEMBULIAMMAN KOIL 6TH STREET , 009015S0101-VEMBULIAMMAN | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1927 Mts | 2025-26 | 237450000 | 7900000 |  |  |  | 0 | 2025-06-06 | 0.79 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 7900000 | 0 | 0 | 2025-05-08 |  | 237450000 | No | Yes
1176 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00336 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00336-Relaying of Road-Cement Concrete Road009017S0120-Kulakarai Street , 009017R1068-SANGAVI STREET- SUBAM NAGAR PART-1 , 009017R1049-KRISHNA NAGAR 1ST STREET , 009017R1055-Annai Anjugam 2nd Cross Street , 009017R1059-ANNAI ANJUGAM SALAI 3RD CROSS STREET , 009017R1067-UNITED SALAI , 009017R1045-KRISHNA NAGAR 2ND STREET , 009017R1057-ANNAI ANJUGAM STREET-SUBAM NAGAR PART-3 , 009017S0136-KRISHNA NAGAR 4TH STREET , 009017R1046-KRISHNA NAGAR 5TH STREET , 009017R1048-KRISHNA NAGAR 6TH STREET , 009017R10 | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2029 Mts | 2025-26 | 237450000 | 15200000 |  |  |  | 0 | 2025-06-06 | 1.52 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 15200000 | 0.58 | 37.91 | 2025-05-08 |  | 237450000 | No | Yes
1177 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00337 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00337-Relaying of Road-Cement Concrete Road009019L0250-Ganesh Nagar 2nd Main Road 2nd Lane , 009020R1241-BASKAR NAGAR 2ND CROSS STREET , 009020S0215-BASKAR NAGAR 2ND CROSS STREET , 009020R5807-KUMARAN COLONY 3RD CROSS STREET , 009020R5811-Rangasammy Street Extn. , 009020L0253-Duraikannu Salai 7th Cross Street , 009020S0609-RANGASAMY 2ND STREET , 009020R5831-VELUSAMY NAGAR 7TH ST , 009020S0610-Thiruvengadamudaiyan Kovil Street Extn. , 009020L0255-Saai 2nd Street , 009021R1428-SWAMI MALAI NAGAR , 009021 | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :2060.1 Mts | 2025-26 | 237450000 | 13500000 |  |  |  | 1.24 | 2025-06-06 | 1.35 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 13500000 | 1.24 | 91.51 | 2025-05-08 |  | 237450000 | No | Yes
1178 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00338 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00338-Relaying of Road-Cement Concrete Road009005R0329-KAMARAJAPURAM PERIYAR STREET , 009005L0001-DAASAN STREET , 009005R5770-GANAPATHY STREET LIC COLONY , 009005R0324-KAMARAJAPURAM THOMAIYAR ST , 009005R0323-THIRUVALLUVAR STREET KAMARAJA PURAM , 009005R0332-KAMARAJAPURAM GANDHI CROSS STREET , 009005R0430-5TH CROSS STREET LIC COLONY , 009005R0431-6TH CROSS STREET LIC COLONY , 009005S0008-VELLAISWAMY STREET , 009005R0422-CHANDRAN CROSS STREET , 009005R0416-MUTHARAMMAN KOIL STREET , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1578 Mts | 2025-26 | 237450000 | 9500000 |  |  |  | 0 | 2025-06-06 | 0.95 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 9439724 |  |  |  | 60276 | 0.85 | 89.68 | 2025-05-08 |  | 237450000 | No | Yes
1179 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00339 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00339-Relaying of Road-Cement Concrete Road009005R0423-V.O.C NAGAR PRAKALATHAN STREET , 009005S0011-DHASAN STREET PATHIMA NAGAR , 009005R5771-LIC Colony Srinivasan Cross street , 009005R0341-Silapathikaram 1st Street (Park Road) , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :548 Mts | 2025-26 | 237450000 | 4000000 |  |  |  | 0 | 2025-06-06 | 0.4 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4000000 | 0.36 | 90.04 | 2025-05-08 |  | 237450000 | No | Yes
1180 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00340 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00340-Relaying of Road-Cement Concrete Road009006R0440-THANDAI PERIYAR STREET V O C NAGAR , 009006R5775-N.S.K. Street (Way to Eri) , 009006R0472-PANDIYAN STREET , 009006S0019-RAJENDRAPRASATH STREET , 009006S0020-M G R NAGAR 5TH STREET , 009006R0479-NAGARADHANAM STREET , 009006R0492-KAMARAJA STREET , 009006R0461-SENDHALAMMAN CROSS STREET , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :766 Mts | 2025-26 | 237450000 | 4200000 |  |  |  | 0 | 2025-06-06 | 0.42 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4200000 | 0.27 | 64.26 | 2025-06-08 |  | 237450000 | No | Yes
1181 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00341 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00341-Relaying of Road-Cement Concrete Road009006S0035-PRABUDAS STREET PASUMPON NAGAR , 009006R0485-VEDAGIRI CROSS STREET , 009006R0456-DEVARAJAN STREET V O C NAGAR , 009006S0034-VADIVEL STRRET PASUMPON NAGAR , 009006R0504-MUTHU KARUPPAN STREET PASUMPON NAGAR , 009006R0432-3RD STREET LIC COLONY , 009006R0435-VOC NAGAR RADHAKRISHANAN STREET , 009006L0013-LAST CROSS STREET PASUMPON NAGAR , 009006S0017-6TH STREET M.G.R NAGAR , 009006S0031-DEVARAJ STREET PASUMPON NAGAR , 009006L0012-CHAKKARA | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1464 Mts | 2025-26 | 237450000 | 7150000 |  |  |  | 0 | 2025-06-06 | 0.72 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 7143221 |  |  |  | 6779 | 0.64 | 90.16 | 2030-06-06 |  | 237450000 | No | Yes
1182 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00342 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00342-Relaying of Road-Cement Concrete Road009007R0512-KAKKAN 2ND CROSS STREET H.L. COLONY , 009006S0039-BURIAL ROAD , 009007R0550-ANBALAGAN STREET , 009007S0047-MARUTHI CROSS STREET , 009007R0562-GANDHI ROAD ANNA NAGAR , 009007S0043-MARUTHU PANDIYAN STREET E LE COLONY , 009007R0624-ST THOMAS STREET , 009007R0514-6TH MAIN ROAD 2ND LANE , 009007R0619-RAJAGOPALAN STREET MUTHAMIZH NAGAR , 009007S0040-VEERARAGAVAN STREET H.L. COLONY , 009007S0046-SAMI KANNU STREET , 009007S0048-ELANGO CROSS | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1402 Mts | 2025-26 | 237450000 | 9100000 |  |  |  | 0 | 2025-06-06 | 0.91 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 9097893 |  |  |  | 2107 | 0.82 | 90.23 | 2025-06-08 |  | 237450000 | No | Yes
1183 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00343 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00343-Relaying of Road-Cement Concrete Road009007S0044-6TH MAIN ROAD ANNA NAGAR , 009007S0042-RAJA STREET H.L COLONY , 009007S0041-PRABAKAERAN STREET H L COLONY , 009007R0548-MARUTHI STREET , | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :536 Mts | 2025-26 | 237450000 | 2700000 |  |  |  | 0 | 2025-06-06 | 0.27 | Completed | 100 | Completed | 100 |  |  | 2025-07-10 |  | 2697156 |  |  |  | 2844 | 0.24 | 90.01 | 2025-05-08 |  | 237450000 | No | Yes
1184 | Tambaram | SPECIAL FUND FOR IMPROVEMENT OF ROADS | CHENGALPATTU | SF-ROAD/2025-26/009/ROAD/00344 |  |  | SPECIAL FUND FOR IMPROVEMENT OF ROADS SF-ROAD/2025-26/009/ROAD/00344-Relaying of Road-Cement Concrete Road009008L0016-THIRUVALLUVAR STREET 3RD STREET , 009008L0019-THIRUVALLUVAR NAGAR JAMES STREET , 009008S0052-AMBETHKAR STREET , 009008R0593-RANGASAMY STREET THIRUVALLUVAR NAGAR , 009008R0599-MUNUAADHI STREET , 009008LOO23-THIRU VI KA 2ND STREET , 009008L0024-MUNUATHI CROSS STREET , 009008S0060-MANIMEGALAI STREET THIRUVALLUVAR NAGAR , 009008r0586-ANANDHAN 1ST CROSS STREET , 009008S0053-THIRU VI KA 5TH STREET LANE , 009008R0649-TEACHER KRISHNASMAY STREET | Roads | Cement Concrete Road | 18th Meeting CPS, dt02.04.2025Dated:02/04/25Road DetailsRoad Length :1357 Mts | 2025-26 | 237450000 | 7200000 |  |  |  | 0 | 2025-06-06 | 0.72 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 7200000 |  |  |  | 0 | 0.65 | 90.24 | 2025-06-08 |  | 237450000 | No | Yes
1185 | Tambaram | TURIP | CHENGALPATTU | TURIP/2024-25/009/ROAD/00170 |  |  | TURIP TURIP/2024-25/009/ROAD/00170-Relaying of Road-Cement Concrete Road009002R0156-GANDHI STREET , 009002R0119-Raghavendra Koil 1st Cross Street , 009002R0138-BALAJI NAGAR EXTN., , 009002R0127-BALAJIJ NAGAR 4TH STREET , 009002R0128-BALAJI NAGAR 5TH STREET , 009002R0117-VENKATESWARA NAGAR EXTENSION , 009002R0116-G.K.NAGAR 4TH STREET , 009002R0186-KENNADI NAGAR 1ST STREET , 009002R0131-BALAJI NAGAR 8TH STREET , 009002R0113-G.K. NAGAR 1ST STREET , 009002R0176-Balaji Nagar A.N.Pandian 2nd Cross Street , 009002R0158-RAGAVENDRA KOIL S | Roads | Cement Concrete Road | 2459/2024/SS1-2Dated:22/07/24Road DetailsRoad Length :3825 Mts | 2024-25 | 197393000 | 18500000 |  |  |  | 0 | 26/09/24 | 0 | Completed | 100 | Completed | 100 |  |  | 20/01/26 |  | 18375789 |  |  | 0 | 124211 | 1.66 | 89.89 | - |  | 197393000 | No | Yes
1186 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00185 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00185-Relaying of Road-009001R0043-MUTHURULANDI NAGAR 1ST STREET , 009001R0044-MUTHURULANDI NAGAR IIND STREET , 009001R0045-MUTHURULANDI NAGAR IIIRD STREET , 009002R0081-VENKATESWARA NAGAR OVAI STREET , 009002R0082-VENKATESWARA NAGAR KAMARAJAR STREET , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :382 Mts | 2023-24 | 319260000 | 1280000 |  |  |  | 0.13 | 2023-03-08 | 0.13 | Completed | 100 | Work Completed | 100 |  |  | 28/11/22 |  | 1237764 |  |  |  | 42236 | 0.12 | 96.7 | - |  | 319260000 | Yes | Yes
1187 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00186 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00186-Relaying of Road-009002R5745-BALAJI NAGAR 17TH CROSS ST , 009002R0129-BALAJI NAGAR 6TH STREET , 009002R0175-Periyar street , 009002R0191-THIRUNAGAR KAKKAN STREET , 009002R5746-Balaji nagar kumaran street , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :692 Mts | 2023-24 | 319260000 | 2650000 |  |  |  | 0.27 | 2023-03-08 | 0.27 | Completed | 100 | Work Completed | 100 |  |  | 28/11/22 |  | 2650000 |  |  |  | 0 | 0.26 | 99.98 | 2023-01-11 |  | 319260000 | Yes | Yes
1188 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00187 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00187-Relaying of Road-009030R1913-VENGATESAN STREET, LAKSHMIPURAM, CHENNAI-44 , 009030R1891-3RD PILLAIYAR KOIL STREET, LAKSHMIPURAM, CHENNAI-44 , 009031R1970-NSK SALAI, RANGA NAGAR, THIRUNEERMALAI, CHENNAI-600 044. , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :501 Mts | 2023-24 | 319260000 | 1800000 |  |  |  | 0.15 | 28/07/23 | 0.18 | Completed | 100 | Work Completed | 100 |  |  | 14/09/24 |  | 1519014 |  |  |  | 280986 | 0.15 | 84.39 | 26/10/23 |  | 319260000 | No | Yes
1189 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00181 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00181-Relaying of Road-009005R0345-Silapathikaram 2nd Street, 1st Cross Street , 009005R0341-Silapathikaram 1st Street (Park Road) , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :325 Mts | 2023-24 | 319260000 | 1470000 |  |  |  | 0.13 | 27/09/23 | 0.15 | Completed | 100 | Work Completed | 100 |  |  | 15/03/24 |  | 1449232 |  |  |  | 20768 | 0.13 | 88.98 | - |  | 319260000 | No | Yes
1190 | Tambaram | Nagarpura Salai Mempattu Thittam | CHENGALPATTU | NSMT/2023-24/009/ROAD/00182 |  |  | Nagarpura Salai Mempattu Thittam NSMT/2023-24/009/ROAD/00182-Relaying of Road-009010R0707-1ST STREET AYYAPPA NAGAR , 009010R0714-2ND STREET AYYAPPA NAGAR , 009010R0713-3RD STREET IYYAPPA NAGAR , | Roads | Cement Concrete Road | G.O. (D) No. 350Dated:22/06/23Road DetailsRoad Length :373 Mts | 2023-24 | 319260000 | 1250000 |  |  |  | 0.11 | 27/09/23 | 0.13 | Completed | 100 | Work Completed | 100 |  |  | 15/03/24 |  | 1247973 |  |  |  | 2027 | 0.11 | 90.1 | - |  | 319260000 | No | Yes
1191 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00103 | Zone III | 37 | General Fund GENERAL/2025-26/009/ROAD/00103-Providing and Laying Paver Block Road to Thirukkural street (Part) & Tholkappiyar Street in Ward NO.37 in Zone III | Roads | Paver Block Road | 471-2Dated:24/06/25Road DetailsRoad Length :Mts | 2025-26 | 1500000 | 1500000 |  |  |  | 0 | 18/07/25 | 0.14 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | 23/10/25 |  | 1500000 | No | Yes
1192 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00006 | Zone I | 29 | MLA Fund MLA/2023-24/009/WS/00006-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at Jaya Sri Muthukumarasamy Higher secondary school in ward No.29, Zone I | Water Supply | Borewell | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 26/02/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2024-06-08 |  | 930000 |  |  |  | 40000 | 0.09 | 95.89 | - |  | 5820000 | Yes | Yes
1193 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/WS/00007 | Zone III | 22 | MLA Fund MLA/2023-24/009/WS/00007-Providing borewell with 2000 LPH (RO Plant) Reverse Osmosis Plant at ward No.22, zone III | Water Supply | Borewell | 3042/2023/A3-5Dated:30/12/23 | 2023-24 | 5820000 | 970000 |  |  |  | 0 | 20/02/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 30/04/25 |  | 0 |  |  |  | 970000 | 0 | 0 | 16/11/24 |  | 5820000 | Yes | Yes
1194 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00272 | Zone I | 2 | MLA Fund MLA Fund/2021-22/009/WS/00272-Providing Deep Borewell with Mini Power Pump OHT at Ward No.2 in Anakaputhur | Water Supply | Borewell | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 280000 | 0 |  |  | 0.03 | 2022-08-06 | 0.02 | Completed | 100 | Completed | 100 | 28/12/22 |  | 26/10/22 |  | 278233 |  |  |  | 1767 | 0 | 0 | 2022-08-07 |  | 4710000 | No | Yes
1195 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00423 | Zone II | 13 | MLA Fund MLA Fund/2021-22/009/WS/00423-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.13 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 845000 |  |  |  | 0.07 | 25/05/22 | 0.07 | Completed | 100 | Completed | 100 |  |  | 29/12/22 |  | 0 |  |  |  | 845000 | 0.07 | 86.27 | 25/07/22 |  | 14858000 | Yes | Yes
1196 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00415 | Zone II | 19 | MLA Fund MLA Fund/2021-22/009/WS/00415-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.19 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 282000 |  |  |  | 0.03 | 25/05/22 | 0.02 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 282000 |  |  |  | 0 | 0.03 | 90.25 | 26/07/22 |  | 14858000 | Yes | Yes
1197 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00416 | Zone II | 14 | MLA Fund MLA Fund/2021-22/009/WS/00416-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.14 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 282000 |  |  |  | 0.02 | 25/05/22 | 0.02 | Completed | 100 | Completed | 100 | 13/09/22 |  | 2024-09-09 |  | 282000 |  |  |  | 0 | 0.02 | 88.48 | 26/06/22 |  | 14858000 | Yes | Yes
1198 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00418 | Zone II | 17 | MLA Fund MLA Fund/2021-22/009/WS/00418-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.17 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 282000 |  |  |  | 0.03 | 25/05/22 | 0.02 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 282000 |  |  |  | 0 | 0.03 | 89.36 | 25/06/22 |  | 14858000 | Yes | Yes
1199 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00419 | Zone II | 20 | MLA Fund MLA Fund/2021-22/009/WS/00419-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.20 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0.1 | 25/05/22 | 0.09 | Completed | 100 | Completed | 100 | 29/11/22 |  | 2024-09-09 |  | 929700 |  |  |  | 40300 | 0.08 | 84.23 | 25/07/22 |  | 14858000 | Yes | Yes
1200 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00420 | Zone II | 20 | MLA Fund MLA Fund/2021-22/009/WS/00420-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.20 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 547000 |  |  |  | 0.05 | 25/05/22 | 0.05 | Completed | 100 | Completed | 100 | 19/09/22 |  | 2024-09-09 |  | 543500 |  |  |  | 3500 | 0.05 | 89.67 | 25/07/22 |  | 14858000 | Yes | Yes
1201 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00421 | Zone II | 17 | MLA Fund MLA Fund/2021-22/009/WS/00421-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.17 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 1920000 |  |  |  | 0.19 | 25/05/22 | 0.17 | Completed | 100 | Completed | 100 | 29/09/22 |  | 2024-09-09 |  | 1820000 |  |  |  | 100000 | 0.16 | 84.64 | 25/07/22 |  | 14858000 | Yes | Yes
1202 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00312 | Zone IV | 33 | MLA Fund MLA Fund/2021-22/009/WS/00312-Providing Borewell at Amar Nagar in ward No.33 | Water Supply | Borewell | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 270000 |  |  |  | 0.03 | 2022-08-06 | 0.03 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 256365 |  |  |  | 13635 | 0.03 | 94.95 | 2022-09-09 |  | 5038000 | Yes | Yes
1203 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00442 | Zone II | 17 | MLA Fund MLA Fund/2021-22/009/WS/00442-Providing Deep Bore Well and Construction of Mini Over Head Tank at Ward No.17 | Water Supply | Borewell | 4593/2021/E1Dated:30/07/22 | 2021-22 | 282000 | 282000 |  |  |  | 0.03 | 2022-02-09 | 0.03 | Completed | 100 | Completed | 100 | 28/09/22 |  | 2024-09-09 |  | 282000 |  |  |  | 0 | 0.03 | 90.07 | 2022-02-12 |  | 282000 | Yes | Yes
1204 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/WS/00214 | Zone V | 47 | General Fund GENERAL/2024-25/009/WS/00214-Providing deep bore well with mini power pump at Andal street park ward 47 in Tambaram City Municipal Corporation | Water Supply | Borewell | 390Dated:06/01/25 | 2024-25 | 200000 | 200000 |  |  |  | 0 | 21/04/25 | 0.02 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 200000 | 0 | 0 | 28/06/25 |  | 200000 | No | No
1205 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00011 | Zone V | 63 | MLA Fund MLA Fund/2022-23/009/WS/00011-Providing Borewell and RO facilities to Nagathamman kovil street in ward No.63 in Tambaram Corporation | Water Supply | Borewell | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 1070000 |  | 0 | 0 | 0 | 2023-06-03 | 0.09 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 0 |  |  |  | 1070000 | 0 | 0 | 2023-09-05 |  | 7500000 | Yes | Yes
1206 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00012 | Zone IV | 51 | MLA Fund MLA Fund/2022-23/009/WS/00012-Providing Borewell with Minipower pump and styntex tank at Periyar street in ward No.51 in Tambaram Corporation | Water Supply | Borewell | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 350000 |  |  |  | 0.04 | 17/04/23 | 0.03 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 4 |  |  |  | 349996.5 | 0.02 | 71.28 | - |  | 7500000 | Yes | Yes
1207 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00013 | Zone IV | 51 | MLA Fund MLA Fund/2022-23/009/WS/00013-Providing Borewell with minipower pump and sintex tank at Rajagopal Nagar in ward No.51 in Tambaram Corporation | Water Supply | Borewell | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 350000 | 0 |  |  | 0.04 | 17/04/23 | 0.03 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 249470 |  |  |  | 100530 | 0.02 | 67.67 | - |  | 7500000 | Yes | Yes
1208 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/WS/00002 | Zone I | 2 | MLA Fund MLA Fund/2022-23/009/WS/00002-Providing 2000 LPH Reverse Osmosis Plant with Deep Borewell at (Ward No. 2) Near Pillayair Koil in TCMC | Water Supply | Borewell | 3607/2022/A3Dated:30/11/22 | 2022-23 | 6285000 | 970000 |  | 0 |  | 0 | 2023-11-01 | 0.07 | Completed | 100 | Work Fully Completed | 100 | 23/07/23 |  | 19/07/23 |  | 951755 |  |  |  | 18245 | 0 | 0 | 26/01/23 |  | 6285000 | No | Yes
1209 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00270 | Zone I | 1 | MLA Fund MLA Fund/2021-22/009/WS/00270-Providing Deep Borewell with Mini Power Pump OHT at Ward No.1 in Anakaputhur | Water Supply | Borewell | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 280000 |  |  | 0 | 0.03 | 2022-08-06 | 0.02 | Completed | 100 | Work Fully Completed | 100 |  |  | 2023-01-03 |  | 280000 |  |  |  | 0 | 0.03 | 100 | 2022-08-07 |  | 4710000 | Yes | Yes
1210 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00429 | Zone II | 21 | MLA Fund MLA Fund/2021-22/009/WS/00429-Providing Deep Borewell and Construction of Mini Over Head Tank at Ward No.21 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 845000 |  |  |  | 0.08 | 25/05/22 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 845000 |  |  |  | 0 | 0.08 | 90.3 | 25/07/22 |  | 14858000 | Yes | Yes
1211 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00430 | Zone II | 17 | MLA Fund MLA Fund/2021-22/009/WS/00430-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.17 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0.1 | 25/05/22 | 0.09 | Completed | 100 | Completed | 100 | 29/11/22 |  | 2024-09-09 |  | 0 |  |  |  | 970000 | 0.08 | 84.54 | 25/07/22 |  | 14858000 | Yes | Yes
1212 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00431 | Zone II | 18 | MLA Fund MLA Fund/2021-22/009/WS/00431-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.18 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0.08 | 25/05/22 | 0.09 | Completed | 100 | Completed | 100 |  |  | 20/12/22 |  | 0 |  |  |  | 970000 | 0.08 | 86.08 | 25/07/22 |  | 14858000 | Yes | Yes
1213 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00425 | Zone II | 14 | MLA Fund MLA Fund/2021-22/009/WS/00425-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.14 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0.1 | 25/05/22 | 0.09 | Completed | 100 | Completed | 100 | 29/11/22 |  | 2024-09-09 |  | 917500 |  |  |  | 52500 | 0.09 | 94.59 | 25/06/22 |  | 14858000 | Yes | Yes
1214 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/WS/00426 | Zone II | 15 | MLA Fund MLA Fund/2021-22/009/WS/00426-Supply and Erection of 2000 LPH Reverse Osmosis Water Treatment Plant with Deep Borewell in Ward No.15 | Water Supply | Borewell | ROC No.4593/21/A3Dated:18/04/22 | 2021-22 | 14858000 | 970000 |  |  |  | 0.11 | 25/05/22 | 0.08 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 900000 |  |  |  | 70000 | 0.08 | 82.47 | 25/07/22 |  | 14858000 | Yes | Yes
1215 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00239 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00239-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 990000 |  |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 988000 |  |  |  | 2000 | 0.1 | 99.82 | 2022-05-04 |  | 39126000 | Yes | Yes
1216 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00240 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00240-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 950000 | 0 |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 944000 |  |  |  | 6000 | 0.09 | 99.35 | 2022-05-04 |  | 39126000 | Yes | Yes
1217 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00241 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00241-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 900000 |  |  |  | 0.09 | 2022-03-01 | 0.09 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 897000 |  |  |  | 3000 | 0.09 | 99.62 | 2022-05-04 |  | 39126000 | Yes | Yes
1218 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00243 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00243-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 740000 |  |  |  | 0.07 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 740000 |  |  |  | 0 | 0.07 | 99.96 | 2022-05-04 |  | 39126000 | Yes | Yes
1219 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00244 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00244-Rejunavation and desilting 3nos of Deepborewell at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 1000000 |  |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 990000 |  |  |  | 10000 | 0 | 0 | 2022-05-04 |  | 39126000 | Yes | Yes
1220 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00039 | Zone II |  | 15th CFC 15thCFC/2022-23/009/WS/00039-Providing and laying 1.610 km 200mm dia DI K7 pumping Main line at Thirusulam ground level service reservoir to Bharathi nagar ground level service reservoir. zone II in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 5000000 |  |  |  | 0.5 | 25/04/23 | 0.5 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 4908348 |  |  |  | 91652 | 0.49 | 98.14 | 25/10/23 |  | 28650000 | Yes | Yes
1221 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00246 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00246-Rejunavation and desilting 3nos of Deepborewell at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 1000000 | 0 |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 990000 |  |  |  | 10000 | 0.1 | 99.95 | 2022-05-04 |  | 39126000 | No | Yes
1222 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00247 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00247-Repairing and maintenance of 15HP,25HP & 35HP at Palar river Head works in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 610000 |  |  |  | 0.06 | 2022-03-01 | 0.06 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 606000 |  |  |  | 4000 | 0.06 | 99.38 | 2022-05-04 |  | 39126000 | Yes | Yes
1223 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00049 |  |  | 15th CFC 15thCFC/2022-23/009/WS/00049-Providing and Laying of Pipeline 1444m ( 250mm dia DI K9-100m, 200mm DI K9 pipeline) arrangements from Pammal to Thiruneermalai Lakshmipuram and Construction of 3 LL capacity Ground level Reservoir at Thiruneermalai | Water Supply | Water Supply Improvement Works | 18698/2022/CFC--1Dated:25/01/23 | 2022-23 | 20000000 | 20000000 |  |  |  | 0 | 2023-05-05 | 1.61 | Completed | 100 | Completed | 100 |  |  | 2025-03-06 |  | 19965572 |  |  |  | 34428 | 1.75 | 87.64 | 30/01/24 |  | 20000000 | No | Yes
1224 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00236 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00236-Supply Delivery and fixing of 50 sq mm cable at Villiyambakkam , malacherry Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 980000 | 0 |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 976000 |  |  |  | 4000 | 0.1 | 99.62 | 28/05/22 |  | 39126000 | Yes | Yes
1225 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00237 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00237-Supply Delivery and fixing of 50 sq mm cable at Villiyambakkam , malacherry Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 760000 | 0 |  |  | 0.07 | 2022-03-01 | 0.07 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 757000 |  |  |  | 3000 | 0.08 | 99.55 | 28/05/22 |  | 39126000 | Yes | Yes
1226 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00264 |  |  | 15th CFC 15th CFC/2020-21/009/WS/00264-Supply and delivery of 120HP Turbine Pump & Motor and Base Frame and laying of LTUG cable at Melachery Head Works Unit No.i in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 7979/2020/E-TBMDated:30/06/22 | 2020-21 | 17500000 | 3800000 |  |  |  | 0.38 | 17/01/22 | 0.38 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 3398000 |  |  |  | 402000 | 0.31 | 81.32 | 17/03/22 |  | 17500000 | No | Yes
1227 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00265 |  |  | 15th CFC 15th CFC/2020-21/009/WS/00265-Supply, delivery and fixing of 150HP Turbine Pump, Motor & Starter 25 HP Submersible pump motor & Starter, and 7.5HP Submersible pump motor & Starter, CI Pipe, Specials, 240 Sqmm UG cable laying and labour at Melachery Head Works Unit I & Melachery Down & Old scheme in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 7979/2020/E-TBMDated:30/06/22 | 2020-21 | 17500000 | 5000000 | 0 |  |  | 0.5 | 2022-03-01 | 0.54 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 4910000 |  |  |  | 90000 | 0.45 | 89.4 | 2022-03-03 |  | 17500000 | No | Yes
1228 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00266 |  |  | 15th CFC 15th CFC/2020-21/009/WS/00266-Providing connecting Main DI pipe line to Infiltration well Bore well with Anchoring arrangements to Melachery Head works in in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 7979/2020/E-TBMDated:30/06/22 | 2020-21 | 17500000 | 5000000 | 0 |  |  | 0.51 | 2022-03-01 | 0.51 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 5134000 |  |  |  | -134000 | 0.47 | 94.39 | 2022-03-03 |  | 17500000 | Yes | Yes
1229 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00267 |  |  | 15th CFC 15th CFC/2020-21/009/WS/00267-Construction of Infiltration well Pumps and 7.50 HP Submersible Motor connection Pipe line works and LTUG Cable connection ,removal and replacement of 3 HP submersible pump sets on Bore wells at Melachery Head works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 7979/2020/E-TBMDated:30/06/22 | 2020-21 | 17500000 | 3700000 | 0 |  |  | 0.37 | 2022-03-01 | 0.37 | Completed | 100 | Completed | 100 |  |  | 2022-10-10 |  | 3703475 |  |  |  | -3475 | 0.34 | 91.02 | 2022-03-03 |  | 17500000 | Yes | Yes
1230 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2021-22/009/WS/00018 | Zone IV | 49 | MP Fund MP Fund/2021-22/009/WS/00018-Providing 1000 Ltr Capacity RO Plant with Water Supply and Infrastructure facilities at Bagath Singh Street Ward 49 Zone 4 in Tambaram City Municipal Corportion | Water Supply | Water Supply Improvement Works | 2829/2022/A3-4Dated:30/07/22 | 2021-22 | 950000 | 950000 |  |  |  | 0.1 | 16/11/22 | 0.08 | Completed | 100 | Completed | 100 |  |  | 2024-04-05 |  | 950000 |  |  |  | 0 | 0.1 | 100 | 16/12/22 |  | 950000 | Yes | Yes
1231 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/WS/00037 | Zone IV | 32 | 15th CFC 15thCFC/2022-23/009/WS/00037-Construction of 60,000 litres capacity ground level reservoir (Sump) with Motor Pumpset arrangements at Kadaperi Bajanai Koil street west tambaram, ward no. 32 zone IV in Tambaram City Municipal Corporation | Water Supply | Water Supply Improvement Works | 18698/2022/CFC-1Dated:25/01/23 | 2022-23 | 28650000 | 3350000 |  |  |  | 0.34 | 2023-05-05 | 0.33 | Completed | 100 | Completed | 100 | 2025-03-03 |  | 2025-03-03 |  | 3320000 |  |  |  | 30000 | 0.06 | 18.89 | 2023-05-11 |  | 28650000 | No | Yes
1232 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00284 | Zone II | 13 | 15th CFC 15th CFC/2020-21/009/WS/00284-Ward No.13 Providing deep borewell with power pump at Veeramamunivar street, Ranga Colony Main road and State Bank Colony | Water Supply | Water Supply Improvement Works | 7979/2020/LA3 SEM -4Dated:30/06/21 | 2020-21 | 1000000 | 1000000 | 0 |  |  | 0.1 | 2021-12-08 | 0.1 | Completed | 100 | Completed | 100 |  |  | 30/10/21 |  | 979523 |  |  |  | 20477 | Excel0.10 | 97.95 | 2021-10-11 |  | 1000000 | No | Yes
1233 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00285 | Zone I | 1 | 15th CFC 15th CFC/2020-21/009/WS/00285-Laying of pvc pipe main and distribution line at Thirumalai Nagar 1st, 2nd main road, Thirumalai Nagar 1st, 2nd, 3rd, 3rd cross, 4th, 5th, 6th and 7th street in ward no.1 | Water Supply | Water Supply Improvement Works | 7979/2020/LA3 SEM -5Dated:30/06/21 | 2020-21 | 1000000 | 1000000 |  |  |  | 0.1 | 2021-12-08 | 0.1 | Completed | 100 | Completed | 100 |  |  | 2021-01-11 |  | 997074 |  |  |  | 2926 | Excel0.10 | 99.71 | 2021-10-11 |  | 1000000 | No | Yes
1234 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/WS/00286 | Zone I | 1 | 15th CFC 15th CFC/2020-21/009/WS/00286-Laying of pvc pipe main and distribution line at Thirumalai Nagar 3rd main road, Thirumalai Nagar 8th, 9th, 10th, 10th cross, 11th, 12th, 13th, 13th extn, 14th, 15th, 16th street, Vijayakumar Avenue and Airport Colony in ward no.1 | Water Supply | Water Supply Improvement Works | 7979/2020/LAM SEM -6Dated:30/06/21 | 2020-21 | 1000000 | 1000000 | 0 |  |  | 0.1 | 2021-12-08 | 0.1 | Completed | 100 | Completed | 100 |  |  | 2021-08-11 |  | 999317 |  |  |  | 683 | Excel0.10 | 99.93 | 2021-10-11 |  | 1000000 | No | Yes
1235 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00238 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00238-Supply Delivery and fixing of 100 D.I at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 970000 |  |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 966000 |  |  |  | 4000 | 0.1 | 99.6 | 28/05/22 |  | 39126000 | Yes | Yes
1236 | Tambaram | State Disaster Response Fund | CHENGALPATTU | State Disa/2021-22/009/WS/00245 |  |  | State Disaster Response Fund State Disa/2021-22/009/WS/00245-Rejunavation and desilting 4nos of Deepborewell at Villiyambakkam, Malachery Pump house to Palar river hear works in Tambaram Municipality | Water Supply | Water Supply Improvement Works | 31442/2021/E3-TambaramDated:15/12/21 | 2021-22 | 39126000 | 1000000 |  |  |  | 0.1 | 2022-03-01 | 0.1 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 989000 |  |  |  | 11000 | 0.1 | 99.7 | 2022-05-04 |  | 39126000 | No | Yes
1237 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/UGSS/00136 |  |  | CGF CGF/2021-22/009/UGSS/00136- Providing and Installation of Online Continuous Effluent Monitoring System (OCEMS) in Sewage Treatment Plant at Tambaram Corporation | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 1011Dated:10/11/21 | 2021-22 | 4264000 | 4264000 |  |  | 0 | 0.42 | 26/07/22 | 0.38 | Completed | 100 | Completed | 100 |  |  | 15/07/24 |  | 3793664 |  |  |  | 470336 | 0.38 | 88.97 | 25/10/22 |  | 4264000 | No | Yes
1238 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/UGSS/00108 | Zone V |  | Namakku Naame Thittam NNT/2022-23/009/UGSS/00108-Providing UGD pipeline in Sumuru City area at Zone No.V | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 3400000 |  |  |  | 0.06 | 31/05/23 | 0.28 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 3393000 |  |  |  | 7000 | 0 | 0 | 31/08/23 |  | 15130000 | No | Yes
1239 | Tambaram | 15th CFC Tied Grant | CHENGALPATTU | 15thCFC/2024-25/009/UGSS/00043 | Zone III | 22 | 15th CFC Tied Grant 15thCFC/2024-25/009/UGSS/00043-Construction of Lifting stations at Om sakthi Nagar in ward No.22 zone III | Under Ground Sewerage Scheme | Under Ground Sewerage Scheme | 28485/2024/EA-2Dated:15/10/24 | 2024-25 | 48950000 | 3800000 |  |  |  | 0 | 2024-12-12 | 0.38 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3800000 | 0 | 0 | 2025-08-09 |  | 48950000 | No | Yes
1240 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2024-25/009/CULVERT/00014 | Zone II | 26 | General Fund GENERAL/2024-25/009/CULVERT/00014-Construction of RCC Bridge at Naidu shop road near GGN school in Ward NO 26 Zone-2 | Culverts | Culverts | 528-4 / 30-12-2024Dated:30/12/24 | 2024-25 | 4000000 | 4000000 |  |  |  | 0 | 19/03/25 | 0.4 | Shuttering | 50 | Completed | 100 |  |  |  |  | 0 |  |  |  | 4000000 | 0 | 0 | 19/05/25 |  | 4000000 | No | Yes
1241 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | Namakku Na/2021-22/009/CULVERT/00039 |  |  | Namakku Naame Thittam Namakku Na/2021-22/009/CULVERT/00039-Construction of RCC Slab Culvert Crossing at Pappan Cannal at Durgas Road Side in West Tambaram | Culverts | Culverts | Roc.No. 28244-21/2021/P2 -Construction of RCC Slab Culvert - Tambaram CorpnDated:28/02/22 | 2021-22 | 4200000 | 4200000 |  |  |  | 0.42 | 20/10/22 | 0.35 | Deck Slab Rcc 1:1:5:3 | 0 | Completed | 100 |  |  | 17/09/24 |  | 4197975 |  |  |  | 2025 | 0.42 | 99.95 | 18/04/23 |  | 4200000 | Yes | Yes
1242 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/SWD/00198 | Zone II | 15 | General Fund GENERAL/2025-26/009/SWD/00198-Construction of SWD at vembuliamman koil 2 nd street in ward-15 at zone-II,TCMC | Storm Water Drain | Construction of Drain | 37-09/2025-26Dated:29/08/25 | 2025-26 | 730000 | 730000 |  |  |  | 0 | 26/09/25 | 0.07 | Earth Work | 30 | Completed | 100 |  |  | 21/01/26 |  | 727900 |  |  | 0 | 2100 | 0 | 0 | 26/12/25 |  | 730000 | No | Yes
1243 | Tambaram | CMBFS-COMMON KITCHEN | CHENGALPATTU | CMBFS/2023-24/009/BUILDING/00070 | Zone III |  | CMBFS-COMMON KITCHEN CMBFS/2023-24/009/BUILDING/00070-Construction of Common kitchen building at Corporation Primary school Chitlpakkam Zone 3 | Buildings | Buildings | 17404/2022/M1Dated:10/03/23 | 2023-24 | 13750000 | 2750000 |  |  |  | 0.24 | 17/04/23 | 0.24 | Completed | 100 | Work Completed | 100 |  |  | 23/06/23 |  | 2360000 |  |  |  | 390000 | 0.24 | 85.82 | 18/05/23 |  | 13750000 | Yes | Yes
1244 | Tambaram | CMBFS-COMMON KITCHEN | CHENGALPATTU | CMBFS/2023-24/009/BUILDING/00068 | Zone I |  | CMBFS-COMMON KITCHEN CMBFS/2023-24/009/BUILDING/00068-Construction of Common kitchen building at Corporation middle school at Thiruneermalai zone I | Buildings | Buildings | 17404/2022/M1Dated:10/03/23 | 2023-24 | 13750000 | 2750000 |  |  |  | 0 | 17/04/23 | 0.24 | Completed | 100 | Work Completed | 100 |  |  | 2022-12-07 |  | 2450000 |  |  |  | 300000 | 0.21 | 78 | 18/05/23 |  | 13750000 | Yes | Yes
1245 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00456 |  |  | Elementary Education Fund EE/2024-25/009/BUILDING/00456-Construction of Toilet and Providing shed at Ponniamman Corporation primary school in wd no 17 | Buildings | Buildings | 446/21.10.2024Dated:21/10/25 | 2024-25 | 24000000 | 6000000 |  |  |  | 0.53 | 2024-08-11 | 0.6 | Completed | 100 | Completed | 100 |  |  | 2025-04-11 |  | 5998849 |  |  |  | 1151 | 0.54 | 90.43 | 2025-08-05 |  | 24000000 | Yes | Yes
1246 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00313 | Zone IV | 59 | MLA Fund MLA Fund/2021-22/009/BUILDING/00313-Construction of Primary Health center at Peerkankaranai in ward No.59 | Buildings | Buildings | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 2504000 |  |  |  | 0.25 | 2022-08-07 | 0.25 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 2497000 |  |  |  | 7000 | 0.21 | 83.87 | 2022-11-10 |  | 5038000 | Yes | Yes
1247 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00488 | Zone I | 7 | MLA Fund MLA Fund/2021-22/009/BUILDING/00488-Construction of Public Distribution Shop at Ward No. 7 in Tambaram City Municipal Corporation | Buildings | Buildings | 4593/2021/A3/Dated:01/09/22 | 2021-22 | 2115000 | 1000000 |  |  |  | 0 | 23/09/22 | 0.09 | Completed | 100 | Completed | 100 |  |  | 23/08/23 |  | 1000000 |  |  |  | 0 | 0.1 | 100 | 22/12/22 |  | 2115000 | Yes | Yes
1248 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00003 | Zone I | 8 | MLA Fund MLA Fund/2022-23/009/BUILDING/00003-Construction of Community Hall at (Ward No. 8), TCMC, Zone -1 | Buildings | Buildings | 3607/2022/A3Dated:30/11/22 | 2022-23 | 6285000 | 2500000 |  |  |  | 0 | 2023-11-01 | 0.21 | Completed | 100 | Completed | 100 |  |  | 2024-10-04 |  | 2500000 |  |  |  | 0 | 0.13 | 52.99 | 2023-11-04 |  | 6285000 | No | Yes
1249 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00273 | Zone I | 3 | MLA Fund MLA Fund/2021-22/009/BUILDING/00273-Construction of Public Distribution Shop at Ward No.3 in Anakaputhur | Buildings | Buildings | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 1000000 |  |  |  | 0.09 | 2022-08-06 | 0.09 | Completed | 100 | Completed | 100 |  |  | 30/01/23 |  | 1000000 |  |  |  | 0 | 0.09 | 90.93 | 2022-06-09 |  | 4710000 | Yes | Yes
1250 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00274 | Zone I | 4 | MLA Fund MLA Fund/2021-22/009/BUILDING/00274-Construction of Public Distribution Shop at Ward No.4 in Anakaputhur | Buildings | Buildings | 4593/2021/A3Dated:20/04/22 | 2021-22 | 4710000 | 1000000 |  |  |  | 0 | 2022-08-06 | 0.09 | Completed | 100 | Completed | 100 |  |  | 30/01/23 |  | 1000000 |  |  |  | 0 | 0 | 0 | 2022-06-09 |  | 4710000 | No | Yes
1251 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/BUILDING/00026 | Zone III | 25 | CGF CGF/2021-22/009/BUILDING/00026-CONSTRUCTION OF KNOWLEDGE AND STUDY CENTER (TYPE I) AT PARALI NELLIAPPER SCHOOL, CHROMPET WARD NO.25 (ZONE – III) | Buildings | Buildings | 19089/2021/SS2Dated:14/12/22 | 2021-22 | 15000000 | 15000000 |  |  |  | 1.5 | 14/06/22 | 1.22 | Completed | 100 | Completed | 100 |  |  | 28/02/25 |  | 15000000 |  |  |  | 0 | 1.39 | 92.56 | 14/03/23 | ... | 15000000 | No | Yes
1252 | Tambaram | CMBFS-COMMON KITCHEN | CHENGALPATTU | CMBFS/2023-24/009/BUILDING/00072 | Zone V |  | CMBFS-COMMON KITCHEN CMBFS/2023-24/009/BUILDING/00072-Construction of Common kitchen building at Corporation Higher secondary school, Selaiyur Zone 5 | Buildings | Buildings | 17404/2022/M1Dated:10/03/23 | 2023-24 | 13750000 | 2750000 |  |  |  | 0.22 | 17/04/23 | 0.24 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 2360000 |  |  |  | 390000 | 0.21 | 77 | 18/05/23 |  | 13750000 | Yes | Yes
1253 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00016 | Zone III | 40 | MLA Fund MLA Fund/2022-23/009/BUILDING/00016-Construction of PDS shop at Ambedkar street (near park) PD158 Selaiyur at n ward No.40 in Tambaram Corporation | Buildings | Other Buildings | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 1200000 |  |  |  | 0.12 | 28/02/23 | 0.1 | Basement Level | 20 | Work Completed | 100 |  |  | 2023-11-10 |  | 0 |  |  |  | 1200000 | 0 | 0 | 30/04/23 |  | 7500000 | No | Yes
1254 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00187 | Zone V | 45 | MLA Fund MLA/2024-25/009/BUILDING/00187-Construction of Cremation shed at Selaiyur Kullakkarai in ward No. 45 zone V in Tambaram City Municipal Corporation | Buildings | Other Buildings | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 850000 |  |  |  | 0.08 | 29/10/24 | 0.07 | Roof Laid | 60 | Completed | 100 |  |  | 2025-05-03 |  | 847914 |  |  |  | 2086 | 0.08 | 99.75 | 26/07/25 |  | 9650000 | Yes | Yes
1255 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00015 | Zone V | 46 | MLA Fund MLA Fund/2022-23/009/BUILDING/00015-Construction of Kariyapandapam at Manimegalai street in ward No.46 in Tambaram Corporation | Buildings | Other Buildings | 4408/2021/A3Dated:30/11/22 | 2022-23 | 7500000 | 850000 |  |  |  | 0 | 25/01/23 | 0.07 | Completed | 100 | Completed | 100 |  |  | 25/04/24 |  | 846833 |  |  |  | 3167 | 0 | 0 | 2023-07-08 |  | 7500000 | No | Yes
1256 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00366 | Zone V | 48 | MLA Fund MLA Fund/2021-22/009/BUILDING/00366-Construction of PDS at Vayasar street in ward No.48 | Buildings | Other Buildings | 4592/2021/A3-PDS-5Dated:27/04/22 | 2021-22 | 3000000 | 1000000 |  |  |  | 0.1 | 2022-11-07 | 0.1 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 1000000 |  |  |  | 0 | 0.09 | 90.97 | 29/01/23 |  | 3000000 | Yes | Yes
1257 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2022-23/009/SANITATION/00163 | Zone V | 69 | SBM 2.0 SWACHH BHA/2022-23/009/SANITATION/00163-construction of community toilet at Narikuravar colony in ward no.69, zone no.5 | Sanitation Work | Constn of Community Toilet | 5990/2022/SBM-1Dated:11/03/22 | 2022-23 | 2700000 | 2700000 |  |  |  | 0.27 | 2022-01-09 | 0.22 | Roof Laid | 75 | Completed | 100 |  |  | 2024-12-02 |  | 0 |  |  |  | 2700000 | 0.23 | 84.3 | 2022-01-12 |  | 2700000 | Yes | Yes
1258 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/SANITATION/00105 | Zone II |  | Namakku Naame Thittam NNT/2022-23/009/SANITATION/00105-Reconstruction of Common Toilet inear Chrompet Bus stand in Zone II | Sanitation Work | Constn of Community Toilet | 8880/2022/p1-2Dated:20/04/23 | 2022-23 | 15130000 | 1500000 |  |  |  | 0.15 | 29/05/23 | 0.15 | Plastering | 65 | Completed | 100 |  |  | 2024-09-09 |  | 1500000 |  |  |  | 0 | 0.15 | 100 | - |  | 15130000 | Yes | Yes
1259 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS | CHENGALPATTU | SFCOANDM/2024-25/009/BUILDING/00151 | Zone III | 23 | SFC -SCHOOL IMPROVEMENT GRANT-O&M WORKS SFCOANDM/2024-25/009/BUILDING/00151-Construction of Gents Toilet at Zamin Royapettai higher secondary school in ward No.23 in Zone No.3 | Buildings | Buildings | 21616/2024/SS2Dated:22/07/24 | 2024-25 | 750000 | 750000 |  |  | 0 | 0 | 28/08/24 | 0 | Plastering | 85 | Completed | 100 |  |  |  |  | 0 |  |  |  | 750000 | 0.04 | 54.13 | 25/05/25 |  | 750000 | No | Yes
1260 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00457 | Zone II |  | Elementary Education Fund EE/2024-25/009/BUILDING/00457-Construction of Toilet and comound wall and providing paver block CC TV PA system and UPVC window at essa pallavaram in wd no 13 in Zone II | Buildings | Buildings | 446/21.10.2024Dated:21/10/25 | 2024-25 | 24000000 | 6000000 |  |  |  | 0 | 2024-08-11 | 0.6 | Plastering | 90 | Completed | 100 |  |  | 2025-04-11 |  | 5993818 |  |  |  | 6182 | 0 | 0 | - |  | 24000000 | No | Yes
1261 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00077 | Zone V | 70 | MLA Fund MLA/2023-24/009/BUILDING/00077-Construction of Kariyamandapam near Noothanacheri Kulam in ward No.70, Zone V in Tambaram City Municipal Corporation | Buildings | Buildings | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 850000 |  |  |  | 0 | 2024-12-06 | 0 | Plastering | 85 | Completed | 100 |  |  | 15/04/25 |  | 849289 |  |  |  | 711 | 0 | 0 | - |  | 11040000 | No | Yes
1262 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00078 | Zone III | 40 | MLA Fund MLA/2023-24/009/BUILDING/00078-Construction of Kariyamandapam near Gowrivakkam kulam in ward No.40, Zone III in Tambaram City Municipal Corporation | Buildings | Buildings | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 1200000 |  |  |  | 0 | 2024-11-07 | 0 | Plastering | 55 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1200000 | 0 | 0 | 2025-07-04 |  | 11040000 | No | Yes
1263 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2024-25/009/BUILDING/00009 | Zone II |  | Elementary Education Fund EE/2024-25/009/BUILDING/00009-Construction of Additional school building at zamin pallavaram primary school in wd no 17 tcmc Zone-2 | Buildings | Buildings | 358Dated:30/08/24 | 2024-25 | 6000000 | 6000000 |  |  |  | 0 | 30/09/24 | 0.6 | Plastering | 90 | Completed | 100 |  |  | 2025-04-11 |  | 5999065 |  |  |  | 935 | 0 | 0 | 30/03/25 |  | 6000000 | No | Yes
1264 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00489 | Zone I | 5 | MLA Fund MLA Fund/2021-22/009/BUILDING/00489-Construction of ICDS centre @ (Ward No. 5) in Zone-1, TCMC | Buildings | Anganwadi | 4593/2021/A3/Dated:01/09/22 | 2021-22 | 2115000 | 1115000 |  |  |  | 0 | 23/09/22 | 0.07 | Completed | 100 | Completed | 100 |  |  | 20/02/23 |  | 0 |  |  |  | 1115000 | 0 | 0 | 22/12/22 |  | 2115000 | No | Yes
1265 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/BUILDING/00022 | Zone I | 11 | MP Fund MP/2023-24/009/BUILDING/00022-Construction of Anganwadi Building at ward No.11, Eswaran Nagar 10th street Pallavapuram Constituency, Chengalpattu District, Zone I | Buildings | Anganwadi | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 1115000 |  |  |  | 0 | 2024-03-02 | 0.09 | Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1115000 |  |  |  | 0 | 0 | 0 | 2025-05-05 |  | 11435000 | No | Yes
1266 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/OTHERS/00283 | Zone II |  | General Fund GENERAL/2025-26/009/OTHERS/00283-Engaged tata ace and labour for fallen tree cutting and removing at various places in zone-2 | Others | Miscellaneous Works | 6-1 / 2025-26Dated:28/01/26 | 2025-26 | 980000 | 980000 |  |  |  | 0 | 2025-03-11 | 0.1 | Works | 40 | Completed | 100 |  |  | 26/12/25 |  | 947900 |  |  | 0 | 32100 | 0 | 0 | 2026-03-02 |  | 980000 | No | Yes
1267 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00479 | Zone IV | 33 | MLA Fund MLA Fund/2021-22/009/BUILDING/00479-Construction of a Bus Shelter Near Fire Station GST Road Ward No.33 West Tambaram in Tambaram City Municipal Corporation | Buildings | Bus Shelter | 4592/2021/A3 TambaramDated:09/09/22 | 2021-22 | 1400000 | 1400000 |  |  |  | 0.14 | 2022-11-10 | 0.14 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 14 |  |  |  | 1399986.36 | 0.14 | 97.45 | 2022-10-11 |  | 1400000 | Yes | Yes
1268 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00369 | Zone V | 64 | MLA Fund MLA Fund/2021-22/009/BUILDING/00369-Providing Bus shelter to Christ king Near to madha statue in ward No.64, Zone V. | Buildings | Bus Shelter | 4592/2021/A3-East TambaramDated:28/09/22 | 2021-22 | 1400000 | 1400000 |  |  |  | 0.14 | 30/08/22 | 0.14 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 1400000 |  |  |  | 0 | 0.13 | 90.88 | 15/11/22 |  | 1400000 | Yes | Yes
1269 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00190 | Zone V | 64 | MLA Fund MLA/2024-25/009/BUILDING/00190-Providing bus shelters at krishthuking Higher secondary school bus stop in ward No.64 zone V in Tambaram City Municipal Corporation | Buildings | Bus Shelter | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 1000000 |  |  |  | 0 | 29/10/24 | 0.08 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0.09 | 89.13 | 26/07/25 |  | 9650000 | Yes | Yes
1270 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2021-22/009/BUILDING/00314 | Zone IV | 56 | MLA Fund MLA Fund/2021-22/009/BUILDING/00314-Providing Bus shelter to Old Perungalathur Mudichur road near Ambedkar statue in ward No.56 | Buildings | Bus Shelter | 4593/2021/A3 (Tambaram)Dated:18/04/22 | 2021-22 | 5038000 | 738000 |  |  |  | 0.07 | 2022-08-06 | 0.07 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 598000 |  |  |  | 140000 | 0.07 | 100 | 2022-08-09 |  | 5038000 | Yes | Yes
1271 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00188 | Zone V | 69 | MLA Fund MLA/2024-25/009/BUILDING/00188-Providing Bus shelter at Agaram then road in ward No. 69 zone V in Tambaram City Municipality | Buildings | Bus Shelter | 1694/2024/A3Dated:20/09/24 | 2024-25 | 9650000 | 900000 |  |  |  | 0 | 29/10/24 | 0.07 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 900000 | 0.08 | 86.72 | 26/07/25 |  | 9650000 | No | Yes
1272 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00018 | Zone II | 17 | MLA Fund MLA/2023-24/009/BUILDING/00018-Providing Bus shelter at ward No.17 Near Play ground training zone II | Buildings | Bus Shelter | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 500000 |  |  |  | 0 | 29/12/23 | 0.05 | Completed | 95 | Completed | 100 |  |  | 30/12/24 |  | 495000 |  |  |  | 5000 | 0 | 0 | 29/03/24 |  | 8230000 | No | Yes
1273 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00019 |  |  | MLA Fund MLA/2023-24/009/BUILDING/00019-Providing New Bus shelter at Chrompet GST ESI bus stop (Towards chennai near pothys) | Buildings | Bus Shelter | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 1500000 |  |  |  | 0 | 29/12/23 | 0.1 | Completed | 95 | Completed | 100 |  |  | 30/09/24 |  | 1500000 |  |  |  | 0 | 0 | 0 | 29/03/24 |  | 8230000 | No | Yes
1274 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00396 | Zone III | 36 | MLA Fund MLA/2024-25/009/BUILDING/00396-Construction of Shelter at Near Kumarakundram kovil main road (NSR road) in ward No.36 Zone III in Tambaram Corporation | Buildings | Bus Shelter | 1695/2024/A3-1Dated:12/12/24 | 2024-25 | 4500000 | 4500000 |  |  |  | 0.45 | 16/04/25 | 0.45 | Completed | 100 | Work Completed | 100 |  |  |  |  | 0 |  |  |  | 4500000 | 0 | 0 | 22/07/25 |  | 4500000 | No | Yes
1275 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00274 | Zone I | 31 | MLA Fund MLA/2023-24/009/BUILDING/00274-Construction of Bus shelter at ward No.31 zone I in Tambaram Corporation | Buildings | Bus Shelter | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 700000 |  |  |  | 0 | - | 0 | Completed | 100 | Work Completed | 100 |  |  | 2024-08-05 |  | 700000 |  |  |  | 0 | 0 | 0 | - |  | 7430000 | No | Yes
1276 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/PARK/00080 | Zone V | 69 | MLA Fund MLA/2023-24/009/PARK/00080-Providing Compound wall to Pazhathottam park in ward No.69 zone V in Tambaram City Municipal Corporation | Parks | Compound Wall Toilet and Security Room | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 2300000 |  |  |  | 0 | 21/06/24 | 0.19 | Colour Washing | 65 | Completed | 100 |  |  | 2025-11-04 |  | 2297744 |  |  |  | 2256 | 0 | 0 | - |  | 11040000 | No | Yes
1277 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/PARK/00119 |  |  | 15th CFC 15th CFC/2020-21/009/PARK/00119-Improvements of VGN Nagar park in Thiruneermalai Town Panchayat | Parks | Compound Wall Toilet and Security Room | 922/TP2/2020Dated:18/08/21 | 2020-21 | 3000000 | 3000000 |  |  | 0 | 0.3 | 2021-03-11 | 0.27 | Completed | 100 | Work Completed | 100 |  |  | 19/07/23 |  | 3000000 |  |  |  | 0 | 0.12 | 39.67 | 2022-03-05 |  | 3000000 | No | Yes
1278 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/OTHERS/00275 | Zone I | 12 | MLA Fund MLA/2023-24/009/OTHERS/00275-Providing Police booth at ward No.12, zone I in Tambaram Corporation | Others | Infrastructure and Amenities | 3042/2023/A3Dated:26/10/23 | 2023-24 | 7430000 | 380000 |  |  |  | 0 | 18/11/23 | 0 | Completed | 100 | Completed | 100 |  |  | 19/08/24 |  | 380000 |  |  |  | 0 | 0 | 0 | - |  | 7430000 | No | Yes
1279 | Tambaram | State Finance Commission-URDF | CHENGALPATTU | SFC-URDF/2024-25/009/ROAD/00056 | Zone V |  | State Finance Commission-URDF SFC-URDF/2024-25/009/ROAD/00056-Formation of New Road-Earthern to BT Road009062R6261-Narmatha Street 8th Cross Cross , 009062R6259-Narmatha 7th Cross Street , 009062R6260-Kurunji Nagar Main Road , 009069R6365-Andal Nagar(Thirumal Nagar Main Road) , 009069R6368-Andal Nagar 2nd street , 009069R6367-Andal Nagar 1st street , 009069R6366-Thirumal Nagar 1st Street , 009070R6356-A.S.K.NAGAR 1ST CROSS STREET , 009070R6378-Raj Paris (Mud Road) , Zone V (Package No.I | Roads | Earthern to BT Road | 2767/2024/SS2Dated:01/02/24Road DetailsRoad Length :1064 Mts | 2024-25 | 10200000 | 7400000 |  |  |  | 0.67 | 27/02/24 | 0.72 | Completed | 100 | Completed | 100 |  |  | 2025-12-02 |  | 7250895 |  |  |  | 149105 | 0.67 | 90 | - |  | 10200000 | Yes | Yes
1280 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/ROAD/00105 |  |  | General Fund GENERAL/2025-26/009/ROAD/00105-Formation of New Road-Earthern to CC Road- , | Roads | Earthern to CC Road | 767-1 / 2025-26Dated:31/10/25Road DetailsRoad Length :Mts | 2025-26 | 20000000 | 20000000 |  |  |  | 0 | 2025-12-11 | 2 | Completed | 100 | Picking/earthwork/milling | 100 |  |  |  |  | 0 |  |  |  | 20000000 | 0 | 0 | 2026-12-01 |  | 20000000 | No | Yes
1281 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/ROAD/00200 | Zone IV | 55 | Namakku Naame Thittam NNT/2022-23/009/ROAD/00200-Formation of New Road-Earthern to CC Road-Venkateshwara nagar ward 55 | Roads | Earthern to CC Road | 8880/2022/P1-3Dated:07/07/23Road DetailsRoad Length :Mts | 2022-23 | 5325000 | 4750000 |  |  |  | 0.48 | 2023-04-09 | 0.39 | Completed | 100 | Completed | 100 |  |  | 17/05/24 |  | 4750000 |  |  |  | 0 | 0.42 | 89.19 | 2023-03-12 |  | 5325000 | No | Yes
1282 | Tambaram | State Finance Commission-URDF | CHENGALPATTU | SFC-URDF/2024-25/009/ROAD/00057 | Zone V |  | State Finance Commission-URDF SFC-URDF/2024-25/009/ROAD/00057-Formation of New Road-Earthern to PaverBlock009045R6070-Masque Street , 009062R6257-Narmatha 1st Cross Street , 0090646R4844-NAGARAJAN IYER STREET , 009067R5253-AMBIKA NAGAR 4TH STREET , 009070R6375-Krishna Nagar 1st Street , 009070R6376-Krishna Nagar 2nd street , 009070R6373-Bala Garden Extn 3rd street , Zone V, (Package No.II) | Roads | Earthern to PaverBlock | 2767/2024/SS2Dated:01/02/24Road DetailsRoad Length :446 Mts | 2024-25 | 10200000 | 2800000 |  |  |  | 0.28 | 27/02/24 | 0.28 | Completed | 100 | Completed | 100 |  |  | 30/04/24 |  | 0 |  |  |  | 2800000 | 0.25 | 90 | - |  | 10200000 | No | Yes
1283 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/OTHERS/00234 | Zone II |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/OTHERS/00234-Supply and fixing of 400nos of new retro reflective name board and s ticking of 4oo nos of retro reflective street on the existing name board for the streets in zone II | Others | Road Sign | 16479/2023/EA2Dated:09/08/23 | 2023-24 | 55600000 | 9000000 |  |  |  | 1.8 | 24/01/24 | 0.88 | Work Under Progress | 75 | Completed | 100 |  |  | 2025-07-05 |  | 8694354 |  |  |  | 305646 | 0.81 | 90.55 | 24/04/24 |  | 55600000 | No | Yes
1284 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/OTHERS/00235 | Zone III |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/OTHERS/00235-Supply and fixing of 500nos of new retro reflective name board and s ticking of 4oo nos of retro reflective street on the existing name board for the streets in zone III | Others | Road Sign | 16479/2023/EA2Dated:09/08/23 | 2023-24 | 55600000 | 10950000 |  |  |  | 1.1 | 2024-06-01 | 1.09 | Completed | 100 | Completed | 100 |  |  | 26/05/25 |  | 10939540 |  |  |  | 10460 | 0.99 | 90.01 | 2024-02-10 |  | 55600000 | Yes | Yes
1285 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/OTHERS/00236 | Zone IV |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/OTHERS/00236-Supply and fixing of 600nos of new retro reflective name board and s ticking of 6oo nos of retro reflective street on the existing name board for the streets in zone IV | Others | Road Sign | 16479/2023/EA2Dated:09/08/23 | 2023-24 | 55600000 | 13450000 |  |  |  | 1.35 | 29/12/23 | 1.32 | Completed | 100 | Completed | 100 |  |  | 2026-08-01 |  | 13338700 |  |  | 0 | 111300 | 1.2 | 89.4 | 24/09/24 |  | 55600000 | No | Yes
1286 | Tambaram | 15th CFC UnTied Grant | CHENGALPATTU | 15thCFCunt/2023-24/009/OTHERS/00237 | Zone V |  | 15th CFC UnTied Grant 15thCFCunt/2023-24/009/OTHERS/00237-Supply and fixing of 400nos of new retro reflective name board and s ticking of 4oo nos of retro reflective street on the existing name board for the streets in zone V | Others | Road Sign | 16479/2023/EA2Dated:09/08/23 | 2023-24 | 55600000 | 9000000 |  |  |  | 1.8 | 18/01/24 | 0.88 | Completed | 100 | Completed | 100 |  |  | 27/05/25 |  | 8892800 |  |  |  | 107200 | 0.89 | 98.81 | - |  | 55600000 | Yes | Yes
1287 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00076 | Zone III | 42 | MLA Fund MLA/2023-24/009/BUILDING/00076-Construction of Library Building at Annai anjugam Nagar Park in ward No.42 in Tambaram Corporation | Buildings | Library | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 1500000 |  |  |  | 0 | 2024-11-07 | 0.11 | Roof Level | 88 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1500000 | 0 | 0 | 2025-07-04 |  | 11040000 | No | Yes
1288 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2021-22/009/BUILDING/00073 | Zone II | 19 | MLA Fund MLA/2021-22/009/BUILDING/00073-Construction of Library Building at ward No. 19, Zone II, in Tambaram City Municipal Corporation | Buildings | Library | 4593/2021/A3-2Dated:19/02/24 | 2021-22 | 4000000 | 4000000 |  |  |  | 0.4 | 14/03/24 | 0.4 | Plastering | 95 | Completed | 100 |  |  | 24/12/24 |  | 0 |  |  |  | 4000000 | 0.29 | 72.38 | 14/06/24 |  | 4000000 | No | Yes
1289 | Tambaram | MP Fund | CHENGALPATTU | MP/2023-24/009/BUILDING/00021 | Zone I | 11 | MP Fund MP/2023-24/009/BUILDING/00021-Construction of Public Library Building at ward No.11 Periyar Nagar Pallavapuram Constituency, Chengalpattu District, Zone I | Buildings | Library | 4093/2023/A3Dated:28/11/23 | 2023-24 | 11435000 | 1500000 |  |  |  | 0 | 22/01/24 | 0.12 | Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1500000 |  |  |  | 0 | 0 | 0 | - |  | 11435000 | No | Yes
1290 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00018 | Zone II | 15 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00018-Retrofitting and Public Toilet at Sudukadu streetin ward No.15 zone II | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 250000 |  |  |  | 0 | 24/04/25 | 0.03 | Plastering | 95 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 250000 | 0 | 0 | - |  | 12070000 | No | Yes
1291 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00019 | Zone II | 16 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00019-Retrofitting and Public Toilet at Ambedkar Nagar street in ward No.16 zone II | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 260000 |  |  |  | 0 | 24/04/25 | 0.03 | Plastering | 80 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 260000 | 0 | 0 | - |  | 12070000 | No | Yes
1292 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00038 | Zone V | 64 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00038-Repair and maintaining of Community toilet at Vinoba Nagar in ward No.64 zone V | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 420000 |  |  |  | 0 | 13/01/25 | 0.04 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 420000 | 0 | 0 | - |  | 12070000 | No | Yes
1293 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00026 | Zone I | 4 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00026-Repair and maintaining of Community toilet at Malliamma street in ward No.04 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 270000 |  |  |  | 0 | 2025-03-01 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-02-06 |  | 269976 |  |  |  | 24 | 0.03 | 99.99 | - |  | 12070000 | Yes | Yes
1294 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00027 | Zone I | 29 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00027-Repair and maintaining of Community toilet at Uyalliamman street in ward No.29 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 320000 |  |  |  | 0.03 | 2025-06-01 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-02-06 |  | 319866 |  |  |  | 134 | 0.03 | 99.96 | - |  | 12070000 | Yes | Yes
1295 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00029 | Zone I | 7 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00029-Repair and maintaining of Community toilet at Dhayalu street in ward No.07 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 210000 |  |  |  | 0.02 | 2025-06-01 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-02-06 |  | 210000 |  |  |  | 0 | 0.02 | 100 | - |  | 12070000 | Yes | Yes
1296 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00023 | Zone I | 1 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00023-Repair and maintaining of Community toilet at Shellamman Nagar in ward No.01 zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 350000 |  |  |  | 0.04 | 2025-03-01 | 0 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 350000 | 0.03 | 99.28 | - |  | 12070000 | Yes | Yes
1297 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2024-25/009/SANITATION/00016 | Zone I | 1 | SBM 2.0 SBM 2.0/2024-25/009/SANITATION/00016-Repair and maintenance of Public Toilet at Anakaputhur bus stand in ward No.01 , Zone I | Sanitation Work | Retrofitting and Reconstruction | 26740/2024/SBM-1Dated:26/09/24 | 2024-25 | 12070000 | 330000 |  |  |  | 0 | 18/12/24 | 0.03 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 330000 | 0 | 0 | - |  | 12070000 | No | Yes
1298 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2020-21/009/UGSS/00265 | Zone II |  | UGD-Internal Plumbing UGSS-IP/2020-21/009/UGSS/00265-Laying UGSS pipe line for 500 mm DI pipe at keelkatalai pumping station (Nanmangalam pumping main ) laying 200 mm SWP UGSS pipe line at dhansing salai and mahaveer salai and repairing of UGSS sewerage non clock motor at keelkatalai main pumping station and rajendiran nagar pumping station at zone-2 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 998/25-26Dated:29/12/25 | 2020-21 | 920000 | 920000 |  |  |  | 0 | 30/11/20 | 0.09 | Earth Work | 20 | Completed | 100 |  |  | 29/03/21 |  | 907732 |  |  | 0 | 12268 | 0 | 0 | 30/05/21 |  | 920000 | No | Yes
1299 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2020-21/009/UGSS/00271 |  |  | UGD-Internal Plumbing UGSS-IP/2020-21/009/UGSS/00271-Attending the UGSS pipe line burst and replacing the 750mm and 200mm Dipipe at keelkattalai main pumping station and 200 feet radial road , laying of 200mm PVC pipe at mahaveer salai and repair and maintenance of 10HP non clog submersible pump at RKV avenue road side lifiting station contruction of manhole at kannabiran street. | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 997/25-26Dated:29/12/25 | 2020-21 | 540000 | 540000 |  |  |  | 0 | 30/11/20 | 0.05 | Earth Work | 20 | Completed | 100 |  |  | 29/03/21 |  | 534211 |  |  | 0 | 5789 | 0 | 0 | 28/02/21 |  | 540000 | No | Yes
1300 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2020-21/009/UGSS/00272 |  |  | UGD-Internal Plumbing UGSS-IP/2020-21/009/UGSS/00272-Laying 200mm dia PVC UGSS pipe line at gangaiamman koil street, repair and maintanace of 120 hp non clog motor at keelkatalai main pumping station and 20 hp at ramasamy kuttai sub pumping station. | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 1001/25-26Dated:29/12/25 | 2020-21 | 580000 | 580000 |  |  |  | 0 | 24/07/20 | 0.06 | Earth Work | 20 | Completed | 100 |  |  | 2020-11-09 |  | 579763 |  |  | 0 | 237 | 0 | 0 | 24/10/20 |  | 580000 | No | Yes
1301 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2019-20/009/UGSS/00273 |  |  | UGD-Internal Plumbing UGSS-IP/2019-20/009/UGSS/00273-Laying 500mm dia CI pipe under ground sewerage pipe line in kamaraj nagar service road. | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 1000/25-26Dated:29/12/25 | 2019-20 | 400000 | 400000 |  |  |  | 0 | 28/02/20 | 0.04 | Earth Work | 30 | Completed | 100 |  |  | 2020-10-04 |  | 397573 |  |  | 0 | 2427 | 0 | 0 | 28/05/20 |  | 400000 | No | Yes
1302 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2020-21/009/UGSS/00269 | Zone II |  | UGD-Internal Plumbing UGSS-IP/2020-21/009/UGSS/00269-Laying 200mm dia PVC UGSS pipe line at thirumalai nagar north extension cross streetand aishwaryanagar at zone-2 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 999/25-26Dated:29/12/25 | 2020-21 | 480000 | 480000 |  |  |  | 0 | 30/11/20 | 0.05 | Earth Work | 20 | Completed | 100 |  |  | 30/03/21 |  | 474004 |  |  | 0 | 5996 | 0 | 0 | 28/02/21 |  | 480000 | No | Yes
1303 | Tambaram | UGD-Internal Plumbing | CHENGALPATTU | UGSS-IP/2019-20/009/UGSS/00261 | Zone II |  | UGD-Internal Plumbing UGSS-IP/2019-20/009/UGSS/00261-Providing and laying under ground sewerage pipe line at gangai amman nagar 8 th main road thirutani nagar north 1 st main road, ambal nagar cross street at zone-2 | Under Ground Sewerage Scheme | Internal Plumbing - UGSS | 1002/25-26Dated:29/12/25 | 2019-20 | 2500000 | 2500000 |  |  |  | 0 | 2019-08-03 | 0.25 | Pipe Line Supply | 20 | Completed | 100 |  |  | 30/09/20 |  | 2498000 |  |  | 0 | 2000 | 0 | 0 | 2019-08-09 |  | 2500000 | No | Yes
1304 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00079 | Zone V | 48 | MLA Fund MLA/2023-24/009/BUILDING/00079-Construction of 2 class room at Misriyammal Government Girls Higher secondary school in ward No.48 Zone V in Tambaram City Municipal Corporation | Buildings | School Building | 3041/2023/A3Dated:08/03/24 | 2023-24 | 11040000 | 3250000 |  |  |  | 0 | 2024-12-06 | 0 | Plastering | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 3250000 | 0 | 0 | - |  | 11040000 | No | Yes
1305 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2022-23/009/BUILDING/00277 | Zone I | 1 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2022-23/009/BUILDING/00277-Construction of 2+2 class room at Primary School in ward No.01, Anakaputhur, Zone I in Tambaram Corporation | Buildings | School Building | 6002/2023/SS2Dated:25/10/23 | 2022-23 | 28000000 | 7000000 |  |  |  | 0.21 | 2024-10-01 | 0.7 | Completed | 0 | Completed | 100 |  |  | 28/02/25 |  | 0 |  |  |  | 7000000 | 0.65 | 93.31 | - |  | 28000000 | No | Yes
1306 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2022-23/009/BUILDING/00278 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2022-23/009/BUILDING/00278-Construction of 4 class room at Zamin Pallavapuram High secondary school North side in ward No.17, Pallavapuram zone II in Tambaram Corporation | Buildings | School Building | 6002/2023/SS2Dated:25/10/23 | 2022-23 | 28000000 | 7000000 |  |  |  | 0.7 | 30/01/24 | 0.7 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 7000000 |  |  |  | 0 | 0.62 | 89 | 30/04/24 |  | 28000000 | No | Yes
1307 | Tambaram | Namakku Naame Thittam | CHENGALPATTU | NNT/2022-23/009/BUILDING/00101 | Zone IV | 59 | Namakku Naame Thittam NNT/2022-23/009/BUILDING/00101-Construction of school room in government higher secondary school at zone 4 ward no 59 , peerkankaranai area in tambaram city municipal corporation | Buildings | School Building | 8880/2022/P1Dated:21/03/23 | 2022-23 | 900000 | 900000 |  |  |  | 0.09 | 25/05/23 | 0.07 | Completed | 100 | Completed | 100 |  |  | 13/09/24 |  | 883194 |  |  |  | 16806 | 0.09 | 98.13 | 23/08/23 |  | 900000 | No | Yes
1308 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00174 | Zone V | 70 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00174-Construction of Additional 4 class room building at Corporation Primary school at Madambakkam ward No.70 Zone V in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 6800000 |  |  |  | 0 | 13/11/24 | 0.67 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6800000 | 0.55 | 81.29 | 2025-10-08 |  | 40950000 | No | Yes
1309 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00175 | Zone V | 64 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00175-Construction of Additional 4 class room building at Corporation Primary school at Vinoba Nagar ward No. 64, Zone V in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 6800000 |  |  |  | 0 | 13/11/24 | 0.67 | Completed | 100 | Completed | 100 |  |  | 29/01/26 |  | 6727173 |  |  | 0 | 72827 | 0.61 | 90 | 13/08/25 |  | 40950000 | No | No
1310 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2024-25/009/BUILDING/00176 | Zone III | 44 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2024-25/009/BUILDING/00176-Construction of 2+2 school building Chitalapakkam, Ramakrishnapuram school in ward No. 44 Zone III in Tambaram City Municipal Corporation | Buildings | School Building | 18484/2023/DO1Dated:09/09/24 | 2024-25 | 40950000 | 6800000 |  |  | 0 | 0 | 2024-10-12 | 0.68 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  | 0 | 6800000 | 0.27 | 40.22 | 2025-07-09 |  | 40950000 | No | No
1311 | Tambaram | Elementary Education Fund | CHENGALPATTU | EE/2023-24/009/BUILDING/00197 | Zone V | 70 | Elementary Education Fund EE/2023-24/009/BUILDING/00197-Construction of Additional School Building at Madambakkam Primary schoolcampus in ward No.70 | Buildings | School Building | 6840/2023/MCA3Dated:26/06/23 | 2023-24 | 6000000 | 6000000 |  |  |  | 0.6 | 2023-11-09 | 0.5 | Completed | 100 | Completed | 100 |  |  | 30/04/24 |  | 5986308 |  |  |  | 13692 | 0.6 | 99.77 | 2023-11-12 |  | 6000000 | Yes | Yes
1312 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2022-23/009/BUILDING/00280 | Zone III | 38 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2022-23/009/BUILDING/00280-Construction of 4 class room at Hasthinapuram Higher secondary school in ward No.38 zone III in Tambaram City Municipal Corporation | Buildings | School Building | 6002/2023/SS2Dated:25/10/23 | 2022-23 | 28000000 | 7000000 |  |  |  | 0.21 | 2024-06-01 | 0.68 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 7000000 | 0.44 | 62.3 | 2024-02-10 |  | 28000000 | No | Yes
1313 | Tambaram | MP Fund | CHENGALPATTU | MP Fund/2022-23/009/BUILDING/00017 |  |  | MP Fund MP Fund/2022-23/009/BUILDING/00017-Construction of New Building to accommodate the class rooms for the Adi-dravidar school at Kadaperi village at the New site as identifeid and resolved by the Corporation of Tambaram | Buildings | School Building | 2829/2022/A3-1Dated:16/11/22 | 2022-23 | 5000000 | 5000000 |  |  |  | 0.5 | 30/12/22 | 0.48 | Completed | 100 | Completed | 100 |  |  | 15/07/24 |  | 4998959 |  |  |  | 1041 | 0.5 | 99.98 | 28/06/23 |  | 5000000 | No | Yes
1314 | Tambaram | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS | CHENGALPATTU | SFC-SCHOOL/2022-23/009/BUILDING/00279 | Zone II | 17 | SFC -SCHOOL IMPROVEMENT GRANT - INFRASTRUCTURE WORKS SFC-SCHOOL/2022-23/009/BUILDING/00279-Construction of 4 class room at Zamin Pallavapuram High secondary school West side in ward No.17, Pallavapuram zone II in Tambaram Corporation | Buildings | School Building | 6002/2023/SS2Dated:25/10/23 | 2022-23 | 28000000 | 7000000 |  |  |  | 0.7 | 30/01/24 | 0.7 | Completed | 100 | Completed | 100 |  |  | 26/02/25 |  | 6917487 |  |  |  | 82513 | 0.61 | 87.8 | 30/04/24 |  | 28000000 | No | Yes
1315 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/009/BUILDING/00002 |  |  | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/009/BUILDING/00002-Construction of LPG Gasifier Crematorium at Selaiyur Burial Ground East Tambaram in Tambaram Municipality | Buildings | Crematorium | G.O.(Ms) No.92 MAWS (NS) Dept.Dated:30/10/21 | 2021-22 | 15000000 | 15000000 |  |  |  | 0.92 | 21/01/22 | 1.24 | Completed | 100 |  | 100 |  |  |  |  | 0 |  |  |  | 15000000 | 0.92 | 61 | 2022-04-04 | ... | 15000000 | No | Yes
1316 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2022-23/009/BUILDING/00198 | Zone V | 70 | 15th CFC 15thCFC/2022-23/009/BUILDING/00198-Additional work of Madambakkam LPG Crematorium with the provision of Automatic Operational system zone V in ward No.70 in Tambaram City Municipal Corporation | Buildings | Crematorium | 18698/2022/CFC1-2Dated:29/05/23 | 2022-23 | 4734000 | 4734000 |  |  |  | 0.47 | 2023-08-09 | 0.4 | Completed | 100 | Completed | 100 |  |  | 16/09/24 |  | 4725000 |  |  |  | 9000 | 0.47 | 99.81 | 2023-11-11 |  | 4734000 | Yes | Yes
1317 | Tambaram | 15th CFC | CHENGALPATTU | 15thCFC/2023-24/009/BUILDING/00138 | Zone II | 28 | 15th CFC 15thCFC/2023-24/009/BUILDING/00138-Modernization of Crematorium in GST Road at Ward No. 28 | Buildings | Crematorium | 16479/2023/CFCDated:26/05/23 | 2023-24 | 10800000 | 6680000 | 0 |  |  | 0.67 | 2023-03-11 | 0.64 | Completed | 100 | Completed | 100 |  |  | 27/05/25 |  | 4065405 |  |  |  | 2614595.36 | 0.34 | 50.96 | 2024-02-08 |  | 10800000 | No | Yes
1318 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/BUILDING/00063 | Zone IV | 56 | CGF CGF/2021-22/009/BUILDING/00063-Construction of LPG Gasifier Crematorium in Perungalathur Burial Ground at Ward No 56 (S. No. 288) | Buildings | Crematorium | 19089/2021/E2 -1 TAMBARAM-2Dated:25/03/22 | 2021-22 | 25000000 | 25000000 |  |  |  | 2.5 | 15/07/22 | 2.5 | Completed | 100 | Completed | 100 |  |  | 25/03/25 |  | 22850000 |  |  |  | 2150000 | 2.53 | 101.27 | 2024-06-01 | To be expedited | 25000000 | Yes | Yes
1319 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00057 | Zone III | 40 | General Fund GENERAL/2025-26/009/BUILDING/00057-Construction of Compound Wall and Dry Waste Shed At Micro Compost Center Sembakkam In ward No.40 In Zone III | Buildings | Construction of Compound Wall | 57Dated:17/02/25 | 2025-26 | 1000000 | 1000000 |  |  |  | 0 | 15/05/25 | 0.1 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 22/08/25 |  | 1000000 | No | Yes
1320 | Tambaram | MLA Fund | CHENGALPATTU | MLA Fund/2022-23/009/BUILDING/00005 | Zone I | 6 | MLA Fund MLA Fund/2022-23/009/BUILDING/00005- Providing Compound wall at Sooriyamman Koil Kulam at Ward No. 6, TCMC, Zone -1 | Buildings | Construction of Compound Wall | 3607/2022/A3Dated:30/11/22 | 2022-23 | 6285000 | 1535000 | 0 |  |  | 0 | 2023-11-01 | 0.12 | Completed | 100 | Completed | 100 |  |  | 20/07/23 |  | 1534621 |  |  |  | 378.66 | 0.15 | 99.98 | 2023-11-04 |  | 6285000 | Yes | Yes
1321 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00256 | Zone III |  | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00256-Construction of Urban Health Centre at Kulakkaraia , zone III (Kulakkarai behind saravana stores ) | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 20/11/23 | 0.25 | Completed | 100 | Completed | 100 |  |  | 2024-10-09 |  | 0 |  |  |  | 2500000 | 0.25 | 100 | 27/02/24 |  | 22500000 | No | Yes
1322 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00261 | Zone III | 23 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00261-Construction of Diagnostics centre (LAB) at Kulakkarai street, ward No.23, Zone III | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1-2Dated:12/10/22 | 2022-23 | 2200000 | 2200000 |  |  |  | 0.22 | 20/11/23 | 0.22 | Completed | 100 | Completed | 100 |  |  | 2024-11-09 |  | 2200000 |  |  |  | 0 | 0.2 | 89.65 | 23/08/24 |  | 2200000 | No | Yes
1323 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00249 | Zone V | 69 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00249-Construction of Urban Health Centre at Madambakkam Secretary coloney in ward No.69, zone V | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-05-10 | 0.25 | Completed | 100 | Completed | 100 |  |  | 27/08/24 |  | 2491548 |  |  |  | 8452 | 0 | 0 | - |  | 22500000 | No | Yes
1324 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00250 | Zone V | 27, 57 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00250-Construction of Urban Health Centre at CLC Jamin Pallavapuram in ward No.27, zone V Alternative site @ Zone-4 Ward No.57, Gundumedu area. | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-04-09 | 0.25 | Completed | 100 | Completed | 100 |  |  | 2024-12-09 |  | 0 |  |  |  | 2500000 | 0.23 | 90.07 | 2024-11-06 |  | 22500000 | No | Yes
1325 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00252 | Zone V | 70 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00252-Construction of Urban Health Centre at Periyar Nagar , Madambakkam in ward No.70, zone V | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-05-10 | 0.25 | Completed | 100 | Completed | 100 |  |  | 2025-05-03 |  | 2499343 |  |  |  | 657 | 0 | 0 | 13/01/24 |  | 22500000 | Yes | Yes
1326 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00253 | Zone I | 8 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00253-Construction of Urban Health Centre at Bajanai koviol street and Pammal in ward No.8, zone I | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-05-10 | 0.25 | Completed | 100 | Completed | 100 |  |  | 2024-09-08 |  | 2238202 |  |  |  | 261798 | 0.13 | 53.56 | - |  | 22500000 | No | Yes
1327 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00248 | Zone IV | 56 | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00248-Construction of Urban Health Centre at Perungalathur Peruratchi mandra street in ward No.56, zone IV | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.25 | 2023-04-09 | 0.21 | Completed | 100 | Completed | 100 |  |  | 14/08/24 |  | 2499995 |  |  |  | 5 | 0.22 | 89.99 | 2024-04-06 |  | 22500000 | No | Yes
1328 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2022-23/009/BUILDING/00254 | Zone I |  | 15thCFC-Health 15thCFCUPC/2022-23/009/BUILDING/00254-Construction of Urban Health Centre at Pammal , zone I | Buildings | Urban Health And Wellness Center | 35132/2022/CFC1Dated:12/10/22 | 2022-23 | 22500000 | 2500000 |  |  |  | 0.23 | 2024-10-01 | 0 | Completed | 100 | Work Completed | 100 |  |  | 14/08/24 |  | 1421522 |  |  |  | 1078478 | 0.14 | 56.86 | - |  | 22500000 | No | Yes
1329 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15thCFCUPC/2023-24/009/BUILDING/00266 | Zone I |  | 15thCFC-Health 15thCFCUPC/2023-24/009/BUILDING/00266-Construction of New Urban PHC at Anakaputhur I, Annal Gandhi 3rd street, Anakaputhur, Zone I | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015-2Dated:03/08/22 | 2023-24 | 24000000 | 12000000 |  |  |  | 0.84 | 2024-08-02 | 0 | Completed | 100 | Completed | 100 |  |  | 17/12/25 |  | 11680707 |  |  |  | 319293 | 1.08 | 89.69 | - |  | 24000000 | No | Yes
1330 | Tambaram | National Urban Health Mission | CHENGALPATTU | National U/2022-23/009/BUILDING/00028 | Zone II | 14 | National Urban Health Mission National U/2022-23/009/BUILDING/00028-Construction of UPHC at Annai Anjugam Nagar in Pallavapuram ward No.14 in Tambaram Corporation | Buildings | Urban Primary Health Center | 1869/NUHM/SHS/2015Dated:14/10/22 | 2022-23 | 12000000 | 12000000 |  |  |  | 1.2 | 2023-08-03 | 0.96 | Completed | 100 | Completed | 100 | 28/06/23 |  | 26/02/25 |  | 11892185 |  |  |  | 107815 | 1.04 | 86.63 | 2023-08-09 |  | 12000000 | Yes | Yes
1331 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/007/BUILDING/00071 |  |  | 15thCFC-Health 15th CFC/2021-22/007/BUILDING/00071-UPHC Zamin Pallavapuram- Building- 1 No. | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/Tambaram(Pallavapuram)Dated:17/12/21 | 2021-22 | 10000000 | 2500000 | 0 |  |  | 0.25 | 25/01/22 | 0.23 | Completed | 80 | Completed | 100 |  |  | 2024-09-09 |  | 2438000 |  |  |  | 62000 | 0.22 | 87.2 | 25/07/22 |  | 10000000 | Yes | Yes
1332 | Tambaram | 15thCFC-Health | CHENGALPATTU | 15th CFC/2021-22/007/BUILDING/00070 |  |  | 15thCFC-Health 15th CFC/2021-22/007/BUILDING/00070-UPHC Kulakarai St- Building- 1 No. | Buildings | Urban Primary Health Center | 32454/2021/AMRUT-2/Tambaram(Pallavapuram)Dated:17/12/21 | 2021-22 | 10000000 | 2500000 |  |  |  | 0.25 | 25/01/22 | 0.23 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 2500000 |  |  |  | 0 | 0.22 | 87.66 | 25/07/22 |  | 10000000 | Yes | Yes
1333 | Tambaram | CGF | CHENGALPATTU | CGF/2021-22/009/BUILDING/00066 | Zone V | 64 | CGF CGF/2021-22/009/BUILDING/00066-Construction of Knowledge Centre at Corporation Higher Secondary School at Selaiyur East Tambaram In Ward No. 64, Zone No V | Buildings | Knowledge Centre | 19089/2021/E2- -1 -TAMBARAM -5Dated:25/03/22 | 2021-22 | 25000000 | 25000000 |  |  |  | 2.25 | 13/06/22 | 2.06 | Completed | 100 | Completed | 100 |  |  | 26/04/24 |  | 24997955 |  |  |  | 2045 | 1.93 | 77.15 | 14/12/22 | To be expedited | 25000000 | No | Yes
1334 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | Kalaignar /2021-22/017/BUILDING/00001 |  |  | Kalaignar Nagarpura Mempatu Thittam Kalaignar /2021-22/017/BUILDING/00001-Construction of Daily Market | Buildings | Market | G.O.(Ms) No.138 MAWS (NS) Dept & G.O.(Ms) No. 15 MAWS (NS) DeptDated:20/01/22 | 2021-22 | 12700000 | 12700000 |  | 0 | 0 | 1.14 | 25/01/22 | 1.16 | Completed | 100 | Completed | 100 |  |  | 2025-02-03 |  | 10789974 |  |  |  | 1910026 | 1.2 | 94.49 | 22/10/22 | ... | 12700000 | Yes | Yes
1335 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00243 | Zone V | 70 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00243-Rejuvenation of Noothanseri at Madambakkam ward No.70, Survey no. 649 of Tambaram City Municipal in zone V | WaterBodies | Improvement of Water Bodies | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 5700000 |  |  |  | 0 | 28/11/23 | 0.56 | Completed | 100 | Completed | 100 |  |  | 21/04/25 |  | 5697855 |  |  |  | 2145 | 0.41 | 72.31 | - |  | 80000000 | Yes | Yes
1336 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.0/2023-24/009/WB/00244 | Zone III | 40 | AMRUT 2.O AMRUT 2.0/2023-24/009/WB/00244-Rejuvenation and Rain water Harvesting of Kulakkarai street Kulam at ward No.40, Survey No.91/16, in area of Sembakkam in Tambaram City Municipal Corporation in zone III | WaterBodies | Improvement of Water Bodies | 26467/2021/AMRUTDated:29/09/23 | 2023-24 | 80000000 | 6400000 |  |  |  | 0.64 | 28/11/23 | 0.63 | Completed | 75 | Completed | 100 |  |  |  |  | 0 |  |  |  | 6400000 | 0.34 | 53.18 | 24/08/24 |  | 80000000 | No | Yes
1337 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.O/2022-23/009/WB/00394 | Zone IV |  | AMRUT 2.O AMRUT 2.O/2022-23/009/WB/00394-Rejuvenation of Vettri Nagar Kanniamman kovil street kulam ward (D) 54,. Survey No.66 zone 4 in Tambaram city Municipal Corporation | WaterBodies | Improvement of Water Bodies | G.O. (Ms) No. 122Dated:09/09/22 | 2022-23 | 11280000 | 6880000 |  |  |  | 1.38 | 25/11/22 | 0.56 | Completed | 100 | Completed | 100 |  |  | 23/05/24 |  | 6819392 |  |  |  | 60608 | 0.97 | 141.69 | 22/08/23 |  | 11280000 | No | Yes
1338 | Tambaram | AMRUT 2.O | CHENGALPATTU | AMRUT 2.O/2022-23/009/WB/00395 | Zone V | 45 | AMRUT 2.O AMRUT 2.O/2022-23/009/WB/00395-Improvement Desilting Deepening strengthening rainwater harvesting and green space development to Gangaiamman kovil pond ward no.45 zone V | WaterBodies | Improvement of Water Bodies | G.O. (Ms) No. 122Dated:09/09/22 | 2022-23 | 11280000 | 4400000 |  |  |  | 0.44 | 25/11/22 | 0.36 | Completed | 100 | Completed | 100 |  |  | 29/04/24 |  | 4368548 |  |  |  | 31452 | 0.4 | 90 | 22/08/23 |  | 11280000 | No | Yes
1339 | Tambaram | Kalaignar Nagarpura Mempatu Thittam | CHENGALPATTU | KNMT/2023-24/009/WB/00282 | Zone I | 30 | Kalaignar Nagarpura Mempatu Thittam KNMT/2023-24/009/WB/00282-Rejunevation of Water Bodies at ward no. 30, Survey No. 339, Zone 1 | WaterBodies | Improvement of Water Bodies | G.O. (4D) No. 44Dated:03/11/23 | 2023-24 | 3300000 | 3300000 |  |  |  | 0.3 | 31/01/24 | 0 | Completed | 100 | Completed | 100 |  |  | 14/03/25 |  | 3233457 |  |  |  | 66543 | 0.29 | 86.7 | - |  | 3300000 | No | Yes
1340 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2022-23/009/SANITATION/00033 |  |  | SBM 2.0 SBM 2.0/2022-23/009/SANITATION/00033-Construction of 240no of Individual Households latrine in Tambaram City Municipal Corporation | Sanitation Work | IHHL Sanitation | 18856/2022/SBM2Dated:13/07/22 | 2022-23 | 7200000 | 7200000 |  |  |  | 0.16 | 2023-07-02 | 0 | Completed | 100 | Roof Laid | 100 |  |  |  |  | 0 |  |  |  | 7200000 | 0.16 | 21.9 | 2023-04-11 |  | 7200000 | No | No
1341 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00085 | Zone V | 62 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00085-Construction of Community Toilet at Erikkarai street in ward No.62, Zone 5 in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 21/06/24 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-06-06 |  | 599485 |  |  |  | 515 | 0 | 0 | - |  | 35640000 | No | Yes
1342 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00161 | Zone IV | 55 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00161-Construction of CT (Type-I) at Annai Anjugam nagar, ward 55, Perungulathur, Zone-4 | Sanitation Work | Constn of Community Toilet | 5990/2022/SBMDated:11/04/22 | 2021-22 | 5400000 | 2700000 |  |  |  | 0.27 | 2022-01-09 | 0.22 | Completed | 100 | Completed | 100 |  |  | 2024-06-02 |  | 2690669 |  |  |  | 9331 | 0.27 | 99.65 | 31/12/22 |  | 5400000 | No | Yes
1343 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00089 | Zone V | 70 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00089-Construction of Community Toilet at Secretariat colony in ward No.70, Zone 5 in Tambaram City Municipal Corporation | Sanitation Work | Constn of Community Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 600000 |  |  |  | 0 | 21/06/24 | 0.06 | Completed | 98 | Completed | 100 |  |  |  |  | 0 |  |  |  | 600000 | 0 | 0 | 26/09/24 |  | 35640000 | No | Yes
1344 | Tambaram | General Fund | CHENGALPATTU | GENERAL/2025-26/009/BUILDING/00143 | Zone II | 20 | General Fund GENERAL/2025-26/009/BUILDING/00143-Renovation of PDS Shop at ayothidasa pandithar street in ward no-20 Zone II, TCMC | Buildings | Public Distriibution Shop | 913-7/2025-26Dated:31/10/25 | 2025-26 | 1400000 | 1400000 |  |  |  | 0 | 28/11/25 | 0.14 | Lintel Level | 70 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1400000 | 0 | 0 | 28/01/26 |  | 1400000 | No | Yes
1345 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00015 | Zone III | 23 | MLA Fund MLA/2023-24/009/BUILDING/00015-Construction of Public Distribution shop with Toilet facilities at ward No.23, zone III | Buildings | Public Distriibution Shop | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 1250000 |  |  |  | 0 | 28/02/24 | 0.1 | Roof Level | 82 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1250000 | 0 | 0 | 24/11/24 |  | 8230000 | No | Yes
1346 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00016 | Zone II | 9 | MLA Fund MLA/2023-24/009/BUILDING/00016-Construction of Public Distribution shop with Toilet facilities at ward No.09, zone II | Buildings | Public Distriibution Shop | 3042/2023/A3-6Dated:02/12/23 | 2023-24 | 8230000 | 1300000 |  |  |  | 0.13 | 29/12/23 | 0.13 | Roof Laid | 65 | Completed | 100 |  |  | 2024-09-09 |  | 1296000 |  |  |  | 4000 | 0.13 | 99.69 | 29/03/24 |  | 8230000 | Yes | Yes
1347 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2024-25/009/BUILDING/00195 | Zone II | 19 | MLA Fund MLA/2024-25/009/BUILDING/00195-Construction of PDS shop Toilet at ward No. 19 zone II in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 1695/2024/A3Dated:20/09/24 | 2024-25 | 16540000 | 1300000 |  |  |  | 0.13 | 23/10/25 | 0.11 | Completed | 100 | Completed | 100 |  |  | 25/10/25 |  | 1298680 |  |  |  | 1319.74 | 0.13 | 99.9 | 23/01/26 |  | 16540000 | Yes | Yes
1348 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2023-24/009/BUILDING/00047 | Zone V | 66 | MLA Fund MLA/2023-24/009/BUILDING/00047-Construction of Public Distribution shop at Rajaji main street shop no. 2 pd 130,SK in ward No.66, Zone V in Tambaram City Municipal Corporation | Buildings | Public Distriibution Shop | 3041/2023/A3-8Dated:08/01/24 | 2023-24 | 4570000 | 1000000 |  |  |  | 0 | 31/01/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 15/02/25 |  | 997782 |  |  |  | 2218 | 0 | 0 | - |  | 4570000 | No | Yes
1349 | Tambaram | MLA Fund | CHENGALPATTU | MLA/2025-26/009/BUILDING/00121 | Zone IV | 32 | MLA Fund MLA/2025-26/009/BUILDING/00121-Construction of PDS Shop to Arputham Nagar ward No.32 in Zone 4 TCMC | Buildings | Public Distriibution Shop | 0982/3Dated:25/04/25 | 2025-26 | 1300000 | 1300000 |  |  |  | 0 | 23/05/25 | 0.11 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1300000 | 0 | 0 | 21/08/25 |  | 1300000 | No | Yes
1350 | Tambaram | 15th CFC | CHENGALPATTU | 15th CFC/2020-21/009/SWM/00143 |  |  | 15th CFC 15th CFC/2020-21/009/SWM/00143-Remove the legacy waste dumped approximate Quantity 7675 cubic meter on private land s.no. 150, 152, 153 through biomining process on disposal | Solid Waste Management | RRC - Material Recovery Facility | 56Dated:31/05/19 | 2020-21 | 5000000 | 5000000 |  |  |  | 0.5 | 2019-04-09 | 0.49 | Completed | 100 | Completed | 100 |  |  | 2022-12-09 |  | 40 |  |  |  | 4999959.76 | 0.4 | 80.5 | 2019-04-12 |  | 5000000 | Yes | Yes
1351 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00106 | Zone III | 38 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00106-Construction of Public Toilet at Thiru .Vi.Ka Nagar MCC in ward No.38 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-01-07 | 0.07 | Plastering | 80 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | 28/03/25 |  | 35640000 | No | Yes
1352 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00116 | Zone V | 70 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00116-Construction of Public Toilet at Madambakkam MCC in ward No.70 Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0 | Plastering | 75 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0.04 | 40.7 | - |  | 35640000 | No | Yes
1353 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00117 | Zone V | 62 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00117-Construction of Public Toilet at Arul Nagar in ward No.62. Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0 | Plastering | 80 | Completed | 100 |  |  | 2024-02-12 |  | 997668 |  |  |  | 2332 | 0 | 0 | - |  | 35640000 | Yes | Yes
1354 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00157 | Zone IV | 49 | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00157-construction of Public Toilet at Tambaram Old bus stand , ward 49, Zone -IV | Sanitation Work | Public Toilet | 5990/2022/SBM-2Dated:11/04/22 | 2021-22 | 13000000 | 3250000 |  |  |  | 0.33 | 2022-01-09 | 0.21 | Plastering | 95 | Completed | 100 |  |  | 29/08/23 |  | 3019080 |  |  |  | 230920 | 0.3 | 92.89 | 2022-01-12 |  | 13000000 | Yes | Yes
1355 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00118 | Zone V | 64 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00118-Construction of Public Toilet at Adhi nagar OCC in ward No.64. Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0 | Completed | 100 | Completed | 100 |  |  | 17/02/25 |  | 999552 |  |  |  | 448 | 0.1 | 99.95 | - |  | 35640000 | No | Yes
1356 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00119 | Zone V | 62 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00119-Construction of Public Toilet at Gayathri nagar ward No.62. Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-12-06 | 0.08 | Completed | 100 | Completed | 100 |  |  | 2025-12-02 |  | 999299 |  |  |  | 701 | 0.1 | 99.93 | - |  | 35640000 | No | Yes
1357 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00120 | Zone V | 63 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00120-Construction of Public Toilet at MES Road ward No.63. Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0 | Completed | 98 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0 | 0 | - |  | 35640000 | No | Yes
1358 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2022-23/009/SANITATION/00164 | Zone III | 18 | SBM 2.0 SWACHH BHA/2022-23/009/SANITATION/00164-Construction of public toilet at Kilkattalai zone no. 3 ward no.18 (Type I) | Sanitation Work | Public Toilet | 5990/2022/SBM-3Dated:24/06/22 | 2022-23 | 3250000 | 3250000 |  |  |  | 0.33 | 25/09/22 | 0.21 | Completed | 100 | Completed | 100 |  |  | 2024-09-09 |  | 2359500 |  |  |  | 890500 | 0.23 | 70.29 | 24/12/22 |  | 3250000 | No | Yes
1359 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00159 |  |  | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00159-construction of public toilet at Tambaram Pudhu Nagar | Sanitation Work | Public Toilet | 5990/2022/SBM-2Dated:11/04/22 | 2021-22 | 13000000 | 3250000 |  |  |  | 0.33 | 2022-01-09 | 0.33 | Completed | 100 | Completed | 100 |  |  | 17/09/24 |  | 3030000 |  |  |  | 220000 | 0.3 | 90.95 | 2022-01-12 |  | 13000000 | Yes | Yes
1360 | Tambaram | SBM 2.0 | CHENGALPATTU | SWACHH BHA/2021-22/009/SANITATION/00160 |  |  | SBM 2.0 SWACHH BHA/2021-22/009/SANITATION/00160-Construction of public toilet at Anakaputhur near market | Sanitation Work | Public Toilet | 5990/2022/SBM-2Dated:11/04/22 | 2021-22 | 13000000 | 3250000 |  |  |  | 0.61 | 2022-01-09 | 0.21 | Completed | 100 | Completed | 100 |  |  | 20/11/23 |  | 2679220 |  |  |  | 570780 | 0.27 | 82.44 | 2022-01-12 |  | 13000000 | No | Yes
1361 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00090 | Zone I | 31 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00090-Construction of Public Toilet at Jain park in ward No.31, Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 2024-02-07 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-03-02 |  | 1000000 |  |  |  | 0 | 0.1 | 100 | - |  | 35640000 | Yes | Yes
1362 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00091 | Zone I | 5 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00091-Construction of Public Toilet at Vishveshapuram park in ward No.5, Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 2024-02-07 | 0 | Completed | 100 | Completed | 100 |  |  | 2025-03-02 |  | 1000000 |  |  |  | 0 | 0.1 | 100 | - |  | 35640000 | Yes | Yes
1363 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00097 | Zone I | 4 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00097- Construction of Public Toilet at EB Colony in ward No.4 Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1000000 |  |  |  | 0 | 0.05 | 45 | - |  | 35640000 | No | Yes
1364 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00098 | Zone II | 21 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00098-Construction of Public Toilet at Zamin Pallavaram in ward No21 Zone II in Tambaram City Municipal Corporatio | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2025-02-01 |  | 1000000 |  |  |  | 0 | 0.1 | 99 | 21/09/24 |  | 35640000 | Yes | Yes
1365 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00115 | Zone V | 46 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00115-Construction of Public Toilet at Selaiyur MCC in ward No.46 Zone V in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 21/06/24 | 0 | Completed | 100 | Completed | 100 |  |  |  |  | 0 |  |  |  | 1000000 | 0.1 | 99.84 | - |  | 35640000 | No | Yes
1366 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00110 | Zone III | 38 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00110-Construction of Public Toilet at Hasthinapuram Bus stand in ward No.38 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-01-07 | 0.07 | Completed | 100 | Completed | 100 |  |  | 30/04/25 |  | 0 |  |  |  | 1000000 | 0.1 | 98.5 | 28/03/25 |  | 35640000 | Yes | Yes
1367 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00111 | Zone IV | 32 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00111-Construction of Public Toilet at Kannadapalayam MCC in ward No.32 Zone IV in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-12-06 | 0.1 | Completed | 100 | Completed | 100 |  |  | 22/01/26 |  | 911954 |  |  |  | 88046 | 0.09 | 91.2 | 2024-12-08 |  | 35640000 | No | Yes
1368 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00105 | Zone III | 22 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00105-Construction of Public Toilet at Arul murugan RCC in ward No.22 Zone III in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 16/08/24 | 0.08 | Completed | 100 | Completed | 100 |  |  | 30/04/25 |  | 932589 |  |  |  | 67411.5 | 0.09 | 93.26 | 13/05/25 |  | 35640000 | No | Yes
1369 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00093 | Zone I | 7 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00093-Construction of Public Toilet at SBI colony in ward No.7 Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 2024-05-07 | 0 | Completed | 0 | Completed | 100 |  |  | 24/02/25 |  | 1000000 |  |  |  | 0 | 0 | 0 | - |  | 35640000 | No | Yes
1370 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00094 | Zone I | 11 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00094-Construction of Public Toilet at Anna Salaiin ward No.11 Zone I in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0 | 28/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2025-05-05 |  | 1000000 |  |  |  | 0 | 0.1 | 100 | - |  | 35640000 | Yes | Yes
1371 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00100 | Zone II | 16 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00100-Construction of Public Toilet at Katcheri malai in ward No16 Zone II in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2024-12-12 |  | 0 |  |  |  | 1000000 | 0.09 | 90.19 | 21/09/24 |  | 35640000 | Yes | Yes
1372 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00102 | Zone II | 20 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00102-Construction of Public Toilet at Pumping station in ward No.20 Zone II in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 2024-09-12 |  | 0 |  |  |  | 1000000 | 0.09 | 90.18 | 21/09/24 |  | 35640000 | Yes | Yes
1373 | Tambaram | SBM 2.0 | CHENGALPATTU | SBM 2.0/2023-24/009/SANITATION/00103 | Zone II | 13 | SBM 2.0 SBM 2.0/2023-24/009/SANITATION/00103-Construction of Public Toilet at GST Road near olymbia in ward No.13 Zone II in Tambaram City Municipal Corporation | Sanitation Work | Public Toilet | 6450/2024/SBM-1(1)Dated:14/03/24 | 2023-24 | 35640000 | 1000000 |  |  |  | 0.1 | 21/06/24 | 0.07 | Completed | 100 | Completed | 100 |  |  | 30/12/24 |  | 989500 |  |  |  | 10500 | 0.1 | 98.95 | 21/09/24 |  | 35640000 | Yes | Yes